## Version control
National Energy Market
Regulatory Implementation Roadmap
Version | Date | Description
v1.0 | 2020-04-17 | First draft for review with industry and consumers at stakeholder forum of 21 April 2020.
v2.0 | 2020-05-06 | Second iteration, following further AEMO internal review and participant feedback. Presented to stakeholder forum on 8 May 2020, and published as part of market bodies prioritisation advice on 17 May 2020.
v3.0 - draft | 2020-08-04 | Next iteration, incorporating AEMC final determinations on WDR and 5MS/GS deferral, and other updates for presentation to stakeholder forum on 10 August 2020.
v3.0 - final | 2020-08-31 | Finalised version 3, incorporating outcomes following stakeholder engagement in August 2020, including some additional minor updates.
v4.0 - draft | 2021-02-24 | Draft version 4, incorporating implementation delays to 5MS retail solution, Metering Coordinator Planned Interruptions and MSATS standing data review go-live and other updates, for presentation at stakeholder forum on 24 Feb 2021
v4.0 - final | 2021-03-18 | Finalised version 4, incorporates implementation schedule for 2021 and schema changes for 2021-23. Delays to 5MS retail solution, Metering Coordinator Planned Interruptions and MSATS standing data review go-live dates,and other updates.
v5.0 - draft | 2021-07-09 | Draft version 5, incorporating updates since version 4 including 5MS program and 5MS contingency scenario
v5.0 - final | 2021-08-05 | Final version 5 incorporates some minor changes to roadmap and detailed implementation schedule.
This version also includes an additional tab ‘5MS contingency scenario’ which is for information only and is the subject of an AEMO rule change request on the AEMC website.

## Roadmap v5 - Final
National Energy Market and Gas Markets
Regulatory Implementation Roadmap |  |  |  |  | Key:
[6 empty] | Policy development/market design | [6 empty] | Rules development | [10 empty] | Procedure/guideline development
[6 empty] | Implementation - IT systems, processes | [6 empty] | Indicative IT implementation | [10 empty] | Engineering Implementation
[5 empty] | l | Committed Go-Live Date |  |  |  | p | Proposed Go-Live |  |  |  | n | Indicative Go-Live | [6 empty] | u | Estimated Go-Live | [6 empty] | + | Updated for version 5
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative |  | 2020 | [6 empty] | 2021 | [9 empty] | 2022 | [11 empty] | 2023 | [7 empty] | 2024 |  |  |  | 2025 |  |  |  | 2026
[5 empty] | Q1 |  | Q2 |  | Q3 | Q4 |  | Q1 | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | Q2 |  | Q3 | Q4 |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Five Minute Settlement (5MS) | + | [9 empty] | 5MS (IT platform) | l |  |  |  | l | AEMC final determination - go-live 1 Oct 2021
Retail | Consumer | Committed | Reducing Customer Switching Times | [15 empty] | l | Updated to align with 5MS go-live - 1 Oct 2021
Industry-wide | Consumer | Committed | Wholesale Demand Response Mechanism | [15 empty] | l | AEMC final determination - go live 24 Oct 2021
Retail | Consumer | Committed | Electricity B2B changes | [16 empty] | l | v3.5 and v3.6 - 10 Nov 2021
Gas |  | Committed | Gas B2B changes | [16 empty] | l | IN003/20 (business enhancements, schema uplift) - 29 Nov 2021
Industry-wide | Market | Committed | Global Settlements | + | [10 empty] | GS soft start |  |  |  | l |  |  |  | GS (extern) |  |  | l | AEMC final determination - go-live 1 May 2022
Retail | Consumer | Committed | Metering Coordinator Planned Interruptions (MCPI) | [22 empty] | l | AEMO notice to reschedule to 1 May 2022, bundled with MSDR
Retail | Operational | Committed | MSATS Standing Data Review (MSDR) | [21 empty] | v1 | l |  |  | v2 (small) |  |  | l | v1 AEMO consulted to reschedule to 1 May 2022, aligned with MCPI implementation
Retail | Market | In progress | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | + | [24 empty] | n | AEMC recommended implementation 12 months after law and rule changes made
Retail | Consumer | Proposed - Review | Energy Consumer Data Right | [26 empty] | n | Implementation dictated by Treasury timings, assumed to be Q3 2022
Retail | Consumer | In progress | Updating the Regulatory Frameworks for Embedded Networks | [33 empty] | u | Implementation based on understanding of current scope
Retail | Market | Proposed - Review | Review of Regulatory Framework for Metering Services | [28 empty] | u | (if required) | [6 empty] | u | IT implementation likely but not yet clear, dependent on review outcomes
Wholesale | Reliability | Proposed - Review | ST PASA - Replacement project and methodology update | [26 empty] | u | Estimated timing, subject to rule change process
Wholesale | Market | In progress | Integrating Energy Storage Systems (ESS) | + | [31 empty] | p
Wholesale | Security | Committed | Fast Frequency Response Market Ancillary Services (B) | + | [34 empty] | l | Rule change process co-ordinated with ESB initiatives.
Wholesale | Security | In progress | Primary Frequency Response Incentive Arrangements (B) | + | [17 empty] | Indicative Execution Range: Procedures, IT | [23 empty] | Rule change process co-ordinated with ESB initiatives.
Wholesale | Reliability | In progress | Operating Reserve Market (B) | + | [23 empty] | Indicative Execution Range: Procedures, IT | [15 empty] | Rule change process co-ordinated with ESB initiatives.
Wholesale | Security | In progress | Introduction of ramping services (B) | + | [23 empty] | Indicative Execution Range: Procedures, IT | [15 empty] | Rule change process co-ordinated with ESB initiatives.
Wholesale | Security | In progress | Synchronous Services Markets (B) | + | [23 empty] | Indicative Execution Range: Procedures, IT | [15 empty] | Rule change process co-ordinated with ESB initiatives.
Wholesale | Security | In progress | Capacity commitment mechanism for system security and reliability services (B) | + | [23 empty] | Indicative Execution Range: Procedures, IT | [15 empty] | Rule change process co-ordinated with ESB initiatives.
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Proposed - Review | Resource Adequacy Mechanisms and Ageing Thermal Generation (A)
Industry-wide | Market | Proposed - Review | Essential System Services, Scheduling and Ahead Mechanisms (B) | + | High Level Design | [6 empty] | Market Design |  |  |  |  | Indicative Execution Range: Legislation, Rules, Procedures, IT | [24 empty] | Extended Execution Range
Industry-wide | Security | Proposed - Review | Demand Side Participation (C)
Industry-wide | Market | Proposed - Review | Transmission and Access (D)
INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS
Wholesale | Security | Committed | Mandatory Primary Frequency Response |  |  |  |  | l | [7 empty] | Implementation timing shown is indicative and depends on individual generator circumstances, managed through the self-assessment process
Network |  | In progress | Technical Standards for Distributed Energy Resources | + | [16 empty] | l
Wholesale | Security | In progress | Efficient management of system strength on the power system (B) | + | [25 empty] | p |  |  |  |  | p
Wholesale |  | In progress | Generator Registrations and Connections | + | [19 empty] | p
Industry-wide |  | Committed | NEM Settlement in Zero and Negative Demand Conditions | + | [13 empty] | l
Network |  | In progress | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | + | [11 empty] | p
Network |  | Committed | Connection of Dedicated Connection Assets | [12 empty] | l
Network |  | Committed | Implementing a General Power System Risk Review | + | [17 empty] | l
Industry-wide |  | In progress | Enhancing Operational Resilience to Indistinct Events | +
ESB INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Renewable Energy Zones - Planning (Stage 1) (D) | + | [9 empty] | l
Industry-wide | Market | In progress | Renewable Energy Zones - Implementation (Stage 2) (D)
Wholesale | Security | Committed | Visibility and Security of Dispatch (Stage 1) - Interim | + | [8 empty] | l
Networks | Market | Proposed - Pending | Governance of DER Technical Standards | + | [17 empty] | Indicative timing, subject to rule change process
GAS INITIATIVES
Gas |  | Committed | DWGM simpler wholesale price | [29 empty] | l
Implemented as a single AEMO project
Gas |  | Committed | DWGM improvement to AMDQ regime | [28 empty] | l
Gas |  | In progress | Measures to Improve Transparency in the Gas Market | + | [22 empty] | n | Subject to passage of legislation

## Implem. schedule v5 - Final
National Energy Market and Gas Markets
Implementation Schedule |  | Key: | [40 empty] | Key:
|  |  |  | Pre-Production Test |  |  |  | Market Trial | [36 empty] | Pre-Production Test |  |  |  | Market Trial
|  | l | Production Date |  |  | ¨ | Schema Change |  |  |  |  | n | Technical Specifications | [6 empty] | u | Checkpoint (Production Readiness) | [5 empty] | ¡ | Data Model release | [14 empty] | l | Production Date |  |  | ¨ | Schema Change |  |  |  |  | n | Technical Specifications |  |  | u | Checkpoint (Production Readiness) |  |  |  | ¡ | Data Model release
Reform Initiative | 2021 | [40 empty] | 2022
| Jan |  |  |  | Feb |  |  | Mar |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  | Aug |  |  | Sep |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec | Jan |  |  |  | Feb |  |  | Mar |  |  | Apr |  |  | May |  | Jun |  | Jul |  | Aug |  |  | Sep | Oct | Nov |  | Dec | Jan
Five Minute Settlement (5MS) and Global Settlement
Bidding and Dispatch | Pre-Production Bidding and Dispatch | [9 empty] | l | Bidding Platform 1/4
Settlements | [9 empty] | Pre-Production Settlements | [6 empty] | l | Settlement Platform 17/5
Retail | [8 empty] | u | Checkpoint |  |  |  | Pre-Production Metering | [7 empty] | l | Metering Platform 21/6
[22 empty] | ¨ | Schema R39_P1
5MS Market | [24 empty] | 5MS Market Trial: 19/7-10/9 | [6 empty] | l | 5MS Market 1/10
Global Settlements | [49 empty] | GS Market Trial: proposed timing |  |  |  |  | l | Global Settlements 1/5
Reducing Customer Switching Times | [24 empty] | Pre-Production Industry Test | [6 empty] | l | Customer Switching 1/10
Wholesale Demand Response Mechanism | [21 empty] | l | WDR Registration Open 24/6 | [6 empty] | ¡ | EMMS data model 16/9 |  |  |  | l | WDR Rule Commencement 24/10
[19 empty] | n | Technical Specifications | [9 empty] | Pre-Production Industry Test
Electricity B2B changes | [31 empty] | Pre-Production Industry Test | [5 empty] | l | B2B Go-Live 10/11
[38 empty] | ¨ | Schema Change R41
Gas B2B changes (life support) | [15 empty] | Pre-Production R40 Recertification | [17 empty] | Pre-Production Industry Test | [5 empty] | l | Ghub 28/11 - 29/11
[40 empty] | ¨ | Schema Change R40
MSATS Standing Data Review (MSDR) | [54 empty] | l | New & Modified DATA Fields in MSATS 1/5 | [9 empty] | l | Deprecated Fields 1/11
[51 empty] | Pre-Production Industry Test | [13 empty] | Pre-Production Industry Test
DWGM Enhancements | [58 empty] | l | CC Auctions and Registry | [5 empty] | l | Markets Systems Deployment |  | l | Go Live
Notes:
5MS Staging available since December 2019
Global Settlements - Proposed timing of the market trial is from mid March 2022 to end of April 2022. This is to be reviewed and validated by 5MS stakeholder forums.
Electricity B2B changes - Electricity Validation Module (EVM) will be made available during the pre-production industry test period and by no later than 10 October 2021

## Schema changes v5 - final
Retail Go Live Roadmap |  |  |  | p | B2M/B2B Schema Release
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative | 2021 | [6 empty] | 2022 | [8 empty] | 2023
|  |  |  | Q1 |  | Q2 |  | Q3 | Q4 |  | Q1 | Q2 |  | Q3 |  |  | Q4 |  |  | Q1 | Q2 | Q3 | Q4
Schema Changes
Industry-wide | Market | Committed | Five Minute Settlement (5MS) and Global Settlement |  |  |  | p
Retail | Consumer | Committed | Reducing Customer Switching Times |  |  |  | p
Retail |  | Committed | Electricity B2B changes | [6 empty] | p
Retail |  | Committed | Gas B2B changes | [6 empty] | p
Retail | Operational | In progress | MSATS Standing Data Review (includes MCPI) | [9 empty] | p |  |  |  |  | p
Retail | Market | Proposed - Review | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | [10 empty] | p | if required
`
Retail | Market | Proposed - Review | Energy Consumer Data Right | [12 empty] | p | if required
Retail | Market | Proposed - Review | Review of Competition in Metering | [14 empty] | p | if required |  |  |  |  | p | if required
Note: |  | No schema changes required for WDR
|  | Customer Switching | Schema change made in June 2021 but effective from October 2021
Electricity B2B changes - v3.5 (business enhancements, schema changes) and v3.6 (Life support procedural and WDR B2B guide changes only)
AEMO notes schema releases in 2022 could be more aligned. Options for alignment will be explored once the scope and timing of initiatives have been firmed up.

## 5MS contingency scenario
PRECAUTIONARY CONTINGENCY SCENARIO - INCLUDED FOR INFORMATION AND SUBJECT TO AN AEMC RULE CHANGE REQUEST
National Energy Market and Gas Markets
Regulatory Implementation Roadmap |  |  |  |  | Key:
[6 empty] | Policy development/market design | [6 empty] | Rules development | [10 empty] | Procedure/guideline development
[6 empty] | Implementation - IT systems, processes | [6 empty] | Indicative IT implementation | [10 empty] | Engineering Implementation
[5 empty] | l | Committed Go-Live Date |  |  |  | p | Proposed Go-Live |  |  |  | n | Indicative Go-Live | [6 empty] | u | Estimated Go-Live | [6 empty] | + | Updated for version 5
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative |  | 2020 | [6 empty] | 2021 | [9 empty] | 2022 | [11 empty] | 2023 | [7 empty] | 2024 |  |  |  | 2025 |  |  |  | 2026
[5 empty] | Q1 |  | Q2 |  | Q3 | Q4 |  | Q1 | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | Q2 |  | Q3 | Q4 |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Five Minute Settlement (5MS) | + | [9 empty] | 5MS (IT platform) | l |  |  |  |  | l | AEMO rule change - go-live 1 Dec 2021
Retail | Consumer | Committed | Reducing Customer Switching Times | [16 empty] | l | AEMO rule change - bundle with 5MS go-live 1 Dec 2021
Industry-wide | Consumer | Committed | Wholesale Demand Response Mechanism | [16 empty] | l | AEMO rule change - bundle with 5MS go-live 1 Dec 2021
Retail | Consumer | Committed | Electricity B2B changes | [16 empty] | l | v3.5 and v3.6 updated to align with 5MS go-live on 1 Dec 2021
Industry-wide | Market | Committed | Global Settlements | + | [11 empty] | GS soft start |  |  |  | l |  |  | GS (extern) |  |  | l | AEMC final determination - go-live 1 May 2022
Gas |  | Committed | Gas B2B changes | [16 empty] | l | IN003/20 (business enhancements, schema uplift) - 29 Nov 2021
Retail | Consumer | Committed | Metering Coordinator Planned Interruptions (MCPI) | [22 empty] | l | AEMO notice to reschedule to 1 May 2022, bundled with MSDR
Retail | Operational | Committed | MSATS Standing Data Review (MSDR) | [21 empty] | v1 | l |  |  | v2 (small) |  |  | l | v1 AEMO consulted to reschedule to 1 May 2022, aligned with MCPI implementation
Retail | Market | In progress | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | + | [24 empty] | n | AEMC recommended implementation 12 months after law and rule changes made
Retail | Consumer | Proposed - Review | Energy Consumer Data Right | [26 empty] | n | Implementation dictated by Treasury timings, assumed to be Q3 2022
Retail | Consumer | In progress | Updating the Regulatory Frameworks for Embedded Networks | [33 empty] | u | Implementation based on understanding of current scope
Retail | Market | Proposed - Review | Review of Regulatory Framework for Metering Services | [28 empty] | u | (if required) | [6 empty] | u | IT implementation likely but not yet clear, dependent on review outcomes
Wholesale | Reliability | Proposed - Review | ST PASA - Replacement project and methodology update | [26 empty] | u | Estimated timing, subject to rule change process
Wholesale | Market | In progress | Integrating Energy Storage Systems (ESS) | + | [31 empty] | p
Wholesale | Security | Committed | Fast Frequency Response Market Ancillary Services (B) | + | [34 empty] | l | Rule change process co-ordinated with ESB initiatives.
Wholesale | Security | In progress | Primary Frequency Response Incentive Arrangements (B) | + | [17 empty] | Indicative Execution Range: Procedures, IT | [23 empty] | Rule change process co-ordinated with ESB initiatives.
Wholesale | Reliability | In progress | Operating Reserve Market (B) | + | [23 empty] | Indicative Execution Range: Procedures, IT | [15 empty] | Rule change process co-ordinated with ESB initiatives.
Wholesale | Security | In progress | Introduction of ramping services (B) | + | [23 empty] | Indicative Execution Range: Procedures, IT | [15 empty] | Rule change process co-ordinated with ESB initiatives.
Wholesale | Security | In progress | Synchronous Services Markets (B) | + | [23 empty] | Indicative Execution Range: Procedures, IT | [15 empty] | Rule change process co-ordinated with ESB initiatives.
Wholesale | Security | In progress | Capacity commitment mechanism for system security and reliability services (B) | + | [23 empty] | Indicative Execution Range: Procedures, IT | [15 empty] | Rule change process co-ordinated with ESB initiatives.
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Proposed - Review | Resource Adequacy Mechanisms and Ageing Thermal Generation (A)
Industry-wide | Market | Proposed - Review | Essential System Services, Scheduling and Ahead Mechanisms (B) | + | High Level Design | [6 empty] | Market Design |  |  |  |  | Indicative Execution Range: Legislation, Rules, Procedures, IT | [24 empty] | Extended Execution Range
Industry-wide | Security | Proposed - Review | Demand Side Participation (C)
Industry-wide | Market | Proposed - Review | Transmission and Access (D)
INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS
Wholesale | Security | Committed | Mandatory Primary Frequency Response |  |  |  |  | l | [7 empty] | Implementation timing shown is indicative and depends on individual generator circumstances, managed through the self-assessment process
Network |  | In progress | Technical Standards for Distributed Energy Resources | + | [16 empty] | l
Wholesale | Security | In progress | Efficient management of system strength on the power system (B) | + | [25 empty] | p |  |  |  |  | p
Wholesale |  | In progress | Generator Registrations and Connections | + | [19 empty] | p
Industry-wide |  | Committed | NEM Settlement in Zero and Negative Demand Conditions | + | [13 empty] | l
Network |  | In progress | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | + | [11 empty] | p
Network |  | Committed | Connection of Dedicated Connection Assets | [12 empty] | l
Network |  | Committed | Implementing a General Power System Risk Review | + | [17 empty] | l
Industry-wide |  | In progress | Enhancing Operational Resilience to Indistinct Events | +
Wholesale |  | Committed | Prioritising arrangements for system security during Market Suspension | +
ESB INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Renewable Energy Zones - Planning (Stage 1) (D) | + | [9 empty] | l
Industry-wide | Market | In progress | Renewable Energy Zones - Implementation (Stage 2) (D)
Wholesale | Security | Committed | Visibility and Security of Dispatch (Stage 1) - Interim | + | [8 empty] | l
Networks | Market | Proposed - Pending | Governance of DER Technical Standards | + | [17 empty] | Indicative timing, subject to rule change process
GAS INITIATIVES
Gas |  | Committed | DWGM simpler wholesale price | [29 empty] | l
Implemented as a single AEMO project
Gas |  | Committed | DWGM improvement to AMDQ regime | [28 empty] | l
Gas |  | In progress | Measures to Improve Transparency in the Gas Market | + | [22 empty] | n | Subject to passage of legislation

## Log of changes
Log of Changes
Roadmap Version | Date | Reform | Change
Version 4 - Draft | 2021-02-24 | Schema Changes v3 - final | Deleted 'Schema changes v3 - final' tab as schema changes are incorporated into implementation view - draft. Note, this reflects schema changes in 2021 only. The only schema changes beyond 2021 for which there is certainty is for MCPI/MSDR.
Version 4 - Draft | 2021-02-24 | Implementation Sch v4 - draft | Included 'Implementation Sch v4 - draft' tab. Note, while this is the first time the Implementation Schedule has been included, it has been named v4 to align with same iteration of the roadmap.
Version 4 - Draft | 2021-02-24 | 5MS | IT platform implementation delayed from 9 March 2021 to 31 May 2021
Version 4 - Draft | 2021-02-24 | Metering Coordinator Planned Interruptions | Rescheduled to 1 May 2022
Version 4 - Draft | 2021-02-24 | MSATS standing data review | Rescheduled to 1 May 2022
Version 4 - Draft | 2021-02-24 | Standalone Power Systems | Delayed indicative go-live date by 3 months to Mar 2022 given NEL amendments have not passed SA Parliament and assuming one year implementation. Updated status to 'in progress'.
Version 4 - Draft | 2021-02-24 | MT PASA | Completed in Dec 2020 - removed
Version 4 - Draft | 2021-02-24 | Updating the Regulatory Frameworks for Embedded Networks | Extended rule development phase until March 2021
Version 4 - Draft | 2021-02-24 | Review of Competition in Metering | Updated rule development phase to Oct 2021 to align with consultation paper and extended rule development phase (if required)
Version 4 - Draft | 2021-02-24 | ST PASA replacement and methodology update | Updated rule development phase to March - December 2021 and updated estimated go-live date to Q3 2022
Version 4 - Draft | 2021-02-24 | Energy Storage Systems | Updated status to 'in progress' as consultation has commenced
Version 4 - Draft | 2021-02-24 | Synchronous services | 3 month delay to rule change process, Final Determination expected 1 July 2021
Version 4 - Draft | 2021-02-24 | Operating Reserve Market | 6 month delay to rule change process, Final Determination expected 16 Sept 2021
Version 4 - Draft | 2021-02-24 | Fast Frequency Response Market Ancillary Services | Rule change process shortened by 2 months, Final Determination expected 15 July 2021
Version 4 - Draft | 2021-02-24 | Efficient management of system strength on the power system | 4 month delay to rule change process, Final Determination expected 21 July 2021
Version 4 - Draft | 2021-02-24 | Capacity commitment mechanism for system security and reliability services | 3 month delay to rule change process, Final Determination expected 1 July 2021
Version 4 - Draft | 2021-02-24 | Introduction of ramping services | 6 month delay to rule change process, Final Determination expected 16 Sept 2021
Version 4 - Draft | 2021-02-24 | Primary Frequency Response Incentive Arrangements | 6 month delay to rule change process, Draft Determination expected 16 Sept 2021, Final Determination expected 17 Dec 2021, indicative implementation date of 1 July 2023
Version 4 - Draft | 2021-02-24 | Generator Registrations and Connections | Included on roadmap. Rule change process initiated in October 2020, assumes rules development phase longer than standard process, draft determination expected June 2021
Version 4 - Draft | 2021-02-24 | System Strength Framework Review | Removed as review completed in Oct 2020, recommendations being progressed through Efficient management of system strength on the power system rule change
Version 4 - Draft | 2021-02-24 | Economy wide Cyber Security Strategy and Systems of National Security (Cth) | Renamed initiative to Protecting Critical Infrastructure and Systems of National Significance, renamed technical design phase to detailed design phase
Version 4 - Draft | 2021-02-24 | Two-Sided Market - Intermediate | Consolidate with DER integration (intermediate) and rename Demand Side Participation
Version 4 - Draft | 2021-02-24 | Ahead Market - Intermediate | Consolidate with System Security Services and rename Essential System Services & Scheduling & Ahead Mechanisms
Version 4 - Draft | 2021-02-24 | System Security Services - Intermediate | Consolidate with Ahead Market (Intermediate) and rename Essential System Services & Scheduling & Ahead Mechanisms
Version 4 - Draft | 2021-02-24 | DER Integration - Intermediate | Consolidate with Two-sided Market (Intermediate) and rename Demand Side Participation
Version 4 - Draft | 2021-02-24 | Coordination of Generation and Transmission Investment - Intermediate | Rename Transmission and Access (reflects congestion information, transition pathways and locational marginal pricing and financial transmission rights initiatives only)
Version 4 - Draft | 2021-02-24 | Capacity Mechanisms - Long Term | Consolidate with Thermal Generation Strategy (Long Term) and rename Resource Adequacy Mechanisms and Ageing Thermal Generation Strategy
Version 4 - Draft | 2021-02-24 | Thermal Generation Strategy - Long Term | Consolidate with Capacity Mechanisms (Long Term) and rename Resource Adequacy Mechanisms and Ageing Thermal Generation Strategy
Version 4 - Draft | 2021-02-24 | NEM settlements under zero and negative demand conditions | Included on roadmap. Rule change submitted in Feb 2021
Version 4 - Draft | 2021-02-24 | Connection of Dedicated Connection Assets | Included on roadmap.
Version 4 - Draft | 2021-02-24 | Implementing a General Power System Risk Review | Included on roadmap. Rule change process initiated in Feb 2021
Version 4 - Draft | 2021-02-24 | Enhancing Operational Resilience to Indistinct Events | Included on roadmap. Rule change process initiated in Dec 2020
Version 4 - Draft | 2021-02-24 | Prioritising arrangements for system security during Market Suspension | Included on roadmap. Rule change process initiated in Dec 2020
Version 4 - Draft | 2021-02-24 | System restart services, standards and testing | Completed - removed
Version 4 - Draft | 2021-02-24 | Guidelines to make ISP actionable | Completed - removed
Version 4 - Draft | 2021-02-24 | Reliability Measures - Interim | Completed - removed
Version 4 - Draft | 2021-02-24 | Renewable Energy Zones - Planning (Stage 1) | Stage 1 near completed, rules development process extended by 2 months awaiting Energy Ministers approval
Version 4 - Draft | 2021-02-24 | Renewable Energy Zones - Implementation (Stage 2) | Included on roadmap. Stage 2 policy developed commenced in Q4 2020, recommendations to Ministers expected April 2021, with draft rules consultation to follow
Version 4 - Draft | 2021-02-24 | Visibility and Security of Dispatch (Stage 1) - Interim | 3 month delay to rule change process, Final Determination expected 11 March 2021, status updated to 'in progress'
Version 4 - Draft | 2021-02-24 | Visibility and Security of Dispatch (Stage 2) - Interim | Policy development phase extended by two months, status updated to 'proposed - review'
Version 4 - Draft | 2021-02-24 | Minimum Mandatory DER Technical Standards - Interim | Renamed Technical Standards for Distributed Energy Resources, updated the rules development phase to align with draft determination, re-categorised as non-ESB initative with limited IT system implementation impacts
Version 4 - Draft | 2021-02-24 | Governance for DER Technical Standards | Included. Rule Change Request submitted in Sept 2020
Version 4 - Draft | 2021-02-24 | Cost Allocation Methodology - Inter-Regional Transmission - Interim | Removed
Version 4 - Draft | 2021-02-24 | Measures to Improve Transparency in the Gas Market | Delayed with Final Rules package to go to SA Parliament Q1 2021, go-live date Oct 2021, GBB and GSOO procedures have to be updated (prior to go-live date)
Version 4 - Final | 2021-03-18 | Connection of Dedicated Connection Assets | Delay to Final Determination, expected 8 July 2021
Version 4 - Final | 2021-03-18 | Review of Competition in Metering | Renamed Review of Regulatory Framework for Metering Services
Version 4 - Final | 2021-03-18 | Schema changes v4 - final | Reintroduction of schema changes tab for period 2021-2023
Version 4 - Final | 2021-03-18 | Implementation Sch v4 - final | Inclusion of a note to clarify for the wholesale demand response initiative, the ongoing availability of pre-production industry test environment following go-live.
Version 4 - Final | 2021-03-18 | Implementation Sch v4 - final | Inclusion of a note on the timing of the availability of EVM for Electricity B2B changes
Version 4 - Final | 2021-03-18 | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | Extended rule development phase until June 2021, as Energy Senior Officials consulting on rule amendments. Energy Ministers expected to approve final rule change package in mid 2021.
Version 4 - Final | 2021-03-18 | Fast Frequency Response Market Ancillary Services | Extended indicative execution range to mid 2024
Version 5 - Draft | 2021-07-09 | Five-minute settlement | Roadmap: Updated go-live date of IT platform to reflect retail MDM solution going live on 21 June 2021, established global settlements as separate line item
Version 5 - Draft | 2021-07-09 | Five-minute settlement | Schedule: Updated go-live date of metering IT platform to 21 June 2021, updated the 5MS market trial dates to 19 July - 10 September 2021 and updated pre-production period
Version 5 - Draft | 2021-07-09 | Wholesale Demand Response Mechanism | Schedule: Aligned pre-production test start with completion of 5MS market trial
Version 5 - Draft | 2021-07-09 | Global settlement | Established global settlements as separate line item
Version 5 - Draft | 2021-07-09 | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | Final rules are expected to be made by SA Minister in mid 2021
Version 5 - Draft | 2021-07-09 | Consumer Data Right | Extended rules development period by 3 months to Sep 2021
Version 5 - Draft | 2021-07-09 | Updating the Regulatory Frameworks for Embedded Networks | Extended rules development period to July 2021.
Version 5 - Draft | 2021-07-09 | ST PASA - Replacement project and methodology update | Extended rules development period by 2 months to Feb 2022
Version 5 - Draft | 2021-07-09 | Energy Storage Systems | Rules development period is assumed to continue to end of 2021, with Draft Determination extended until 29 July 2021
Version 5 - Draft | 2021-07-09 | Fast Frequency Response Market Ancillary Services | Updated for draft determination published on 22 April 2021 to reflect proposed go-live date of July 2024
Version 5 - Draft | 2021-07-09 | Primary Frequency Response Incentive Arrangements | Updated presentation of this rule change process to be consistent with other system services rule changes.
Version 5 - Draft | 2021-07-09 | Operating Reserve Market | Extended rules development period by 6 months, following extension of draft determination until 9 December 2021
Version 5 - Draft | 2021-07-09 | Introduction of ramping services | Extended rules development period by 6 months, following extension of draft determination until 9 December 2021
Version 5 - Draft | 2021-07-09 | Capacity commitment mechanism for system security and reliability services | Extended rules development period by 6 months, following extension of draft determination until 16 December 2021
Version 5 - Draft | 2021-07-09 | Synchronous services | Extended rules development period by 6 months, following extension of draft determination until 16 December 2021
Version 5 - Draft | 2021-07-09 | Efficient management of system strength on the power system | Draft determination (29 April 2021) proposed go-live dates of Sept 2022 and Mar 2023 included. Moved under limited IT systems impacts section
Version 5 - Draft | 2021-07-09 | Generator Registrations and Connections | Draft determination (24 June 2021) proposed go-live date of 30 Mar 2022 included. Moved under limited IT systems impacts section.
Version 5 - Draft | 2021-07-09 | Protecting Critical Infrastructure and Systems of National Security (Cth) | Removed. Reforms have broader application and are being managed through specialist forums.
Version 5 - Draft | 2021-07-09 | ESB Initiatives with IT System impacts | Extended Market Design period to July 2021 as ESB's Final Report is yet to be published
Version 5 - Draft | 2021-07-09 | Technical Standards for DER | Updated go-live date to 18 Dec 2021 as per Final Determination and Rule
Version 5 - Draft | 2021-07-09 | NEM Settlement in Zero and Negative Demand Conditions | Final Determination made on 17 June 2021, with implementation date of 1 Sept 2021. Updated status to committed
Version 5 - Draft | 2021-07-09 | Network Planning and Access for Distributed Energy Resources | Removed from roadmap. This rule change is considered concurrently with Access, Pricing and Incentive Arrangements for DER
Version 5 - Draft | 2021-07-09 | Allowing DNSPs to Charge for Exports to the Network | Removed from roadmap. This rule change is considered concurrently with Access, Pricing and Incentive Arrangements for DER
Version 5 - Draft | 2021-07-09 | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | Included proposed go-live date of 1 Jul 2021 as per Draft Determination, update when Final Determination is published on 8 July 2021
Version 5 - Draft | 2021-07-09 | Connection of Dedicated Connection Assets | Proposed go-live date of Jan 2022 as per Draft Determination (rule to commence 6 months after Final Determination). Update when Final Determination is published on 8 July 2021
Version 5 - Draft | 2021-07-09 | Implementing a General Power System Risk Review | Final Determination made on 3 June 2021, with implementation date of 10 January 2021. Status updated to committed.
Version 5 - Draft | 2021-07-09 | Enhancing Operational Resilience to Indistinct Events | Extended rules development period to Dec 2021 with Draft Determination delayed until 28 Oct 2021
Version 5 - Draft | 2021-07-09 | Prioritising arrangements for system security during Market Suspension | Final Determination made on 17 June 2021. No final rule made.
Version 5 - Draft | 2021-07-09 | Renewable Energy Zones - Planning (Stage 1) | Status updated to committed. Final Rules made by SA Energy Minister with commencement date of 13 May 2021
Version 5 - Draft | 2021-07-09 | Visibility and Security of Dispatch (Stage 1) - Interim | Status updated to committed. Final Determination made on 11 Mar 2021, with go-live on 12 Apr 2021
Version 5 - Draft | 2021-07-09 | Visibility and Security of Dispatch (Stage 2) - Interim | Removed from roadmap. Interim measures will not be progressed as superseded by other regulatory initiatives, in particular ESB initiatives
Version 5 - Draft | 2021-07-09 | Governance of DER Technical Standards | Extended rules development period by 6 months to Dec 2021. Rule change remains as pending
Version 5 - Draft | 2021-07-09 | Measures to Improve Transparency in the Gas Market | Extended rules development period to Dec 2021, with an indicative go-live date of mid-2022 based on DISER update
Version 5 - Draft | 2021-07-09 | 5MS Scenario - Draft | "5MS scenario - draft" presents 29 November 5MS go-live, bundled with other initiatives scheduled to commence in late 2021
Version 5 - Final | 2021-08-05 | Global settlement (financial start) | Implementation schedule updated to align global settlement market trial with MSATS standing data review preproduction industry test
Version 5 - Final | 2021-08-05 | Wholesale Demand Response Mechanism | Implementation schedule updated to reflect EMMS data model to be released 16 September
Version 5 - Final | 2021-08-05 | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | Extended rule development phase until August 2021. Energy Ministers expected to approve final rule change package in mid 2021.
Version 5 - Final | 2021-08-05 | Integrating Energy Storage Systems | Draft Determination made on 15 July. Proposed go-live date of 28 April 2023
Version 5 - Final | 2021-08-05 | Fast Frequency Response Market Ancillary Services | Final Determination made on 15 July. Committed go-live date of 9 October 2023
Version 5 - Final | 2021-08-05 | Connection of Dedicated Connection Assets | Final Determination made on 8 July. Committed go-live date of 22 July 2021
Version 5 - Final | 2021-08-05 | Prioritising arrangements for system security during Market Suspension | Final Determination made on 17 June 2021. No final rule made. Removed from roadmap
Version 5 - Final | 2021-08-05 | 5MS Contingency Scenario (for information only) | 5MS go-live 1 December 2021 as per AEMO's rule change request (short delay)
Version 5 - Final | 2021-08-05 | 5MS Contingency Scenario (for information only) | Reducing customer switching go-live 1 December 2021 as per AEMO's rule change request (short delay)
Version 5 - Final | 2021-08-05 | 5MS Contingency Scenario (for information only) | Wholesale demand response mechanism go-live 1 December 2021 as per AEMO's rule change request (short delay)
Version 5 - Final | 2021-08-05 | 5MS Contingency Scenario (for information only) | Electricity B2B changes go-live 1 December 2021 as per AEMO's rule change request (short delay)
Version 5 - Final | 2021-08-05 | 5MS Contingency Scenario (for information only) | Global Settlements (soft start) go-live 1 December 2021 as per AEMO's rule change request (short delay)

## Definitions
Definitions and Instructions for Regulatory Implementation Roadmap
Heading / Term | Definition and Instructions
Impacted Industry Sector | Indicates the primary section of the industry that is impacted by the regulatory change. If two sections of industry are impacted, choose the primary section. If more that two sections are impacted, choose 'Industry-wide'. Wholesale = Generation, Wholesale Market and/or Contracting impacted by the rule change Networks = Transmission and Distribution networks impacted by the rule change Retail = Retailers, other contestable service providers and/or customers are primarily impacted by the rule change Industry-wide = More that two sections of the industry are impacted by the rule change
Reform Status | Committed = Final determination made; and/or implementation in progress In progress = Rule change in process e.g. consultation and draft determination stages Proposed - Pending = Rule change has been proposed but not yet initiated Proposed - Review = Review underway but outcomes (including potential rule changes) not yet confirmed Note: A reference to rule change may also include a law change; or a reference to a review process where the outcome will be a law or rule change
Go-live Date Status | Committed = Go-live date decided in final rule determination Proposed = Go-live date proposed in draft rule determination Indicative = An indicative go-live date has been suggested by the proponent or foreshadowed during review process Estimated = AEMO estimated go-live date (where no proposed timeline currently exists)
Implementation Status | Policy development / market design = early stage of the reform process i.e. prior to a rule change process commencing Rules development = a rule change process is in progress i.e. from rule change request submitted through to final rule determination Procedure/Guideline development = Procedural changes are in progress or required to implement the rule change Implementation - IT systems, processes implementation and engineering implementation
Key IT regulatory projects | Signficant implementation impact = Medium or major IT/system capex project required to implement the rule change by AEMO and/or industry Strategic reform initiatives = Initiatives identified by COAG Energy Council and/or Energy Security Board
Include on Roadmap? | Yes - Material (i.e. High or Medium impact) IT, system or engineering implementation project Yes - Strategic Reform e.g. COAG EC priority No - Not Material or Strategic No - Complete
Definitions and Instructions for Detailed Implementation Schedule
Heading / Term | Definition and Instructions
Industry Test | Participants can get into the pre-prod environment and conduct unstructured tests as they see fit
Invitation industry Test | Where a subset of participants agree (on a volunteer basis) to participate in an Industry Test. AEMO does not develop formal scenarios, but participants conduct bilateral testing on an agreed basis
Market Trial | Where AEMO develops structured scenarios which are designed for widespread participation from our industry colleagues and structured to demonstrate/test particular scenarios. High effort required from all, generally reserved for new markets or big market changes (like 5MS)