## Version control
National Energy Market
Regulatory Implementation Roadmap
Version | Date | Description
v1.0 | 2020-04-17 | First draft for review with industry and consumers at stakeholder forum of 21 April 2020.
v2.0 | 2020-05-06 | Second iteration, following further AEMO internal review and participant feedback. Presented to stakeholder forum on 8 May 2020, and published as part of market bodies prioritisation advice on 17 May 2020.
v3.0 - draft | 2020-08-04 | Next iteration, incorporating AEMC final determinations on WDR and 5MS/GS deferral, and other updates for presentation to stakeholder forum on 10 August 2020.
v3.0 - final | 2020-08-31 | Finalised version 3, incorporating outcomes following stakeholder engagement in August 2020, including some additional minor updates.
v4.0 - draft | 2021-02-24 | Draft version 4, incorporating implementation delays to 5MS retail solution, Metering Coordinator Planned Interruptions and MSATS standing data review go-live and other updates, for presentation at stakeholder forum on 24 Feb 2021
v4.0 - final | 2021-03-18 | Finalised version 4, incorporates implementation schedule for 2021 and schema changes for 2021-23. Delays to 5MS retail solution, Metering Coordinator Planned Interruptions and MSATS standing data review go-live dates,and other updates.
v5.0 - draft | 2021-07-09 | Draft version 5, incorporating updates since version 4 including 5MS program and 5MS contingency scenario
v5.0 - final | 2021-08-05 | Final version 5 incorporates final and draft rules on fast frequency response and integrating energy storage systems respectively. 5MS contingency scenario updated in align with AEMO's rule change request.
v6.0 - draft | 2021-11-24 | Draft version 6 includes updates for MSATS standing data review, standalone power systems and consumer data right. Consolidation of the roadmap to remove initiatives that have been implemented.
v6.0 - final | 2021-12-22 | Final version 6 incorporates final and draft rules for integrating energy storage systems and ST PASA update, as well as initiatives identified for inclusion by stakeholders e.g. Electricity B2B changes v3.7. The rule change process has been extended for a number of key initiatives

## Roadmap v6 Final
National Energy Market and Gas Markets
Regulatory Implementation Roadmap | [10 empty] | Key:
[12 empty] | Policy development/market design | [11 empty] | Rules development | [8 empty] | Procedure/guideline development | [9 empty] | AEMO preferred
[12 empty] | Implementation - IT systems, processes | [11 empty] | Indicative IT implementation | [8 empty] | Engineering Implementation | [9 empty] | Implementation
[11 empty] | l | Committed Go-Live Date | [6 empty] | p | Proposed Go-Live | [5 empty] | n | Indicative Go-Live | [5 empty] | u | Estimated Go-Live | [5 empty] | + | Updated for version 6
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative |  | 2020 |  |  |  |  | 2021 | [9 empty] | 2022 | [10 empty] | 2023 | [9 empty] | 2024 | [6 empty] | 2025 |  |  |  | 2026
[5 empty] | Q1 | Q2 |  | Q3 | Q4 | Q1 |  | Q2 |  |  | Q3 |  | Q4 |  |  | Q1 |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | Q2 |  |  | Q3 |  | Q4 |  |  | Q1 |  | Q2 |  |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Five Minute Settlement (5MS) | [9 empty] | 5MS (IT platform) | l |  |  | l | AEMC final determination - go-live 1 Oct 2021
Retail | Consumer | Committed | Reducing Customer Switching Times | [13 empty] | l | Updated to align with 5MS go-live - 1 Oct 2021
Industry-wide | Consumer | Committed | Wholesale Demand Response Mechanism | [13 empty] | l | AEMC final determination - go live 24 Oct 2021
Retail | Consumer | Committed | Electricity B2B changes | [14 empty] | l | v3.5 and v3.6 - 10 Nov 2021
Gas |  | Committed | Gas B2B changes | [14 empty] | l | IN003/20 (business enhancements, schema uplift) - 29 Nov 2021
Industry-wide | Market | Committed | Global Settlements | [10 empty] | GS soft start |  |  | l |  |  |  | GS (extern) |  | l | AEMC final determination - go-live 1 May 2022
Retail | Consumer | Committed | Metering Coordinator Planned Interruptions (MCPI) | [19 empty] | l | AEMO notice to reschedule to 1 May 2022, bundled with MSDR
Retail | Operational | Committed | MSATS Standing Data Review (MSDR) | [18 empty] | v1 | l |  |  |  |  | v2 | l | v1 MCPI and schema for MSDR go-live 1 May 2022 and v2 majority of MSDR go-live 7 Nov 2022
Retail |  | Committed | Electricity B2B changes v3.7 | [25 empty] | l | v3.7 B2B changes go-live 7 Nov 2022
Retail | Market | In progress | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | + | [24 empty] | n | [5 empty] | AEMC recommended implementation 12 months after law and rule changes made
Retail | Consumer | Committed | Energy Consumer Data Right Rules | + | [23 empty] | T1 | l |  |  |  | T2 | l |  |  |  | T3 | l |  |  |  | T4 | l | CDR go-live has 4 tranches - 15 Nov 2022, 15 May 2023, 1 Nov 2023 and 1 May 2024
Retail |  | In progress | Energy Consumer Data Right (National Electricity Law and National Electricity Rules) | [21 empty] | Indicative only, subject to SA Parliament and Ministerial processes
Retail | Market | Proposed - Review | Review of Regulatory Framework for Metering Services | + | [39 empty] | u | Indicative only, dependent on review outcomes
Wholesale | Reliability | In progress | ST PASA - Replacement project and methodology update | + | [32 empty] | p | Subject to rule change process, earliest commencement is Q3 2023
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide |  | In progress | Resource Adequacy Mechanisms and Ageing Thermal Generation | + | [5 empty] | Market Design | [20 empty] | Indicative Execution Range, Legislation, Rules, Procedures, IT | [16 empty] | Extended Execution Range
Wholesale |  | In progress | MT PASA - Information Availability Enhancements | + | [31 empty] | Immediate ESB reform. Implementation planning co-ordinated through Reform Delivery Committee
Industry-wide | Market | In progress | Essential System Services, Scheduling and Ahead Mechanisms | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [23 empty] | Extended Execution Range
Wholesale | Security | Committed | Efficient management of system strength on the power system | + | [25 empty] | l |  | l
Wholesale | Security | Committed | Fast Frequency Response Market Ancillary Services | [34 empty] | l | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Primary Frequency Response Incentive Arrangements | + | [37 empty] | p |  |  |  |  | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Reliability | In progress | Operating Reserve Market | + | [36 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Introduction of ramping services | + | [36 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Synchronous Services Markets | [27 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through RDC
Wholesale | Security | In progress | Capacity commitment mechanism for system security and reliability services | [27 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through RDC
Industry-wide | Market | In progress | Demand Side Participation | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [23 empty] | Extended Execution Range
Wholesale | Market | Committed | Integrating Energy Storage Systems (IESS) | + | [27 empty] | l | [12 empty] | l
Industry-wide | Market | In progress | Transmission and Access | + | [5 empty] | Market Design | [20 empty] | Indicative Execution Range, Legislation, Rules, Procedures, IT | [16 empty] | Extended Execution Range
Industry-wide | Market | In progress | Renewable Energy Zones - Implementation (Stage 2) | + | [12 empty] | Final report published
Wholesale |  | In progress | Congestion Management Model | + | [26 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Initial ESB reform. Implementation planning co-ordinated through RDC
Network |  | Proposed - Review | Transmission Planning and Investment Review | + | [26 empty] | Subject to review process - stages 2 and 3 expected to be completed in Sept 2022 and Dec 2022
Network |  | In progress | Material change in network infrastructure project costs | + | [22 empty] | Subject to rule change process
INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS (including ESB initiatives)
Wholesale | Security | Committed | Mandatory Primary Frequency Response | + |  |  | l | [17 empty] | Implementation timing shown is indicative and depends on individual generator circumstances, managed through the self-assessment process
Network |  | Committed | Technical Standards for Distributed Energy Resources | [15 empty] | l
Wholesale |  | Committed | Generator Registrations and Connections | + | [17 empty] | l
Network |  | Committed | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | + | [11 empty] | l | [8 empty] | l
Network |  | Committed | Implementing a General Power System Risk Review | [16 empty] | l
Industry-wide |  | In progress | Enhancing Operational Resilience to Indistinct Events | + | [21 empty] | p
Networks | Market | In progress | Governance of DER Technical Standards | + | [17 empty] | Indicative timing, subject to rule change process
GAS INITIATIVES
Gas |  | Committed | DWGM simpler wholesale price | [26 empty] | l
Implemented as a single AEMO project
Gas |  | Committed | DWGM improvement to AMDQ regime | + | [25 empty] | l
Gas |  | In progress | Measures to Improve Transparency in the Gas Market | [25 empty] | n | Indicative only, subject to passage of legislation
Gas |  | Proposed - Review | Extending the Regulatory Framework to Hydrogen and Renewable Gases | +
Gas |  | In progress | DWGM Distribution Connected Facilities | +
INITIATIVES WITH LIMITED CERTAINTY
Retail | Consumer | In progress | Updating the Regulatory Frameworks for Embedded Networks | + | [35 empty] | u | Assumes rules development is re-initiated

## Implem. schedule v6 - Final
National Energy Market and Gas Markets
Implementation Schedule |  | Key: | [42 empty] | Key:
|  |  |  | Pre-Production Test |  |  |  | Market Trial | [38 empty] | Pre-Production Test |  |  |  | Market Trial
|  | l | Production Date |  |  | ¨ | Schema Change |  |  |  |  | n | Technical Specifications | [6 empty] | u | Checkpoint (Production Readiness) | [5 empty] | ¡ | Data Model release | [16 empty] | l | Production Date |  |  | ¨ | Schema Change |  |  |  | n | Technical Specifications |  |  |  | u | Checkpoint (Production Readiness) |  |  |  |  | ¡ | Data Model release
Reform Initiative | 2021 | [42 empty] | 2022
| Jan |  |  |  | Feb |  |  | Mar |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  | Aug |  |  | Sep |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  | Jan |  |  |  | Feb |  |  | Mar |  | Apr |  |  | May |  |  | Jun |  |  | Jul |  | Aug |  |  | Sep |  | Oct | Nov |  |  | Dec | Jan |  | Feb
Five Minute Settlement (5MS) and Global Settlement
Bidding and Dispatch | Pre-Production Bidding and Dispatch | [9 empty] | l | Bidding Platform 1/4
Settlements | [9 empty] | Pre-Production Settlements | [6 empty] | l | Settlement Platform 17/5
Retail | [8 empty] | u | Checkpoint |  |  |  | Pre-Production Metering | [7 empty] | l | Metering Platform 21/6
[22 empty] | ¨ | Schema R39_P1
5MS Market | [24 empty] | 5MS Market Trial: 19/7-10/9 | [6 empty] | l | 5MS Market 1/10
Global Settlements | [51 empty] | GS Market Trial: proposed timing |  |  |  | l | Global Settlements 1/5
Reducing Customer Switching Times | [24 empty] | Pre-Production Industry Test | [6 empty] | l | Customer Switching 1/10
Wholesale Demand Response Mechanism | [21 empty] | l | WDR Registration Open 24/6 | [6 empty] | ¡ | EMMS data model 16/9 |  |  |  | l | WDR Rule Commencement 24/10
[19 empty] | n | Technical Specifications | [9 empty] | Pre-Production Industry Test
Electricity B2B changes | [31 empty] | Pre-Production Industry Test | [5 empty] | l | B2B v3.5 and v 3.6 Go-Live 10/11 | [31 empty] | l | B2B v3.7 Go-Live 7/11
[38 empty] | ¨ | Schema Change R41
Gas B2B changes (life support) | [15 empty] | Pre-Production R40 Recertification | [17 empty] | Pre-Production Industry Test | [5 empty] | l | Ghub 28/11 - 29/11
[40 empty] | ¨ | Schema Change R40
[56 empty] | ¨ | Schema change R42
MSATS Standing Data Review (MSDR and MCPI) | [39 empty] | ¨ | Schema R42 | n | MCPI Tech Spec | [8 empty] | Pre-Production Industry Test |  |  |  | l | MCPI in MSATS and schema released 1/5 | [11 empty] | Pre-production ind test | l | New, amended and deprecated fields for MSDR 7/11
DWGM Enhancements | [57 empty] | Pre-Production Industry Test |  |  |  | l | Issue Auction Notice |  |  |  |  | Pre-Production Industry Test |  | l | Markets Systems Deployment (dormant) |  |  | l | Go Live (effective date 1/1)
Energy Consumer Data Right | [39 empty] | n | CDR Data Standards | [19 empty] | Pre-Production Avaliable | [8 empty] | l | CDR Tranche 1 Go-Live
[71 empty] | ¨ | if required
Notes:
Global Settlements - Timing of the market trial is from late March 2022 to end of April 2022 and coincides with MSDR industry test.
CDR - schedule based on draft CDR rules and subject to change

## Schema changes v6 - Final
Retail Go Live Roadmap |  |  |  | p | B2M/B2B Schema Release
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative | 2021 | [6 empty] | 2022 | [6 empty] | 2023
|  |  |  | Q1 |  | Q2 |  | Q3 | Q4 |  | Q1 | Q2 |  | Q3 | Q4 |  |  | Q1 | Q2 | Q3 | Q4
Schema Changes
Industry-wide | Market | Committed | Five Minute Settlement (5MS) and Global Settlement |  |  |  | p
Retail | Consumer | Committed | Reducing Customer Switching Times |  |  |  | p
Retail |  | Committed | Electricity B2B changes | [6 empty] | p
Retail |  | Committed | Gas B2B changes | [6 empty] | p
Retail | Operational | In progress | MSATS Standing Data Review (includes MCPI) | [9 empty] | p
Retail | Market | In progress | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | [12 empty] | p | if required
`
Retail | Market | In progress | Energy Consumer Data Right | [12 empty] | p | if required
Notes: |  | CDR - if schema changes are a co-requisite requirement, these will be bundled with MSDR MSATS changes.

## Roadmap v6 Draft
National Energy Market and Gas Markets
Regulatory Implementation Roadmap | [10 empty] | Key:
[12 empty] | Policy development/market design | [11 empty] | Rules development | [8 empty] | Procedure/guideline development | [8 empty] | AEMO preferred
[12 empty] | Implementation - IT systems, processes | [11 empty] | Indicative IT implementation | [8 empty] | Engineering Implementation | [8 empty] | Implementation
[11 empty] | l | Committed Go-Live Date | [6 empty] | p | Proposed Go-Live | [5 empty] | n | Indicative Go-Live | [5 empty] | u | Estimated Go-Live |  |  |  |  | + | Updated for version 6
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative |  | 2020 |  |  |  |  | 2021 | [9 empty] | 2022 | [10 empty] | 2023 | [8 empty] | 2024 | [6 empty] | 2025 |  |  |  | 2026
[5 empty] | Q1 | Q2 |  | Q3 | Q4 | Q1 |  | Q2 |  |  | Q3 |  | Q4 |  |  | Q1 |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | Q2 |  |  | Q3 | Q4 |  |  | Q1 |  | Q2 |  |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Five Minute Settlement (5MS) | [9 empty] | 5MS (IT platform) | l |  |  | l | AEMC final determination - go-live 1 Oct 2021
Retail | Consumer | Committed | Reducing Customer Switching Times | [13 empty] | l | Updated to align with 5MS go-live - 1 Oct 2021
Industry-wide | Consumer | Committed | Wholesale Demand Response Mechanism | [13 empty] | l | AEMC final determination - go live 24 Oct 2021
Retail | Consumer | Committed | Electricity B2B changes | [14 empty] | l | v3.5 and v3.6 - 10 Nov 2021
Gas |  | Committed | Gas B2B changes | [14 empty] | l | IN003/20 (business enhancements, schema uplift) - 29 Nov 2021
Industry-wide | Market | Committed | Global Settlements | [10 empty] | GS soft start |  |  | l |  |  |  | GS (extern) |  | l | AEMC final determination - go-live 1 May 2022
Retail | Consumer | Committed | Metering Coordinator Planned Interruptions (MCPI) | [19 empty] | l | AEMO notice to reschedule to 1 May 2022, bundled with MSDR
Retail | Operational | Committed | MSATS Standing Data Review (MSDR) | [18 empty] | v1 | l |  |  |  |  | v2 | l | v1 MCPI and schema for MSDR go-live 1 May 2022 and v2 majority of MSDR go-live 7 Nov 2022
Retail | Market | In progress | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | + | [24 empty] | n | [5 empty] | AEMC recommended implementation 12 months after law and rule changes made
Retail | Consumer | In progress | Energy Consumer Data Right | + | [23 empty] | T1 | l |  |  |  | T2 | l |  |  | T3 | l |  |  |  | T4 | l | CDR go-live has 4 tranches - 15 Nov 2022, 15 May 2023, 1 Nov 2023 and 1 May 2024
Retail | Market | Proposed - Review | Review of Regulatory Framework for Metering Services | + | [38 empty] | u | IT implementation likely but not yet clear, dependent on review outcomes
Wholesale | Reliability | In progress | ST PASA - Replacement project and methodology update | + | [22 empty] | n | Estimated timing, subject to rule change process
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide |  | In progress | Resource Adequacy Mechanisms and Ageing Thermal Generation | + | [5 empty] | Market Design | [20 empty] | Indicative Execution Range, Legislation, Rules, Procedures, IT | [15 empty] | Extended Execution Range
Wholesale |  | In progress | MT PASA - Information Availability Enhancements | + | [31 empty] | Immediate ESB reform. Implementation planning co-ordinated through Reform Delivery Committee
Industry-wide | Market | In progress | Essential System Services, Scheduling and Ahead Mechanisms | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Wholesale | Security | Committed | Efficient management of system strength on the power system | + | [25 empty] | l |  | l
Wholesale | Security | Committed | Fast Frequency Response Market Ancillary Services | [33 empty] | l | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Primary Frequency Response Incentive Arrangements | + | [36 empty] | p |  |  |  |  | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Reliability | In progress | Operating Reserve Market | + | [35 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Introduction of ramping services | + | [35 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Synchronous Services Markets | [21 empty] | Indicative Execution Range: Procedures, IT | [19 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Capacity commitment mechanism for system security and reliability services | [21 empty] | Indicative Execution Range: Procedures, IT | [19 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Industry-wide | Market | In progress | Demand Side Participation | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Wholesale | Market | In progress | Integrating Energy Storage Systems (IESS) | + | [28 empty] | p | [10 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Industry-wide | Market | In progress | Transmission and Access | + | [5 empty] | Market Design | [20 empty] | Indicative Execution Range, Legislation, Rules, Procedures, IT | [15 empty] | Extended Execution Range
Industry-wide | Market | In progress | Renewable Energy Zones - Implementation (Stage 2) | + | [12 empty] | Final report published
Wholesale |  | In progress | Congestion Management Model | + | [26 empty] | Indicative Execution Range: Procedures, IT | [15 empty] | Initial ESB reform. Implementation planning co-ordinated through RDC
Network |  | Proposed - Review | Transmission Planning and Investment Review | + | [17 empty] | Subject to review process
INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS (including ESB initiatives)
Wholesale | Security | Committed | Mandatory Primary Frequency Response | + |  |  | l | [17 empty] | Implementation timing shown is indicative and depends on individual generator circumstances, managed through the self-assessment process
Network |  | In progress | Technical Standards for Distributed Energy Resources | [15 empty] | l
Wholesale |  | Committed | Generator Registrations and Connections | + | [17 empty] | l
Network |  | Committed | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | + | [11 empty] | l | [8 empty] | l
Network |  | Committed | Implementing a General Power System Risk Review | [16 empty] | l
Industry-wide |  | In progress | Enhancing Operational Resilience to Indistinct Events | + | [21 empty] | p
Networks | Market | In progress | Governance of DER Technical Standards | + | [17 empty] | Indicative timing, subject to rule change process
GAS INITIATIVES
Gas |  | Committed | DWGM simpler wholesale price | [26 empty] | l
Implemented as a single AEMO project
Gas |  | Committed | DWGM improvement to AMDQ regime | + | [25 empty] | l
Gas |  | In progress | Measures to Improve Transparency in the Gas Market | [20 empty] | n | Subject to passage of legislation
Gas |  | Proposed - Review | Extending the Regulatory Framework to Hydrogen and Renewable Gases | +
INITIATIVES WITH LIMITED CERTAINTY
Retail | Consumer | In progress | Updating the Regulatory Frameworks for Embedded Networks | + | [34 empty] | u | Assumes rules development is re-initiated

## Previous View (hidden)
National Energy Market and Gas Markets
Regulatory Implementation Roadmap | [10 empty] | Key:
[12 empty] | Policy development/market design | [12 empty] | Rules development | [9 empty] | Procedure/guideline development
[12 empty] | Implementation - IT systems, processes | [12 empty] | Indicative IT implementation | [9 empty] | Engineering Implementation
[11 empty] | l | Committed Go-Live Date | [6 empty] | p | Proposed Go-Live | [6 empty] | n | Indicative Go-Live | [5 empty] | u | Estimated Go-Live |  |  |  | + | Updated for version 6
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative |  | 2020 |  |  |  |  | 2021 | [9 empty] | 2022 | [11 empty] | 2023 | [7 empty] | 2024 |  |  |  |  | 2025 |  |  |  | 2026
[5 empty] | Q1 | Q2 |  | Q3 | Q4 | Q1 |  | Q2 |  |  | Q3 |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  | Q2 |  | Q3 | Q4 |  |  | Q1 |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Five Minute Settlement (5MS) | [9 empty] | 5MS (IT platform) | l |  |  | l | AEMC final determination - go-live 1 Oct 2021
Retail | Consumer | Committed | Reducing Customer Switching Times | [13 empty] | l | Updated to align with 5MS go-live - 1 Oct 2021
Industry-wide | Consumer | Committed | Wholesale Demand Response Mechanism | [13 empty] | l | AEMC final determination - go live 24 Oct 2021
Retail | Consumer | Committed | Electricity B2B changes | [14 empty] | l | v3.5 and v3.6 - 10 Nov 2021
Gas |  | Committed | Gas B2B changes | [14 empty] | l | IN003/20 (business enhancements, schema uplift) - 29 Nov 2021
Industry-wide | Market | Committed | Global Settlements | [10 empty] | GS soft start |  |  | l |  |  |  | GS (extern) |  |  | l | AEMC final determination - go-live 1 May 2022
Retail | Consumer | Committed | Metering Coordinator Planned Interruptions (MCPI) | [20 empty] | l | AEMO notice to reschedule to 1 May 2022, bundled with MSDR
Retail | Operational | Committed | MSATS Standing Data Review (MSDR) | [19 empty] | v1 | l |  |  |  |  | v2 | l | v1 MCPI and schema for MSDR go-live 1 May 2022 and v2 majority of MSDR go-live 7 Nov 2022
Retail | Market | In progress | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | + | [25 empty] | n | AEMC recommended implementation 12 months after law and rule changes made
Retail | Consumer | In progress | Energy Consumer Data Right | + | [24 empty] | T1 | l | [6 empty] | T2 | l | CDR rules go-live Nov 2022 and Nov 2023
Retail | Market | Proposed - Review | Review of Regulatory Framework for Metering Services | + | [33 empty] | u | IT implementation likely but not yet clear, dependent on review outcomes
Wholesale | Reliability | In progress | ST PASA - Replacement project and methodology update | + | [23 empty] | n | Estimated timing, subject to rule change process
Wholesale | Market | In progress | Integrating Energy Storage Systems (IESS) (C) | [30 empty] | p | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | Committed | Fast Frequency Response Market Ancillary Services (B) | [33 empty] | l | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Primary Frequency Response Incentive Arrangements (B) | + | [36 empty] | p | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Reliability | In progress | Operating Reserve Market (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Introduction of ramping services (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Synchronous Services Markets (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
Wholesale | Security | In progress | Capacity commitment mechanism for system security and reliability services (B) | [22 empty] | Indicative Execution Range: Procedures, IT | [16 empty] | Implementation planning co-ordinated through Reform Delivery Committee
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide |  | In progress | Resource Adequacy Mechanisms and Ageing Thermal Generation (A) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
Industry-wide | Market | In progress | Essential System Services, Scheduling and Ahead Mechanisms (B) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
Industry-wide | Market | In progress | Demand Side Participation (C) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
Industry-wide | Market | In progress | Transmission and Access (D) | + | [5 empty] | Market Design | [6 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [22 empty] | Extended Execution Range
Immediate:
Initial:
INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS (including ESB initiatives)
Wholesale | Security | Committed | Mandatory Primary Frequency Response |  |  |  | l | [18 empty] | Implementation timing shown is indicative and depends on individual generator circumstances, managed through the self-assessment process
Network |  | In progress | Technical Standards for Distributed Energy Resources | [15 empty] | l
Wholesale | Security | Committed | Efficient management of system strength on the power system (B) | + | [26 empty] | l |  | l
Wholesale |  | Committed | Generator Registrations and Connections | + | [17 empty] | l
Network |  | Committed | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | + | [11 empty] | l | [9 empty] | l
Network |  | Committed | Implementing a General Power System Risk Review | [16 empty] | l
Industry-wide |  | In progress | Enhancing Operational Resilience to Indistinct Events | + | [22 empty] | p
Industry-wide | Market | In progress | Renewable Energy Zones - Implementation (Stage 2) (D)
Networks | Market | In progress | Governance of DER Technical Standards | + | [18 empty] | Indicative timing, subject to rule change process
GAS INITIATIVES
Gas |  | Committed | DWGM simpler wholesale price | [27 empty] | l
Implemented as a single AEMO project
Gas |  | Committed | DWGM improvement to AMDQ regime | + | [26 empty] | l
Gas |  | In progress | Measures to Improve Transparency in the Gas Market | [21 empty] | n | Subject to passage of legislation
Gas |  | Proposed - Review | Extending the Regulatory Framework to Hydrogen and Renewable Gases | +
INITIATIVES WITH LIMITED CERTAINTY
Retail | Consumer | In progress | Updating the Regulatory Frameworks for Embedded Networks | + | [34 empty] | u | Assumes rules development is re-initiated

## Log of changes
Log of Changes
Roadmap Version | Date | Reform | Change
Version 5 - Draft | 2021-07-09 | Five-minute settlement | Roadmap: Updated go-live date of IT platform to reflect retail MDM solution going live on 21 June 2021, established global settlements as separate line item
Version 5 - Draft | 2021-07-09 | Five-minute settlement | Schedule: Updated go-live date of metering IT platform to 21 June 2021, updated the 5MS market trial dates to 19 July - 10 September 2021 and updated pre-production period
Version 5 - Draft | 2021-07-09 | Wholesale Demand Response Mechanism | Schedule: Aligned pre-production test start with completion of 5MS market trial
Version 5 - Draft | 2021-07-09 | Global settlement | Established global settlements as separate line item
Version 5 - Draft | 2021-07-09 | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | Final rules are expected to be made by SA Minister in mid 2021
Version 5 - Draft | 2021-07-09 | Consumer Data Right | Extended rules development period by 3 months to Sep 2021
Version 5 - Draft | 2021-07-09 | Updating the Regulatory Frameworks for Embedded Networks | Extended rules development period to July 2021.
Version 5 - Draft | 2021-07-09 | ST PASA - Replacement project and methodology update | Extended rules development period by 2 months to Feb 2022
Version 5 - Draft | 2021-07-09 | Energy Storage Systems | Rules development period is assumed to continue to end of 2021, with Draft Determination extended until 29 July 2021
Version 5 - Draft | 2021-07-09 | Fast Frequency Response Market Ancillary Services | Updated for draft determination published on 22 April 2021 to reflect proposed go-live date of July 2024
Version 5 - Draft | 2021-07-09 | Primary Frequency Response Incentive Arrangements | Updated presentation of this rule change process to be consistent with other system services rule changes.
Version 5 - Draft | 2021-07-09 | Operating Reserve Market | Extended rules development period by 6 months, following extension of draft determination until 9 December 2021
Version 5 - Draft | 2021-07-09 | Introduction of ramping services | Extended rules development period by 6 months, following extension of draft determination until 9 December 2021
Version 5 - Draft | 2021-07-09 | Capacity commitment mechanism for system security and reliability services | Extended rules development period by 6 months, following extension of draft determination until 16 December 2021
Version 5 - Draft | 2021-07-09 | Synchronous services | Extended rules development period by 6 months, following extension of draft determination until 16 December 2021
Version 5 - Draft | 2021-07-09 | Efficient management of system strength on the power system | Draft determination (29 April 2021) proposed go-live dates of Sept 2022 and Mar 2023 included. Moved under limited IT systems impacts section
Version 5 - Draft | 2021-07-09 | Generator Registrations and Connections | Draft determination (24 June 2021) proposed go-live date of 30 Mar 2022 included. Moved under limited IT systems impacts section.
Version 5 - Draft | 2021-07-09 | Protecting Critical Infrastructure and Systems of National Security (Cth) | Removed. Reforms have broader application and are being managed through specialist forums.
Version 5 - Draft | 2021-07-09 | ESB Initiatives with IT System impacts | Extended Market Design period to July 2021 as ESB's Final Report is yet to be published
Version 5 - Draft | 2021-07-09 | Technical Standards for DER | Updated go-live date to 18 Dec 2021 as per Final Determination and Rule
Version 5 - Draft | 2021-07-09 | NEM Settlement in Zero and Negative Demand Conditions | Final Determination made on 17 June 2021, with implementation date of 1 Sept 2021. Updated status to committed
Version 5 - Draft | 2021-07-09 | Network Planning and Access for Distributed Energy Resources | Removed from roadmap. This rule change is considered concurrently with Access, Pricing and Incentive Arrangements for DER
Version 5 - Draft | 2021-07-09 | Allowing DNSPs to Charge for Exports to the Network | Removed from roadmap. This rule change is considered concurrently with Access, Pricing and Incentive Arrangements for DER
Version 5 - Draft | 2021-07-09 | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | Included proposed go-live date of 1 Jul 2021 as per Draft Determination, update when Final Determination is published on 8 July 2021
Version 5 - Draft | 2021-07-09 | Connection of Dedicated Connection Assets | Proposed go-live date of Jan 2022 as per Draft Determination (rule to commence 6 months after Final Determination). Update when Final Determination is published on 8 July 2021
Version 5 - Draft | 2021-07-09 | Implementing a General Power System Risk Review | Final Determination made on 3 June 2021, with implementation date of 10 January 2021. Status updated to committed.
Version 5 - Draft | 2021-07-09 | Enhancing Operational Resilience to Indistinct Events | Extended rules development period to Dec 2021 with Draft Determination delayed until 28 Oct 2021
Version 5 - Draft | 2021-07-09 | Prioritising arrangements for system security during Market Suspension | Final Determination made on 17 June 2021. No final rule made.
Version 5 - Draft | 2021-07-09 | Renewable Energy Zones - Planning (Stage 1) | Status updated to committed. Final Rules made by SA Energy Minister with commencement date of 13 May 2021
Version 5 - Draft | 2021-07-09 | Visibility and Security of Dispatch (Stage 1) - Interim | Status updated to committed. Final Determination made on 11 Mar 2021, with go-live on 12 Apr 2021
Version 5 - Draft | 2021-07-09 | Visibility and Security of Dispatch (Stage 2) - Interim | Removed from roadmap. Interim measures will not be progressed as superseded by other regulatory initiatives, in particular ESB initiatives
Version 5 - Draft | 2021-07-09 | Governance of DER Technical Standards | Extended rules development period by 6 months to Dec 2021. Rule change remains as pending
Version 5 - Draft | 2021-07-09 | Measures to Improve Transparency in the Gas Market | Extended rules development period to Dec 2021, with an indicative go-live date of mid-2022 based on DISER update
Version 5 - Draft | 2021-07-09 | 5MS Scenario - Draft | "5MS scenario - draft" presents 29 November 5MS go-live, bundled with other initiatives scheduled to commence in late 2021
Version 5 - Final | 2021-08-05 | Global settlement (financial start) | Implementation schedule updated to align global settlement market trial with MSATS standing data review preproduction industry test
Version 5 - Final | 2021-08-05 | Wholesale Demand Response Mechanism | Implementation schedule updated to reflect EMMS data model to be released 16 September
Version 5 - Final | 2021-08-05 | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | Extended rule development phase until August 2021. Energy Ministers expected to approve final rule change package in mid 2021.
Version 5 - Final | 2021-08-05 | Integrating Energy Storage Systems | Draft Determination made on 15 July. Proposed go-live date of 28 April 2023
Version 5 - Final | 2021-08-05 | Fast Frequency Response Market Ancillary Services | Final Determination made on 15 July. Committed go-live date of 9 October 2023
Version 5 - Final | 2021-08-05 | Connection of Dedicated Connection Assets | Final Determination made on 8 July. Committed go-live date of 22 July 2021
Version 5 - Final | 2021-08-05 | Prioritising arrangements for system security during Market Suspension | Final Determination made on 17 June 2021. No final rule made. Removed from roadmap
Version 5 - Final | 2021-08-05 | 5MS Contingency Scenario (for information only) | 5MS go-live 1 December 2021 as per AEMO's rule change request (short delay)
Version 5 - Final | 2021-08-05 | 5MS Contingency Scenario (for information only) | Reducing customer switching go-live 1 December 2021 as per AEMO's rule change request (short delay)
Version 5 - Final | 2021-08-05 | 5MS Contingency Scenario (for information only) | Wholesale demand response mechanism go-live 1 December 2021 as per AEMO's rule change request (short delay)
Version 5 - Final | 2021-08-05 | 5MS Contingency Scenario (for information only) | Electricity B2B changes go-live 1 December 2021 as per AEMO's rule change request (short delay)
Version 5 - Final | 2021-08-05 | 5MS Contingency Scenario (for information only) | Global Settlements (soft start) go-live 1 December 2021 as per AEMO's rule change request (short delay)
Version 6 - Draft | 2021-11-24 | MSATS Standing Data Review | Note updated to reflect change of scope of v1 and v2 MSDR changes. v1 MCPI and schema for MSDR and v2 majority of MSDR.
Version 6 - Draft | 2021-11-24 | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | Updated proposed go-live date to November 2022, consistent with AEMC's recommendation of 12 month implementation window following law/rules being made. Included AEMO's preferred implementation timeframe
Version 6 - Draft | 2021-11-24 | Energy Consumer Data Right | Updated CDR implementation for final CDR rules (published 15 Nov 2021). Staggered commencement in four tranches - 15 Nov 2022, 15 May 2023, 1 Nov 2023 and 1 May 2024. CDR included on implementation schedule.
Version 6 - Draft | 2021-11-24 | Updating the Regulatory Frameworks for Embedded Networks | Moved to bottom of roadmap as initiative has limited certainty regarding regulatory process. Former COAG EC agreed to further consider AEMC's recommendations. Response being prepared for Energy Ministers consideration.
Version 6 - Draft | 2021-11-24 | Review of Regulatory Framework for Metering Services | Updated review timeframes based on AEMC notification on 18 November 2021 that review would have a short pause and recommence in April 2022. Rule change process indicative only.
Version 6 - Draft | 2021-11-24 | ST PASA - Replacement project and methodology update | Extended rules development phase to March 2022 as per AEMC consultation paper (26 Aug 2021)
Version 6 - Draft | 2021-11-24 | MT PASA - Information Availability Enhancements | Included MT PASA rule change process, noting this is an immediate reform identified by the ESB. AEMO submitted rule change request on 15 Dec 2021.
Version 6 - Draft | 2021-11-24 | Primary Frequency Response Incentive Arrangements | Draft determination (16 Sept 2021) proposed go-live date of March 2024. Included AEMO's preferred implementation timeframe
Version 6 - Draft | 2021-11-24 | Operating Reserve Market | Extended rule development phase until end of 2023 to reflect AEMC's notice to extend draft determination until 30 June 2023.
Version 6 - Draft | 2021-11-24 | Introduction of ramping services | Extended rule development phase until end of 2023 to reflect AEMC's notice to extend draft determination until 30 June 2023.
Version 6 - Draft | 2021-11-24 | Integrating Energy Storage Systems | Included AEMO's preferred implementation timeframe.
Version 6 - Draft | 2021-11-24 | Interim Framework for Renewable Energy Zones - Implementation (Stage 2) | Updated to reflect final report published in June 2021.
Version 6 - Draft | 2021-11-24 | Congestion Management Model | Included on the roadmap. Timeframes align with ESB's transmission access reform project initiation paper (published 18 November 2021)
Version 6 - Draft | 2021-11-24 | Transmission Planning and Investment Review | Included on the roadmap. Timeframes align with Consultation Paper (published 19 August 2021)
Version 6 - Draft | 2021-11-24 | Mandatory Primary Frequency Response | Extended engineering implementation given significant number of renewable generators are yet to implement changes for MPFR
Version 6 - Draft | 2021-11-24 | Efficient management of system strength on the power system | Final Determination made on 21 October 2021, with effective dates of 1 December 2022 and 15 March 2023. Status updated to committed.
Version 6 - Draft | 2021-11-24 | Generator Registrations and Connections | Final Determination made on 21 October 2021, with implementation date of 21 April 2022. Status updated to committed.
Version 6 - Draft | 2021-11-24 | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | Final Determination made on 12 August 2021, with implementation dates of 19 August 2021 and 1 July 2022. Status updated to committed.
Version 6 - Draft | 2021-11-24 | Enhancing Operational Resilience to Indistinct Events | Draft Determination made on 28 October 2021 with proposed go-live date of 18 August 2022. Final Determination and Rule expected in February 2022.
Version 6 - Draft | 2021-11-24 | Governance of DER Technical Standards | Updated to reflect timeframes set out in AEMC consultation paper (2 Sept 2021). Status updated to "in progress"
Version 6 - Draft | 2021-11-24 | DWGM improvement to AMDQ regime | Updated go-live date to December 2022 (minor error correction)
Version 6 - Draft | 2021-11-24 | Extending the Regulatory Framework to Hydrogen and Renewable Gases | Review commenced on 21 October 2021 and is expected to be completed by November 2022. This currently includes DWGM distribution connected facilitites rule change.
Version 6 - Draft | 2021-11-24 | Five-minute settlement | Removed as initiative has been implemented
Version 6 - Draft | 2021-11-24 | Customer switching | Removed as initiative has been implemented
Version 6 - Draft | 2021-11-24 | Wholesale Demand Response | Removed as initiative has been implemented
Version 6 - Draft | 2021-11-24 | Electricity B2B procedures | Removed as initiative has been implemented
Version 6 - Draft | 2021-11-24 | NEM Settlement in Zero and Negative Demand Conditions | Removed as initiative has been implemented
Version 6 - Draft | 2021-11-24 | Connection of Dedicated Connection Assets | Removed as initiative has been implemented
Version 6 - Draft | 2021-11-24 | Renewable Energy Zones - Planning (Stage 1) | Removed as initiative has been implemented
Version 6 - Draft | 2021-11-24 | Visibility and Security of Dispatch (Stage 1) - Interim | Removed as initiative has been implemented
Version 6 - Final | 2021-12-22 | Electricity B2B procedures changes v3.7 | Included B2B Procedures v3.7 changes as some participant systems require changes on both roadmap and the implementation schedule
Version 6 - Final | 2021-12-22 | Energy Consumer Data Right (National Electricity Law and National Electricity Rules) | Updated to present CDR NEL and NER amendments as a separate line item
Version 6 - Final | 2021-12-22 | ST PASA - Replacement project and methodology update | Updated for draft determination published on 2 December 2021. Go-live date uncertain, earliest commencement is Q3 2023
Version 6 - Final | 2021-12-22 | Primary Frequency Response Incentive Arrangements | Extended rules development phase to 7 July 2022 to reflect AEMC's notice to extend final determination. Commencement date retained as March 2024 as well as AEMO's preferred go-live date of Sept 2024
Version 6 - Final | 2021-12-22 | Synchronous services market | Extended rules development phase until end of 2022 to reflect AEMC's notice to extend draft determination until 30 June 2022
Version 6 - Final | 2021-12-22 | Capacity commitment mechanism for system security and reliability services | Extended rules development phase until end of 2022 to reflect AEMC's notice to extend draft determination until 30 June 2022
Version 6 - Final | 2021-12-22 | Integrating Energy Storage Systems | Final Determination made on 2 December 2021, with an early implementation date of 31 March 2023 and a go-live date of 4 June 2024
Version 6 - Final | 2021-12-22 | Transmission Planning and Investment Review | Updated review timeframes based on AEMC notification on 2 December 2021 of a revised approach and information provided at 13 December directions forum
Version 6 - Final | 2021-12-22 | Material Change in Network Infrastructure Project Costs | Included this rule change request as a separate line item, noting that this has been progressed in parallel with the transmission planning and investment review
Version 6 - Final | 2021-12-22 | Measures to Improve Transparency in the Gas Market | Extended rules development phase to May 2022 given delay in legislative package being passed by SA Parliament.
Version 6 - Final | 2021-12-22 | DWGM Distribution Connected Facilities | Included DWGM distribution connected facilities on the roadmap

## Definitions
Definitions and Instructions for Regulatory Implementation Roadmap
Heading / Term | Definition and Instructions
Impacted Industry Sector | Indicates the primary section of the industry that is impacted by the regulatory change. If two sections of industry are impacted, choose the primary section. If more that two sections are impacted, choose 'Industry-wide'. Wholesale = Generation, Wholesale Market and/or Contracting impacted by the rule change Networks = Transmission and Distribution networks impacted by the rule change Retail = Retailers, other contestable service providers and/or customers are primarily impacted by the rule change Industry-wide = More that two sections of the industry are impacted by the rule change
Reform Status | Committed = Final determination made; and/or implementation in progress In progress = Rule change in process e.g. consultation and draft determination stages Proposed - Pending = Rule change has been proposed but not yet initiated Proposed - Review = Review underway but outcomes (including potential rule changes) not yet confirmed Note: A reference to rule change may also include a law change; or a reference to a review process where the outcome will be a law or rule change
Go-live Date Status | Committed = Go-live date decided in final rule determination Proposed = Go-live date proposed in draft rule determination Indicative = An indicative go-live date has been suggested by the proponent or foreshadowed during review process Estimated = AEMO estimated go-live date (where no proposed timeline currently exists)
Implementation Status | Policy development / market design = early stage of the reform process i.e. prior to a rule change process commencing Rules development = a rule change process is in progress i.e. from rule change request submitted through to final rule determination Procedure/Guideline development = Procedural changes are in progress or required to implement the rule change Implementation - IT systems, processes implementation and engineering implementation
Key IT regulatory projects | Signficant implementation impact = Medium or major IT/system capex project required to implement the rule change by AEMO and/or industry Strategic reform initiatives = Initiatives identified by COAG Energy Council and/or Energy Security Board
Include on Roadmap? | Yes - Material (i.e. High or Medium impact) IT, system or engineering implementation project Yes - Strategic Reform e.g. COAG EC priority No - Not Material or Strategic No - Complete
Definitions and Instructions for Detailed Implementation Schedule
Heading / Term | Definition and Instructions
Industry Test | Participants can get into the pre-prod environment and conduct unstructured tests as they see fit
Invitation industry Test | Where a subset of participants agree (on a volunteer basis) to participate in an Industry Test. AEMO does not develop formal scenarios, but participants conduct bilateral testing on an agreed basis
Market Trial | Where AEMO develops structured scenarios which are designed for widespread participation from our industry colleagues and structured to demonstrate/test particular scenarios. High effort required from all, generally reserved for new markets or big market changes (like 5MS)