## Slide 1: Five-Minute Settlement Program: Executive Forum 2
AEMO 5MS Program Team
MONDAY 10 SEPTEMBER 2018
For information only – meeting not held

## Slide 2: Agenda
NO | Time | AGENDA ITEM | Responsible
1 | - | Minutes and actions from previous meeting | Peter Geers (AEMO)
2 | - | Program update | Graeme Windley (AEMO)
3 | - | Industry risks & issues | Graeme Windley (AEMO)
 | - | 1-on-1 engagement | Chris Muffett (AEMO)
5 | - | Small participant engagement | Chris Muffett (AEMO)
6 | - | Forward meeting plan | Peter Geers (AEMO)

## Slide 3: Minutes and actions from previous meeting
Peter Geers

## Slide 4: Previous meeting
Executive Forum met on Wednesday 18 July 2018
Meeting pack and notes from the meeting are published at: http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement/Program-Management/Executive-Forum
No actions identified during the meeting

## Slide 5: Program update
Graeme Windley

## Slide 6: High-level status
Procedures work is progressing well, with all activities on track:
  Working groups and focus groups have been constructive
Systems work is ramping up:
  Stakeholder engagement has commenced
  Development work to commence in Q4 2018
Rule changes:
  Global settlement draft determination published 30 August
  Potential additional rule change to address drafting amendments – as agreed, this will be considered as part of the procedure activities
Stakeholder engagement is proceeding:
  Procedure and System Working Groups meeting regularly
  Program Consultative Forum held its 3rd meeting on 3 September
  1-on-1 discussions have been held

## Slide 7: Industry risks & issues
Graeme Windley

## Slide 8: Summary
Latest risk/issue register included with meeting pack
Risk/issue register is published on 5MS Program Consultative Forum page: http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement/Program-Management/Program-Consultative-Forum
AEMO welcomes any feedback from the Executive Forum on the risks & issues

## Slide 9: Risk/issue updates
Two risks added following PWG:
  R08: Procedure changes arising from IT activities
  R09: Future rule changes could affect the implementation of 5MS
Two issues closed following PCF discussions:
  I02: Small participant engagement (covered by R01)
  I03: Competing projects, impact on stakeholders (covered R06)
Industry champions nominated:
  R01: Small participant engagement
  R06: Interaction with other industry changes

## Slide 10: 1-on-1 discussions
Chris Muffett

## Slide 11: 1-on-1 discussions
AEMO has held discussions with a cross-section of participants, to understand:
  How participants are going about preparing for 5MS?
  Are there other risks and issues which need to considered?
  Is AEMO’s program helpful for participants?
Feedback received indicates:
  Participants are at different stages of development
  Several learnings from Power of Choice program have been taken on board (particularly starting early)
  Working with external software partners and service providers has some challenges
  Regular 1-on-1 meetings with AEMO are worthwhile
Next steps:
  AEMO is considering whether to publish a summary
  Proposing to conduct an online survey in October

## Slide 12: Small participant engagement
Chris Muffett

## Slide 13: Engagement approach
AEMO is engaging in order to:
  Keep participants updated with program status
  Consultation on procedure changes
  Develop IT changes
  Facilitate industry readiness
  Help participants understand their obligations and changes requires
The primary method of engagement is through multiple levels of forums/working groups:
  Executive Forum (EF)
  Program Consultative Forum (PCF)
  Working Groups (PWG, SWG & RWG)
  Focus Groups

## Slide 14: Resource-constrained stakeholders
AEMO recognises the engagement approach can be resource intensive, if stakeholders engage at all levels
  This is not practical for smaller participants and potential new entrants
A summary document (included in the meeting pack) has been provided to help outline the supporting activities and methods of engagement that smaller participants can use to achieve each of the objectives
AEMO welcomes feedback on the approach, and if there’s any other activities to consider

## Slide 15: Forward meeting plan
Peter Geers

## Slide 16: Further information
Global Settlement rule change:
  AEMC website: https://www.aemc.gov.au/rule-changes/global-settlement-and-market-reconciliation
AEMO 5MS Program contacts:
  Graeme Windley, 5MS Program Manager
  Chris Muffett, 5MS Business Lead
  Emily Brodie, 5MS Procedure Lead
  Hamish McNeish, 5MS Systems Lead
  Gary Eisner, 5MS Stakeholder Liaison
Contact details:
  5MS email: 5ms@aemo.com.au
  5MS webpage: http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement

## Slide 17: Upcoming meetings
Next Executive Forum:
  Tuesday 13 November
Program Consultative Forums:
  Thursday 4 October
Next Procedure Working Group:
  Thursday 13 September
Next Systems Working Group:
  Monday 17 September
Meetings and forum dates: http://www.aemo.com.au/-/media/Files/Electricity/NEM/5MS/5MS-2018-Industry-Meeting-Schedule---External-Version.xlsx