## Slide 1: 5MS & GS Executive Forum #12
Thursday 25 March 2021
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law ​ Meeting Protocol​
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.​
Participants in AEMO discussions must: ​
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion ​
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO​
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol​
Participants in AEMO meetings must not discuss or agree on the following topics:​
Which customers they will supply or market to​
The price or other terms at which Participants will supply​
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid​
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)​
Refusing to supply a person or company access to any products, services or inputs they require​
​
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
No. | Time | Agenda Item | Presenter
1 | 10:00 – 10:05 | Welcome, Introductions and Apologies | Violette Mouchaileh
2 | 10:05 – 10:10 | Minutes and Actions | Violette Mouchaileh
3 | 10:10 – 10:30 | Program Update | Rowena Leung
4 | 10:30 -10:50 | Readiness Dashboard | Greg Minney
5 | 10:50 – 11:00 | Cost Recovery | Antara Mascarenhas
6 | 11:00 – 11:10 | Key Industry Risks and Issues | Peter Carruthers
7 | 11:10 – 11:20 | Regulatory Implementation Roadmap | Peter Carruthers
8 | 11:20 – 11:40 | General Questions | Violette Mouchaileh
9 | 11:40 – 11:45 | Meeting Close | Violette Mouchaileh

## Slide 4: Welcome
Violette Mouchaileh

## Slide 5: Action Items
No. | Status | Action | Comments
11.6.1 | Closed | AEMO to add 5MS, Customer Switching and WDR approach to managing interdependency risk to the March Executive Forum Agenda. | To be covered during this session

## Slide 6: Program Update
Rowena Leung

## Slide 7: 5MS & GS Program Timeline
Current as at 05-03-2021

## Slide 8: 5MS Program – IT Systems Status
Stream | Status | Commentary
Retail |  | AEMO is targeting a Retail Go-Live timeline for the 31-May-21 with regular checkpoints with the PCF and a fall-back date of up to 21 June 21. The next slide provides detail on the status of the Retail Go-Live measured against 31-May and the March checkpoint status as presented to PCF on 18-Mar-21
Dispatch |  | On schedule for 01-Apr-21 go-live Industry Test period completed Industry go-live plan finalised
Settlements |  | Cutover of Settlements release into pre-production on 19-Mar-21 as scheduled to commence Settlements industry test period on track for 22 Mar 21 Additional testing of the new Settlements solution with the current MDM solution progressing Overall, no significant defects or issues, high level of confidence in product for 30-minute functionality - progressive testing on 5-minute functionality continuing Independent certification of settlements calculations complete. Parallel run complete. Performance testing and cutover activities are underway. Industry go-live plan issued for review by RWG. Final version due 01-Apr-21
Overall AEMO Status |  | Overall, the AEMO 5MS program remains Amber. Although good progress has been made across all workstreams and we are tracking to the re-baselined schedule, the Retail workstream remains Amber.
 | Go-live date impacted
 | At risk
 | On schedule

## Slide 9: Approach to Retail Status Updates
18-Feb PCF
Forward Planning for Retail
Update on Interim Checkpoint Criteria Status
08-Apr
18-Mar PCF
March Checkpoint Criteria – assessment and outcomes
Pre-prod – status and go/no-go date
Production go-live – checkpoint date and criteria, go/no-go date
Pre-Prod Go/No-Go email
19-Apr
Retail Industry Testing Commences
12-May [TBC]
Retail Go/No-Go Communicated to PCF via email
23-Apr PCF
April Checkpoint Criteria - assessment and outcomes
Go/No-Go – confirm date
19-May PCF
Confirming Go/No-Go
Issue management
Replanning (if necessary)
31-May
5MS Retail/ Metering Solution Go-Live
Key milestones
Communication timeline

## Slide 10: March Retail checkpoint status
Criteria | Status | Commentary
Enterprise Azure migration successfully completed |  | Successfully completed.
Build for critical defects completed | Target achieved | Build/test for known/back-log critical defects completed on schedule Focus is now on fixing defects as they arise.
Target execution of test cases achieved, with no critical defects that cannot be remedied for 31 May go-live | Open | UAT testing has progressed but is behind target Blockers encountered during February, but have now been cleared and E2E operation is stabilising
Successful completion of Dress Rehearsal (DR2B) |  | Successfully completed
Pre-Production environment established |  | Successfully completed.
Performance remediation for RM11 & RM16 completed, no new performance blockers | Open | Remediation of RM11/16 satisfactory for go-live completed. Remediation of internal operational reports underway.
Overall |  | AEMO is satisfied that the checkpoint criteria have been sufficiently progressed to maintain a Retail go-live target date of 31-May-21 and 21 June fallback date. Pre-prod deployment is on track for 19-Apr-21. Go/No-Go email will be issued 08-Apr-21. Checkpoint path will continue to be followed with the next checkpoint at PCF on 23-Apr-21

## Slide 11: April Retail Checkpoint Criteria
Criteria represent activities scheduled for completion by first week of April.
Aim is to fully meet all criteria. If criteria not met, remedies to be developed and implications assessed before any change to 31 May target go-live date.
Pre-prod go/no-go date is 8 April – industry to be notified via email.
Criteria​ | Description
Testing | All UAT test cases executed with no critical defects that cannot be remedied for 31 May go-live.
Solution Stability | End-to-end solution operating stably in Test with no process blockers or unexplainable pauses/interruptions to processing.
Remediation | Known remediation work (internal reports performance, business activity monitoring) completed and remediation for any new defects scheduled.
Performance | “Day in the Life Testing” completed with no performance issues identified that cannot be remedied for 31 May go-live.
Pre-Production | Data migration on track and no blockers to meeting criteria/schedule for pre-production deployment.
Industry Test | On track to commence Retail Industry Test on 19 April.

## Slide 12: Readiness Dashboard
Greg Minney

## Slide 13: 5MS Rule Commencement Round 6
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
Activity | Status | Comments
AEMO Business Readiness for 5MS and GS (Part A) |  | Bidding platform operating successfully in Industry test, on schedule for 1 April Go-live. Retail Platform go-live rescheduled to 31 May, Settlements platform rescheduled to 17 May. Rescheduling of platform deliveries is not expected to impact 5MS Rule commencement or 5MS market trials.
Essential Industry Capabilities for 5MS commencement (Part A) |  | On track for 1 Oct 21 commencement Metering Data Providers and MPs reporting on track with minor exceptions. Generators reporting on-track delivery.
Summary: 5MS Rule Commencement |  | Overall Industry and AEMO components of essential capability currently on track for 5MS Rule commencement.
Other industry capabilities for 5MS and GS (Part B) |  | Other Participant readiness activities proceeding in line with 5MS rule commencement. Individual participant readiness risks noted in regards Global Settlement population activities. No systemic issues noted
On track
On track
On track
On track
Risk 1
Risk 2
Risk 1
*** round 6- as at 8/3

## Slide 14: Part A 5MS Essential Capability
Responsible Participant | Essential Criteria | Status | Comments
Generator | Generators and MNSPs are able to submit 5-min offers |  | 16/17 Generators representing 95% of NEM volume reporting on-track. 15/17 intend to participate in Market Trials. Average program completion in range 50-74%. 12/17 intend to commence 5 minute bidding within transition period.
MP, MC | All essential meters* are able to produce and store 5-min data |  | 9/10 MPs reporting on track, 1 MP reporting “late” with identified remediation Rollout plans received for 99% of Tranche 1 meters, with all plans indicating completion prior to 1 October, 30% of meters currently 5 minute capable
MDP | All essential meters* are able to deliver 5-min metering data |  | 3/3 MDPs for Essential meters are reporting programs on track. Rollout plans (due 1 May) to be used to validate responses
AEMO | The 5-minute bidding and dispatch solution, including the web bidding interface is deployed |  | AEMO platform deployed for Industry test, on track for 1 April production deployment.
 | The Metering Data Management (MDM) solution is deployed |  | Mitigation Action: Retail Platform Deployment rescheduled to 31 May, criteria rated Amber to reflect the increase in delivery risk
 | The 5-minute settlements solution is deployed |  | AEMO Settlement Platform deployment rescheduled to 17th May. Industry test period extended to reflect changed order of platform deployment. Certification testing of platform successfully completed
Summary - Essential Criteria | - | - | All components on track for delivery at 5MS rule commencement, AEMO Metering rating reflects shift in planned go-lives and subsequent compression of transitional activity.
On track
On track
On track
On track
Risk 1
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
On track
Risk 1
Risk 2
*** Round 6 – as at 8/3
On track

## Slide 15: Part B – Other Industry Capabilities
Responsible Participant | Criteria | Status | Comments
Retailer | Receive and process 5-minute metering data. Receive and process 5-minute settlement data. |  | All responding retailers (18, representing 95% of retail load) reporting ‘On track’. 17/18 retailers plan to participate in Market trials. 6/18 intend to perform in Bi-Lateral Testing. 18/18 ‘On-track’ for 5 min settlement data, with 2 late for UFE Allocation
DNSP | Receive and process 5-minute metering data. |  | 10/10 DNSPs reporting ‘On track’ to receive 5-minute data and planning on participating in market trials.
 | Provide GS metering and standing data updates (incl. NCONUML). |  | 10/10 DNSPs reporting ‘On track’ with average program completion of 50-74% GS Standing Data updates reported as ‘On track’ (including NCONUML). Type 7 Metering Data “On Track” 1 Participant reporting ‘At-risk’ for the delivery of NCONUML,
TNSP | Receive and process 5-minute metering data |  | 6/6 TNSPs reporting ‘On track' to receive 5-minute data 2/6 have the intention to receive 5-minute data prior to the Rule commencement date
 | Provide GS metering and standing data updates |  | 6/6 reporting ‘On track’.
MDP | Provide 5-minute metering data T1-3 distribution connected meters, type 7 meters. |  | 16/17 MDPs reporting ‘On track’, representing 100% coverage of Tranche 1 NMIS 1 participant ‘At risk’, recovery plan is in place 17/17 MDPs report ‘On track’ for the delivery of interval metering data by 1 October, including 1 MDP flagging “A risk” for delivery of T1-3 customer meters
 | Provide type 4, 4A, Vic Ami metering data at 5-minute granularity by 1 December 2022 |  | Majority of Roll-out scheduled to commence 3rd quarter of 2021. Rollout plans requested from impacted participants by 1 March 2021 100% of MDPs reporting ‘On track’ for interval meter delivery by Rule commencement.
 | Provide basic metering data for tier 1 NMIs to AEMO. |  | 3 MDPs reporting ‘Completed’, 6 MDPs reporting “On Track” 1 MDP reporting ‘Late’, with plan to commence delivery prior to 1 Oct
MP, MC | All T1-3,4* meters are able to produce and store 5-minute data. |  | 18 /19 MPs representing tranche 1 meters reporting ‘On track’, 1 reporting ‘Late’ with a stated remediation plan 16 Rollout plans covering 93% of tranche 1 meters received, 25% of tranche 1 meters currently 5 minute capable.
Summary | - | - | Overall summary “on track” , no systemic issues identified, individual exceptions noted
*** Round 6 – as at 8/3
On track
On track
On track
On track
On track
On track

## Slide 16: Cost Recovery
Antara Mascarenhas

## Slide 17: Financial Consultative Committee
AEMO has initiated a Financial Consultative Committee (FCC) for more structured consultation on AEMO’s annual budget and fees.
  The 2021/22 FCC is an interim Committee, for review after this financial year.
Role: provide review and advice, through the FCC, to inform the AEMO Board’s decision.
Membership:
  AEMO sought industry nominees through industry associations (AEC, CEC, ENA);
  Energy Consumers Australia will represent consumers;
  Jurisdictions have been invited as observers.
Meeting schedule: 3-4 meetings from April-May 2021.
Stakeholders will also have the opportunity to provide feedback through the public consultation process.

## Slide 18: Key Industry Risks and Issues
Peter Carruthers

## Slide 19: Summary
The last Executive Forum has been tracking three key risks.
The purpose of this slide is to summarise key changes to these risks:
  No remaining contingency for Retail Solution deployment
    Converted to an issue. This remains a “high” status issue.
    As set out in the Program Update section, this issue is being actively managed by AEMO and monitored through checkpoint criteria with monthly updates being provided to PCF.
  Volume of regulatory change
    Further actions outlined in the section on Regulatory Implementation Roadmap have been completed.
    This remains a “significant” risk.
  Participant and AEMO readiness
    Changes to status outlined in section on Readiness Dashboard. Risk remains “medium” for industry readiness and “significant” for AEMO readiness
    AEMO will continue to track industry readiness through readiness surveys
    AEMO readiness being tracked and managed as set out in previous section
Industry Risks and Issues Register is reviewed quarterly with PCF – next review is scheduled for 23-April-21

## Slide 20: Regulatory Roadmap Update
Peter Carruthers

## Slide 21: Regulatory Implementation Roadmap
Regulatory Implementation Roadmap forum conducted on 24 Feb 2021
  Previous version (V3) was published in August 2020
  Updated roadmap presented
  Detailed Implementation Schedule for 2021 added
Participant feedback received
  Questions at the forum and 4 written feedback items
Regulatory Implementation Roadmap V4.0 and 2021 Implementation Schedule published 18 March 2021, with stakeholder response document
  Roadmap reviewed 2 – 3 times per year, or if significant timeline changes occur
  https://aemo.com.au/en/initiatives/major-programs/regulatory-implementation-roadmap

## Slide 22: General Questions
Violette Mouchaileh

## Slide 23: Upcoming Executive Forums
Date | Topics
07-Jul-21 | Market Trial Update Debrief on systems deployment Readiness Reporting incl update against Rule commencement criteria
02-Sep-21 | Rule Commencement review Market Trial results summary Preparing for 1 October 2021 – Industry Go-Live Plan
For discussion: Is the current schedule sufficient?

## Slide 24: Upcoming meetings
Current as at 24/03/2021
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement