## Consultations Calendar
2024 Gas and Electricity Retail Consultations |  |  | Q4 2023 | [12 empty] | Q1 2024 | [12 empty] | Q2 2024 | [12 empty] | Q3 2024 | [12 empty] | Q4 2024
Last updated: 13 March 2024 |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
This spreadsheet is indicative only. Please refer to AEMO's website for authoritative consultation dates. |  | Cat | W1 | W2 | W3 | W4 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5
 | time axis 2023-10-02 to 2024-12-30
Gas
2023 Package 5- (IN002-23 plus others) RoLR changes Effective 1 May 2024 | bar: 2023-10-02; 2023-10-30; 2024-05-06
2023 Package 3A-(IN007-22 plus others) Modifications to HVZs and the HV information that AEMO provides in Victoria. Target effective 1 May 2024* |  | P,S | bar: 2023-10-02 to 2023-10-16; 2023-11-06 to 2023-11-27; 2023-12-18
2023 Package 3B- (IN007-21 plus others) Victorian Hydrogen integration includes DCF and AEMC Victorian hydrogen review changes (Vic - DWGM) 1 May 2024* | bar: 2023-10-02 to 2023-10-16; 2023-11-06 to 2023-11-27; 2023-12-18
2023 Package 6 (WA RMP changes) | bar: 2024-03-11 to 2024-03-25; 2024-04-15 to 2024-04-22; 2024-05-06 to 2024-05-27; 2024-06-24 to 2024-08-26; 2024-09-16
2023 Package 4- (IN006-23) Renewable Gas Integration (excluding Victoria) for STTM and Non STTM markets) (QLD, SA and NSW/ACT - STTM) 3 March 2025*
Electricity
MSATS, Metering Services, and Metrology
Metering Services Review (MSR)
B2M Package 1 (Accelerating smart meter rollout) |  | P,S | 2024-05-06: Expected to commence in May 2024, exact timings dependent on the AEMC's associated Rule Change process
B2M Package 2 (Testing/Inspections/Exemptions) |  | P | 2024-08-05: Expected to commence in August 2024, exact timings dependent on the AEMC's associated Rule Change process
B2M Retailer of Last Resort (RoLR) and Industry Change Forms (ICFs) |  | P,S | 2024-04-01: Expected to commence Q2 2024, exact timings TBD
Business to Business (B2B)
Metering Services Review (MSR)
B2B Package 1 (Accelerating smart meter rollout) |  | P,S
B2B Package 2 (Testing/Inspections/Exemptions) |  | N/A
B2B Retailer of Last Resort (RoLR) and Industry Change Forms (ICFs) |  | P,S | 2024-04-01: Expected to commence Q2 2024, exact timings TBD
Legend
Gas | Electricity
GMI | Initial consult
PPC | Draft det
IIR | Final det
AEMO Decision | IEC Recom
ERA Review / Approval (WA only) | AEMO Decision
Effective date
AEMO Review | AEMO Review
Consultation is completed
Consultation is withdrawn or postponed for current program of work
"Green text" = added post prioritisation session
Catagory= "P" = Procedure, "S" = System, "G" Guideline, "R" = Rules, "TBA" To be advised
* - see GAS Package details tab for more information about the changes
Click to view the National Energy Market (NEM) Reform Implementation Roadmap
-------LATEST CONSULTATION TIMELINE WINDOW | TIMING TO BE ADVISED -----
---------------------POST IIR DATES TENTATIVE - TO BE CONFIRMED ------------------

## GAS Package details
Package id# | IN# | Description
2023 Package 3A | IN007-22 | Modifications to HVZs and the HV information that AEMO provides in Victoria (Proponent Minister/DELWP) targeting 1 May 2024
2023 Package 3A | IN015-22 | Harmonise the definition of Heating Value within east coast RMP (As noted in AEMO final report on HB and Renewable Gases Procedures Review) (Proponent AEMO)
2023 Package 3B | IN007-21 | Victorian Hydrogen integration (AEMC rule changes). (Proponent AEMC). Vic (DWGM). Effective 1 May 2024
2023 Package 3B | IN017-22 | VIC RMPs changes pertaining to HB Distribution Connected facilities (DCF) (Proponent AEMC). Effective 1 May 2024
2023 Package 5 | IN012-22 | RoLR T1005 transaction - Decommissioned MIRNs without Meters (Proponent AEMO).
2023 Package 5 | IN009-22 | The RoLR provision (section 6.14A to 6.23) within the CSV Data format Specification need updating to reflect new delivery method (Proponent AEMO).
2023 Package 5 | IN003-23 | Add equivalent NSW-ACT RMPs (Clause 7.2.1. b) into the SA RMP for error corrections when a RoLR event occurs (Proponent AEMO).
2023 Package 5 | IN002-23 | Adding additional fields to the existing T1010 RoLR file. (Proponent Origin Energy). [Secretariat note: This has been assigned IN002/23]
2023 Package 5 | IN008-17 | Include SA RoLR process flows (Proponent AEMO).
2023 Package 5 | IN008-20 | AEMO has identified and issues with section 2.1.17 of the ICD. It retales to circumstances / concept of a participant GBO-ID becoming “suspended”. AGL raised this Issue
2023 Package 4 | IN006-23 | Renewable Gas Integration (excluding Victoria) for STTM and Non STTM markets) (Proponent AEMC). QLD, SA and NSW/ACT (STTM). Effective 3 Mar 2025
2023 Package 6 | IN002-22W | Potential gap with clause 377B (2).
2023 Package 6 | IN002-21W | Anticipated Annual Consumption in WA. (Proponent AEMO).
2023 Package 6 | IN009-20W | Possible typographical error in append 4 (Auditor’s deed of undertaking) clause 9 of WA RMP. Reference to clause 359 should be clause 358.
2023 Package 6 | IN002-23W | Minor documentation errors with WA Technical Protocol​
2023 Package 6 | IN001-24W | Correct clause numbering in Appendix 2 of WA RMP
Partially Committed Packages
2024 Package 1 | TBA
2024 Package 2 | TBA

## Disclaimer
Please note: this consultations calendar is intended only as a rough guide of when AEMO will hold consultations. The dates are indicative only and are subject to change without notice. It will be updated only periodically, so there is no guarantee that the information contained therein is current. Authoritative consultation dates are published either in the relevant distribution lists for the consultative forums or in the Consultations section of AEMO's website:
Link