## Slide 1: PROGRAM CONSULTATIVE FORUM Meeting pack
DATE: Thursday 11 August 2017
TIME: 9.00 AM – 10.30 PM (AEST)
VENUE: AEMO OFFICES; MEL, SYD, ADE, BRI
TELECONFERENCE: DIAL IN: 1800 055 132; PIN: 35475394
CONTACT: poc@aemo.com.au

## Slide 2: Power of Choice PROGRAM UPDATE

## Slide 3: Actions from previous meeting
# | Description | Date due | Status | Owner | Comments/Outcomes
A04 | M Norris to share copy of Ergon’s handbook to other attendees. | 07 Jul 17 | Closed | Ergon | 
A05 | LNSPs to circulate to all retailers draft’s T&C’s (per 11.86.7 of the new Rules) and any associated publications that they are developing (for example a ‘Retailer Handbook’) with industry. | 07 Jul 17 18 Aug 17 | Open | ActewAGL D | • Currently in the final stages of drafting the T&Cs, plan to circulate 18 August.
 |  | 07 Jul 17 | Open | Ausgrid | • Will be released at the start of next week (WC 31 July)
 |  | 07 Jul 17 | Open | AusNet Services | • Targeting to publish the draft T&Cs in mid-August
 |  | 07 Jul 17 | Open | CitiPower PC | • Targeting to publish the T&Cs for comment in mid-August
 |  | 07 Jul 17 | Open | Endeavour Energy | • Published 17 July for comment, close date 28 July.
 |  | 07 Jul 17 | Open | Energex & Ergon | • Will be circulating mid to late August.
 |  | 07 Jul 17 | Open | Essential Energy | • T&Cs are currently being reviewed by legal and should be published by mid-August
 |  | 07 Jul 17 | Open | SA Power Net | • Working on these internally, expect to publish in late August
 |  | 07 Jul 17 | Open | Jemena Networks | • Jemena’s commercial area is having discussions with retailers and the draft is being released through that process between mid to end of August
 |  | 07 Jul 17 | Open | TasNetworks | • T&Cs are currently under a final legal review, hoping to release by mid-August
 |  | 07 Jul 17 | Open | United Energy | • T&Cs also under a final review, and plan to release mid-August
A06 | Industry Test Lead to report at next PCF on progress of testing. | 04 Jul 17 24 Aug 17 | Open | AEMO (ITWG Lead) | • Note: report on first days of market trial
A07 | B. Healy to circulate test results publishing on HPQC. | 07 Jul 17 | Closed | AEMO | • Circulated via email on date 23 Jun 17
A08 | Testing results to be included in PCF pack monthly | 04 Jul 17 | Closed | AEMO | • Circulated via email on date 23 Jun 17
A09 | AEMO to speak to AEMC regarding communications, potentially with the AER. | 04 Jul 17 | Closed | AEMO | • AER/AEMC/AEMO have discussed the possibility of a joint communication.

## Slide 4: Actions from previous meeting
# | Description | Date due | Status | Owner | Comments/Outcomes
A10 | LNSPs to circulate to all retailers ‘end of life meter replacement programs’ for existing fleets to facilitate adequate retailer and MC planning by Friday 7th July. | 07 Jul 17 | Open | ActewAGL D | •
 |  | 07 Jul 17 | Open | Ausgrid | • Currently meeting with retailers and sending as requested
 |  | 07 Jul 17 | Open | Endeavour Energy | • Currently meeting with retailers and providing the total number in the network area and ask retailers to portion that based on their proportion of National Metering Identifiers (NMIs) in that network area
 |  | 07 Jul 17 | Open | Energex & Ergon | • Energex is working closely with Ergon and providing information where requested
 |  | 07 Jul 17 | Open | Essential Energy | •
 |  | 07 Jul 17 | Open | SA Power Net | • Very broad numbers are being shared with retailers however the next level of detail will not be available until later in year (November) due to testing needing to be completed prior to analysis
 |  | 07 Jul 17 | Open | TasNetworks | • Currently meeting with retailers and sending as requested
A11 | Retailers / LNSPs to provide forecasts of new connections over the period of December to February to feed into transition and cut-over planning and contingency planning activities. | 07 Jul 17 | Closed | LNSP & Retailers | • Forecasts provided as part of Transition and cut-over planning
A12 | LNSPs to provide example of corrective works program undertaken to rectify customer supply as a result of a natural disaster. Example program to focus on metering installations. | 07 Jul 17 | Open | LNSP | • Energex: ~42,000 meters required replacing following the 2011 Brisbane Floods. Replacement rate is TBC by Energex • AusNet: noted that 30 day meter stock was sufficient coverage for both, many meters followed new connection processes.
A13 | Retailers to provide an information request regarding end of life replacement meters to AEMO for circulation. | 04 Aug 17 | Open | Retailers (Alinta lead)) | • Information provided to AEMO and circulated with PoC-PCF Pack for 11 August discussion. Note attachment : Item 2

## Slide 5: AEMO Program Update
General:
PWC results circulated as part of pack.
Executive Forum; approx. two weeks, late August
PCF next session will be held 24 August 2017
AEMO Procedures
AEMO Procedure pack 3 submission closed on 9 August ~ 15 submissions
Final determination will be published on 1 September 2017; effective date 1 December 2017
B2B Procedures
Current list of clarifications is available on AEMO website Power of Choice B2B consultation
Any suggested improvements or changes not identified as error corrections will be the subject to a consultation in 2018.
Systems
AMEO system release expected in outage window from 16 August 2017
Hotfixes may be applied during period 16 Aug – 20 Aug 17

## Slide 6: AEMO Program Update
Readiness:
Industry Testing Planning:
  B2B Testing (Phase 2) – completed
  Market Trial (Phase 3) – final test plan published – commences 21 August
Accreditation and Registration Industry Plan
  First MC registration has been completed
Transition and Cutover
  Requirements have been finalised – draft plan available for industry review no later than 23 Aug
Upcoming sessions
  ITCFG 17 Aug 2017 – Staged approach (transitional model)
  RWG 18 August 2017 – Contingency planning, including scenario development and decision criteria
Readiness reporting:
  Aug compiled report due 14 Aug
  3 x new reporting parties (1 x retailer; 1 x MC/MDP/MP; 1 x ENM)

## Slide 7: Industry Issues Register
System cut-over:
Industry raised an issue for discussion:
  Current assumptions are that the existing market arrangements and systems will cease to operate on Thursday 30 November, new arrangements (Rules, Procedures etc.) will commence morning of Friday 1st December.
  In effect, an overnight cut-over.
Discussion:
  Participants have advised a range of systems outage timings spanning from 12 to 48+ hours.
  Participants raised impacts to month end processes.
Actions taken:
AEMO seeking feedback on a proposed cut-over period spanning COB Friday 2 December to commencement of business, Monday 4 December.
Industry feedback provided by Wednesday, 26 May 2017.
AEMO discussing with AER approaches that may be required to give effect to a weekend system cut-over
AEMO / AER considering ‘letter of no action’ that may be required for weekend cutover approach.
AEMO expects that final mechanisms will be in place by end of September.

## Slide 8: Watching briefs
Translation Tool
  Translation tool delivered to industry for testing
  It is reported to AEMO that the tool will be available to participants who may require it in time to support testing cycle 2 of Market Trials
Proposed Decision framework (as circulated by Jemena)
  Discussed at IEC – IEC supportive of actively engaging a B2B-WG member in early stages of process (during daily defect meetings for example) to expedite triage processes
  IEC typically comfortable with SLAs for resolution, however noted not willing to meet regularly – therefore will provide some delegation to the B2B-WG
  AEMO comfortable with providing SLAs around issue resolution for B2M and system related defects / issues
  AEMO releasing an update on Wednesday 16 August – intent is to include process in Test Plan

## Slide 9
Program schedule

## Slide 10
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview
High Level Program V6.2 – 18 Jul 2017
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & B2B
Effective Date (Go-Live)
DNSPs & Retailers to publish amended standard contracts
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
B2B – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
B2B – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Transition & Cut Over Planning
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
B2B
Plan
Execute
Plan
Registration & Accreditation
Pre-Prod Release
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination
P
P
Industry Test Planning
Phase 1
Transition
Phase 2
Market Trial – Phase 3

## Slide 11
2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 | 
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview – Readiness Work Stream
High Level Program V6.2 – 18 Jul 2017
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Industry Test Planning EN/MC
Phase 1 Execution EN/MC
Accreditation & Registration
Transition & Cutover
Transition Planning
P
Publish
Readiness reporting
Industry Testing
1 Dec
Go-live date
17 Nov
Industry Test Report
10 Apr
EN/MC changes in pre-production
06 Mar
B2B Procedures Published
28 Feb
WP2 Procedures Published
Industry Test Planning B2B/Market Trial
Phase 2 Execution B2B
Planning
Accreditation and Registration Period
Phase 3 Market Trial Execution
Transition
Heightened Support
2 Oct
Industry Transition & Cutover Plan Published
5 Jun
Industry Test Plan B2B Published
Readiness Reporting
5 Jun
10 Jul
7 Aug
11 Sep
9 Oct
6 Nov
4 Dec
8 May
3 Apr
6 Mar
8 Feb
16 Aug
Pre-Production system release
22 May
EN/MC patch release
Test Set-up
EN/MC
Cutover Planning
1 Sep
Draft Transition and cutover plan
29 Sep
Final Transition and cutover plan review
Outage Window
11 Aug
Submit entry Criteria checklist
21 Aug
Commence Phase 3 Market Trials
System Cutover
1 Mar
Qualification, registration & accreditation checklists published
24 Mar
Second draft plan published
28 Apr
Registration & Accreditation plan published
9 May
Participant Information Session
31 Oct
Confirmation of registration and accreditation status
14 Aug
Commence daily meetings
16 Aug
E-Hub Certification screens released
28 Jul
Market Trial workbook complete
Cycle 1
Cycle 2
Cycle 3

## Slide 12: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description | Planned date | Expected date | Status
Phase 1 Test Execution Complete | Industry Testing |  | 30 Jun 17 |  | 
Phase 3 Market Trial Workbook Published | Industry Testing |  | 28 Jul 17 |  | 
Phase 2 Test Execution Complete | Industry Testing |  | 28 Jul 17 |  | 
Transition planning workshops conclude | Trans & Cut Over |  | 08 Aug 17 |  | 
Market Trial daily meetings commence | Industry Testing |  | 14 Aug 17 |  | 
AEMO releases updates systems into pre-production | Systems |  | 16 Aug 17 |  | 
E-Hub Certification screens released | Readiness |  | 16 Aug 17 |  | 
Phase 3 Market Trial cycle 1 commences | Industry Testing |  | 21 Aug 17 |  | 
Transition and cutover plan draft released | Trans & Cut Over |  | 01 Sep 17 |  | 
DNSPs publish T&C’s on which it will act as the initial MC | DNSPs |  | 01 Sep 17 |  | 
Phase 3 Market Trial cycle 1 concludes | Industry Testing |  | 08 Sep 17 |  | 
Phase 3 Market Trial cycle 2 commences | Industry Testing |  | 18 Sep 17 |  | 
Transition and cutover plan published | Trans & Cut Over |  | 02 Oct 17 |  | 
Phase 3 Market Trial cycle 2 concludes | Industry Testing |  | 06 Oct 17 |  | 
Phase 3 Market Trial cycle 3 commences | Industry Testing |  | 16 Oct 17 |  | 
Registration & accreditation confirmation status | Readiness |  | 31 Oct 17 |  | 
Phase 3 Market Trial cycle 3 concludes | Industry Testing |  | 03 Nov 17 |  | 
Transition activities commence | Trans & Cut Over |  | 13 Nov 17 |  | 
Phase 3 Market Trial Report released | Industry Testing |  | 17 Nov 17 |  | 
PoC Effective date | All | Allowance for weekend system cutover | 01 Dec 17 | 04 Dec 17 | 
Cutover Activities commence | Trans & Cut Over | COB Friday 1 Dec 17 | 01 Dec 17 |  | 
Cutover Activities conclude | Trans & Cut Over | OOB Monday 4 Dec 17 | 04 Dec 17 |  | 
Transition activities concludes | Trans & Cut Over |  | 08 Dec |  | 
Heightened Support Period | All |  | 02 Mar 18 | 07 Apr 18 | 
Notes: Intent to Publish

## Slide 13: PoC - Program Overview Version history
This table summarises the changes between the Program Overview as information changes or becomes available.
Version | Date | Amendments
4.0 | 10 Jun 16 | Arranged Program Overview into key workstreams Removed IEC milestones in lieu of SMP Draft Determination
4.1 | 23 Jun 16 | Increased AEMO’s “design phase” to carry on until the end of consultation (1 Mar 17) Altered WP 1 Procedure Change Process dates to accommodate additional four business days of consultation.
4.2 | 19 Aug 16 | Updated tracking; removed dates associated with B2B Procedures as a result of B2B Framework Rule being published
4.3 | 02 Sep 16 | Updated B2B Procedure consultation with AEMO’s proposed dates (pending IEC approval)
4.4 | 10 Oct 16 | Updated terminology – added ‘6 month outlook’ for Procedure development / consultation processes Updated key dates in relation to AEMO WP2 Procedures and B2B Procedure development / consultation Included key dates identified in Readiness strategy
4.5 | 17 Nov 16 | Amended dates for Fee Methodology consultation Updated B2B Procedure Consultation dates
4.6 | 16 Dec 16 | Updated Tracking
4.7 | 21 Dec 16 | Updated Industry Testing and Transition and cut-over activities to commence earlier. Removed achieved milestones (Sep 15 – Nov 16)
4.8 | 25 Jan 17 | Updated Fee Methodology timetable in accordance with AEMO consultation
4.9 | 16 Feb 17 | Removed version control updates prior to 3.5 Removed Industry meeting dates from Program overview (refer to the industry calendar publishes on www.aemo.com.au) Included a draft Readiness overview slide
5.0 | 21 Mar 17 | Removed Procedures Work stream outlook. Updated ‘As Built’ package timeframes
5.1 | 6 Apr 17 | Updated Readiness Work Stream overview following RWG and ITWG (Apr 2017)
5.2 | 19 Apr 17 | Removed Industry Test Box and extended Market Trial Box
6.0 | 19 May 17 | Updated Tracking
6.1 | 26 May 17 | Updated Tracking
6.2 | 18 Jul 17 | Updates Tracking Update WP 3 / As Built consultation dates amended Updated Readiness work stream program overview

## Slide 14
Risk Register Review
See attached Risk Register

## Slide 15: Forward Meeting Plan
POC-PCF meeting dates | Dates
POC-PCF Meeting #11 | 27-Jul-17
POC-PCF Meeting #11A | 11-Aug-17
POC-PCF Meeting #12 | 24-Aug-17
POC-PCF Meeting #12A | 13-Sep-17
POC-PCF Meeting #13 | 28-Sep-17
POC-PCF Meeting #14 | 26-Oct-17
POC-PCF Meeting #15 | 23-Nov-17
POC-PCF Meeting #16 | 14-Dec-17
Facilities:
Melbourne, Sydney, Brisbane, Adelaide offices
Video conference
Webinar (when required)