## Slide 1: PROGRAM CONSULTATIVE FORUM Meeting pack
DATE: Thursday 28 September 2017
TIME: 10.00 AM – 11.15 AM (AEST) Session 1
11.30 AM – 1.00PM (AEST) Session 2
VENUE: AEMO OFFICES; MEL, SYD, ADE, BRI
TELECONFERENCE: DIAL IN: 02 8602 3002
CONTACT: poc@aemo.com.au

## Slide 2: Power of Choice PROGRAM UPDATE

## Slide 3: Actions from previous meeting
# | Description | Date due | Status | Owner | Comments/Outcomes
A05 | LNSPs to circulate to all retailers draft’s T&C’s (per 11.86.7 of the new Rules) and any associated publications that they are developing (for example a ‘Retailer Handbook’) with industry. | 13 Sep 17 | Closed | AusNet Services | • provided to retailers, sending AEMO a copy.
 |  | 13 Sep 17 | Closed | Jemena Networks | • provided to retailers.
 |  | 13 Sep 17 | Closed | United Energy | • provided to retailers via ROCL list
A06 | Industry Test Lead to report at next PCF on progress of testing. | 13 Sep 17 | Closed | AEMO (ITWG Lead) | • T. Grant will continue to provide update on testing at each PCF
.
Other Actions from last meeting

## Slide 4: AEMO Program Update
General:
Upcoming meetings:
  Executive Forum Thursday 5 October 2017
AEMO Procedures
Procedures Finalised and published
B2B Procedures
Current list of clarifications is available on AEMO website Power of Choice B2B consultation
Systems
AEMO system released into pre-production environment 20 September

## Slide 5: AEMO Program Update
Communication Plan:
As noted at the POC Executive Forum on 28 August, AEMO is coordinating discussions on industry PoC communications.
First meeting was held on 30 August and included:
  AEMO, officials for the Commonwealth Department of Environment and Energy, the AEMC, the AER, ENA representing networks, the AEC representing its members, a metering representative (Doug Ross) and a small retailer representative (Andrew Mair).
Purpose of the discussions is to clarify which parties will communicate PoC changes with whom, and to establish consistent messaging.
Please work with your representative to engage in the process in the first instance.
If you have any further questions, please contact poc@aemo.com.au.
Further updates will be provided at PoC Forums, including the PCF and Executive Forum.

## Slide 6: AEMO Program Update
Readiness:
Industry Testing:
  Cycle 2 - 18 September to 6 October
  Cycle 3 – 16 October to 3 November
Accreditation and Registration:
  Full MCs: approx. 11 parties expressed interest, 1 completed, 5 in progress, awaiting applications from others
  ENMs: approx. 20 parties expressed interest, none completed, 4 in progress, awaiting applications from others
  Generator MCs have been contacted by AEMO
  B2B accreditation window is open
Transition and Cutover
  21 September: final draft (version 0.2) of the Industry Transition & Cutover Plan was sent to the ITCFG – feedback requested by no later than 28 September
  Final version to published week beginning 2 October
Contingency planning
  AEMO is updating the final list of industry contingency scenarios based on CPWG feedback – this will be incorporated into Market Readiness Strategy and circulated to the RWG for review

## Slide 7: Power of Choice Program Schedule

## Slide 8
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview
High Level Program V6.6 – 28 Sep 2017
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & B2B
Effective Date (Go-Live)
DNSPs & Retailers to publish amended standard contracts
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
B2B – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
B2B – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Transition & Cut Over Planning
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
B2B
Plan
Execute
Plan
Registration & Accreditation
Pre-Prod Release
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination
P
P
Industry Test Planning
Phase 1
Transition
Phase 2
Market Trial – Phase 3

## Slide 9
2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 | 
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview – Readiness Work Stream
High Level Program V6.6 – 28 Sep 2017
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Industry Test Planning EN/MC
Phase 1 Execution EN/MC
Accreditation & Registration
Transition & Cutover
Transition Planning
P
Publish
Readiness reporting
Industry Testing
1 Dec
Go-live date
17 Nov
Industry Test Report
10 Apr
EN/MC changes in pre-production
06 Mar
B2B Procedures Published
28 Feb
WP2 Procedures Published
Industry Test Planning B2B/Market Trial
Phase 2 Execution B2B
Planning
Accreditation and Registration Period
Phase 3 Market Trial Execution
Transition
Heightened Support
2 Oct
Industry Transition & Cutover Plan Published
5 Jun
Industry Test Plan B2B Published
Readiness Reporting
5 Jun
10 Jul
7 Aug
11 Sep
9 Oct
6 Nov
4 Dec
8 May
3 Apr
6 Mar
8 Feb
16 Aug
Pre-Production system release
22 May
EN/MC patch release
Test Set-up
EN/MC
Cutover Planning
1 Sep
Draft Transition and cutover plan
29 Sep
Final Transition and cutover plan review
Outage Window
11 Aug
Submit entry Criteria checklist
21 Aug
Commence Phase 3 Market Trials
System Cutover
1 Mar
Qualification, registration & accreditation checklists published
24 Mar
Second draft plan published
28 Apr
Registration & Accreditation plan published
9 May
Participant Information Session
31 Oct
Confirmation of registration and accreditation status
14 Aug
Commence daily meetings
16 Aug
E-Hub Certification screens released
28 Jul
Market Trial workbook complete
Cycle 1
Cycle 2
Cycle 3
Contingency Planning

## Slide 10: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description | Planned date | Expected date | Status
Phase 1 Test Execution Complete | Industry Testing |  | 30 Jun 17 |  | 
Phase 3 Market Trial Workbook Published | Industry Testing |  | 28 Jul 17 |  | 
Phase 2 Test Execution Complete | Industry Testing |  | 28 Jul 17 |  | 
Transition planning workshops conclude | Trans & Cut Over |  | 08 Aug 17 |  | 
Market Trial daily meetings commence | Industry Testing |  | 14 Aug 17 |  | 
AEMO releases updates systems into pre-production | Systems |  | 16 Aug 17 |  | 
E-Hub Certification screens released | Readiness |  | 21 Aug 17 |  | 
Phase 3 Market Trial cycle 1 commences | Industry Testing |  | 21 Aug 17 |  | 
Transition and cutover plan draft released | Trans & Cut Over |  | 01 Sep 17 |  | 
DNSPs publish T&C’s on which it will act as the initial MC | DNSPs |  | 01 Sep 17 |  | 
Phase 3 Market Trial cycle 1 concludes | Industry Testing |  | 08 Sep 17 |  | 
Phase 3 Market Trial cycle 2 commences | Industry Testing |  | 18 Sep 17 |  | 
Transition and cutover plan published | Trans & Cut Over |  | 02 Oct 17 |  | 
Phase 3 Market Trial cycle 2 concludes | Industry Testing |  | 06 Oct 17 |  | 
Phase 3 Market Trial cycle 3 commences | Industry Testing |  | 16 Oct 17 |  | 
Registration & accreditation confirmation status | Readiness |  | 31 Oct 17 |  | 
Phase 3 Market Trial cycle 3 concludes | Industry Testing |  | 03 Nov 17 |  | 
Transition activities commence | Trans & Cut Over |  | 13 Nov 17 |  | 
Phase 3 Market Trial Report released | Industry Testing |  | 17 Nov 17 |  | 
PoC Effective date | All | Allowance for weekend system cutover | 01 Dec 17 | 04 Dec 17 | 
Cutover Activities commence | Trans & Cut Over | COB Friday 1 Dec 17 | 01 Dec 17 |  | 
Cutover Activities conclude | Trans & Cut Over | OOB Monday 4 Dec 17 | 04 Dec 17 |  | 
Transition activities concludes | Trans & Cut Over |  | 08 Dec |  | 
Heightened Support Period | All |  | 02 Mar 18 | 07 Apr 18 | 
Notes: Intent to Publish

## Slide 11: PoC - Program Overview Version history
This table summarises the changes between the Program Overview as information changes or becomes available.
Version | Date | Amendments
4.2 | 19 Aug 16 | Updated tracking; removed dates associated with B2B Procedures as a result of B2B Framework Rule being published
4.3 | 02 Sep 16 | Updated B2B Procedure consultation with AEMO’s proposed dates (pending IEC approval)
4.4 | 10 Oct 16 | Updated terminology – added ‘6 month outlook’ for Procedure development / consultation processes Updated key dates in relation to AEMO WP2 Procedures and B2B Procedure development / consultation Included key dates identified in Readiness strategy
4.5 | 17 Nov 16 | Amended dates for Fee Methodology consultation Updated B2B Procedure Consultation dates
4.6 | 16 Dec 16 | Updated Tracking
4.7 | 21 Dec 16 | Updated Industry Testing and Transition and cut-over activities to commence earlier. Removed achieved milestones (Sep 15 – Nov 16)
4.8 | 25 Jan 17 | Updated Fee Methodology timetable in accordance with AEMO consultation
4.9 | 16 Feb 17 | Removed version control updates prior to 3.5 Removed Industry meeting dates from Program overview (refer to the industry calendar publishes on www.aemo.com.au) Included a draft Readiness overview slide
5.0 | 21 Mar 17 | Removed Procedures Work stream outlook. Updated ‘As Built’ package timeframes
5.1 | 6 Apr 17 | Updated Readiness Work Stream overview following RWG and ITWG (Apr 2017)
5.2 | 19 Apr 17 | Removed Industry Test Box and extended Market Trial Box
6.0 | 19 May 17 | Updated Tracking
6.1 | 26 May 17 | Updated Tracking
6.2 | 18 Jul 17 | Updates Tracking Update WP 3 / As Built consultation dates amended Updated Readiness work stream program overview
6.3 | 14 Aug 17 | Updated Tracking
6.4 | 24 Aug 17 | Updated Tracking
6.5 | 8 Sep 17 | Updated Tracking – Included Contingency planning activity
6.6 | 28 Sep 17 | Updated Tracking

## Slide 12
Risk Register Review
See attached Risk Register

## Slide 13: Forward Meeting Plan
POC-PCF meeting dates | Dates
POC-PCF Meeting #13 | 28-Sep-17
POC-PCF Meeting #14 | 26-Oct-17
POC-PCF Meeting #15 | 23-Nov-17
POC-PCF Meeting #16 | 14-Dec-17
Facilities:
Melbourne, Sydney, Brisbane, Adelaide offices
Video conference
Webinar (when required)