## Slide 1: PROGRAM CONSULTATIVE FORUM Meeting pack
DATE: Thursday 08 November 2017
TIME: 09.30 AM – 11.00AM (AEST)
VENUE: AEMO OFFICES; MEL, SYD, ADE, BRI
TELECONFERENCE: DIAL IN: 1800 055 132 ID: 35990745
CONTACT: poc@aemo.com.au

## Slide 2: Power of Choice PROGRAM UPDATE

## Slide 3: Actions from previous meeting
# | Description | Date due | Status | Owner | Comments/Outcomes
A15 | LNSPs and MCs are to review each scenario provided under a change of role in the attached spreadsheet and notify what action their specific organisation will take, either object (y) or not (n). Refer to attachment: ACT 2 Change Request Objection Clarifications. Responses to 6800 and 6300 messages | 28 Sep 17 18 Oct 17 | Open | All parties | 
A16 | How do LNSPs plan to deal with any backlog of DNP transactions that are not processed during the periods of 24/11 to 4/12 and the NERR protected period 20/12 to 31/12? | 26 Oct 17 | Closed | ActewAGL | 
 |  | 26 Oct 17 | Closed | Ausgrid | 
 |  | 26 Oct 17 | Closed | Ausnet | Will resolve all immediately following embargo windows.
 |  | 26 Oct 17 | Closed | CP / PC | 
 |  | 26 Oct 17 | Closed | Endeavour | 
 |  | 26 Oct 17 | Open | Energex | 
 |  | 26 Oct 17 | Open | Ergon | 
 |  | 26 Oct 17 | Open | Essential | 
 |  | 26 Oct 17 | Closed | SAPN | 
 |  | 26 Oct 17 | Closed | Jemena | 
 |  | 26 Oct 17 | Open | TasNetworks | 
 |  | 26 Oct 17 | Closed | UE | 
Attachment PCF Action Summary

## Slide 4: AEMO Program Update
General
Executive Forum Tuesday 31 October 2017
  Focus on finalisation of registration & accreditations activities
  AEMO have contacted all prospective MCs to provide consolidated individual responses
Systems
AEMO has released a patches on:
  Thursday 26 October Defect fixes
  Wednesday 1 Nov Defect fixes
  Friday 3 Nov Defect & performance fixes
All defects related to Market Trial have been released
New version of Validation Module released Tuesday 31 October
Communication Plan:
Published PoC Fact Sheets
FAQs have been revised by industry and will be published on AEMOs website

## Slide 5: AEMO Program Update
Readiness:
Verbal update on testing – Final report due 17 Nov 17
Readiness Reporting:
  November readiness report’s are now required. Includes updated template
Dress rehearsal will be conducted on 15 – 17 November
Accreditation and Registration:
  Full MCs: 1 registration approved, 12 applications received. 5 in progress/under assessment, feedback provided to all potential MCs,
  Initial MCs: 7 registrations approved, all DNSP applications received, 6 in progress/under assessment
  Type 7 MCs: 7 registrations approved, all DNSP applications received, 6 in progress/under assessment
  TNSP MCs: none approved, 5 applications received; 2 outstanding, awaiting support documentation from all others (AEMO proactively pursuing)
  Generator MCs: all have been contacted by AEMO
  ENMs: 1 complete, 9 ENMs with final audits booked or completed, 23 applications received
  B2B Accreditations: 64 completed, 138 participant IDs

## Slide 6: Power of Choice Risk / Issue log updates

## Slide 7: Risk & Issue Update
Refer to attachments PoC Industry Register - Master & B2B Working Group Teleconference 20 October

## Slide 8: Power of Choice Other Business

## Slide 9: Other Business
Availability of Pre-Production for bi-lateral testing
As at 6 November
Commonwealth / Jurisdictional Safety Regs
AEMO will circulate meeting notes when available.
SMP/MSATS Pre-prod availability |  |  | 
Date | Outage Start | Outage End | Description
9th Oct to 13th Oct | - | - | AEMO performance and load testing - may cause intermittent outages or delays
12th Oct | 10am | 3pm | MSATS maintenance
12th Oct | 5pm | 7pm | Defect release for Market trials - Cycle 3
19th Oct | 5pm | 7pm | Place holder for defect release
26th Oct | 5pm | 7pm | Place holder for defect release
16th Oct to 3rd Nov | - | - | Market trials - Cycle 3
6th Nov to 10th Nov | - | - | AEMO performance and load testing - may cause intermittent delays
9th Nov | 5pm | 7pm | Place holder for defect release
15 Nov to 17 Nov | 6pm | 6pm | Dress Rehearsal with Batch Handler outages
16th Nov | 5pm | 7pm | Place holder for final pre-prod release

## Slide 10: Power of Choice Program Schedule

## Slide 11
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview
High Level Program V6.9 – 06 Nov 2017
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & B2B
Effective Date (Go-Live)
DNSPs & Retailers to publish amended standard contracts
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
B2B – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
B2B – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Transition & Cut Over Planning
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
B2B
Plan
Execute
Plan
Registration & Accreditation
Pre-Prod Release
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination
P
P
Industry Test Planning
Phase 1
Transition
Phase 2
Market Trial – Phase 3

## Slide 12
2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 | 
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview – Readiness Work Stream
High Level Program V6.9 – 06 Nov 2017
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Industry Test Planning EN/MC
Phase 1 Execution EN/MC
Accreditation & Registration
Transition & Cutover
Transition Planning
P
Publish
Readiness reporting
Industry Testing
1 Dec
Go-live date
17 Nov
Industry Test Report
10 Apr
EN/MC changes in pre-production
06 Mar
B2B Procedures Published
28 Feb
WP2 Procedures Published
Industry Test Planning B2B/Market Trial
Phase 2 Execution B2B
Planning
Accreditation and Registration Period
Phase 3 Market Trial Execution
Transition
Heightened Support
2 Oct
Industry Transition & Cutover Plan Published
5 Jun
Industry Test Plan B2B Published
Readiness Reporting
5 Jun
10 Jul
7 Aug
11 Sep
9 Oct
6 Nov
4 Dec
8 May
3 Apr
6 Mar
8 Feb
16 Aug
Pre-Production system release
22 May
EN/MC patch release
Test Set-up
EN/MC
Cutover Planning
1 Sep
Draft Transition and cutover plan
29 Sep
Final Transition and cutover plan review
Outage Window
11 Aug
Submit entry Criteria checklist
21 Aug
Commence Phase 3 Market Trials
System Cutover
1 Mar
Qualification, registration & accreditation checklists published
24 Mar
Second draft plan published
28 Apr
Registration & Accreditation plan published
9 May
Participant Information Session
31 Oct
Confirmation of registration and accreditation status
14 Aug
Commence daily meetings
16 Aug
E-Hub Certification screens released
28 Jul
Market Trial workbook complete
Cycle 1
Cycle 2
Cycle 3
Contingency Planning

## Slide 13: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description | Planned date | Expected date | Status
Phase 1 Test Execution Complete | Industry Testing |  | 30 Jun 17 |  | 
Phase 3 Market Trial Workbook Published | Industry Testing |  | 28 Jul 17 |  | 
Phase 2 Test Execution Complete | Industry Testing |  | 28 Jul 17 |  | 
Transition planning workshops conclude | Trans & Cut Over |  | 08 Aug 17 |  | 
Market Trial daily meetings commence | Industry Testing |  | 14 Aug 17 |  | 
AEMO releases updates systems into pre-production | Systems |  | 16 Aug 17 |  | 
E-Hub Certification screens released | Readiness |  | 21 Aug 17 |  | 
Phase 3 Market Trial cycle 1 commences | Industry Testing |  | 21 Aug 17 |  | 
Transition and cutover plan draft released | Trans & Cut Over |  | 01 Sep 17 |  | 
DNSPs publish T&C’s on which it will act as the initial MC | DNSPs |  | 01 Sep 17 |  | 
Phase 3 Market Trial cycle 1 concludes | Industry Testing |  | 08 Sep 17 |  | 
Phase 3 Market Trial cycle 2 commences | Industry Testing |  | 18 Sep 17 |  | 
Transition and cutover plan published | Trans & Cut Over |  | 02 Oct 17 |  | 
Phase 3 Market Trial cycle 2 concludes | Industry Testing |  | 06 Oct 17 |  | 
Phase 3 Market Trial cycle 3 commences | Industry Testing |  | 16 Oct 17 |  | 
Registration & accreditation confirmation status | Readiness |  | 31 Oct 17 |  | 
Phase 3 Market Trial cycle 3 concludes | Industry Testing |  | 03 Nov 17 | 04 Nov 17 | 
Transition activities commence | Trans & Cut Over | Per industry plan | 13 Nov 17 | 01 Nov 17 | 
Phase 3 Market Trial Report released | Industry Testing |  | 17 Nov 17 |  | 
PoC Effective date | All | Allowance for weekend system cutover | 01 Dec 17 | 04 Dec 17 | 
Cutover Activities commence | Trans & Cut Over | COB Friday 1 Dec 17 | 01 Dec 17 |  | 
Cutover Activities conclude | Trans & Cut Over | OOB Monday 4 Dec 17 | 04 Dec 17 |  | 
Transition activities concludes | Trans & Cut Over |  | 08 Dec |  | 
Heightened Support Period | All |  | 02 Mar 18 | 30 Mar 18 | 
Notes: Intent to Publish

## Slide 14: PoC - Program Overview Version history
This table summarises the changes between the Program Overview as information changes or becomes available.
Version | Date | Amendments
5.0 | 21 Mar 17 | Removed Procedures Work stream outlook. Updated ‘As Built’ package timeframes
5.1 | 6 Apr 17 | Updated Readiness Work Stream overview following RWG and ITWG (Apr 2017)
5.2 | 19 Apr 17 | Removed Industry Test Box and extended Market Trial Box
6.0 | 19 May 17 | Updated Tracking
6.1 | 26 May 17 | Updated Tracking
6.2 | 18 Jul 17 | Updates Tracking Update WP 3 / As Built consultation dates amended Updated Readiness work stream program overview
6.3 | 14 Aug 17 | Updated Tracking
6.4 | 24 Aug 17 | Updated Tracking
6.5 | 8 Sep 17 | Updated Tracking – Included Contingency planning activity
6.6 | 28 Sep 17 | Updated Tracking
6.7 | 13 Oct 17 | Updated Tracking
6.8 | 24 Oct 17 | Updated tracking – Included amended dates according to Industry Transition and Cut-over plan
6.9 | 06 Nov 17 | Updated Tracking

## Slide 15: Forward Meeting Plan
POC-PCF meeting dates | Dates
POC-PCF Meeting #13a | 13-Oct-17
POC-PCF Meeting #14 | 26-Oct-17
POC-PCF Meeting #14a | 08-Nov-17
POC-PCF Meeting #15 | 23-Nov-17
POC-PCF Meeting #15a | 08-Dec-17
POC-PCF Meeting #16 | 14-Dec-17
Facilities:
Melbourne, Sydney, Brisbane, Adelaide offices
Video conference
Webinar (when required)