## PCF Actions List
# | Description | Due Date | Status | Owner
A01
A02
A03
A04 | M Norris to share copy of Ergon’s handbook to other attendees. | 2017-07-07 | Closed | Ergon
A05 | LNSPs to circulate to all retailers draft’s T&C’s (per 11.86.7 of the new Rules) and any associated publications that they are developing (for example a ‘Retailer Handbook’) with industry. | 07 Jul 17 18 Aug 17 | Closed | LNSPS
A06 | Industry Test Lead to report at next PCF on progress of testing. | 4/07/2017 24/08/2017 | Closed | AEMO (ITWG Lead)
A07 | B. Healy to circulate test results publishing on HPQC. | 2017-07-07 | Closed | AEMO
A08 | Testing results to be included in PCF pack monthly | 2017-07-04 | Closed | AEMO
A09 | AEMO to speak to AEMC regarding communications, potentially with the AER. | 2017-07-04 | Closed | AEMO
A10 | LNSPs to circulate to all retailers ‘end of life meter replacement programs’ for existing fleets to facilitate adequate retailer and MC planning by Friday 7th July. | 07 Jul 17 18 Aug 17 | Closed | LNSPS
A11 | Retailers / LNSPs to provide forecasts of new connections over the period of December to February to feed into transition and cut-over planning and contingency planning activities. | 2017-07-07 | Closed | LNSP & Retailers
A12 | LNSPs to provide example of corrective works program undertaken to rectify customer supply as a result of a natural disaster. Example program to focus on metering installations. | 2017-07-07 | Closed
A13 | Retailers to provide an information request regarding end of life replacement meters to AEMO for circulation. | 2017-08-04 | Closed
A14 | LNSPs are to review and update the attached questionnaire (conducted by the IEC in Q2 this year ) by Friday 15 September. If there are no changes from previously provided response, the LNSPs are requested to reply to poc@aemo.au stating ‘no change’. See attachment ACT 1 Faults Emergencies - Combined Responses | 2017-09-15 | Open | LNSPs
A15 | LNSPs and MCs are to review each scenario provided under a change of role in the attached spreadsheet and notify what action their specific organisation will take, either object (y) or not (n). Refer to attachment: ACT 2 Change Request Objection Clarifications | 2017-09-15 | Open | LNSPs / MCs
A16 | How do LNSPs plan to deal with any backlog of DNP transactions that are not processed during the periods of 24/11 to 4/12 and the NERR protected period 20/12 to 31/12? | 2017-12-26 | Open | LNSPs
A17
A18
A19
A20

## PoC-PCF Actions 5 & 10
| Action 5 - T&C (and handbooks) |  |  |  |  | Action 10 Meter replacement forecasts
| Draft T&Cs | T&Cs point of contact |  | Email Provided to AEMO & circulated (Y/N) | Remarks | Estimated Outstanding at 1 December | Annual Forecast | Remarks | Email Provided & circulated (Y/N)
ActewAGL Distribution | Complete | Michael Monck | Michael.Monck@actewagl.com.au | YES |  | ~ 309 | 2,000 - 3,000
Ausgrid | Complete | Alex Moran | alex.moran@ausgrid.com.au | YES |  | ~ 90,000 | 13,000 - 15,000 | Approx 90,000 known meter replacements will be transferred to FRMP prior to 1 Dec | YES
AusNet Services | Complete | Emma Youill | emma.youill@ausnetservices.com.au
CitiPower / Powercor | Complete | Phil Gardiner | pgardiner@powercor.com.au
Endeavour Energy | Complete | Dino Ou | dino.ou@endeavourenergy.com.au |  |  | ~ 40,000 | 15,000 - 20,000 | Current FRMPs have been provided with a list of NMIs
Energex | Complete | Rebecca Neatnica | rebeccaneatnica@energex.com.au | YES |  | 0 | 9000
Ergon | Complete | See Energex | See Energex |  |  |  |  | The Ergon distribution business has been sharing its meter replacement programs with Ergon Retail
Essential Energy | Complete | Graeme Ferguson | graeme.ferguson@essentialenergy.com.au | YES |  | ~ 113,000 | 15,000 - 20,000 | 10% (86,800) of premises have at least 1 meter identified as family failure. It is forecast that an additional 48,000 meters may be deemed faulty in 2019, this will be confirmed following meter testing in 2018/19. Essential Energy has provided to all retailers that have enquired a count of existing failed meters by postcode to assist in retailers planning for future replacement programs. If any retailer wants updated information please contact Essential Energy directly | YES
SA Power Net | Complete | David Woods | David.Woods@sapowernetworks.com.au | YES |  | 0 | 15,000 - 20,000 | To assist Retailers with further meter planning, SA Power Networks are willing to provide Retailers with a broad view and approximate breakdown of our current Type 5 & 6 meter fleet (approx. 1.1M)*. 1 Phase: 82%; 2 Phase: 1%; 3 Phase: 17% | YES
Jemena Networks | Complete | Jacinta Daws | Jacinta.daws@jemena.com.au |  | Direct to Retailers
TasNetworks | Complete | Warren Brooks | Warren.Brooks@tasnetworks.com.au |  |  | ~ 1,000 | 6,000 - 8,000
United Energy | Complete | Richard McNulty | Richard.McNulty@ue.com.au

## PoC-PCF Act 14 Responses
Act 14
Changes to IEC Questions
ActewAGL Distribution | Going to bypass
Ausgrid | Bypass meters - no change
AusNet Services | N/C
CitiPower / Powercor
Endeavour Energy | N/C
Energex | N/C
Ergon | N/C
Essential Energy | N/C
SA Power Net | N/C
Jemena Networks
TasNetworks
United Energy

## PoC-PCF Act 15 Responses
[5 empty] | Losing MC Objection (Y/N?) | [20 empty] | Prospective MC Objection (Y/N?)
# | Scenario | Activity required | Metering Type | CR Type | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB | Metering Dynamics | Metropolis Metering Services | Powermetric Metering | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB | Metering Dynamics | Metropolis Metering Services | Powermetric Metering | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS
1 | DB meter fault- customer off supply | Meter exchange from faulty DB meter to a contestable meter as a forced replacement | Type 5/6 to Type 4 | 6800 | [10 empty] | N | Y | N/A |  |  | N |  |  |  | N | Y | N |  |  | N |  |  | N
2 | DB meter fault – customer on supply |  |  | 6800 | [10 empty] | N | Y | N/A |  |  | N |  |  |  | N | Y | N |  |  | N |  |  | N
3 | DB meter - family failure of DB meter |  |  | 6800 | [10 empty] | N | Y | N/A |  |  | N |  |  |  | N | Y | N |  |  | N |  |  | N
4 | DB meter - customer requested replacement | Meter exchange from a fully functional DB meter to a contestable meter as a opt-in/opt-out process |  | 6800 | [10 empty] | N | Y | No |  |  | N |  |  |  | N | Y | N |  |  | N |  |  | N
5 | DB meter - retail led DB meter replacement |  |  | 6800 | [10 empty] | N | Y | No |  |  | N |  |  |  | N | Y | N |  |  | N |  |  | N
6 | MC digital meter fault – customer off supply | Meter exchange from a COMMS meter to another COMMS meter | Type 4 to Type 4 | 6800 | [6 empty] | N | [14 empty] | N |  |  | N |  |  | N
7 | MC digital meter fault – customer on supply |  |  | 6800 | [6 empty] | N | [14 empty] | N |  |  | N |  |  | N
8 | MC meter customer requested replacement |  |  | 6800 | [6 empty] | N | [14 empty] | N |  |  | N |  |  | N
9 | MC meter - retail led MC meter replacement |  |  | 6800 | [6 empty] | N | [14 empty] | N |  |  | N |  |  | N
10 | MC meter - family failure of MC digital meter |  |  | 6800 | [6 empty] | N | [14 empty] | N |  |  | N |  |  | N
11
12 | DB meter fault- customer off supply | Meter exchange from faulty DB meter to a contestable meter as a forced replacement | Type 5/6 to Type 4 | 6300 | [10 empty] | N | N | N/A |  |  | N |  |  |  | N | Y | N |  |  | N |  |  | N
13 | DB meter fault – customer on supply |  |  | 6300 | [10 empty] | N | N | N/A |  |  | N |  |  |  | N | Y | N |  |  | N |  |  | N
14 | DB meter - family failure of DB meter |  |  | 6300 | [10 empty] | N | N | N/A |  |  | N |  |  |  | N | Y | N |  |  | N |  |  | N
15 | DB meter - customer requested replacement | Meter exchange from a fully functional DB meter to a contestable meter as a opt-in/opt-out process |  | 6300 | [10 empty] | N | N | No |  |  | N |  |  |  | N | Y | N |  |  | N |  |  | N
16 | DB meter - retail led DB meter replacement |  |  | 6300 | [10 empty] | N | N | No |  |  | N |  |  |  | N | Y | N |  |  | N |  |  | N
17 | MC digital meter fault – customer off supply | Meter exchange from a COMMS meter to another COMMS meter | Type 4 to Type 4 | 6300 | [6 empty] | N | [14 empty] | N |  |  | N |  |  | N
18 | MC digital meter fault – customer on supply |  |  | 6300 | [6 empty] | N | [14 empty] | N |  |  | N |  |  | N
19 | MC meter customer requested replacement |  |  | 6300 | [6 empty] | N | [14 empty] | N |  |  | N |  |  | N
20 | MC meter - retail led MC meter replacement |  |  | 6300 | [6 empty] | N | [14 empty] | N |  |  | N |  |  | N
21 | MC meter - family failure of MC digital meter |  |  | 6300 | [6 empty] | N | [14 empty] | N |  |  | N |  |  | N
Additonal Comments:
Acumen: If a retailer appoints Acumen as a MC for Type 5/6 meter via 6300, however if meter replacement doesn’t progress (customer prevention, etc.), Acumen would like DB to take the MC role back.
UE: For all mass market customers UE will object to a change in MC, MP, MDP etc. unless NMI Classification is LARGE or is to become LARGE, or the MC is not currently UNITED, or where an Embedded Network Child with UE metering is to have that metering removed.
AusNet: Scenarios 1-3 & 15-16 Metering Exclusivity. Scenario 4 & 5: As long as all roles are churned away from ASN in CR68xx, otherwise objection is raised. Scenario 15 & 16: Internal exception raised to ensure all roles are also churned away, else request new MC to Retro change back to ASN as MC
TasNetworks: If a new MC submits a CR6300 on an existing Type 6 NMI, TasNetworks expects that a subsequent submission of a CR6800 and corresponding meter exchange occurs as soon as possible thereafter. TasNetworks will not object to a 6800 being submitted to instigate a meter churn.

## PoC-PCF Act 16 Responses
Act 16
Processing DNP transactions
ActewAGL Distribution
Ausgrid
AusNet Services
CitiPower / Powercor
Endeavour Energy
Energex
Ergon
Essential Energy
SA Power Net
Jemena Networks
TasNetworks
United Energy