## Slide 1: EXECUTIVE forum
DATE: MON 29 MAY 2017
TIME: 1:30 PM– 2.30 PM (AEST)
VENUE: AEMO OFFICES; MEL, SYD, ADE, BRI
TELECONFERENCE: DIAL IN: 1800 055 132; PIN: 34862194
CONTACT: poc@aemo.com.au

## Slide 2: Power of Choice PROGRAM UPDATE

## Slide 3: AEMO Program Update
General:
AEMO released a series of letters to participant organisations CEOs to thank for support to date and to encourage further participation with AEMO and the readiness work.
AEMO Procedures
AEMO published an information paper on 12 May to give clarity to industry on the matters to be addressed in Package 3.
AEMO published Package 3 consultation and procedures on 19 May
Consultation closes on 27 June 2017
The team is working closely with Victorian Government to understand the implications of their announcement to delay metering competition in Victoria at this stage no changes to procedures are anticipated.
B2B Procedures
The IEC decided to accept the recommendation of the B2B Working Group and will not run a formal consultation on B2B Procedures at this stage.
The IEC released a memo detailing this decision and the process for the management of manifest errors identified in the procedures by participant and AEMO.
The B2B Working Group has a compiled a log of small clarifications and corrections which AEMO will publish on the IECs behalf.
Any suggested improvements or changes not identified as error corrections will be the subject to a consultation in 2018.

## Slide 4: AEMO Program Update AND UPCOMING TASKS
Systems
Gas Convergence / Platform was released “Live” into production on Sunday 21 May 2017
The SMP Technical Guide (guide to the new Web Methods interfaces and system) was published on 19th May.
r36 schema published on website + patch release(s) in accordance with B2B Change Log
r37 schema required for API users, currently in draft format on AEMO website – feedback by 1 June, current plan finalised end of June
Readiness:
Industry Testing Planning:
  Industry Testing Strategy – final version has been approved and published
  EN/MC Testing (Phase 1) – final version has been approved; testing to commenced 23 May
  B2B Testing (Phase 2) – test execution targeted to commence early-June
  Market Trial (Phase 3) – test execution targeted to commence mid-August
For Industry Testing Phase 3 (Market Trials) - SMP and MSATS release planned for 21 August
Accreditation and Registration Industry Plan – final version has been published
Transition and Cutover – planning discussions are continuing with the Readiness Working Group

## Slide 5: AEMO Program Update – upcoming MEETINGS / FORUMS
Program:
PCF next session will be held 9th June 2017.
  AEMO to update and facilitate a review of the Industry Risk Register
  Update on External Readiness Review
Systems:
Next SWG meeting is 15th June 2017
Readiness:
Next ITWG meeting will be 2nd June 2017.
First Industry Transition and Cut Over Focus Group Meeting was conducted on 26th May 2017
  Weekly meeting arranged
  Verbal update on process for Transition and Cut-over plan development

## Slide 6
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview
High Level Program V6.1 – 26 May 2017
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & B2B
Effective Date (Go-Live)
DNSPs & Retailers to publish amended standard contracts
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
B2B – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
B2B – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Transition & Cut Over Planning
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
B2B
Plan
Execute
Plan
Registration & Accreditation
Pre-Prod Release
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination
P
P
Industry Test Planning
Industry Test Execution
Transition

## Slide 7
2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 | 
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview – Readiness Work Stream
High Level Program V6.1 – 26 May 2017
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Industry Test Planning EN/MC
Industry Test Execution EN/MC
Accreditation & Registration
Transition & Cutover
Transition & Cutover Planning
P
Publish
Readiness reporting
Industry Testing
1 Dec
Go-live date
Mid-Nov
Final Industry Test Report
10 Apr
EN/MC changes in pre-production
06 Mar
B2B Procedures Published
28 Feb
WP2 Procedures Published
Industry Test Planning B2B/Market Trial
Industry Test Execution B2B
Connectivity/functionality testing
Planning
Accreditation and Registration Period
Market Trial Execution
Transition & Cutover
Post Go-Live
Heightened Support
2 Oct
Industry Transition & Cutover Plan Published
5 Jun
Industry Test Plan B2B Published
Readiness Reporting
5 Jun
10 Jul
7 Aug
11 Sep
9 Oct
6 Nov
4 Dec
8 May
3 Apr
6 Mar
8 Feb
Mid-Aug
B2B changes in pre-production
22 May
EN/MC patch release
Test Set-up
EN/MC

## Slide 8: Industry Issues Register
System cut-over:
Industry raised an issue for discussion:
  Current assumptions are that the existing market arrangements and systems will cease to operate on Thursday 30 November, new arrangements (Rules, Procedures etc.) will commence morning of Friday 1st December.
  In effect, an overnight cut-over
Discussion:
  Participants have advised a range of systems outage timings spanning from 12 to 48+ hours
  Participants raised impacts to month end processes
Next steps:
AEMO seeking feedback on a proposed cut-over period spanning COB Friday 2 December to commencement of business, Monday 5 December.
Industry feedback required by 31 May 2017.

## Slide 9: Watching briefs
Treatment of Vic AMI meters
  Alterations to Market systems (Meter Type identification codes; ‘MRIM’ & ‘RWD’)
  Updates to substitution methodology ‘labels’ in data provision
  Requirement for VIC DBs to accredit against the MDP Type 4 with consideration to arrangements made under clause 11.86.7
  Other obligations: removal of NSRD
Vic Govt announcement on 10 May 2017 intentions for meter classification.
“These Orders will also specify that Victorian smart meters (including new and replacement meters) should continue to be classified as 'type 5 metering installations' (rather than type 4 metering installations) and continue to meet the Victorian Minimum AMI Functionality Specification and Victorian Minimum AMI Service Level Specification going forward.”
Vic Govt. Consultation on Competition in Metering
  Decision made: Option 4
  Detail to be worked through in a focus group
    Basic principle: in Victoria, the FRMP will be required to appoint the LNSP as the MC
  Potential alterations to Procedures & systems to accommodate outcomes
Vic Govt planning on releasing a draft Order-in-Council in May.
AEMO envisages that no subsequent Procedure changes will be required – to be confirmed

## Slide 10: Power of Choice Readiness update Industry Readiness Reporting

## Slide 11: Market readiness update
Market Readiness
May Industry Readiness Reports – received 35 participant reports. Market Readiness Reports can be found here Industry Readiness Reporting.
Accreditation and Registration:
  Final versions of the POC Industry Accreditation and Registration Plan and B2B e-Hub Accreditation Revocation Process published on 28 April.
Industry Testing:
  Final versions of the POC Industry Test Strategy, EN/MC Industry Testing Plan and Test Workbook endorsed on 12 May.
  Testing for Phase 1 (EN/MC changes) commenced on 23 May, concluding on 30 June.
Transition & Cutover:
  Planning discussions continue with the POC Transition & Cutover Focus Group.

## Slide 12: May 2017 READINESS REPORT
Summary:
Project status remains amber in May 2017:
  Status of “at risk” of achieving project deliverables on schedule.
  Progress increased to approximately 30% (from 20%).
  Risk rating of “medium”.
Participant categories:
  Retailer, Distributors, Meter Providers and Meter Data Providers mainly reporting amber (“at risk”).
  Prospective Metering Coordinators mainly reporting amber and red (“not within schedule”) with a high risk rating.
  AEMO and prospective Embedded Network Managers overall reporting green (“within schedule”).

## Slide 13: MAY 2017 READINESS REPORT
Summary (cont.):
Jurisdictional status and risk rating in line with overall project status with additional risks highlighted:
  High risk rating in Victoria from Retailers – due to uncertainty related to the impacts of the Victorian Government decision to defer metering competition.
  High risk rating in NSW from Distribution Businesses – due to risks associated with system delivery in time for industry testing in August 2017.
  High risk rating in all jurisdictions from Metering Providers, Meter Data Providers and Metering Data Providers – due to current status of systems implementation.

## Slide 14: May 2017 READINESS REPORT
Highlighted risks:
Amber status relates primarily to constrained timelines for delivery:
  Uncertainties in operation of business processes (e.g. meter churn), distribution business' faults and emergencies processes, Victorian OIC.
  Compressed timeframes for system design, build and testing.
  Compressed timeframes for registration and accreditation – including e-hub accreditation.
  Compressed timeframes for transition and cutover planning, and timing and implications of cutover activities.
Other issues highlighted include:
  Lack of clarity on safety regulations.
  Number and level of maturity of competitive metering providers, Metering Coordinators and Embedded Network Managers.
Mitigating actions include:
  AEMO progressing industry test planning, with Industry Test Strategy nearing completion and detailed planning commencing.
  AEMO established the Industry Transition and Cutover Focus Group.
  AEMO to encourage competitive metering providers and prospective new participants to actively engage in the POC program.
  Participants encouraged to commence registration and accreditation.

## Slide 15: MAY 2017 READINESS REPORT
Number of submissions:
35 reports received in total representing the following participant roles (increased from 34 in April):
  18 retailers (increased from 17)
  13 distribution businesses (includes initial MC, MP and MDP)
  5 metering companies (MPD, MP) (unchanged)
  5 metering coordinators (MC) (decreased from 6)
  2 embedded network manager (ENM) (decreased from 3)
Approximately 19 retailers are not yet taking part in industry reporting
Note that organisations can nominate for multiple roles and participants can submit combined reports (i.e. one report for two distribution businesses)

## Slide 16
Next Meeting:
Friday 25 July 2017