## Slide 1
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview
High Level Program V7.0 – 14 Nov 2017
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & B2B
Effective Date (Go-Live)
DNSPs & Retailers to publish amended standard contracts
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
B2B – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
B2B – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Transition & Cut Over Planning
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
B2B
Plan
Execute
Plan
Registration & Accreditation
Pre-Prod Release
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination
P
P
Industry Test Planning
Phase 1
Transition
Phase 2
Market Trial – Phase 3

## Slide 2
2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 | 
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview – Readiness Work Stream
High Level Program V7.0 – 14 Nov 2017
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Industry Test Planning EN/MC
Phase 1 Execution EN/MC
Accreditation & Registration
Transition & Cutover
Transition Planning
P
Publish
Readiness reporting
Industry Testing
1 Dec
Go-live date
17 Nov
Industry Test Report
10 Apr
EN/MC changes in pre-production
06 Mar
B2B Procedures Published
28 Feb
WP2 Procedures Published
Industry Test Planning B2B/Market Trial
Phase 2 Execution B2B
Planning
Accreditation and Registration Period
Phase 3 Market Trial Execution
Transition
Heightened Support
2 Oct
Industry Transition & Cutover Plan Published
5 Jun
Industry Test Plan B2B Published
Readiness Reporting
5 Jun
10 Jul
7 Aug
11 Sep
9 Oct
6 Nov
4 Dec
8 May
3 Apr
6 Mar
8 Feb
16 Aug
Pre-Production system release
22 May
EN/MC patch release
Test Set-up
EN/MC
Cutover Planning
1 Sep
Draft Transition and cutover plan
29 Sep
Final Transition and cutover plan review
Outage Window
11 Aug
Submit entry Criteria checklist
21 Aug
Commence Phase 3 Market Trials
System Cutover
1 Mar
Qualification, registration & accreditation checklists published
24 Mar
Second draft plan published
28 Apr
Registration & Accreditation plan published
9 May
Participant Information Session
31 Oct
Confirmation of registration and accreditation status
14 Aug
Commence daily meetings
16 Aug
E-Hub Certification screens released
28 Jul
Market Trial workbook complete
Cycle 1
Cycle 2
Cycle 3
Contingency Planning
Continued Accred / Rego
15 - 27 Nov
System cutover dress rehearsal
Bi-lateral Testing

## Slide 3: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description / Notes | Planned date | Expected date | Status
AEMC publish MRP Directions paper & EN draft determination | EN, MRP |  | 10 Sep 15 |  | 
AEMC publish SMP advice paper | SMP |  | Early-Oct 15 | 10 Oct 15 | 
AEMC publish final rule determination | MC |  | 24 Nov 15 | 26 Nov 15 | 
AEMC release final determination | EN |  | 17 Dec 15 |  | 
AEMC release draft determination | MRP |  | 17 Dec 15 |  | 
AEMC publish draft rule determination | SMP |  | Early-Feb 16 | 07 Apr 16 | 
AEMC publish final rule determination | MRP |  | 10 Mar 16 |  | 
AEMO pre-consultation workshops conclude | MC,EN,MRP |  | 11 Mar 16 |  | 
AEMO releases Pre-Consultation Paper | MC,EN,MRP |  | 08 Apr 16 |  | 
AEMO publishes notice first stage consultation | MC,EN,MRP |  | 22 Apr 16 |  | 
AEMC publish final rule determination | SMP |  | 26 May 16 | 30 Jun 16 | 
AEMO concludes first stage consultation | MC,EN,MRP |  | 31 May 16 |  | 
AEMO commences Readiness Work Stream engagement | MC,EN,MRP |  | 20 Jun 16 | 21 Jun 16 | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 30 Jun 16 | 29 Jun 16 | 
AEMO concludes second stage consultation | MC,EN,MRP |  | 15 Jul 16 | 20 Jul 16 | 
AEMO publishes final procedure determination | MC,EN,MRP | No later than 1 Sep 16 | 26 Aug 16 | 31 Aug 16 | 
AEMO publishes notice first stage consultation (WP2) | MC,EN,MRP |  | 10 Oct 16 |  | 
AEMO publishes notice first stage consultation | B2B: All |  | 10 Oct 16 | 20 Oct 16 | 
IEC Election complete – IEC formed | SMP | Noting this is a no later than date. | 01 Sep 16 | 01 Sep 16 | 
AEMO finalises Industry Readiness Reporting Plan | Readiness |  | 06 Oct 16 |  | 
AEMO commences Systems Work Stream engagement | Systems |  | 07 Oct 16 |  | 
Readiness Reporting commences | Readiness |  | 14 Nov 16 |  | 
AEMO concludes first stage consultation | MC,EN,MRP |  | 15 Nov 16 |  | 
Notes: Intent to Publish

## Slide 4: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description | Planned date | Expected date | Status
AEMO concludes first stage consultation | B2B: All |  | 15 Nov 16 | 02 Dec 16 | 
AEMO commences consultation of Fee Methodology | All |  | Nov 16 | 03 Nov 16 | 
AER publishes ring fencing & network exemption guidelines | - |  | 01 Dec 16 |  | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 13 Dec 16 |  | 
AEMO publish draft procedure determination | B2B: All | No later than 4 January 2017 | 13 Dec 16 | 23 Dec 16 | 
System implementation period commences | All |  | Mid Dec 16 |  | 
AEMO concludes Fee Methodology first stage consultation | All |  | 16 Dec 16 |  | 
AEMO concludes second stage consultation (WP 2) | MC,EN,MRP |  | 30 Dec 16 | 16 Jan 17 | 
AEMO concludes second stage consultation | B2B: All |  | 30 Dec 16 | 20 Jan 17 | 
IEC ‘recommends’ B2B Procedures to AEMO’s Board | B2B: All | TBC Preceding AEMO Feb Board | 22 Jan 17 | 20 Feb 17 | 
AEMO publishes Draft Fee Methodology | All |  | 06 Feb 17 | 23 Feb 17 | 
AEMO concludes second stage consultation Fee Methodology | All |  | 21 Feb 17 | 10 Mar 17 | 
AEMO publishes final procedure determination | MC,EN,MRP | Obligation is no later than 1 Mar 17 | 01 Mar 17 | 28 Feb 17 | 
AEMO publishes final procedure determination | B2B: All | Obligation is no later than 1 Jun 17 | 01 Mar 17 | 06 Mar 17 | 
Commencement of registration / accreditation activities | Readiness | To be determined in readiness strategy | 01 Mar 17 |  | 
AEMO Publishes Final Determination Fee Methodology | All |  | 31 Mar 17 | 21 Apr 17 | 
Industry testing period detailed planning commences | Industry Testing |  | Mar 17 | Mid-Feb 17 | 
Industry detailed cut-over and transition planning commences | Trans & Cut Over |  | Apr 17 | Mid -Mar 17 | 
AEMO releases EN/MC Pre-Prod MSATS | Systems |  | 10 Apr 17 |  | 
Registration and Accreditation Plan Published | Readiness |  | 28 Apr 17 |  | 
AEMO facilitates Industry Information Session (B2B e-hub) | Readiness |  | 09 Mar 17 |  | 
AEMO releases EN/MC Pre-Prod MSATS – PATCH | Systems |  | 22 May 17 |  | 
Phase 2 Test Plan (B2B) Published | Industry Testing |  | 05 Jun 17 |  | 
Phase 2 Test Execution Commences | Industry Testing |  | 19 Jun 17 |  | 
Phase 3 Test Plan (Market Trial) Published | Industry Testing |  | 30 Jun 17 |  | 
Notes: Intent to Publish

## Slide 5: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description | Planned date | Expected date | Status
Phase 1 Test Execution Complete | Industry Testing |  | 30 Jun 17 |  | 
Phase 3 Market Trial Workbook Published | Industry Testing |  | 28 Jul 17 |  | 
Phase 2 Test Execution Complete | Industry Testing |  | 28 Jul 17 |  | 
Transition planning workshops conclude | Trans & Cut Over |  | 08 Aug 17 |  | 
Market Trial daily meetings commence | Industry Testing |  | 14 Aug 17 |  | 
AEMO releases updates systems into pre-production | Systems |  | 16 Aug 17 |  | 
E-Hub Certification screens released | Readiness |  | 21 Aug 17 |  | 
Phase 3 Market Trial cycle 1 commences | Industry Testing |  | 21 Aug 17 |  | 
Transition and cutover plan draft released | Trans & Cut Over |  | 01 Sep 17 |  | 
DNSPs publish T&C’s on which it will act as the initial MC | DNSPs |  | 01 Sep 17 |  | 
Phase 3 Market Trial cycle 1 concludes | Industry Testing |  | 08 Sep 17 |  | 
Phase 3 Market Trial cycle 2 commences | Industry Testing |  | 18 Sep 17 |  | 
Transition and cutover plan published | Trans & Cut Over |  | 02 Oct 17 |  | 
Phase 3 Market Trial cycle 2 concludes | Industry Testing |  | 06 Oct 17 |  | 
Phase 3 Market Trial cycle 3 commences | Industry Testing |  | 16 Oct 17 |  | 
Registration & accreditation confirmation status | Readiness |  | 31 Oct 17 |  | 
Phase 3 Market Trial cycle 3 concludes | Industry Testing |  | 03 Nov 17 | 04 Nov 17 | 
Transition activities commence | Trans & Cut Over | Per industry plan | 13 Nov 17 | 01 Nov 17 | 
Phase 3 Market Trial Report released | Industry Testing |  | 17 Nov 17 |  | 
PoC Effective date | All | Allowance for weekend system cutover | 01 Dec 17 | 04 Dec 17 | 
Cutover Activities commence | Trans & Cut Over | COB Friday 1 Dec 17 | 01 Dec 17 |  | 
Cutover Activities conclude | Trans & Cut Over | OOB Monday 4 Dec 17 | 04 Dec 17 |  | 
Transition activities concludes | Trans & Cut Over |  | 08 Dec 17 |  | 
Heightened Support Period | All |  | 02 Mar 18 | 30 Mar 18 | 
Notes: Intent to Publish

## Slide 6: PoC - Program Overview Version history
This table summarises the changes between the Program Overview as information changes or becomes available.
Version | Date | Amendments
5.0 | 21 Mar 17 | Removed Procedures Work stream outlook. Updated ‘As Built’ package timeframes
5.1 | 6 Apr 17 | Updated Readiness Work Stream overview following RWG and ITWG (Apr 2017)
5.2 | 19 Apr 17 | Removed Industry Test Box and extended Market Trial Box
6.0 | 19 May 17 | Updated Tracking
6.1 | 26 May 17 | Updated Tracking
6.2 | 18 Jul 17 | Updates Tracking Update WP 3 / As Built consultation dates amended Updated Readiness work stream program overview
6.3 | 14 Aug 17 | Updated Tracking
6.4 | 24 Aug 17 | Updated Tracking
6.5 | 8 Sep 17 | Updated Tracking – Included Contingency planning activity
6.6 | 28 Sep 17 | Updated Tracking
6.7 | 13 Oct 17 | Updated Tracking
6.8 | 24 Oct 17 | Updated tracking – Included amended dates according to Industry Transition and Cut-over plan
6.9 | 06 Nov 17 | Updated Tracking
7.0 | 14 Nov 17 | Included continuation of rego / accred Included bi-lateral testing period Included dress rehearsal for industry cutover Updated tracking

## Slide 7
2016 |  |  |  |  |  |  |  |  | 2017 |  | 
APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR
Today
Power of Choice (PoC) Program Overview – Procedure Workstreams (6 month outlook)
High Level Program V 6.1 – 26 May 2017
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
AEMO Review
Stage 2
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Group 1
Accreditation / Deregistration Procedures
Consultation Stage 1
Stage 3
AEMO Review
Stage 4
P
P
P
WORK PACKAGE 1
AEMO Review
Stage 2
Consultation Stage 1
Stage 3
AEMO Review
Stage 4
P
P
P
WORK PACKAGE 2
Group 2
ENM SLP / Accred Procedures
Group 3
NMI Procedure / Glossary
Communication Mapping
30 Jun
SMP Final Determination
29 Jun
AEMO WP1 publishes Draft Determination
Scope / Procedure Structure
Payload / Transaction Design
AEMO Procedure Drafting / Updating
MC /
EN /
MRP
Procedures
Work Package #2
B2B
Procedures
Establish WG
P
Publish
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
MC /
EN /
MRP
Procedures
Work Package #1
22 Apr
WP1 Consultation begins
31 May
WP1 Submissions Close
20 Jul
WP1 second stage submissions close
31 Aug
WP1 AEMO publishes final determination
17 Oct
IEC ‘Request’ AEMO to conduct Procedure Consultation
10 Oct
WP2 Consultation begins
15 Nov
WP2 Submissions Close
13 Dec
AEMO WP2 publishes Draft Determination
16 Jan
WP2 second stage submissions close
B2B Review Stage 2
Consultation Stage 1
Stage 3
B2B Review
Stage 4
P
P
P
B2B PROCEDURES
W/C 19 Dec
B2B IEC endorse draft procedures for consultation
W/C 20 Feb
IEC ‘Recommends’ final Procedures
28 Feb
MC
Registration & EN MSL and Accreditation Documentation Published
Industry Review
27 Oct
B2B Consultation begins
02 Dec
B2B Submissions Close
23 Dec
B2B AEMO publishes Draft Determination
20 Jan
B2B second stage submission close
06 Mar
B2B Procedures Published
Iterative process