## Market Readiness Report Page 1
42800
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2017-03-06
Overall Status |  | Commentary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | The overall project status remains amber with participants reporting ongoing risks of implementing the required systems and process changes on schedule. Participants are undertaking impact assessments – comparing the final B2B procedures with the drafts – and some participants are concerned that the changes will require more effort to implement than originally estimated. A Medium level of risks persists for the project overall due to aggressive timelines combined with a level of uncertainty around the operation of business processes under the new Rules and Procedures and dependency on new and immature market participants. A High level of risk persists in Victoria due to the uncertainty associates with the Victorian Government Transition to Metering Competition decision timing in March 2017. |  |  |  |  | High | Med | Low | #
[7 empty] | 4 | 2 | 3 | 1
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Networks (ENM, ENO) |  | Third party e-hub
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place |  |  |  | #1
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with regulatory changes including jurisdictional regulations and requirements (e.g. safety) |  |  |  | #2 |  | #2 |  |  |  | #2
2.3 |  | Operationally critical commercial contracts in place |  |  |  | #3 |  |  |  | #3 |  | #3 |  | #3
2.4 |  | Accreditation and registration activities completed |  |  |  | #4 |  |  |  | #4 |  |  |  | #4
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place | [5 empty] | #5
4.2 |  | Successfully validated critical business processes during industry testing
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing
5.2 |  | Successfully tested market systems capable of being moved into production |  |  |  | #6 |  | #6 |  | #6 |  | #6 |  | #6
5.3 |  | Performance of, and communication between, market systems validated during industry testing | [5 empty] | #7 |  |  |  | #7 |  | #7
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place | [9 empty] | #8 |  | #8
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals) | [7 empty] | #8 |  | #8 |  | #8
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Networks (ENM, ENO) |  | Third party e-hub
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdictional risk is a reflection of overall project risk.
NSW |  | Jurisdictional risk is a reflection of overall project risk.
QLD |  | Jurisdictional risk is a reflection of overall project risk.
SA |  | Jurisdictional risk is a reflection of overall project risk.
TAS |  | Jurisdictional risk is a reflection of overall project risk.
VIC |  | Jurisdictional risk is a reflection of overall project risk, with additional risk noted due to the uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017, and the treatment of VICAMI meters.

## HIDDEN 25% (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2017-03-06
Variances
Note # | Explanation of Variance |  |  | Mitigating Actions
1 | Variance reported by Retailers: Detailed implementation plan development at risk due to uncertainty of rule and procedural operation and dependency on new and immature market participants and processes.
2 | Variance reported by Participants: Updating policies and procedures on schedule is at risk due to lack of clarity on safety regulation and the upcoming Victorian decision on metering competition. |  |  | Participants are continuing to engage with the relevant departments and safety bodies.
3 | Variance reported by Participants: Updating commercial arrangements on schedule is at risk due to volume of contracts that need to be entered into with industry parties and variable meter service provider maturity.
4 | Variance reported by Participants: Fulfilling registration and accreditation activities on schedule is at risk due to lack of an E-Hub accreditation guideline and compressed timeframes for all registration and accreditation activities |  |  | Participants are awaiting e-hub accreditation guidelines. Vic DBs are continuing to seek confirmation from AEMO, AER and Victorian Government on whether UE's meters can remain as Type 5 MRIM.
5 | Variance reported by DBs: Progress on this is less than expected due to required rework from the final B2B Procedure changes. Rework may also be need to occur depending on the Vic Government Option decided in March 2017. |  |  | Business process activity continuing (impact assessment between final and draft procedures), additional experienced resources and subject matter experts sourced.
6 | Variance reported by Participants: System design and development are dependent on finalisation of procedures and technical specifications for completion. From DBs: The magnitude of change in the final version of the B2B Procedures particularly with regard to the NP and OWN's in the latest B2B Guidelines requires a revisit of requirements and reassessment of design. |  |  | Participants are gathering detailed business and system requirements (undertaking impact assessments between final and draft procedures).
7 | Variance reported by Participants: Testing timelines are contingent on system design and build and are becoming increasingly compressed and unrealistic. |  |  | Participants engaging in development of Industry Testing Strategy
8 | Variance reported by Participants: Transition and cutover is dependent on above activities (business processes, commercial arrangements, system build and testing) and compressed timeframes are a concern.
Notes
Key - Progress and Status | [5 empty] | Key - Risk Rating
Progress |  |  | Status
Harvey balls represent progress towards achieving the criterion |  |  | Colour indicates the readiness status |  |  | Rating
~0% |  | ~50% | Criterion is within agreed schedule and deliverable requirements |  |  | High
~10% |  | ~60% | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~20% |  | ~70% | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~30% |  | ~80% |  |  |  | See POC Industry Risk Register for open risks and issues:
~40% |  | ~90% | Criterion has been achieved |  | ü | POC Industry Register

## Retailer Reports
| 2017-03-06 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Retail | Within schedule | Medium | ActewAGL Retail is still undertaking a high level impact assessment of the changes required by PoC on its business operations and systems, and a project plan is being finalised in order to achieve compliance by the "go live" date.
| AGL | Within schedule | Medium | Project currenly tracking to plan for Dec 2017 delivery. Risk rating remains at medium rating due to key project dependencies such as B2B procedure timing and limited industry testing timeframes. Decision for Victorian derrogation relating to Vic AMI meters also a key risk. | [7 empty] | Risk rating medium due to the number of project interdependencies, B2B impacts and delivery risks such as aggressive industry testing timeframes.
| Alinta Energy | Within schedule | Medium | Project progressing to plan
| Aurora Energy | At risk | Medium | Aurora Energy continues to manage a number of risks with regards to the implementation of the Power of Choice reforms by 1 December 2017. The most significant risks are the aggressive timeline combined with the uncertainty of rule and procedural operation. This is reflected in Aurora Energy's 'at risk' project status. These risks are also impacting on the ability of Aurora Energy's key vendors (including, but not limited to, prospective Metering Coordinators) to meet POC timeframes.
| Energy Australia | At risk | Medium | The Program is making steady progress but is behind schedule in several areas due to the extent of changes in the B2B procedures. There is high risk to schedule due to variations in the Final version of B2B procedures, outstanding decision by the Victorian Government on Options, lack of clarity on safety regulations and conversion of VicAMI type 5 to Type 4. | [7 empty] | The Program is making steady progress but is behind schedule in several areas due to the extent of changes in the B2B procedures. There is high risk to schedule due to variations in the Final version of B2B procedures, outstanding decision by the Victorian Government on Options, lack of clarity on safety regulations and conversion of VicAMI type 5 to Type 4.
| Ergon Energy Queensland (retail) | Within schedule | Medium | Due to the high number of changes to our retail billing system due to procedural and B2B changes, overall this project remains as a 'medium risk'. At this stage no changes have been made to jurisdictional safety requirements which will enable remote re-energisation. This remains a risk that retailers will not achieve the full benefits without these changes. | [7 empty] | Due to the high number of changes to our retail billing system due to procedural and B2B changes, overall this project remains as a 'medium risk'. At this stage no changes have been made to jurisdictional safety requirements which will enable remote re-energisation. This remains a risk that retailers will not achieve the full benefits without these changes.
| M2 Energy Pty Ltd | Within schedule | Medium | Project Scoping by Vendor has commenced. Business operations impact scope has commenced. Business intention is to outsource MC role. Risk considered Medium as few vendors currently available for selection. M2 Energy is maintaining dialogue with potential vendors. | [7 empty] | Business intention is to outsource MC role.
| Mojo Power Pty Ltd | Within schedule | Medium | [8 empty] | Mojo is in process of obtaining its retail license in Victoria, uncertainity about Victoria's metering competition decision making has this ranked higher.
| Momentum Energy | Within schedule | Medium | Work packages and final B2B procedure documentation is not due until March 2017. All current scoping and impact assessments have been based on draft procedures. Any significant changes from draft procedures will have a direct project impact due to constrained timelines for project.
| Origin Energy | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Business and Systems impact assessments are completed and Project Blueprinting is progressing well and to. Amber status is maintained due to high number of delivery risks that will need to be monitored and mitigated for the duration of the project | [7 empty] | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Business and Systems impact assessments are completed and Project Blueprinting is progressing well and to. Amber status is maintained due to high number of delivery risks that will need to be monitored and mitigated for the duration of the project
| Pacific Hydro | Within schedule | Medium | The timing and outcomes of the following outstanding PoC activities have the potential to impact the build, test and implementation phases: 1. MSATS WP3. 2. B2B - As Built Consultation - Commencing 12 April. 3. B2B - technical solution - under review by AEMO and yet to be advised. 4. Meter Churn Issues - recently raised and yet to be resolved. 5. Vic Government decision on AMI meters - expected this month. 6. Jurisdictional safety review of the remote Re-en/De-en process. There is also an issue with other Market changes, e.g. Retail Transfer Errors to take effect 3 August 2017, being introduced within the PoC delivery timeframe.
| People Energy Pty Ltd | Within schedule | Medium | Overall this project remains as a 'medium risk', There is a high number of changes to our retail billing system due to procedural and B2B changes.
| Red Energy | At risk | Medium | Not clear on implications of any Victorian Government decision and additional system and process consequences from the decision | [7 empty] | Finalisation of B2B and SMP protocols required to assess process and system impacts fully Implications of any Victorian Government decision not known
| Simply Energy | Within schedule | Low | [14 empty] | Simply Energy has progressed as per it's internal plan of Power of Choice Program of Work and have prioritised B2M changes in order to commence testing for r35 schema, currently targetting May/June 2017. The program has not yet identified any internal risks apart from issues raised in the Meter Churn Procedures workshop held on the 24th Feb 2017. If the issues raised in the meeting are not resolved in WP3, it can pose a significant market readiness issue.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Retail | Within schedule | Medium | Within schedule | Medium
| AGL | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Alinta Energy |  |  | Within schedule | Medium |  |  | Within schedule | Medium |  |  | Within schedule | Medium
| Aurora Energy | [8 empty] | At risk | Medium
| Energy Australia | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ergon Energy Queensland (retail) |  |  |  |  | Within schedule | Medium
| M2 Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Mojo Power Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | High
| Momentum Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| People Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Red Energy |  |  | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | High
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Red Energy | Simply Energy | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 21% - 30% | 81% - 99% | 25% | 21% - 30% | 71% - 80% | 61% - 70% | 25% | 51% - 60% | 71% - 80% | 50% | Completed (100%) | 21% - 30% | 31% - 40% | 71% - 80%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 11% - 20% | 1% - 10% | 25% | 21% - 30% | 51% - 60% | 31% - 40% | 25% | 1% - 10% | 21% - 30% | 50% | 51% - 60% | 1% - 10% | 1% - 10% | 51% - 60%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 11% - 20% | 61% - 70% | 0% | 11% - 20% | 41% - 50% | 51% - 60% | 0% | 51% - 60% | 11% - 20% | 25% | 51% - 60% | 1% - 10% | 81% - 99% | 21% - 30%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Not started (0%) | Not started (0%) | 0% | 11% - 20% | 1% - 10% | 11% - 20% | 0% | 51% - 60% | Not started (0%) | 25% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Not started (0%) | 1% - 10% | 0% | 1% - 10% | 1% - 10% | 1% - 10% | 0% | 61% - 70% | Not started (0%) | 0% | Not started (0%) | 1% - 10% |  | 21% - 30%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Not started (0%) | N/A | N/A | 1% - 10% | 21% - 30% |  | 0% | N/A | 11% - 20% | 25% | 31% - 40% | 1% - 10% |  | 41% - 50%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Not started (0%) | N/A | N/A | 1% - 10% | Not started (0%) |  | N/A | N/A | 1% - 10% | 0% | Not started (0%) | Not started (0%) |  | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 0% | 11% - 20% | 41% - 50% |  | 0% | 21% - 30% | 1% - 10% | 50% | 31% - 40% | 1% - 10% | 11% - 20% | 21% - 30%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 0% | 21% - 30% | 31% - 40% |  | N/A | 71% - 80% | Not started (0%) | 25% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | 0% | 1% - 10% | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 11% - 20% | 31% - 40% | 0% | 31% - 40% | 51% - 60% | 31% - 40% | 0% | Not started (0%) | 1% - 10% | 50% | 21% - 30% | 1% - 10% | 1% - 10% | 31% - 40%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Not started (0%) | 1% - 10% | 0% | 31% - 40% | 11% - 20% | 1% - 10% | 0% | Not started (0%) | Not started (0%) | 25% | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 1% - 10% | 21% - 30% | 25% | 41% - 50% | 61% - 70% | 31% - 40% | 25% | Not started (0%) | 31% - 40% | 25% | 11% - 20% | 11% - 20% | 1% - 10% | 21% - 30%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Not started (0%) | 11% - 20% | 0% | 1% - 10% | 21% - 30% |  | 0% | Not started (0%) | 1% - 10% | 25% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | 11% - 20% | 0% | Not started (0%) | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | Not started (0%) | 0% | 1% - 10% | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 25% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Red Energy | Simply Energy | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | N/A | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule |  | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule |  | N/A | N/A | Within schedule | At risk | Within schedule | N/A | N/A | N/A
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Red Energy | Simply Energy | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Impact assessment is still in progress |  | In Progress | A detailed assessment of necessary business operational process and systems changes is currently being completed. This continues to be informed by on-going AEMO market procedure consultation. Given the uncertainty of rule and procedure operation, this is considered 'at risk'. | Increasing certainty around procedures (excl Vic) |  |  |  |  | Impact Assessment completed, but will need to be iterated pending consultation outcomes and changes |  |  | Awaiting finalisation of B2B and SMP changes and Victorian government decision
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | A project plan will be finalised after the impact assessment has been completed, see 4.1 and 5.1 below |  | In Progress | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging (only). Additional changes to enable all other core operations post 1 December 2017 are being assessed. The aggressive timelines for systems build and testing, combined with the uncertainty of rule and procedural operation is the basis of the 'at risk' status. | High level of depedency on third parties. Plans are dependent on new and immature market participants and processes. |  |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines |  |  | Awaiting finalisation of B2B and SMP changes and Victorian government decision
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | The ACT Government is reviewing the ACT regulatory framework |  |  | Activity has commenced as part of POC impact assessment. | Assessment in progress and on track but there are still unknowns in regards to jurisdictional safety requirements, and associated obligations on Retailers and MCs. | Queensland jurisdictional safety requirements are yet to be addressed. | shceduled and commenced. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines |  |  | Excludes Victoria and any potential changes required for Victoria | Awaiting jurisdictional safety regulators to publish requirements
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [8 empty] | Preliminary advice has been sough with regards to regulatory compliance. In addition to direct metering competition regulatory changes, a key challenge for Aurora Energy is to consider the wider (/indrect) regulatory implications of metering competition on business-as-usual activities. A key challenge is that the existing regulatory framework was developed in the context of type 6 metering. | Red due to the lack of clarity on safety regulations and the late commencement of our safety work stream | Queensland jurisdictional safety requirements are yet to be addressed. | not yet scheduled. |  |  | Policy changes/decisions still being derived through Blueprinting
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [8 empty] | Activity has commenced. | Due to volume of contracts that need to be entered into with industry parties, plus variable meter service provider maturity. | These processes have commenced. | not yet scheduled. |  |  | Unable to commence until Blueprinting and overall strategy has been developed and endorsed |  |  | Internal management of this item
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy will be required to receive accreditation for using the B2B e-hub, however there is, as yet, no documentation available to prepare for accreditation. The timeline and uncertainty for accreditation and registration activities of other participants (specifically, the Metering Coordinator role) also impacts on Aurora Energy's planning. Dialouge with the jurisdictional safety regulator has commenced. |  |  | not yet scheduled. |  |  | Underway for new Market Roles |  |  | Internal management of this item
2.5 |  | The fulfilment of accreditation and registration obligations | [8 empty] | Aurora Energy will be required to receive accreditation for using the B2B e-hub, however there is, as yet, no documentation available to prepare for accreditation. The timeline and uncertainty for accreditation and registration activities of other participants (specifically, the Metering Coordinator role) also impacts on Aurora Energy's planning. Dialouge with the jurisdictional safety regulator has commenced. | [5 empty] | Unable to commence until Blueprinting and overall strategy has been developed and endorsed |  |  | Internal management of this item | Pending outcome from 2.4
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Will commence after impact assessment has been completed |  |  | This has commenced and will be finalised following with the detailed assessment of operational and systems changes. | Being developed as impacts are understood and target state design is finalised |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | The recruitment of specialist human resources to cater for the rule change has commenced. | As above |  |  |  |  | Policy changes/decisions still being derived through Blueprinting |  |  |  | Scheduled to commence in mid 2017
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [8 empty] | Training requirements are currently being assesed as part of the internal Process review and updates. | As above. |  | not yet scheduled. |  |  | Training requirements and resourcing unable to be accurately determined until High Level Requirements and Blueprint is completed and magnitude of change is understood |  | This task is yet to commence |  | Scheduled to commence in late 2017
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependent on B2B procedures which will determine the scope of required changes to business processes |  |  | All impacted service order, B2B & B2M and business processes have been identified. Assessment of current and future processes is underway to enable gap analysis and identify process and system changes. However as there are likely to be further changes to B2B and possibly B2M procedures, this introduces considerable planning uncertainty for Aurora Energy (and consequently puts the delivery scope and timeline at risk). | Slippage in the schedule - a plan to bring back slippage is underway. Also dependent on finalisation of industry-wide processes. |  | commenced and in schedule |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines |  |  | Awaiting finalisation of B2B and SMP changes and Victorian government decision
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [8 empty] | Future business processes are currently being developed using the details from Work package 1 and 2, as well as the B2B draft procedures. However as there are likely to be further changes to B2B and possibly B2M final published document this is considered by Aurora Energy to be 'at risk'. | As above |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines
4.3 |  | The validation of business processes during industry testing | [8 empty] | Activity has not yet started. |  |  | not yet scheduled. |  |  | Not Commenced |  |  |  | Scheduled to commence in March 2017
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Scoping of changes to systems to be conducted in conjunction with the external vendor |  | Assessment commenced in conjunction with the vendor | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging systems (only). However as advised previously due to possible further changes to B2B procedures this puts Aurora Energy's delivery scope and timelines 'at risk'. Further, the agressive timeframe also impacts on the ability of Aurora Energy's key vendors (including, but not limited to, prospective Metering Coordinators) to deliver the required system changes. | Our plans are dependent on external parties, finalisation of procedures and technical specifications for completion. | Blueprinting complete | Vendor at 35% completion of overall project plan |  | System development is reliant on external vendor, delays in final market procedures will impact readiness activities | Detailed impact assessment of system changes has only just commenced, and is highly dependent on decisions, outcomes and information provided in Systems and B2B Working Groups | A full assessment cannot be undertaken until the technical solution for B2B is known and the Final Determination on the B2B Procedures is released. |  | Awaiting finalisation of B2B and SMP changes and Victorian government decision
5.2 |  | The development and build of appropriate market systems for your business | [8 empty] | Aurora Energy has engaged its key vendors to plan for system changes. However, systems changes will still be impacts by the final full set of changes to the B2B/B2M environment. | As above |  |  |  |  | Systems development commencement is dependent on the outcomes and conclusions of the Systems IA and Requirements being understood |  |  | Awaiting finalisation of B2B and SMP changes and Victorian government decision | Scheduled to commence in 2017
5.3 |  | The internal testing of market systems for your business | [8 empty] | This has not started and not due to start until 2017. | As above |  |  |  |  | Not Commenced |  |  |  | Scheduled to commence in mid 2017
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | This has not started and not due to start until mid-2017. | As above |  |  |  |  | Not Commenced |  |  |  | Scheduled to commence in mid 2017
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | This has not started and not due to start until mid-2017. | As above |  |  |  |  | Not Commenced |  |  |  | Scheduled to commence in mid 2017
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [8 empty] | A Transition Plan will be completed once AEMO packages and commercial agreements with Metering Coordinator(s) are finalised. | Dependent on industry readiness. |  |  |  |  | Transition planning and scheduling cannot be accurately determined until Design & Build is completed
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [8 empty] | Activity has not yet started. | As above |  |  |  |  | Transition planning and scheduling cannot be accurately determined until Design & Build is completed
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Red Energy | Simply Energy | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms, within the context of the timeframe and procedural uncertainty. | Planning to undertake impact analysis after Vic decisions.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Aurora Energy has implemented a program of work to effectively and efficiently work towards market compliance. | [5 empty] | Origin has onboarded additional Business and Technology resources
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [10 empty] | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office. |  |  |  | Origin has onboarded additional Business and Technology resources |  |  |  | Internal assessments have commenced
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [10 empty] | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [14 empty] | Origin has onboarded additional Business and Technology resources
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy has no choice but to proceed on the assumption that accreditation will be received. |  | Awaiting AEMO publication of retailer e-hub requirements |  |  |  | Origin has onboarded additional Business and Technology resources
2.5 |  | The fulfilment of accreditation and registration obligations | [8 empty] | Aurora Energy has no choice but to proceed on the assumption that accreditation will be received. | [5 empty] | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [14 empty] | Origin has onboarded additional Business and Technology resources
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [14 empty] | Origin has onboarded additional Business and Technology resources
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [14 empty] | Origin has onboarded additional Business and Technology resources
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [8 empty] | Aurora Energy continues to invest considerable effort in participating in AEMO procedural consultation. Aurora Energy has no choice but to proceed on the basis of the information to hand and must continue to manage the risk of final procedures changing. | [5 empty] | Origin has onboarded additional Business and Technology resources
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [14 empty] | Origin has onboarded additional Business and Technology resources
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [8 empty] | Aurora Energy is in the process of gathering detailed business and system requirements and engaging with key vendors. | [5 empty] | Origin has onboarded additional Business and Technology resources
5.2 |  | The development and build of appropriate market systems for your business | [8 empty] | Aurora Energy is in the process of gathering detailed business and system requirements and engaging with key vendors. | [5 empty] | Origin has onboarded additional Business and Technology resources
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Retailer Participation
References:
|  | AEMO | http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Participant-information/Current-participants/Current-registration-and-exemption-lists
|  | AER | https://www.aer.gov.au/retail-markets/authorisations/public-register-of-authorised-retailers-and-authorisation-applications
|  | ESC | http://www.esc.vic.gov.au/project/energy/2075-licensing/
Retailer | On March 2017 Report?
1st Energy Pty Ltd | No
ActewAGL Retail | Yes
AGL | Yes
Alinta Energy | Yes
Aurora Energy | Yes
Blue NRG Pty Ltd | No
Click Energy Pty Ltd | No
Covau Pty Limited | No
COzero Energy Retail Pty Ltd | No
Diamond Energy Pty Ltd | No
Energy Locals Pty Ltd | No
EnergyAustralia | Yes
Enova Energy Pty Ltd | No
Ergon Energy Queensland (retail) | Yes
ERM Power Retail Pty Ltd | No
Globird Energy Pty Ltd | No
Lumo Energy (reporting with Red Energy) | Yes
M2 Energy Pty Ltd | Yes
Macquarie Bank Limited | No
Mojo Power Pty Ltd | Yes
Momentum Energy | Yes
Next Business Energy Pty Ltd | No
Online Power and Gas Pty Ltd | No
Onsite Energy Solutions Pty Ltd | No
Origin Energy | Yes
Pacific Hydro | Yes
People Energy Pty Ltd | Yes
Pooled Energy Pty Ltd | No
Powerdirect Pty Ltd | No
Powershop Australia Pty Limited | No
Progressive Green Pty Ltd | No
Qenergy Limited | No
Red Energy | Yes
Sanctuary Energy Pty Ltd | No
Simply Energy | Yes
SparQ Pty Ltd (Sumo Power) | No
Stanwell Corporation Limited (Stanwell Energy) | No
WINenergy Pty Ltd (WINenergy) | No

## Distributor Reports
| 2017-03-06 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule | Medium | Within the constraints and information provided by AEMO, AAD is on schedule. Critical enablers are yet to be released by AEMO to confirm the assessed overall risk position. Concerns are held over the undetermined POC procedure changes, issues register outcomes and the potential need for substantial system changes. | [13 empty] | Accreditation transfer and registration starting 2 March is a risk area and it is noted that AEMO will still be developing systems and processes at the time industry is requested to start this process. AAD received the registration information for initial MC requirements and is currently assessing these requirements. The readiness of AAD to interface with the AEMO B2B hub is a significant risk. In the absence of information, the system changes required to facilitate this new data flow is undefined. It is noted AEMO have 12 mths to develop this and Industry only have 3.5 mths to implement. There is a disparate timeframe for Industry to modify, test, put into production and this is noted as a major area of concern for AAD.
| Ausgrid | At risk | Medium | We have established a formal ICT project and assigned resources. A number of significant IT rebuilds are expected to be required in order to facilitate the new B2B requirements. | [7 empty] | Issues noted [in project comment] impact on all these categories.
| AusNet Services | At risk | High | Project mobilised and development in progress, however the overall risk rating of 'High' is a consequence of; 1. Scope of the changes is significant, with some key areas including the new Schema yet to be drafted or finalised. The extent of changes requires development resources/effort/cost beyond initial estimates. 2. Schedule and Scope risk is significant given the work has not commenced to define strategies for Industry Testing, Industry Systems Implementation and Market Transition, 3. The potential impact if the outcome of the Victorian Government options assessment is delayed, or if the decision varies from one of the options. 4. Uncertainty about the agreed market treatment of Vic AMI Meters as Type 4 or Type 5. 5. Lack of Industry Test Strategy and the limited time available for Testing 6. Lack of an agreed Market Transition Strategy | [7 empty] | The scope of changes to be delivered is greater than anticipated and delivery timeframes are highly compressed. (i.e.; ~5 months between the publication of final B2B Procedures on March 6th and the commencement of Industry Testing in early August). Unable to assess ability to align with Industry Testing and Market Transition phases as strategies for these activities have not been drafted. | [5 empty] | The scope of changes to be delivered is greater than anticipated and delivery timeframes are highly compressed. (i.e.; ~5 months between the publication of final B2B Procedures on March 6th and the commencement of Industry Testing in early August). Final approach to Industry Testing and Market Transition are required to confirm overall delivery scope can be delivered within available timeframes.
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Within schedule | Medium | CitiPower/Powercor is progressing its analysis and build phase in accordance with the program schedule. | [7 empty] | CitiPower/Powercor are intending to only be the initial Metering Co-ordinator/Metering Provider/Meter Data Provider for CitiPower and Powercor's legacy metering fleet. Our assessment of the jurisdictional risk rating is based on Victorian government determining final transitional metering arrangements by the end of Q1, 2017. Similarly, the jurisdictional industry operating model is yet to be agreed amongst jurisdictional participants for key activities such as new connections and metering faults.
| Endeavour Energy | At risk | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures. The initial draft of the B2B procedures suggests that there will be significant system and process changes, however the B2B procedures will not be finalised until 6 March 2017. This only leaves 6-7 months to design and develop to test with the market to achieve accreditation. It is noted that registration as a B2B e-Hub Participants is required before the B2B e-Hub can be used. This registration process is also at risk as there is a dependency to demonstrate system compliance with the B2B procedures. AEMO facilitated a workshop on the meter churn process for participants to highlight issues and more efficient process options. There is a risk that by the time AEMO clarifies the process/procedures with an agreed industry position, it could further shorten system design and build timeframes. To mitigate this we are actively participating in the various working groups including the PoC-WG, B2BWG and SWG to ensure that AEMO procedures and B2B procedures supports the metering contestability and embedded networks rule changes in the most effective and cost efficient manner, and to only include transactions and obligations required for go live as a priority. | [7 empty] | [See project comment] | [5 empty] | This report is for Endeavour Energy as at 28 February 2017. Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5 and 6 metering installations from 1 December 2017. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. Most activities are at early stages because there are still a number of pending decisions such as the B2B procedures, AEMO procedure changes packs 2 and 3, jurisdictional obligations, AER's final classification of network services etc. The activities for the Market Systems testing and cutover are dependent on the development and build of the appropriate market system which is currently at risk.
| Energex Ltd. & Ergon Energy Corporation Ltd. | At risk | Medium | The project is progressing as planned. However, ring-fencing, new B2B Procedures and new system requirements are collectively proving to make planning and delivery challenging in such a tight timeframe. Further changes to B2B Guidelines, particularly in regards to the Notified Party and One Way Notifications now becoming 'May' in place of 'Must', is causing further delay to already very tight timelines. | [7 empty] | The magnitude of change in the final version of the B2B Procedures has impacted planning activities and the associated schedule. The project is currently 'At risk'.
| Essential Energy | At risk | Medium | Essential Energy's PoC program is underway. Significant system and process changes are required to deliver B2B compliance by 1 December 2017, however B2B procedures will not be finalised until early March 2017. Timing is going to be tight to be able to design, develop and build, and complete internal testing, with participation in industry testing to commence from August 2017. The program is at risk. | [7 empty] | [Distributor}: Essential Energy will be an initial MC for Type 5 and 6 meter installations connected as at 1 December 2017. Risk rating is classified as moderate due to commencement of systems build prior to receipt of finalised procedures. [Meter Provider]: Type 5 & 6 basic meters only. [Risk rating classified as low] [Meter Data Provider]: Type 5 & 6 basic meters only. Risk rating is classified as moderate due requirements to update systems for B2B changes, including to receive and process meter exchange information to enable publishing of final readings for Type 5 & 6 meters. | [5 empty] | Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Networks | Within schedule | Medium | With 9 months to go-live on 1 December 2017, the project is rated at MEDIUM risk this report due to 1. the uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017; 2. the adequacy of the proposed industry testing scope and timeframe; 3. the proposed go-live date of 1 December 2017 causing a need to cutover mid week, at a Financial Month End period prior to the Financial & Regulatory Year End period, and during a period of high volumes for Customer new connections, adds and alts pre-Christmas. | [7 empty] | With 9 months to go-live on 1 December 2017, the project is rated at MEDIUM risk this report due to 1. the uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017; 2. the adequacy of the proposed industry testing scope and timeframe; 3. the proposed go-live date of 1 December 2017 causing a need to cutover mid week, at a Financial Month End period prior to the Financial & Regulatory Year End period, and during a period of high volumes for Customer new connections, adds and alts pre-Christmas.
| Sa Power Networks | Within schedule | Medium | Currently on schedule. SA Power Networks has formally raised concerns with the IEC and AEMO with regards to decisions made during the finalisation of the B2B Procedures that will result in risks to customer outcomes.
| TasNetworks | At risk | Medium | TasNetworks plan is to be ready business preparations and the development of specifications with vendors is progressing well, TasNetworks' market systems build schedule could propose a delivery timeline post the industry testing dates, not allowing TasNetworks to fully participate in industry testing before the scheduled go live.
| United Energy | At risk | Medium | Internal preparations continue to progress well. Process and solution designs are complete in most areas not affected by shared market protocol (SMP), and others are nearing completion. System development continues in selected areas. Amber status reflects uncertainty over jurisdictional adoption of Metering Competition, timing of SMP details and other readiness factors. | [7 empty] | UE operates in Victoria only. Jurisdictional status refects overall position. | [5 empty] | Key concerns for UE (and industry) readiness are as follows: 1) The Victorian Government approach to "Transition to Metering Competition" is not finalised, with the options paper still under consideration and a decision not expected until March 2017. Until the Govt. provide a final position, UE's project will continue on the assumption of full adoption in Victoria in Dec 2017. Regulatory changes in Victoria at that point, or later, have the potential to result in changes to project scope and requirements, and may negatively impact readiness. 2) Publication of Package 2 Procedures on 6 Mar 2017 necessitates design of business processes and functionality based on assumptions and draft B2B/SMP documents. Delayed publication of the procedures, failed assumptions and/or any major changes between draft and final procedures will impact project timelines and therefore readiness preparations. Whilst the likelihood of this is now considered low, it remains a risk until the final published procedures have been issued and reviewed. 3) Lack of definitive direction on whether VICAMI meters can remain as Type 5 MRIM is creating uncertainty around whether system changes, data changes and accreditation for Type 4 meters will be required in this area. Continuing to seek confirmation from AEMO, AER and Victorian Government. UE considers that there is no clear requirement in the NER which compels reclassification, UE has provided its views in writing to AEMO/AER on 6 February and we understand that AEMO will document its views which compel the reclassification. 4) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. UE's compliance in this area may also be dependent on existing child metering services being transitioned to non-regulated meter providers on or by 1 Dec 2017, although this is yet to be confirmed. If transition is required, it will be an activity over which UE does not have full control. 5) After 1 Dec 2017, UE may not be able to avoid temporarily providing regulated metering services (via its Initial MP and MDP roles) under a competitive MC if the new MC is unable to organise timely meter exchanges after a churn event. AEMO is going to respond on the meter churn issues raised in the Feb meeting by AGL and other participants. These industry processes may impact ring fencing waivers which the AER will advise on in August/September 2017. This process will influence the MC contract which UE needs to publish on 1 Sept 17. 6) UE is concerned that the lateness of procedures finalisation and the complexity and scale of testing with the increased number of market participants may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections, supply and supply restoration processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers. Supply restoration includes faults, damaged meters, unplanned replacement and associated communication steps for Consumers. Lack of definitive guidelines from safety regulators, and missing or poorly defined after-hours processes for retailers and MCs will hamper the effectiveness of the industry and will negatively impact consumers.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule | Medium
| Ausgrid |  |  | At risk | Medium
| AusNet Services | [10 empty] | At risk | High
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | Within schedule | Medium
| Endeavour Energy |  |  | At risk | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | At risk | Medium
| Essential Energy |  |  | At risk | Medium
| Jemena Electricity Networks | [10 empty] | Within schedule | Medium
| Sa Power Networks | [6 empty] | Within schedule | Medium
| TasNetworks | [8 empty] | At risk | Medium
| United Energy | [10 empty] | At risk | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | Sa Power Networks | TasNetworks | United Energy | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 41% - 50% | Completed (100%) | Completed (100%) | 51% - 60% | 51% - 60% | 71% - 80% | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 51% - 60% | 21% - 30% | 21% - 30% | Completed (100%) | 41% - 50% | 61% - 70% | 31% - 40% | 51% - 60% | 81% - 99% | 41% - 50% | Completed (100%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 21% - 30% | 21% - 30% | 21% - 30% | Completed (100%) | 21% - 30% | 11% - 20% | 61% - 70% | 41% - 50% | 71% - 80% | 31% - 40% | 61% - 70%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 21% - 30% | 21% - 30% | 11% - 20% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 31% - 40% | Not started (0%) | 21% - 30% | 1% - 10%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 11% - 20% | 1% - 10% | 1% - 10% | 31% - 40% | 21% - 30% | 1% - 10% | Not started (0%) | 11% - 20% | 1% - 10% | 1% - 10% | 1% - 10%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 41% - 50% | Not started (0%) | Not started (0%) | 31% - 40% | 31% - 40% | 11% - 20% | 11% - 20% | 1% - 10% | 21% - 30% | 41% - 50% | 1% - 10%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 31% - 40% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | 21% - 30% | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 21% - 30% | 31% - 40% | 11% - 20% | Not started (0%) | 31% - 40% | 11% - 20% | 11% - 20% | Completed (100%) | 1% - 10% | 21% - 30% | Completed (100%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | 31% - 40% | 1% - 10% | Not started (0%) | 31% - 40% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 11% - 20% | 21% - 30% | Not started (0%) | Not started (0%) | 1% - 10% | 1% - 10% | Not started (0%) | 21% - 30% | 1% - 10% | Not started (0%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 21% - 30% | 21% - 30% | 11% - 20% | 61% - 70% | 41% - 50% | 21% - 30% | 31% - 40% | Completed (100%) | 61% - 70% | 41% - 50% | Completed (100%)
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 21% - 30% | 11% - 20% | 11% - 20% | 31% - 40% | 21% - 30% | 11% - 20% | Not started (0%) | 41% - 50% | 41% - 50% | 1% - 10% | 81% - 99%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 21% - 30% | 41% - 50% | 11% - 20% | 31% - 40% | 11% - 20% | 11% - 20% | 11% - 20% | Completed (100%) | 31% - 40% | 71% - 80% | 71% - 80%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 21% - 30% | Not started (0%) | 11% - 20% | 21% - 30% | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | 21% - 30% | Not started (0%) | 11% - 20%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | 1% - 10% | 21% - 30% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | 1% - 10% | 31% - 40% | Not started (0%) | 1% - 10% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | Sa Power Networks | TasNetworks | United Energy | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | At risk | At risk | Completed | Within schedule | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | At risk | Completed | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Not within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule |  | Within schedule | At risk | Within schedule | Within schedule | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Completed
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | At risk | At risk | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | At risk | At risk | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | At risk | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | Sa Power Networks | TasNetworks | United Energy | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Power of Choice reforms have been assessed and impacts on the business have been determined for most areas. Those areas where system changes are yet to be defined or are awaiting finalisation have not been assessed at the time of writing. |  |  |  |  | High-level scope and requirements documents have been signed off by the business. Currently performing the organisational impact assessment. | Unable to finalise impact assessment until review of finalised B2B procedures is complete | Jen is 100% complete on this task for Option 1, however it may have to be repeated should Vic Govt select option 4. |  | Will be completed with the finalisation of pack 2 and a review of the impact assessment
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Work is underway addressing system and business changes except to the extent that those changes have not been released or are yet to be finalised. |  | Implementation plans for internal systems established. Lack of certainty about treatment for AMI Meter Type creates additional risk. Development of Industry implementation and market transition plans required to validate internal scope/approach. |  |  | The magnitude of change in the final version of the B2B Procedures has impacted planning activities and the associated schedule. | Delayed due to delay in completing the high level impact assessment | As above. Replanning may need to occur depending on the Vic Government Option decided in March 2017. | Governance and Plans are in place. Resource recruitment is currently being finalised.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | The AAD PoC team has regular meetings with the legal / regulatory team to ensure compliance with all regulatory requirements. Assessment of impacts is underway with clarity around unknown changes affecting the ability of the business to fully understand the final impacts. In addition to this AAD holds regular forums with external stakeholders including the ACT Govt. to ensure a smooth transition takes place. |  | Impact of possible delay in Victorian Government Options assessment and subsequent changes to Vic Regulatory Codes and safety requirements. Uncertain framework for maintaining Vic AMI Meters Type 5 after 1 December. | Note: This assessment excludes AEMO procedures that remain in draft. |  | Ongoing activity - currently under review by organisational specialists. |  | As above. Rework may need to occur depending on the Vic Government Option decided in March 2017. | Final review of B2B and WP2 procedures |  | Vic. Govt. is considering options for "transition to metering competition". The assessment of legal and regulatory frameworks cannot be completed until a decision is made (expected March 2017). Once the Govt. position is clear, the ESC can also make amendments to reflect the NERR type obligations within Victoria. There are also a number of points of clarification required in regards to on-site safety obligations, particularly for connections work. A number of Vic. Govt. instruments and contracts will also need amendment. This remains well behind UE schedule and has the potential to impact business process and market systems work referenced in the rows below.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Review of legal documentation (contracts, forms, agreements, etc.) has begun in line with the commencement of system and business changes. |  | Impact of possible delay in Victorian Government Options assessment and subsequent changes to Vic Regulatory Codes and safety requirements. Uncertain framework for maintaining Vic AMI Meters Type 5 after 1 December. | Note: In line with CitiPower/Powercor program delivery schedule. |  |  |  | As above. Rework may need to occur depending on the Vic Government Option decided in March 2017. | In line with SAPN program delivery schedule |  | As noted above, Vic. Govt. is considering options for "transition to metering competition". Internal documentation and policies cannot be finalised until a decision is made (expected March 2017). This is well behind UE schedule.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | As above. |  | Definition of B2B Procedures and finalisation of Market Roles required to establish associated commercial arrangements | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently meeting with contract owners and associated business subject matter experts. |  | As above. Rework may need to occur depending on the Vic Government Option decided in March 2017. | In progress |  | Plans are in place to address the commercial implications, and resourcing is now in place. Initial assessments have commenced.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | AAD is presently assessing the requirement released by AEMO late February. Project Team established to define and develop implementation plan for Ring Fencing compliance requirements Type 3 / 4 accreditation document suite complete (work method statements being prepared prior to end March audit). |  | Final Accreditation procedures not published and requirement to be accreditation for Type 4 Meters not confirmed | Note: We have completed our assessment of the required accreditations and registrations. The activities to achieve these are related to AEMO procedures which remain in draft. |  | Initial discussions with AEMO representative on the approach that the existing LNSP, MPB and MDP accreditations will continue. MC will be a registration process given our current RP role. Formal confirmations to follow. |  | As above. Rework may need to occur depending on the Vic Government Option decided in March 2017. | In progress |  | Accreditation requirements for UE are not fully confirmed, due to lack of clarity on whether VICAMI meters will have to be reclassified as Type 4. Recently issued procedures for registration and accreditation are being assessed.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Type 3/4 meter accreditation application submitted to AEMO 17 Feb. On track for March audit / April accreditation. ActewAGL Board approved creation of new entity for contestable works (inc Type 4 MC / MP, MDP if rqd). |  | Final Accreditation procedures not published | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | An Accreditation team has formed, commencing accreditation planning in preparation for the release of the Accreditation and Registration plan by AEMO. Previously, it was assumed that re-accreditation would not be a requirement. |  |  | In line with SAPN program delivery schedule |  | Plans and funding are in place to cover UE accreditation. The final accreditation requirements and checklist are being reviewed for UE impact. Time and effort will be required to ensure that internal processes & policies meet the accreditation criteria. This is expected to take several months, leading to accreditation occurring in late Q3/Q4 2017.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | AAD has begun assessing future requirements. Finalisation by AEMO of procedures and IT Systems will require that this position is reassessed. |  | Has started, however may be impacted by Victorian Government Options assessment and subject to finalisation of market procedures. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently analysing the human resources impact due to POC implementation. |  | As above. Rework may need to occur depending on the Vic Government Option decided in March 2017. | In progress
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not yet begun. Noting PoC removes current functions from existing businesses, this may result in reductions to staff (TBC). |  |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | An Organisational Impact Assessment is in progress to determine POC recruitment and HR requirements to fulfil operational functions. |  |  | In line with SAPN program delivery schedule |  | Not required until late 2017
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not yet begun. |  |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Training approach has commenced. |  | As above. Rework may need to occur depending on the Vic Government Option decided in March 2017. | In progress |  | Development of training strategy is nearing completion.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Detailed reviews of AAD documentation has begun and resourcing for the changes has been completed. AAD is now in the process of carrying out the required reviews, consultation, workshops, etc. required to design and implement the required changes. A new suite of previously unidentified documents have been identified. We are currently assessing the status & impact. |  | Subject to finalisation of market procedures and Vic Gov't approach | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently documenting current and future state processes through development of detailed requirements. Progress on this is less than expected due to required rework, due to the nature of the final B2B Procedure Changes. |  | As above. Rework may need to occur depending on the Vic Government Option decided in March 2017. | Business process mapping for future state currently on schedule. | Will be completed with the finalisation of pack 2 and a review of the impact assessment
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | As above. |  | Subject to finalisation of market procedures and Vic Gov't approach | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently documenting current and future state processes through development of detailed requirements. Progress on this is less than expected due to required rework, due to the nature of the final B2B Procedure Changes. |  | As above. Rework may need to occur depending on the Vic Government Option decided in March 2017. | However, decisions made by the IEC as part of the final B2B Procedure determination (e.g. Notified Party obligations now a "may") will impact on currently develop processes that will require rework. This may effect our ability to meet key schedule milestones. |  | Business processes in certain areas are dependent on, or heavily impacted by, the SMP/B2B procedures. These processes cannot be fully confirmed until procedures are published on 6 Mar 2017. This has delayed the design and development of system changes, putting readiness at risk. Any further delay to the release of the procedures will increase the risk.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not yet begun. |  | Subject to finalisation of market procedures and Vic Gov't approach and Industry Testing approach. Also requires assessment of procedures required to support market transition | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Test approach is ongoing. The Scope of August industry testing remains unclear. Confirming the scope of industry testing as soon as possible would enable businesses to effectively meet the industry testing date. |  |  | In line with SAPN program delivery schedule |  | Plans are in place to execute industry testing. However the current draft of B2B procedures includes the movement of currently enforceable details into a non-binding "guidance" category. The industry considers some of these details to be necessary for uniform, reliable end-to-end processing in the market. UE is concerned that varying interpretations and inconsistencies between industry participants will become apparent during industry testing and may threaten its progress.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Final requirements are yet to be released by AEMO, however, those requirements that are known have been scoped and are in design (we estimate that approximately 75% of requirements are known). | Systems impacts continue to be assessed in detail. Solution design work has commenced. Where required, vendor solutions are being evaluated. | Subject to assessment of variances in B2B Procedures published on March 6th and Vic Gov't approach. Schedule for delivery of market system changes likely may be impacted by extent of changes required. | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. | See above comment | Ongoing activity - currently developing market systems detailed requirements and design documents. The magnitude of change in the final version of the B2B Procedures particularly with regard to the NP and OWN's in the latest B2B Guidelines requires a revisit of requirements and reassessment of design. Timelines are becoming increasingly unrealistic due to these changes. |  | As above. Replanning may need to occur depending on the Vic Government Option decided in March 2017. | In progress |  | Business requirements have been completed and approved. Design is complete or nearing completion in most areas, but is being undertaken "at risk" in those areas that might be impacted by the publication of final B2B procedures on 6 Mar 2017.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Detailed design is in progress for B2B system processes. Limited information is known about the new AEMO B2B hub. This is a major risk area for success. | Waiting for finalisation of the B2B changes. | Build process has commenced based on draft procedures, but delivery is at risk until an assessment has been made of variances in the final procedures made available on March 6th. Current scope of proposed changes is assessed as greater than the minimum required to support market operation. Impact of delay in final decision by Vic' Gov't on Option Assessment unclear. | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | The magnitude of change in the final version of the B2B Procedures particularly with regard to the NP and OWN's in the latest B2B Guidelines requires a revisit of requirements and reassessment of design. Development and build timelines are becoming increasingly compressed and unrealistic. |  | As above. Rework may need to occur depending on the Vic Government Option decided in March 2017. | In progress | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | System development is underway in response to approved designs. Some areas of development will not be able to commence until after 6 March 2017 due to the timing of final B2B procedures (or later, depending on the timing of the Victorian policy and clarity of regulatory changes).
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Definition of internal Test Strategy has commenced, but is subject to finalisation of delivery scope and Industry Testing approach. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Test approach is tracking to schedule. Testing timelines are becoming increasingly compressed and therefore 'At risk'. |  |  | In progress | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | Plans in place and resourcing agreed. Not yet due.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Definition of Industry Test Strategy has commenced. Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  | The magnitude of change in the final version of the B2B Procedures particularly with regard to the NP and OWN's in the latest B2B Guidelines requires a revisit of requirements and reassessment of design. Testing timelines are becoming increasingly compressed and unrealistic. |  |  | In line with SAPN delivery schedule | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | Plans in place and resourcing agreed. Not yet due.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Final specifications of hub required. Role of non-functional testing as part of Industry Testing is required. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Test approach is tracking to schedule. |  |  | In line with SAPN delivery schedule | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | Plans in place and resourcing agreed. Not yet due.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Preliminary works has begun in this area with no decisions or plans being determined at the time of writing. |  | Industry approach has not been defined, therefore ability to meet schedule is unclear | Note: In line with CitiPower/Powercor program delivery schedule. |  | Discussions are continuing with impacted groups and information gathering to inform transition plans. |  | As above. Rework may need to occur depending on the Vic Government Option decided in March 2017. | In line with SAPN delivery schedule |  | Plans in place and resourcing agreed. Not yet due.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not yet begun. |  | Industry approach has not been defined, therefore ability to meet schedule is unclear | Note: In line with CitiPower/Powercor program delivery schedule. |  | Transition planning has commenced. |  |  | In line with SAPN delivery schedule | The AEMO schedule is challenging to deliver in the current timeframe. | Plans in place and resourcing agreed. Not yet due.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | Sa Power Networks | TasNetworks | United Energy | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Stage Gates built into Schedule based on AEMO identified key milestones. Implementation approach that develops solutions as best as practical now and change later when AEMO formally releases information. | [6 empty] | TBC - subject to Vic Govt decision.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD is commencing final design and development activities based on information received to date. The degree to which re-work will be required due to changes in final AEMO documentation will be determined in the weeks immediately following release of said documentation. |  | Ongoing support for definition of market procedures Commencement of build based on draft procedures, based on acceptance of risk that cost and schedule could be impacted by changes to final procedures |  |  | Currently working through the B2B Procedure changes to understand impacts on detailed requirements, design and build. B2B configuration changes occurring in parallel to mitigate timeframe constraints. |  | TBC - subject to Vic Govt decision.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Active participation to address legislative options for Meter Type. Continued participation in Vic' Gov't Stakeholders Forum |  |  |  |  | TBC - subject to Vic Govt decision. |  |  | UE continues to actively participate in the consultation process, and has been encouraging a prompt decision. UE is also encouraging Vic. Govt. to develop a programme plan for the industry and to create a regulatory working group to develop the necessary instrument amendments. UE will actively participate in the working group and any Vic. Govt., ESC and/or ESV consultation processes.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [12 empty] | TBC - subject to Vic Govt decision. |  |  | As above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [12 empty] | TBC - subject to Vic Govt decision.
2.4 |  | An assessment of the required accreditation and registration activities | [12 empty] | TBC - subject to Vic Govt decision. |  |  | Continuing to seek confirmation from AEMO, AER and Victorian Government on whether UE's meters can remain as Type 5 MRIM.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | See above comment
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [12 empty] | TBC - subject to Vic Govt decision.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [12 empty] | TBC - subject to Vic Govt decision.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [10 empty] | Additional experienced resources and subject matter experts have been sourced as a preventative mitigation strategy. |  | TBC - subject to Vic Govt decision.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [10 empty] | Additional experienced resources and subject matter experts have been sourced to support ongoing business process activity and as a preventative mitigation strategy. |  | TBC - subject to Vic Govt decision. |  |  | Business process design is nearing completion within UE, based on a combination of assumptions and draft material from the B2B working group and AEMO. This involves risk of re-work and wasted effort if the final B2B procedures differ from the drafts, but that risk is lower than waiting until Mar 2017 before commencing process design. Likelihood of major impact is now considered low based on IEC position as at 1 March 2017.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | AAD is commencing detailed design and build phases during February/March and will perform rework if/when required as AEMO finalise and release the requirements documentation. | A formal ICT project has been established and is tracking to its' timeline. | Requirement to provision additional resources to be assessed in order to deliver scope within timeframes. |  | See above comment | The Project is reviewing several mitigation strategies; significantly a phased implementation approach. |  | TBC - subject to Vic Govt decision. |  |  | Solution design is continuing within UE, based on a combination of assumptions and final draft B2B procedures. This involves risk of re-work and wasted effort if the final B2B procedures differ from the drafts, but that risk is lower than waiting until Mar 2017 before commencing solution design.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | As above. |  | Development is proceeding based on assumed outcome. Impact of variances between final draft and final processes will be undertaken following publication on March 6th. |  | See above comment | The Project is reviewing several mitigation strategies; significantly a phased implementation approach. |  | TBC - subject to Vic Govt decision. |  |  | System development has commenced in areas not impacted by B2B procedures. Development for B2B-related functionality will commence as soon as there is sufficient confidence in the B2B procedures and associated process and solution designs.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Strategy to be validated when Industry testing Strategy has been defined.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Strategy to be validated when Industry testing Strategy has been fully defined. |  |  | The Project is reviewing several mitigation strategies; significantly a phased implementation approach.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Internal non-functional testing to be undertaken.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Support development of industry approach. |  |  |  |  | TBC - subject to Vic Govt decision.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Support development of industry approach.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2017-03-06 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | [14 empty] | Active Stream is currently accredited and operating as an Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | Within schedule | Medium | Overall project delivery status at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Now that they final determination is complete, Business and Systems impact analysis is underway and gap analysis to be completed shortly. Amber status is maintained due to tight timeframes scope of change | [7 empty] | [Meter Provider: Status "Within Schedule"] [Meter Data Provider: Status "At risk"]
| Metering Dynamics (MD) | Within schedule | Medium | Project risk is due to delayed release of B2B procedures and the complexity of multiple Rule and role changes in a very short timeframe. | [7 empty] | [Meter Provider: Risk "Low"] [Meter Data Provider: Risk "Medium"] - Risk due to the complexity of changes needed.
| Select Solutions | At risk | Medium | The overall timeframes for these industry changes are tight. Select Solutions are working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run our existing systems for our Type 1-4 large meters and MP/MDP participant IDs and under separate participant IDs procure a new system to form part of our accreditation for Type 4 small meters. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. IT system procurement is marginally behind schedule. We have significant resources focussing on delivering this part of the project. In particular, meeting the milestone of industry testing is challenged. | [7 empty] | Risk relates to the current status of new system implementation
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Metering Dynamics (MD) | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Select Solutions | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
0
0
0
0
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics (MD) | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 11% - 20% | 41% - 50% | 75% | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 11% - 20% | 31% - 40% | 50% | 51% - 60%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 51% - 60% | 1% - 10% | 11% - 20% | 75% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 51% - 60% | 1% - 10% | 1% - 10% | 25% | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 51% - 60% | 1% - 10% | 1% - 10% | 0% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | 11% - 20% | 31% - 40% | 50% | 61% - 70%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 71% - 80% | Not started (0%) | 11% - 20% | 25% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 1% - 10% | 11% - 20% | 75% | Not started (0%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 1% - 10% | 25% | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 50% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 51% - 60% | 21% - 30% | 31% - 40% | 75% | 31% - 40%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 21% - 30% | 1% - 10% | 21% - 30% | 50% | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 31% - 40% | 1% - 10% | 51% - 60% | 75% | Not started (0%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 1% - 10% | Not started (0%) | 21% - 30% | 25% | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 1% - 10% | 1% - 10% | 0% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics (MD) | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | At risk | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | At risk | Within schedule | At risk | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | At risk | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics (MD) | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Select Solutions has its strategy in place. A key variable is confirming delivery of the systems which will form the final part of our delivery plan.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Dependent on the finalisation of associated industry documentation. |  | Assessing final accreditation and registration documents that have just been released. | Progressing through requirements for MC and ENM accreditation/registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Dependent on the finalisation of associated industry documentation.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [8 empty] | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role |  | Interdependencies with merger activity
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Resource assessment with respect to the MC role |  |  | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [8 empty] | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Business restructure and merger are requiring additional business process effort and approvals. | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing | [8 empty] | At risk due to system procurement program slippage.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [8 empty] | A significant "blue print process" has been completed highlighting requirements. Still understanding B2B changes. Consequently system procurement is challenged.
5.2 |  | The development and build of appropriate market systems for your business | [8 empty] | Build phase was scheduled to start in February 2017. Build is now not likely to commence until March.
5.3 |  | The internal testing of market systems for your business | [8 empty] | Due in mid 2017, dependant on progress of system build.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | Due in mid 2017, dependant on progress of system build.
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | Due in mid 2017, dependant on progress of system build.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [8 empty] | This action dependent upon finalisation of system procurement.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [8 empty] | This action dependent upon finalisation of system procurement.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics (MD) | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Dedicated resources and strong business focus on the systems delivery project.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Working with Exec on key dates
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [8 empty] | Dedicated resources and strong business focus on the systems delivery project.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
| 2017-03-06 |  |  | Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | [14 empty] | Active Stream is currently accredited and operating as an Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | Within schedule | Medium | Overall project delivery status at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Now that they final determination is complete, Business and Systems impact analysis is underway and gap analysis to be completed shortly. Amber status is maintained due to tight timeframes scope of change
| Energy Australia | At risk | Medium | The Program is making steady progress but is behind schedule in several areas due to the extent of changes in the B2B procedures. There is high risk to schedule due to variations in the Final version of B2B procedures, outstanding decision by the Victorian Government on Options, lack of clarity on safety regulations and conversion of VicAMI type 5 to Type 4. | [7 empty] | The Program is making steady progress but is behind schedule in several areas due to the extent of changes in the B2B procedures. There is high risk to schedule due to variations in the Final version of B2B procedures, outstanding decision by the Victorian Government on Options, lack of clarity on safety regulations and conversion of VicAMI type 5 to Type 4.
| Metering Dynamics (MD) | Within schedule | Medium | Project risk is due to delayed release of B2B procedures and the complexity of multiple Rule and role changes in a very short timeframe. | [7 empty] | New MC role integration into many market and business processes.
| Momentum Energy | Within schedule | Medium | Work packages and final B2B procedure documentation is not due until March 2017. All current scoping and impact assessments have been based on draft procedures. Any significant changes from draft procedures will have a direct project impact due to constrained timelines for project. | [7 empty] | In early stages of scoping and analysis
| Select Solutions | At risk | Medium | The overall timeframes for these industry changes are tight. Select Solutions are working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run our existing systems for our Type 1-4 large meters and MP/MDP participant IDs and under separate participant IDs procure a new system to form part of our accreditation for Type 4 small meters. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. IT system procurement is marginally behind schedule. We have significant resources focussing on delivering this part of the project. In particular, meeting the milestone of industry testing is challenged.
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Energy Australia | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Metering Dynamics (MD) | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Momentum Energy | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Select Solutions | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
0
0
0
0
0
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Energy Australia | Metering Dynamics (MD) | Momentum Energy | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 11% - 20% | 71% - 80% | 41% - 50% | 71% - 80% | 75% | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 11% - 20% | 51% - 60% | 31% - 40% | 21% - 30% | 50% | 51% - 60%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 51% - 60% | 1% - 10% | 41% - 50% | 11% - 20% | 11% - 20% | 75% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 51% - 60% | 1% - 10% | 1% - 10% | 1% - 10% | Not started (0%) | 25% | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 51% - 60% | 1% - 10% | 1% - 10% | 1% - 10% | Not started (0%) | 0% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | 11% - 20% | 21% - 30% | 31% - 40% | 11% - 20% | 50% | 61% - 70%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 71% - 80% | Not started (0%) | Not started (0%) | 11% - 20% | 1% - 10% | 25% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 1% - 10% | 41% - 50% | 11% - 20% | 1% - 10% | 75% | Not started (0%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 31% - 40% | 1% - 10% | Not started (0%) | 25% | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 50% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 51% - 60% | 21% - 30% | 51% - 60% | 31% - 40% | 1% - 10% | 75% | 31% - 40%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 21% - 30% | 1% - 10% | 11% - 20% | 21% - 30% | Not started (0%) | 50% | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 31% - 40% | 1% - 10% | 61% - 70% | 51% - 60% | 31% - 40% | 75% | Not started (0%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 1% - 10% | Not started (0%) | 21% - 30% | 21% - 30% | 1% - 10% | 25% | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10% | Not started (0%) | 0% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Energy Australia | Metering Dynamics (MD) | Momentum Energy | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | At risk | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Not within schedule | Within schedule | Within schedule | At risk | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | Within schedule | Not within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Energy Australia | Metering Dynamics (MD) | Momentum Energy | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Increasing certainty around procedures (excl Vic)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | High level of depedency on third parties. Plans are dependent on new and immature market participants and processes. |  |  | Select Solutions has its strategy in place. A key variable is confirming delivery of the systems which will form the final part of our delivery plan.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Assessment in progress and on track but there are still unknowns in regards to jurisdictional safety requirements, and associated obligations on Retailers and MCs.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | Red due to the lack of clarity on safety regulations and the late commencement of our safety work stream
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | Due to volume of contracts that need to be entered into with industry parties, plus variable meter service provider maturity.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Dependent on the finalisation of associated industry documentation. |  |  | Assessing final accreditation and registration documents that have just been released. |  | Progressing through requirements for MC and ENM accreditation/registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Dependent on the finalisation of associated industry documentation.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [7 empty] | Being developed as impacts are understood and target state design is finalised |  |  | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role |  | As above | Interdependencies with merger activity
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Resource assessment with respect to the MC role |  | As above. |  |  | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | Slippage in the schedule - a plan to bring back slippage is underway. Also dependent on finalisation of industry-wide processes. |  |  | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | As above | Business restructure and merger are requiring additional business process effort and approvals. |  | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing | [10 empty] | At risk due to system procurement program slippage.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Our plans are dependent on external parties, finalisation of procedures and technical specifications for completion. |  | System development is reliant on external vendor, delays in final market procedures will impact readiness activities | A significant "blue print process" has been completed highlighting requirements. Still understanding B2B changes. Consequently system procurement is challenged.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | As above |  |  | Build phase was scheduled to start in February 2017. Build is now not likely to commence until March.
5.3 |  | The internal testing of market systems for your business | [7 empty] | As above |  |  | Due in mid 2017, dependant on progress of system build.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | As above |  |  | Due in mid 2017, dependant on progress of system build.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | As above |  |  | Due in mid 2017, dependant on progress of system build.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Dependent on industry readiness. |  |  | This action dependent upon finalisation of system procurement.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | As above |  |  | This action dependent upon finalisation of system procurement.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Energy Australia | Metering Dynamics (MD) | Momentum Energy | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Planning to undertake impact analysis after Vic decisions.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [10 empty] | Dedicated resources and strong business focus on the systems delivery project.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | Working with Exec on key dates
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [10 empty] | Dedicated resources and strong business focus on the systems delivery project.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Embedded Networks
| 2017-03-06 |  |  | Embedded Networks Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Momentum Energy | Within schedule | Medium | Work packages and final B2B procedure documentation is not due until March 2017. All current scoping and impact assessments have been based on draft procedures. Any significant changes from draft procedures will have a direct project impact due to constrained timelines for project. | [7 empty] | In early stages of scoping and analysis
| Network Energy Services | Within schedule | Low | Preparing for Accreditation | [7 empty] | Getting prepared to implement all aspects
| Select Solutions | At risk | Medium | The overall timeframes for these industry changes are tight. Select Solutions are working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run our existing systems for our Type 1-4 large meters and MP/MDP participant IDs and under separate participant IDs procure a new system to form part of our accreditation for Type 4 small meters. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. IT system procurement is marginally behind schedule. We have significant resources focussing on delivering this part of the project. In particular, meeting the milestone of industry testing is challenged.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Momentum Energy | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Network Energy Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Select Solutions | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
0
0
0
0
0
0
0
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Momentum Energy | Network Energy Services | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 75% | 75%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 21% - 30% | 50% | 50%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 11% - 20% | 75% | 75%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Not started (0%) | 25% | 25%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Not started (0%) | 5% | 0%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 11% - 20% | 50% | 50%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 1% - 10% | 0% | 25%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 1% - 10% | 50% | 75%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | 50% | 25%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | 25% | 50%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 1% - 10% | 50% | 75%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Not started (0%) | 0% | 50%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 0% | 0%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 31% - 40% | 25% | 75%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 1% - 10% | 0% | 25%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | 0% | 0%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | 0% | 0%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | 0% | 0%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 25% | 0%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | 0% | 0%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Momentum Energy | Network Energy Services | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | At risk
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | At risk
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | At risk
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | At risk
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Not within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Momentum Energy | Network Energy Services | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Select Solutions has its strategy in place. A key variable is confirming delivery of the systems which will form the final part of our delivery plan.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [7 empty] | Progressing through requirements for MC and ENM accreditation/registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [7 empty] | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing | [7 empty] | At risk due to system procurement program slippage.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | System development is reliant on external vendor, delays in final market procedures will impact readiness activities | Awaiting further implementation details | A significant "blue print process" has been completed highlighting requirements. Still understanding B2B changes. Consequently system procurement is challenged.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Build phase was scheduled to start in February 2017. Build is now not likely to commence until March.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Due in mid 2017, dependant on progress of system build.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Due in mid 2017, dependant on progress of system build.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Due in mid 2017, dependant on progress of system build.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | This action dependent upon finalisation of system procurement.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | This action dependent upon finalisation of system procurement.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Momentum Energy | Network Energy Services | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Dedicated resources and strong business focus on the systems delivery project.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Dedicated resources and strong business focus on the systems delivery project.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Third Party
| 2017-03-06 |  |  | Third Party Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
0
0
0
0
0
0
0
0
0
0
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2017-03-06 | [5 empty] | Within schedule | Medium | The pending Vic Govt decision and the instruments that are chosen to implement the decision could impact the delivery program. A decision and formal notification in Q1 2017 will be required. Industry Testing and the Transition and Cut-Over planning has commenced. AEMO notes that the collaborative approach requires industry participation and is undertaking to establish ‘focus groups’ to expedite the development of the detail required to effectively transition.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Medium
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | 11% - 20% | Within schedule | Industry Feedback to the first drafts of the Industry Test Strategy and the Accreditation and Registration Plan is being reviewed and incorporated. AEMO has appointed an Industry Test Lead. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies consistent with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 1% - 10% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 61% - 70% | Within schedule | Undertaking detailed planning for AEMO activities during the accreditation and registration phase based on final Qualification Procedure (ENM. MP, MDP) and MC Registration. B2B e-hub accreditation guidelines due to be published by end of March. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule | Final determination for work package 2 published on 28 February 2017. AEMO held POC-PWG meeting on 6 March 2017 to discuss work package 3 contents and key dates |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updated B2B retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule | B2B Procedures Final Determination was published on 6 March 2017. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 11% - 20% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | 31% - 40% | Within schedule | First two sessions (out of 6) held on 28 November 2016. Next sessions scheduled for 24 March 2017 |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS (EN/MC) | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Within schedule | A revised MSATS 46.88 Technical Specification will be published by 13th March 2017. The EN/MC MSATS preproduction release is planned for 22 March 2017. Industry Test planning is underway. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B e-hub and MSATS | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 41% - 50% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 11% - 20% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | Within schedule | Initial planning and strawman development commenced with final procedures available. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
[12 empty] | 41% - 50% | Retailer
[12 empty] | 51% - 60% | Distributor
[12 empty] | 61% - 70% | Meter Provider
[12 empty] | 71% - 80% | Meter Data Provider
[12 empty] | 81% - 99% | Metering Coordinator
[12 empty] | Completed (100%) | Embedded Network Manager
[12 empty] | N/A | Embedded Network Operator
Third Party B2B Participant
Within schedule
At risk
Not within schedule
N/A
[12 empty] | Completed | √
x
Low
Medium
High
N/A

## Harvey Balls 10% (hidden)
ü
Completed
| 100 | 90 | 80 | 70 |  | 60 | 50 | 40 | 30 | 20 | 10 | 0
| 0 | 10 | 20 | 30 |  | 40 | 50 | 60 | 70 | 80 | 90 | 100
WITHIN SCHEDULE | [12 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE
|  |  | ~0% |  | ~50%
|  |  | ~10% |  | ~60%
|  |  | ~20% |  | ~70%
|  |  | ~30% |  | ~80%
|  |  | ~40% |  | ~90%