## Market Readiness Report Page 1
42828
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2017-04-03
Overall Status |  | Commentary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | The overall project status remains amber with participants reporting the overall project delivery at risk of being delivered by 1 December 2017 . A Medium level of risk persists for the project overall due to aggressive timelines combined with a level of uncertainty around the operation of business processes under the new Rules and Procedures and dependency on new and immature market participants. A High level of risk persists in Victoria due the lack of details on the implementation of Victorian Government decision to defer Metering Competition in Victoria. |  |  |  |  | High | Med | Low | #
[7 empty] | 4 | 2 | 3 | 1
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Networks (ENM, ENO) |  | Third party e-hub
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place |  |  |  | #1 |  | #1
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with regulatory changes including jurisdictional regulations and requirements (e.g. safety) |  |  |  | #2 |  | #2
2.3 |  | Operationally critical commercial contracts in place |  |  |  | #3 |  |  |  | #3 |  | #3 |  | #3
2.4 |  | Accreditation and registration activities completed |  |  |  | #4 |  |  |  | #4 |  | #4 |  | #4
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place | [5 empty] | #5
4.2 |  | Successfully validated critical business processes during industry testing
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing
5.2 |  | Successfully tested market systems capable of being moved into production |  |  |  | #6 |  | #6 |  | #6 |  | #6 |  | #6
5.3 |  | Performance of, and communication between, market systems validated during industry testing | [5 empty] | #7 |  |  |  | #7 |  | #7
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place | [9 empty] | #8 |  | #8
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals) | [7 empty] | #8 |  | #8 |  | #8
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Networks (ENM, ENO) |  | Third party e-hub
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdictional risk is a reflection of overall project risk.
NSW |  | Jurisdictional risk is a reflection of overall project risk.
QLD |  | Jurisdictional risk is a reflection of overall project risk.
SA |  | Jurisdictional risk is a reflection of overall project risk.
TAS |  | Jurisdictional risk is a reflection of overall project risk.
VIC |  | Jurisdictional risk is a reflection of overall project risk, with additional risk noted due to the uncertainty associated with the Victorian Government Transition to Metering Competition in Victoria decision timing in March 2017, and the treatment of VICAMI meters.

## HIDDEN 25% (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2017-04-03
Variances
Note # | Explanation of Variance |  |  | Mitigating Actions
1 | Variance reported by Participants: Detailed implementation plan development at risk due to uncertainty of rule and procedural operation and dependency on new and immature market participants and processes. Implementation Plans are being re-assessed due to the Victorian Government deferral decision.
2 | Variance reported by Participants: Updating policies and procedures on schedule is at risk due to lack of clarity on safety regulation and the detailed implementation regarding the Victorian decision to defer metering competition (awaiting the Order in Council). |  |  | Participants are continuing to engage with the relevant departments and safety bodies.
3 | Variance reported by Participants: Updating commercial arrangements on schedule is at risk due to volume of contracts that need to be entered into with industry parties and variable meter service provider maturity.
4 | Variance reported by Participants: Fulfilling registration and accreditation activities on schedule is at risk due to lack of an E-Hub accreditation guideline and compressed timeframes for all registration and accreditation activities. |  |  | AEMO released the draft e-hub accreditation process and application form for feedback from participants on 6 April 2017. Vic DBs are continuing to seek confirmation from AEMO, AER and Victorian Government on whether meters can remain as Type 5 MRIM.
5 | Variance reported by DBs: Progress on this is less than expected due to required rework from the final B2B Procedure changes. Progress has been impacted by the Victorian Government deferral decision. |  |  | Business process activity continuing (impact assessment between final and draft procedures), additional experienced resources and subject matter experts sourced.
6 | Variance reported by Participants: System design and development are dependent on finalisation of procedures and technical specifications for completion. Progress has been impacted by the Victorian Government deferral decision. |  |  | Participants are gathering detailed business and system requirements (undertaking impact assessments between final and draft procedures).
7 | Variance reported by Participants: Testing timelines are contingent on system design and build and are becoming increasingly compressed and unrealistic. |  |  | Participants engaging in development of Industry Testing Strategy
8 | Variance reported by Participants: Transition and cutover is dependent on above activities (business processes, commercial arrangements, system build and testing) and compressed timeframes are a concern.
Notes
Key - Progress and Status | [5 empty] | Key - Risk Rating
Progress |  |  | Status
Harvey balls represent progress towards achieving the criterion |  |  | Colour indicates the readiness status |  |  | Rating
~0% |  | ~50% | Criterion is within agreed schedule and deliverable requirements |  |  | High
~10% |  | ~60% | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~20% |  | ~70% | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~30% |  | ~80% |  |  |  | See POC Industry Risk Register for open risks and issues:
~40% |  | ~90% | Criterion has been achieved |  | ü | POC Industry Register

## Retailer Reports
| 2017-04-03 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Retail | Within schedule | Medium | ActewAGL Retail has completed a high level impact assessment of the changes required by PoC on its business operations and systems, requirements have been baselined and a detailed project plan is being finalised in order to achieve compliance by the "go live" date.
| AGL | Within schedule | Medium | Project currently tracking to plan for Dec 2017 delivery. Work Package 1 build and test is now completed. B2B process updates have been mapped and requirements have been captured. Validation of process updates and key assumptions is now required with external parties. | [7 empty] | Risk rating remains at medium due to the number of parties involved, limited build timeframes, impacts arising from the Victoria competition decision, updated schema timing dependencies and limited industry testing timeframes.
| Alinta Energy | Within schedule | Medium | Project progressing to plan. Impact of Victorian Changes to be determined
| Aurora Energy | At risk | Medium | Aurora Energy continues to manage a number of risks with regards to the implementation of the Power of Choice reforms by 1 December 2017. The most significant risk is the aggressive implementation timeline, reflected in Aurora Energy's 'at risk' project status. This risk is also impacting the ability of Aurora Energy's key vendors (including, but not limited to, prospective Metering Coordinators) to meet POC timeframes.
| Energy Australia | At risk | Medium | The Program is making steady progress but is behind schedule in several areas due to the extent of changes in the B2B procedures and the recent Vic Government decision to delay PoC. There is high risk to schedule due to lack of clarity on safety regulations and conversion of VicAMI type 5 to Type 4. Risks associated with industry coordinated activities, such as BCP, Industry Testing, Transition and Emergency Planning are increasing. | [7 empty] | The Program is making steady progress but is behind schedule in several areas due to the extent of changes in the B2B procedures and the recent Vic Government decision to delay PoC. There is high risk to schedule due to lack of clarity on safety regulations and conversion of VicAMI type 5 to Type 4. Risks associated with industry coordinated activities, such as BCP, Industry Testing, Transition and Emergency Planning are increasing. | [5 empty] | Risks associated with industry coordinated activities, such as BCP, Industry Testing, Transition and Emergency Planning are increasing.
| Ergon Energy Queensland (retail) | Within schedule | Medium | Due to the high number of changes to our retail billing system due to procedural and B2B changes, overall this project remains as a 'medium risk'. At this stage no changes have been made to jurisdictional safety requirements which will enable remote re-energisation. This remains a risk that retailers will not achieve the full benefits without these changes. | [7 empty] | Due to the high number of changes to our retail billing system due to procedural and B2B changes, overall this project remains as a 'medium risk'. At this stage no changes have been made to jurisdictional safety requirements which will enable remote re-energisation. This remains a risk that retailers will not achieve the full benefits without these changes.
| M2 Energy Pty Ltd | Within schedule | Medium | Project Scoping by Vendor is 90% complete. Vic related changes are a substantial risk. Business intention is to outsource MC role. Risk considered Medium as few vendors currently available for selection. M2 Energy is maintaining dialogue with potential vendors. | [7 empty] | Vic withdrawal from POC has introduced risk into System Scoping, and increased training and change management requirements.
| Mojo Power Pty Ltd | Within schedule | Medium | [8 empty] | Decision by Victorian Government not to proceed with metering competition until 2012 eases some risk but treatment of VIC AMI by market is unresolved.
| Momentum Energy | Within schedule | Medium | [8 empty] | Detailed planning being developed
| Origin Energy | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Business and Systems impact assessments are completed and Project Realisation progressing well. VIC derogation extension impact assessment ongoing. Amber status is maintained due to high number of delivery risks that will need to be monitored and mitigated for the duration of the project | [7 empty] | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Business and Systems impact assessments are completed and Project Realisation progressing well. VIC derogation extension impact assessment ongoing. Amber status is maintained due to high number of delivery risks that will need to be monitored and mitigated for the duration of the project
| Pacific Hydro | At risk | Medium | The timing and outcomes of the following outstanding PoC activities have the potential to impact the build, test and implementation phases: 1. MSATS WP3. 2. B2B - As Built Consultation - Commencing 12 April. 3. B2B - technical solution -still under review by AEMO and yet to be formally advised. 4. Meter Churn Issues - recently raised and despite a paper being issued by AEMO, there are still concerns being raised. 5. Vic Government decision not to proceed with PoC. 6. Jurisdictional safety review of the remote Re-en/De-en process. There is also an issue with other Market changes, e.g. Retail Transfer Errors to take effect 3 August 2017, being introduced within the PoC delivery timeframe.
| People Energy Pty Ltd | Within schedule | High | Due to the Decision of the Victorian Government, PE currently trying to understand the full level of impact and the impact to our work streams and system. We are concerned surrounding system changes where by different process and system requirements may exit for NEM states VS Victoria.
| Pooled Energy | Within schedule | Medium | Although the procedural and consultations are on track the project is considered at risk until these are finalised | [7 empty] | Although the procedural and consultations are on track the project is considered at risk until these are finalised
| Powershop | Within schedule | Medium | Powershop is currently undertaking a gap analysis of changed procedures. This will form the scope of change required for Powershop developers.
| Red Energy & Lumo Energy | At risk | High | Not clear on implications of the Victorian Government decision and additional system and process consequences from the decision | [7 empty] | Implications of the Victorian Government decision not known
| Simply Energy | Within schedule | Medium | The program has identified two keys risks: 1. outcome of Meter Churn Procedures workshop held on the 24th Feb 2017 might not be suitable for the industry; 2. VIC Govt decision of deferral of metering competition has opened a few questions that's impacting our design and build, e.g. new connections process in VIC; Plan of approach for VICAMI meters post go-live (type 5 vs type 4 issue), etc. | [13 empty] | Simply Energy has progressed as per it's internal plan of Power of Choice Program of Work and have prioritised B2M changes in order to commence testing for r35 schema, currently targeting May/June 2017.
| Stanwell Corporation Limited | Within schedule | Low | Project progressing as planned.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Retail | Within schedule | Medium | Within schedule | Medium
| AGL | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Alinta Energy |  |  | Within schedule | Medium |  |  | Within schedule | Medium |  |  | Within schedule | Medium
| Aurora Energy | [8 empty] | At risk | Medium
| Energy Australia | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ergon Energy Queensland (retail) |  |  |  |  | Within schedule | Medium
| M2 Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Mojo Power Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Momentum Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro |  |  | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| People Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | High
| Pooled Energy |  |  | Within schedule | Medium
| Powershop |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Red Energy & Lumo Energy |  |  | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | High
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Stanwell Corporation Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  |  |  | Within schedule | Low
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Completed (100%) | 100% | 51% - 60% | 71% - 80% | 61% - 70% | 25% | 51% - 60% | 71% - 80% | 75% | Completed (100%) | 31% - 40% | 31% - 40% | 50% | 41% - 50% | 81% - 99% | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 41% - 50% | 1% - 10% | 75% | 31% - 40% | 51% - 60% | 31% - 40% | 25% | 11% - 20% | 31% - 40% | 50% | 51% - 60% | 11% - 20% | 11% - 20% | 50% | 1% - 10% | 61% - 70% | 11% - 20%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 21% - 30% | 71% - 80% | 25% | 21% - 30% | 41% - 50% | 51% - 60% | 25% | 51% - 60% | 31% - 40% | 25% | 51% - 60% | 11% - 20% | Not started (0%) | 75% | 81% - 99% | 21% - 30% | 61% - 70%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Not started (0%) | Not started (0%) | 0% | 21% - 30% | 31% - 40% | 11% - 20% | 0% | 61% - 70% | Not started (0%) | 25% | Not started (0%) | 1% - 10% | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 11% - 20% | 11% - 20% | 0% | 1% - 10% | 1% - 10% | 1% - 10% | 0% | 61% - 70% | Not started (0%) | 0% | Not started (0%) | 1% - 10% | 11% - 20% | 25% |  | 31% - 40% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Not started (0%) | N/A | N/A | 1% - 10% | 21% - 30% |  | 0% | N/A | 21% - 30% | 25% | 31% - 40% | 1% - 10% | Not started (0%) | 25% |  | 51% - 60% | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Not started (0%) | N/A | N/A | 1% - 10% | 1% - 10% |  | N/A | N/A | 1% - 10% | 0% | Not started (0%) | Not started (0%) | Not started (0%) | N/A |  | Not started (0%) | Completed (100%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 1% - 10% | Not started (0%) | 0% | 21% - 30% | 51% - 60% |  | 0% | Completed (100%) | 11% - 20% | 50% | 41% - 50% | 1% - 10% | 21% - 30% | N/A | 11% - 20% | 21% - 30% | 21% - 30%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 0% | 41% - 50% | 31% - 40% |  | N/A | Completed (100%) | Not started (0%) | 25% | 1% - 10% | Not started (0%) | 11% - 20% | N/A | Not started (0%) | Not started (0%) | 21% - 30%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | 0% | 11% - 20% | Not started (0%) |  | 0% | 1% - 10% | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 51% - 60% | 0% | 61% - 70% | 61% - 70% | 31% - 40% | 0% | 21% - 30% | 1% - 10% | 75% | 21% - 30% | 11% - 20% | 21% - 30% | 50% | 11% - 20% | 41% - 50% | 11% - 20%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 21% - 30% | 11% - 20% | 0% | 31% - 40% | 21% - 30% | 1% - 10% | 0% | Not started (0%) | Not started (0%) | 25% | Not started (0%) | 1% - 10% | Not started (0%) | 50% | Not started (0%) | 11% - 20% | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 25% | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 51% - 60% | 31% - 40% | 75% | 41% - 50% | 61% - 70% | 31% - 40% | 50% | Not started (0%) | 31% - 40% | 75% | 31% - 40% | 21% - 30% | Not started (0%) | 50% | 21% - 30% | 31% - 40% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Not started (0%) | 21% - 30% | 0% | 1% - 10% | 21% - 30% |  | 25% | Not started (0%) | 1% - 10% | 25% | Not started (0%) | 11% - 20% | Not started (0%) | 0% | Not started (0%) | 1% - 10% | 51% - 60%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | 21% - 30% | 0% | 1% - 10% | 1% - 10% |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 1% - 10% | 0% | 1% - 10% | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 25% | Not started (0%) | 1% - 10% | Not started (0%) | 25% | Not started (0%) | Not started (0%) | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) |  | 0% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Completed | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | N/A | At risk | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule |  | At risk | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Completed
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule |  | N/A | N/A | Within schedule | At risk | Within schedule | N/A | Within schedule | N/A | N/A | N/A | N/A
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk |  | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk |  | Within schedule | Within schedule | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk |  | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | High level impact assessment has been conducted. |  |  | A detailed assessment of necessary business operational process and systems changes is currently being completed. This continues to be informed by on-going AEMO market procedure consultation. Given the uncertainty of rule and procedure operation, this is considered 'at risk'. | Increasing certainty around procedures (excl Vic) |  |  |  |  | Impact Assessment completed, but will need to be iterated pending consultation outcomes and changes. VIC derogation extension impact assessment ongoing. |  |  |  | Powershop is currently undertaking a gap analysis of changed procedures. This will form the scope of change required for Powershop developers.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | A high level project plan has been drafted, a detailed plan is in progress, see 4.1 and 5.1 below |  | In Progress Victorian impact to be included | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging. Additional changes to enable all other core operations post 1 December 2017 are being assessed. The aggressive timelines for systems build and testing, combined with contracting and establishment of an MC and the required implementation and testing combined systems is the basis of the 'at risk' status. | High level of dependency on third parties. Plans are dependent on new and immature market participants and processes. Progress has been impacted by the Victorian decision. |  |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension impact assessment ongoing.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | The ACT Government is reviewing the ACT regulatory framework |  |  | Activity has commenced as part of POC impact assessment. | Assessment in progress and on track but there are still unknowns in regards to jurisdictional safety requirements, and associated obligations on Retailers and MCs. Progress has been impacted by the Victorian decision. | Queensland jurisdictional safety requirements are yet to be addressed. | scheduled and commenced. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines |  |  |  |  | Excludes Victoria and any potential changes required for Victoria | Awaiting jurisdictional safety regulators to publish requirements
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | Commenced | Preliminary advice has been sough with regards to regulatory compliance. In addition to direct metering competition regulatory changes, a key challenge for Aurora Energy is to consider the wider (/indirect) regulatory implications of metering competition on business-as-usual activities. A key challenge is that the existing regulatory framework was developed in the context of type 6 metering. | Red due to the lack of clarity on safety regulations | Queensland jurisdictional safety requirements are yet to be addressed. | not yet scheduled. |  |  | Policy changes/decisions still being derived through Blueprinting | Vic Government decision on PoC and timing of regulatory changes to reflect the decision not to proceed with PoC.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Commerical negotiations have commenced and some are in the process of finalisation. |  | Commenced | Activity has commenced for customers and vendors as part of POC implementation. | Due to volume of contracts that need to be entered into with industry parties, plus variable meter service provider maturity. | These processes have commenced. | not yet scheduled. |  |  | Overall strategy has been developed and endorsed |  |  |  |  | Internal management of this item | Meter Churn (Package 3) is causing some issues in finalising high level agreements.
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy will be required to receive accreditation for using the B2B e-hub, however there is, as yet, no documentation available to prepare for accreditation. The timeline and uncertainty for accreditation and registration activities of other participants (specifically, the Metering Coordinator role) also impacts on Aurora Energy's planning. Dialogue with the jurisdictional safety regulator has commenced. |  |  | unclear testing registration requirements and impacts at this time. |  |  | Underway for new Market Roles |  |  |  | Powershop is about to commence a confirmation process with third-parties to ascertain their position | Internal management of this item
2.5 |  | The fulfilment of accreditation and registration obligations | [8 empty] | Aurora Energy will be required to receive accreditation for using the B2B e-hub, however there is, as yet, no documentation available to prepare for accreditation. The timeline and uncertainty for accreditation and registration activities of other participants (specifically, the Metering Coordinator role) also impacts on Aurora Energy's planning. Dialogue with the jurisdictional safety regulator has commenced. | [5 empty] | Unable to commence until Blueprinting and overall strategy has been developed and endorsed |  |  |  |  | Internal management of this item | Pending outcome from 2.4
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | High level impact assessment has commenced. |  |  | This has commenced and will be finalised following with the detailed assessment of operational and systems changes. | Being developed as impacts are understood and target state design is finalised |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | The recruitment of specialist human resources to cater for the rule change has commenced. | As above |  |  |  |  | Policy changes/decisions identified | [5 empty] | Scheduled to commence in mid 2017
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [8 empty] | Training requirements are currently being assessed as part of the internal process review and updates. | The magnitude of change and the number of staff required to be trained make this a high risk activity. |  | not yet scheduled. |  |  | Training requirements and resourcing determined and magnitude of change is understood |  | This task is yet to commence |  |  |  | Scheduled to commence in late 2017
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Detailed assessment has been conducted on the release CATS/B2B procedures. Impact of Meter Churn clarification being assessed. |  | Commenced | All impacted service order, B2B & B2M and business processes have been identified. Assessment of current and future processes is underway to enable gap analysis and identify process and system changes. Possible future changes puts the delivery scope and timeline at risk. | Dependent on finalisation of industry-wide processes. Progress has been impacted by the Victorian decision. |  | commenced and in schedule |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension impact assessment ongoing
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Key end to end processes have been documented and are in review. |  | Commenced | Future business processes are currently being developed using the details from Work Package 1 and 2, as well as the B2B procedures. The timeline for implementation and on-going procedural uncertainty is the basis for Aurora Energy reporting 'at risk'. | As above |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension impact assessment ongoing
4.3 |  | The validation of business processes during industry testing | [8 empty] | Activity has not yet started. |  |  | not yet scheduled. |  |  | Not Commenced | [5 empty] | Due to commence in May 2017
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Requirements have been defined and system changes currently being assessed by the external vendor. Detailed design will commence this month. |  | Assessment commenced in conjunction with the vendor | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging systems. The aggressive timeframe impacts on the ability of Aurora Energy's key vendors (including, but not limited to, prospective Metering Coordinators) to deliver the required system changes. | Dependent on bilateral agreements with external parties. Progress has been impacted by the Victorian decision. | Blueprinting complete | Vendor at 48% completion of overall project plan |  | System development is reliant on external vendor, delays in final market procedures will impact readiness activities | Detailed impact assessment of system changes has completed. Review of updated B2B procedures in progress. VIC derogation extension impact assessment ongoing. Schema version considered for B2B will be R36 and B2M will be R35. Transaction Acknowledgment TBC. | A full assessment cannot be undertaken until the technical solution for B2B is known. This is further complicated by the Vic Government decision not to proceed with PoC. |  |  |  |  | BRDs are being drafted for initial review
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Commenced | Aurora Energy has engaged its key vendors to commence functional and technical design for system changes. However, systems changes will still be impacted by the any further changes to the B2B/B2M environment as part of Work Package 3. | Has been dependent upon final B2B Procedures and R36 schema. |  | vendor at 15% of retail sys build plan |  |  | Systems development commencement is dependent on the outcomes and conclusions of the Systems IA and Requirements being understood | As per the comment in 5.1. Also Business Requirements Specification documents are yet to be approved. |  |  |  |  | Requirement gathering workshops have commenced with vendors, functional specs underway
5.3 |  | The internal testing of market systems for your business | [8 empty] | Test Strategy development has commenced to support internal and industry testing. | Internal test preparation underway. |  |  |  |  | Not Commenced | As per 5.2 |  |  |  |  | Scheduled to commence in mid 2017
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | This has not started and not due to start until mid-2017. | Dependency on AEMO Industry Test Strategy. Build is dependent upon receiving final r36 schema changes. |  |  |  |  | Not Commenced | As per 5.2 |  |  |  |  | Scheduled to commence in mid 2017
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | This has not started and not due to start until mid-2017. | Dependency on AEMO Industry Test Strategy. |  |  |  |  | Not Commenced | As per 5.2 |  |  |  |  | Scheduled to commence in mid 2017
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [8 empty] | A Transition Plan will be completed once AEMO packages and commercial agreements with Metering Coordinator(s) are finalised. | AEMO Cutover and Transition Strategy is a key dependency and has not been published yet. |  |  |  |  | Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, cyclone, etc). Transition & Cutover planning will take this into account.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [8 empty] | Activity has not yet started. | As above |  |  |  |  | Transition planning and scheduling cannot be accurately determined until Design & Build is completed. Outstanding question re Updating Meter Standing Data (MC/ENM role, NMI/Meter Register Status) across industry participants
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms, within the context of the timeframe and procedural uncertainty. | Planning to undertake impact analysis after Vic decisions.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Aurora Energy has implemented a program of work to effectively and efficiently work towards market compliance. | [5 empty] | Origin has onboarded additional Business and Technology resources
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [10 empty] | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office. |  |  |  | Origin has onboarded additional Business and Technology resources | [5 empty] | Internal assessments have commenced
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [10 empty] | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office. |  |  |  |  | Closely monitor Vic Government's progress on this matter.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [14 empty] | Origin has onboarded additional Business and Technology resources | [5 empty] | Package 3 scope should hopefully resolve the issues raised by the industry, however we're awaiting for the outcome.
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy is proceeding on the assumption that accreditation will be received. |  | Awaiting AEMO publication of retailer e-hub requirements |  |  |  | Origin has onboarded additional Business and Technology resources
2.5 |  | The fulfilment of accreditation and registration obligations | [8 empty] | Aurora Energy is proceeding on the assumption that accreditation will be received. | [5 empty] | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [14 empty] | Origin has onboarded additional Business and Technology resources
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [14 empty] | Origin has onboarded additional Business and Technology resources
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [14 empty] | Origin has onboarded additional Business and Technology resources
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [8 empty] | Aurora Energy continues to invest considerable effort in participating in AEMO procedural consultation. Aurora Energy is proceeding on the basis of the currently available information and must continue to manage the risk of final procedures changing. | [5 empty] | Origin has onboarded additional Business and Technology resources
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [14 empty] | Origin has onboarded additional Business and Technology resources
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [8 empty] | Aurora Energy is in the process of gathering detailed business and system requirements and engaging with key vendors. | [5 empty] | Origin has onboarded additional Business and Technology resources | Engaging with AEMO through the Systems WG and closely monitoring Vic Government's progress on the regulatory changes.
5.2 |  | The development and build of appropriate market systems for your business | [8 empty] | Aurora Energy is in the process of gathering detailed business and system requirements and engaging with key vendors. | [5 empty] | Origin has onboarded additional Business and Technology resources | As per the comment in 5.1 and engaging with our vendor to finalise/agree known changes.
5.3 |  | The internal testing of market systems for your business | [15 empty] | As per 5.2
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [15 empty] | As per 5.2
5.5 |  | The validation of performance of market systems during industry testing | [15 empty] | As per 5.2
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [14 empty] | Transition & Cutover planning will take this into account.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Retailer Participation
References:
|  |  | AEMO | http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Participant-information/Current-participants/Current-registration-and-exemption-lists
|  |  | AER | https://www.aer.gov.au/retail-markets/authorisations/public-register-of-authorised-retailers-and-authorisation-applications
|  |  | ESC | http://www.esc.vic.gov.au/project/energy/2075-licensing/
Retailer | On April 2017 Report? | On March 2017 Report?
1st Energy Pty Ltd | No | No
ActewAGL Retail | Yes | Yes
AGL | Yes | Yes
Alinta Energy | Yes | Yes
Aurora Energy | Yes | Yes
Blue NRG Pty Ltd | No | No
Click Energy Pty Ltd | No | No
Covau Pty Limited | No | No
COzero Energy Retail Pty Ltd | No | No
Diamond Energy Pty Ltd | No | No
Energy Locals Pty Ltd | No | No
EnergyAustralia | Yes | Yes
Enova Energy Pty Ltd | No | No
Ergon Energy Queensland (retail) | Yes (using March report) | Yes
ERM Power Retail Pty Ltd | No | No
Globird Energy Pty Ltd | No | No
Lumo Energy (reporting with Red Energy) | Yes | Yes
M2 Energy Pty Ltd | Yes | Yes
Macquarie Bank Limited | No | No
Mojo Power Pty Ltd | Yes | Yes
Momentum Energy | Yes | Yes
Next Business Energy Pty Ltd | No | No
Online Power and Gas Pty Ltd | No | No
Onsite Energy Solutions Pty Ltd | No | No
Origin Energy | Yes | Yes
Pacific Hydro | Yes | Yes
People Energy Pty Ltd | Yes | Yes
Pooled Energy Pty Ltd | Yes | No
Powerdirect Pty Ltd | No | No
Powershop Australia Pty Limited | Yes | No
Progressive Green Pty Ltd | No | No
Qenergy Limited | No | No
Red Energy | Yes | Yes
Sanctuary Energy Pty Ltd | No | No
Simply Energy | Yes | Yes
SparQ Pty Ltd (Sumo Power) | No | No
Stanwell Corporation Limited (Stanwell Energy) | Yes | No
WINenergy Pty Ltd (WINenergy) | No | No

## Distributor Reports
| 2017-04-03 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule | Medium | AAD has commenced system changes and internal business process changes within the constraints of currently known requirements published by AEMO. The work undertaken is subject to review on the basis that AEMO is frequently reviewing and updating industry requirements. | [7 empty] | AAD has reviewed the registration process to become the initial MC and is currently preparing material for submission to AEMO. | [5 empty] | Accreditation transfer and registration starting 2 March is a risk area and it is noted that AEMO will still be developing systems and processes at the time industry is requested to start this process. AAD received the registration information for initial MC requirements and is currently assessing these requirements. The readiness of AAD to interface with the AEMO B2B hub is a significant risk. In the absence of information, the system changes required to facilitate this new data flow is undefined. It is noted AEMO have 12 mths to develop this and Industry only have 3.5 mths to implement. There is a disparate timeframe for Industry to modify, test, put into production and this is noted as a major area of concern for AAD.
| Ausgrid | At risk | Medium | We have established a formal ICT project and assigned resources. A number of significant IT rebuilds are expected to be required in order to facilitate the new B2B requirements. | [7 empty] | Issues noted above (section B) impact on all these categories.
| AusNet Services | At risk | Medium | Project in progress. The overall risk rating is a consequence of; 1. The scope of the changes are significant, requiring development resource/effort/cost beyond initial estimates 2. Schedule and Scope risk is significant given the strategies for Industry Testing, Industry Systems Implementation and Market Transition have not been finalised 3. Uncertainty about the means to be used by the Victorian Government to implement the deferral of Metering Competition after the derogation expires 4. Lack of definition of whether Vic AMI Meters will be treated as Type 4, Type 5 or a mixture 5. Constrained time allowed for Testing | [7 empty] | The scope of changes to be delivered are greater than anticipated and delivery timeframes are highly compressed. Unable to assess ability to align with Industry Testing and Market Transition phases as strategies for these activities have not been finalised. | [5 empty] | The scope of changes to be delivered is greater than anticipated and delivery timeframes are highly compressed. (i.e.; ~5 months between the publication of final B2B Procedures on March 6th and the commencement of Industry Testing in early August). Final approach to Industry Testing and Market Transition are required to confirm overall delivery scope can be delivered within available timeframes.
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Within schedule | Medium | CitiPower/Powercor is progressing its analysis and build phase in accordance with the program schedule. | [7 empty] | The Victorian Government has decided to defer the introduction of metering competition in Victoria for small customers until at least the end of 2020. In line with this decision, CitiPower and Powercor are to become a compliant Metering Coordinator/Metering Provider/Meter Data Provider, limited to small customer metering installations within it's network territory. CitiPower and Powercor has commenced the assessment of additional requirements to provide new and replacement metering services from 1 December 2017.
| Endeavour Energy | At risk | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures. The B2B procedures requires significant system and process changes, however there is only 6-7 months to design and develop and to test with the market to achieve accreditation. It is noted that registration as a B2B e-Hub Participants is required before the B2B e-Hub can be used. This registration process is also at risk as there is a dependency to demonstrate system compliance with the B2B procedures. AEMO facilitated a workshop on the meter churn process for participants to highlight issues and more efficient process options. There is a risk that by the time AEMO clarifies the process/procedures with an agreed industry position, it could further shorten system design and build timeframes. The final determination for the "as built" consultation for AEMO procedures and B2B procedures will not be published until 30 November 2017 which leaves no time to implement any changes for market start on 1 December 2017. To mitigate this we are actively participating in the various working groups including the PoC-WG, B2BWG and SWG to ensure that AEMO procedures and B2B procedures supports the metering contestability and embedded networks rule changes in the most effective and cost efficient manner, and to only include transactions and obligations required for go live as a priority. | [7 empty] | [See project comment] | [5 empty] | This report is for Endeavour Energy as at 31 March 2017. Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5, 6 & 7 metering installations from 1 December 2017. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. The activities for the Market Systems testing and cutover are dependent on the development and build of the appropriate market system which is currently at risk.
| Energex Ltd. & Ergon Energy Corporation Ltd. | At risk | Medium | The project is progressing as planned. However, ring-fencing, new B2B Procedures and new system requirements are collectively proving to make planning and delivery challenging in such a tight timeframe. Further changes to B2B Guidelines, particularly in regards to the Notified Party and One Way Notifications now becoming 'May' in place of 'Must', is causing further delay to already very tight timelines. | [7 empty] | The magnitude of change in the final version of the B2B Procedures has impacted planning activities and the associated schedule. The project is currently 'At risk'. | [5 empty] | Both Ergon Energy Corporation Ltd and Energex Ltd sustained severe damage to its Distribution Networks as a result of Tropical Cyclone Debbie. Business resources have been re allocated to assist with the emergency response efforts for both businesses during a critial phase of the project. As we are still in the midst of dealing with this event we are yet to fully understand the impacts this has had on the Power of Choice project and its readiness.
| Essential Energy | At risk | Medium | Essential Energy's PoC program is underway. Significant system and process changes are required to deliver compliance by 1 December 2017. Critical path includes delivery of system changes for B2B compliance, timing is tight to finalise design, complete build, and undertake internal testing, in readiness to participate in industry testing for August 2017. | [7 empty] | [Distributor]:Essential Energy will be an Initial MC for Type 5 and 6 meter installations connected as at 1 December 2017. Risk rating is moderate due short timeframe to design, build and implement systems required to meet compliance timeframe. [Meter Provider]:Type 5 & 6 basic meters only. Risk rating is low. [Meter Data Provider]: Type 5 & 6 basic meters only. Risk rating is classified as moderate due requirements to short timeframe to update systems for B2B changes, including to receive and process meter exchange information to enable publishing of final readings for Type 5 & 6 meters. | [5 empty] | Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Networks | Within schedule | Medium | With 9 months to go-live on 1 December 2017, the project is rated at MEDIUM risk this report due to 1. the uncertainty of delivery scope associated with the Victorian Government Option 4 - Defer Competition decision; 2. the adequacy of the proposed industry testing scope and timeframe; 3. the proposed go-live date of 1 December 2017 causing a need to perform a Type 4 data conversion and cutover mid week, at a Financial Month End period prior to the Financial & Regulatory Year End period, and during a period of high volumes for Customer new connections, adds and alts pre-Christmas. | [7 empty] | With 9 months to go-live on 1 December 2017, the project is rated at MEDIUM risk this report due to 1. the uncertainty of delivery scope associated with the Victorian Government Option 4 - Defer Competition decision; 2. the adequacy of the proposed industry testing scope and timeframe; 3. the proposed go-live date of 1 December 2017 causing a need to perform a Type 4 data conversion and cutover mid week, at a Financial Month End period prior to the Financial & Regulatory Year End period, and during a period of high volumes for Customer new connections, adds and alts pre-Christmas.
| SA Power Networks | Within schedule | Medium | Currently within SAPN delivery schedule tolerance. Closely monitoring IT system development/build to ensure timely delivery of system changes.
| TasNetworks | At risk | Medium | TasNetworks plan is to be ready business preparations and the development of specifications with vendors is progressing well, TasNetworks' market systems build schedule could propose a delivery timeline post the industry testing dates, not allowing TasNetworks to fully participate in industry testing before the scheduled go live.
| United Energy | At risk | High | Internal preparations continue to progress well. The amber status reflects the impact the Vic. Govt. deferral decision, which has necessitated revisions to previously-completed designs and is putting pressure on the critical path. High risk rating reflects uncertainty over meter specifications, meter classification requirements and accreditation requirements. | [7 empty] | [Distributor]: Risk rating is Medium. UE operates in Victoria only. Jurisdictional status refects overall position. [Meter Coordinator, Meter Provider and Meter Data Provider]: Risk rating is High. Vic deferral has created uncertainty over meter specifications / classification. | [5 empty] | Key concerns for UE (and industry) readiness are as follows: 1) The Victorian Government decision to defer metering competition has created a number of uncertainties, including: a) whether the DB role as newly-appointed MC after 1 Dec is regulated or contenstable, what controls will apply and whether ring-fencing waiver will be necessary, b) whether new meters after 1 Dec 2017 will be classified as Type 5 or Type 4 and c) whether new meters 1 Dec 2017 will be required to meet the national specification as well as Victorian AMI. These uncertainties may result in additional scope and cost, and potentially an inability to be fully compliant by 1 Dec 2017. 2) Lack of definitive direction on whether UE's existing VICAMI meters can remain as Type 5 MRIM is creating uncertainty around whether system changes, data changes and accreditation for Type 4 meters will be required in this area. Continuing to seek confirmation from AEMO, AER and Victorian Government. UE considers that there is no clear requirement in the NER which compels reclassification, UE has provided its views in writing to AEMO/AER on 6 February and we understand that AEMO will document its view that these meters are Type 4 and outlining how the reclassification can be avoided. 3) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. UE's compliance in this area may also be dependent on existing child metering services being transitioned to meter providers on or by 1 Dec 2017, although this is yet to be confirmed. If transition is required, it will be an activity over which UE does not have full control. 4) UE is concerned that the lateness of procedures finalisation and the complexity and scale of testing with the increased number of market participants may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections and supply processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule | Medium
| Ausgrid |  |  | At risk | Medium
| AusNet Services | [10 empty] | At risk | Medium
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | Within schedule | Medium
| Endeavour Energy |  |  | At risk | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | At risk | Medium
| Essential Energy |  |  | At risk | Medium
| Jemena Electricity Networks | [10 empty] | Within schedule | Medium
| SA Power Networks | [6 empty] | Within schedule | Medium
| TasNetworks | [8 empty] | At risk | Medium
| United Energy | [10 empty] | At risk | High
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 41% - 50% | 71% - 80% | Completed (100%) | 61% - 70% | 51% - 60% | 81% - 99% | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 51% - 60% | 21% - 30% | 31% - 40% | Completed (100%) | 51% - 60% | 61% - 70% | 41% - 50% | 61% - 70% | 81% - 99% | 81% - 99% | Completed (100%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 41% - 50% | 21% - 30% | 31% - 40% | Completed (100%) | 31% - 40% | 11% - 20% | 61% - 70% | 51% - 60% | 81% - 99% | 31% - 40% | 61% - 70%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 31% - 40% | 21% - 30% | 31% - 40% | 21% - 30% | 11% - 20% | Not started (0%) | Not started (0%) | 31% - 40% | 11% - 20% | 21% - 30% | 11% - 20%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 21% - 30% | 1% - 10% | 1% - 10% | 41% - 50% | 21% - 30% | 1% - 10% | Not started (0%) | 11% - 20% | 1% - 10% | 1% - 10% | 11% - 20%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 41% - 50% | Not started (0%) | Not started (0%) | 41% - 50% | 61% - 70% | 11% - 20% | 21% - 30% | 1% - 10% | 21% - 30% | 41% - 50% | 1% - 10%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 31% - 40% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | 21% - 30% | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 21% - 30% | 31% - 40% | 11% - 20% | Not started (0%) | 31% - 40% | 11% - 20% | 11% - 20% | 41% - 50% | 11% - 20% | 21% - 30% | Completed (100%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 1% - 10% | 31% - 40% | 1% - 10% | Not started (0%) | 31% - 40% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 11% - 20% | 21% - 30% | Not started (0%) | Not started (0%) | 1% - 10% | 1% - 10% | Not started (0%) | 11% - 20% | 1% - 10% | Not started (0%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 31% - 40% | 21% - 30% | 11% - 20% | 71% - 80% | 61% - 70% | 21% - 30% | 31% - 40% | 51% - 60% | 81% - 99% | 51% - 60% | Completed (100%)
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 31% - 40% | 11% - 20% | 11% - 20% | 61% - 70% | 31% - 40% | 11% - 20% | Not started (0%) | 41% - 50% | 71% - 80% | Completed (100%) | 81% - 99%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 31% - 40% | Completed (100%) | 21% - 30% | 41% - 50% | 51% - 60% | 31% - 40% | 11% - 20% | 71% - 80% | 41% - 50% | 81% - 99% | 81% - 99%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 21% - 30% | 1% - 10% | 21% - 30% | 21% - 30% | Not started (0%) | Not started (0%) | Not started (0%) | 11% - 20% | 21% - 30% | 11% - 20% | 21% - 30%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | 11% - 20% | 21% - 30% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | 1% - 10%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10% | 1% - 10% | 21% - 30% | Not started (0%) | 1% - 10% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | At risk | At risk | Completed | Within schedule | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | At risk | Completed | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Not within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | N/A | Within schedule | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Completed
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | At risk | At risk | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | At risk | At risk | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | At risk | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | At risk | Within schedule | N/A | Within schedule | At risk | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Power of Choice reforms have been assessed and impacts on the business have been determined for most areas. Those areas where system changes are yet to be defined or are awaiting finalisation have not been assessed at the time of writing. |  | Impact assessment of Victorian Government decision is in progress |  |  | High-level scope and requirements documents have been signed off by the business. Currently performing the organisational impact assessment. | Working to finalise impact assessment following release of B2B procedures | JEN was 100% complete based on option 1. Now that Vic Government has chosen option 4, we are undertaking a new assessment - still waiting for OIC scope clarification. |  |  | Completed documents are being checked/revised for deferral impact
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD is commencing testing on the first round of system changes which will be subject to further review depending on changes to requirements issued by AEMO in future. Business processes and procedures are also undergoing review with all work practices and supporting documentation for two major branches currently underway. |  | Implementation plans for internal systems established and in progress. Lack of certainty about treatment for AMI Meter Type creates significant scope risk. Development of Industry implementation and market transition plans required to validate internal scope/approach. |  |  | The magnitude of change in the final version of the B2B Procedures has impacted planning activities and the associated schedule. | Delayed due to delay in completing the high level impact assessment | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | Governance and Plans are in place. Resource recruitment is currently being finalised. |  | Completed documents are being checked/revised for deferral impact
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | In conjunction with regular internal legal briefings AAD is engaging with local industry and government bodies to maintain compliance with the new regulatory framework together with revising network technical requirements, documentation, etc. to ensure they are valid within the local jurisdiction. Current areas of focus include: - Contracts and other agreements with customers - Terms and conditions for the provision of data and other information to energy consumers - Legal implications of changes to internal procedures relating to faults and emergencies. |  | Possible delay in definition of the method to be used by the Victorian Government to implement the deferral of metering competition following the end of derogation. Uncertain framework for treatment of Vic AMI Meters (Type 4/5). |  |  | Ongoing activity - currently under review by organisational specialists. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | Monitor of changes from WP3 & B2B "As Built" procedures for impacts and changes |  | The Vic Govt. deferral decision has raised a number of uncertainties, including: 1: The nature of UE's role as MC role for new meters after 1 Dec (i.e. regulated service, or unregulated service with additional controls?) 2: Whether new meters after 1 Dec will be required to meet both Vic AMI and national specifications or just Vic AMI. 3: Whether existing and/or new meters will be classified as Type 5 or Type 4.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Review of legal documentation (contracts, forms, agreements, etc.) is continuing in line with the commencement of system and business changes. AAD has identified all documentation that requires review. |  | Possible delay in definition of the method to be used by the Victorian Government to implement the deferral of metering competition following the end of derogation. Uncertain framework for treatment of Vic AMI Meters (Type 4/5). | Note: In line with CitiPower/Powercor program delivery schedule. |  | Commencement will occur upon completion of activity 2.1. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In line with SAPN program delivery schedule |  | This work is dependent on finalisation of the deferral details and resolution of the uncertainties listed above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | As above. |  | Definition of B2B Procedures (e.g. New Connections) and finalisation of Market Roles required to complete establishment of commercial arrangements | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - amendments under consideration by each contract owner, updates will be made using existing procurement and contractual processes. Assessment of new agreements/contracts also ongoing. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress; no major changes |  | Plans are in place to address the commercial implications, and resourcing is now in place. Initial assessments have commenced.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | AAD has reviewed the requirements to register as an initial MC and is preparing the required materials for submission to AEMO. |  | Final Accreditation procedures not published and requirement for Type 4 accreditation not confirmed | Note: Following the state government decision to defer the introduction of metering competion in Victoria, CitiPower and Powercor will need to further assess our accrediation and registrations requirements. |  | Received notification from AEMO representatives that state the existing LNSP, MPB and MDP accreditations will continue. MC will be a registration process given our current RP role, and eHub Accreditation will be required. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress; no major changes |  | Accreditation requirements for UE are not clear, due to lack of clarity on whether VICAMI meters will have to be reclassified as Type 4 and whether new meters will be Type 5 or Type 4. Details of accreditation requirements (eg the subset of checklists that will applied to the Vic DBs with existing Type 5 accreditation) are not yet confirmed.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | AAD has reviewed the requirements to register as an initial MC and is preparing the required materials for submission to AEMO. |  | Final Accreditation procedures not published | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | An Accreditation team has formed, commencing accreditation planning in preparation for the release of the Accreditation and Registration plan by AEMO. |  |  | In line with SAPN program delivery schedule |  | Plans and funding are in place to cover UE accreditation, but requirements are still not fully clear. Time and effort will be required to ensure that internal processes & policies meet the accreditation criteria. This is expected to take several months, leading to accreditation occurring in late Q3/Q4 2017.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | AAD has begun assessing future requirements. Finalisation by AEMO of procedures and IT Systems will require that this position is reassessed. |  | Assessment of the impact of the deferral of Metering Competition in Victoria following the expiry of derogation in progress. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently analysing the human resources impact due to POC implementation. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | PoC removes current functions from existing businesses, this may result in reductions to staff in some areas and increases in others. Early recruitment activity is underway to supliment the LNSP PoC requirements. Detailed requirement plans to be developed. |  |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | An Organisational Impact Assessment is in progress to determine POC recruitment and HR requirements to fulfil operational functions. |  |  | In line with SAPN program delivery schedule |  | Not required until late 2017
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Identification of training requriements has begun, however, development of this training is yet to commence as it is dependent on other changes (processes, systems, etc.) that are currently underway. |  |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Training approach has commenced. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress |  | Development of training strategy is nearing completion.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Detailed reviews of AAD documentation has begun and resourcing for the changes has been completed. AAD is now in the process of carrying out the required reviews, consultation, workshops, etc. required to design and implement the required changes. Additional project team resources are being committed to address the increase in the number of documents required to be reviewed and updated. |  | Subject to finalisation of market procedures and implementation of Vic Gov't preferred option. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently documenting current and future state processes through development of detailed requirements. Progress on this is less than expected due to required rework, due to the nature of the final B2B Procedure Changes. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In line with SAPN program delivery schedule |  | Completed documents are being checked/revised for deferral impact
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | As above. |  | Subject to finalisation of market procedures and Vic Gov't approach. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently documenting current and future state processes through development of detailed requirements. Progress on this is less than expected due to required rework, due to the nature of the final B2B Procedure Changes. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In line with SAPN program delivery schedule |  | With the publication of SMP/B2B procedures on 6 Mar 2017, the remaining business process documents were completed and approved in mid March. Since then, the Victorian deferral decision has necessitated a full review of all process designs, with some being rendered irrelevant until 2021 or later, and many others requiring revisions. This work has impacted the critical path of solution design and build.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not yet begun. |  | Subject to finalisation of market procedures Industry Testing approach. Also requires assessment of procedures required to support market transition. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Test approach is ongoing. The Scope of August industry testing remains unclear. Confirming the scope of industry testing as soon as possible would enable businesses to effectively meet the industry testing date. |  |  | In line with SAPN program delivery schedule |  | Plans are in place to execute industry testing. However the current draft of B2B procedures includes the movement of currently enforceable details into a non-binding "guidance" category. The industry considers some of these details to be necessary for uniform, reliable end-to-end processing in the market. UE is concerned that varying interpretations and inconsistencies between industry participants will become apparent during industry testing and may threaten its progress.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Final requirements are yet to be released by AEMO, however, those requirements that are known have been scoped and are in design (we estimate that approximately 75% of requirements are known). | System impacts have been assessed in detail. The overall solution design is complete. Preparation of detailed designs has commenced. | Subject to assessment of variances in B2B Procedures published on March 6th and Vic Gov't approach to deferral of MC. Schedule for delivery of market system changes may be impacted by extent of changes required. | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | Ongoing activity - currently developing market systems detailed requirements and design documents. The magnitude of change in the final version of the B2B Procedures particularly with regard to the Notified Party and OWN transactions in the latest B2B Guidelines requires a revisit of requirements and reassessment of design. Timelines are becoming increasingly unrealistic due to these changes. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress |  | The Vic Govt. deferral decision has necessitated updates to numerous business process and functional designs that had previously been approved. This has impacted the critical path of solution design and build activities.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | The first round of system changes is entering test but will be subject review and possible change depending on further AEMO updates. | The implementation phase has begun. Detailed designs are being prepared. Final build estimates will be prepared as the designs complete. | Build process underway. Impact of changes required to support option selected by Vic' Gov't in progress. | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | The magnitude of change in the final version of the B2B Procedures particularly with regard to the NP and OWN's in the latest B2B Guidelines requires a revisit of requirements and reassessment of design. Development and build timelines are becoming increasingly compressed and unrealistic. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress; no major changes | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | The Vic Govt. deferral decision has necessitated updates to numerous business process and functional designs that had previously been approved. This has impacted the critical path of solution design and build activities.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Definition of internal Test Strategy has commenced. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Test approach is tracking to schedule. Testing timelines are becoming increasingly compressed and therefore 'At risk'. |  |  | In progress; no major changes | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | Limited system testing has commenced in areas unaffected by the deferral decision. Testing in remaining areas will commence later than planned due to redesign work.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Definition of Industry Test Strategy has commenced. Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  | The magnitude of change in the final version of the B2B Procedures particularly with regard to the NP and OWN's in the latest B2B Guidelines requires a revisit of requirements and reassessment of design. Testing timelines are becoming increasingly compressed and unrealistic. |  |  | In line with SAPN delivery schedule | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | Plans in place and resourcing agreed. Not yet due.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Final specifications of hub required. Role of non-functional testing as part of Industry Testing is required. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Test approach is tracking to schedule. |  |  | In line with SAPN delivery schedule | The plan is to be ready development of specifications with vendors is progressing well, the build schedule could be passed the industry testing dates, limiting industry testing participation | Plans in place and resourcing agreed. Not yet due.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Preliminary works has begun in this area with no decisions or plans being determined at the time of writing. |  | Industry approach has not been defined, therefore ability to meet schedule is unclear. | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Discussions are continuing with impacted groups and information gathering to inform transition plans. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In line with SAPN delivery schedule |  | Plans in place and resourcing agreed. Not yet due.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not yet begun. |  | Industry approach has not been defined, therefore ability to meet schedule is unclear. | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Transition planning has commenced. |  |  | In line with SAPN delivery schedule | The AEMO schedule is challenging to deliver in the current timeframe. | Plans in place and resourcing agreed. Not yet due.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Stage Gates built into Schedule based on AEMO identified key milestones. Implementation approach that develops solutions as best as practical now and change later when AEMO formally releases information. | [6 empty] | TBC - subject to Vic Govt OIC detail.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD is continuing final design and development activities based on information received to date. The degree to which re-work will be required due to changes in final AEMO documentation will be determined in the weeks immediately following release of said documentation. |  | Ongoing support for definition and refinement of market procedures |  |  | Currently working through the B2B Procedure changes to understand impacts on detailed requirements, design and build. B2B configuration changes occurring in parallel to mitigate timeframe constraints. |  | TBC - subject to Vic Govt OIC detail.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Continued participation in Vic' Gov't Stakeholders Forum Active participation in assessment of options for Meter Type treatment. |  |  |  |  | TBC - subject to Vic Govt OIC detail. |  |  | UE has attended Vic Govt briefings and the AEMO-hosted PCF meeting 29 Mar, providing feedback about the implications of and uncertainty created by the deferral. UE continues to urge prompt drafting of the final decision (via Order-in-Council) in order to clarify the remaining items that are likely to impact scope and effort. UE has already indicated that it will not be in a position to provide meters that meet both Vic AMI and national specifications by 1 Dec.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [12 empty] | TBC - subject to Vic Govt OIC detail. |  |  | As above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [12 empty] | TBC - subject to Vic Govt OIC detail. |  |  | Confirmation is required as to whether UE will be providing a regulated service/charge as MC for new meters, or will need to negotiate commercial charges in contracts with retailers.
2.4 |  | An assessment of the required accreditation and registration activities | [12 empty] | TBC - subject to Vic Govt OIC detail. |  |  | Continuing to seek written confirmation from AEMO on the proposed solution regarding Type 5 metrology (which was requested when UE provided its legal advice to AEMO on 15 Feb 2017). Also seeking confirmation from Victorian Government on policy decision in relation to Type 5 regulated or Type 4 unregulated meter classification.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | See above comment | [5 empty] | As above.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [12 empty] | TBC - subject to Vic Govt OIC detail.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [12 empty] | TBC - subject to Vic Govt OIC detail.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Requirements for additional testers and a business analyst have been identifed. Recruitment to occur in the next reporting period. |  |  |  |  | Additional experienced resources and subject matter experts have been sourced as a preventative mitigation strategy. |  | TBC - subject to Vic Govt OIC detail.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [10 empty] | Additional experienced resources and subject matter experts have been sourced to support ongoing business process activity and as a preventative mitigation strategy. |  | TBC - subject to Vic Govt OIC detail. |  |  | Every effort is being made to complete the revised process designs and quickly as possible and to continue work on solution design and build in areas that are not impacted by deferral.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | AAD is continuing detailed design and build phases and will perform rework if/when required as AEMO finalise and release the requirements documentation. |  | Requirement to provision additional resources to be assessed in order to deliver scope within timeframes. |  | See above comment | The Project is reviewing several mitigation strategies; significantly a phased implementation approach. |  | TBC - subject to Vic Govt OIC detail. |  |  | Every effort is being made to complete the revised process designs and quickly as possible and to continue work on solution design and build in areas that are not impacted by deferral.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | As above. | All available resources have been assigned to the design tasks. |  |  | See above comment | The Project is reviewing several mitigation strategies; significantly a phased implementation approach. |  | TBC - subject to Vic Govt OIC detail. |  |  | System development continues in areas not impacted by the deferral decision, and will commence in the remaining areas as soon as the revisisons to process and solution designs can be completed and approved.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Strategy to be validated when Industry testing Strategy has been defined.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Strategy to be validated when Industry testing Strategy has been fully defined. |  |  | The Project is reviewing several mitigation strategies; significantly a phased implementation approach.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Internal non-functional testing to be undertaken.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Support development of industry approach. |  |  |  |  | TBC - subject to Vic Govt OIC detail.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Support development of industry approach.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2017-04-03 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | [14 empty] | Active Stream is currently accredited and operating as an Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | Within schedule | Medium | Overall project delivery status at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Now that they final determination is complete, Business and Systems impact analysis is underway and gap analysis to be completed shortly. Amber status is maintained due to tight timeframes scope of change | [7 empty] | [Meter Provider: Status "Within Schedule"] [Meter Data Provider: Status "At risk"]
| Metering Dynamics | Within schedule | Medium | Project risk is due to the delayed release of B2B procedures and the complexity of multiple Rule and role changes in a very short timeframe. | [7 empty] | [Meter Provider: Risk "Low"] [Meter Data Provider: Risk "Medium"] - Risk due to the complexity of changes needed.
| Select Solutions | Not within schedule | Medium | The overall timeframes for these industry changes are tight. Select Solutions is working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs and procure a new system to form part of our accreditation for Type 4 small meters. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. IT system procurement is now well behind schedule. A significant numbers of resources is focussed on delivering this aspect of the project. Notwithstanding, meeting the milestone of industry testing is challenged. | [7 empty] | Risk relates to the current status of new system implementation
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Metering Dynamics | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Select Solutions | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 11% - 20% | 41% - 50% | 75% | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 11% - 20% | 31% - 40% | 75% | 61% - 70%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 61% - 70% | 1% - 10% | 11% - 20% | 75% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 61% - 70% | 1% - 10% | 1% - 10% | 75% | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 51% - 60% | 1% - 10% | 1% - 10% | 25% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | 11% - 20% | 41% - 50% | 50% | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 71% - 80% | Not started (0%) | 21% - 30% | 25% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 1% - 10% | 11% - 20% | 75% | 11% - 20%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 11% - 20% | 25% | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 50% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 61% - 70% | 21% - 30% | 31% - 40% | 75% | 51% - 60%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 21% - 30% | 1% - 10% | 21% - 30% | 50% | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 41% - 50% | 1% - 10% | 51% - 60% | 75% | 11% - 20%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 11% - 20% | Not started (0%) | 21% - 30% | 25% | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 1% - 10% | 1% - 10% | 0% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | At risk | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | At risk | Within schedule | At risk | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule | At risk | At risk | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Not within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Select Solutions has its strategy in place. A key variable is confirming delivery of the systems which will form the final part of our delivery plan.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Dependent on the finalisation of associated industry documentation. |  |  | Progressing through requirements for MC and ENM accreditation/registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Dependent on the finalisation of associated industry documentation.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [8 empty] | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role |  | Impacted by EQL merger and restructuring activity
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Resource assessment with respect to the MC role |  |  | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [8 empty] | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Delays experienced due to change in key system component. | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing | [8 empty] | At risk due to system procurement program slippage.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Delays experienced due to change in key system component. | A significant "blue print process" has been completed highlighting requirements. Still understanding B2B changes. Consequently system procurement is challenged.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Delays experienced due to change in key system component. | Build phase was scheduled to start in February 2017. Build is now not likely to commence until May.
5.3 |  | The internal testing of market systems for your business | [8 empty] | Due in mid 2017, dependant on progress of system build.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | Due in mid 2017, dependant on progress of system build.
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | Due in mid 2017, dependant on progress of system build.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [8 empty] | This action dependent upon finalisation of system procurement.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [8 empty] | This action dependent upon finalisation of system procurement.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Dedicated resources and strong business focus on the systems delivery project.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Working with Exec on key dates
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Update plan with required dates and allocate resources.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Update plan with required dates and allocate resources.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Update plan with required dates and allocate resources. | Dedicated resources and strong business focus on the systems delivery project.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
| 2017-04-03 |  |  | Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | [14 empty] | Active Stream is currently accredited and operating as an Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | Within schedule | Medium | Overall project delivery status at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Now that they final determination is complete, Business and Systems impact analysis is underway and gap analysis to be completed shortly. Amber status is maintained due to tight timeframes scope of change
| Metering Dynamics | Within schedule | Medium | Project risk is due to the delayed release of B2B procedures and the complexity of multiple Rule and role changes in a very short timeframe. | [7 empty] | New MC role integration into many market and business processes.
| Momentum Energy | Within schedule | Medium | [8 empty] | Detailed planning being developed
| Select Solutions | Not within schedule | Medium | The overall timeframes for these industry changes are tight. Select Solutions is working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs and procure a new system to form part of our accreditation for Type 4 small meters. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. IT system procurement is now well behind schedule. A significant numbers of resources is focussed on delivering this aspect of the project. Notwithstanding, meeting the milestone of industry testing is challenged. | [7 empty] | Risk relates to the current status of new system implementation
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Metering Dynamics | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Momentum Energy | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Select Solutions | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Momentum Energy | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 11% - 20% | 41% - 50% | 71% - 80% | 75% | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 11% - 20% | 31% - 40% | 31% - 40% | 75% | 61% - 70%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 61% - 70% | 1% - 10% | 11% - 20% | 31% - 40% | 75% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 61% - 70% | 1% - 10% | 1% - 10% | Not started (0%) | 75% | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 51% - 60% | 1% - 10% | 1% - 10% | Not started (0%) | 25% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | 11% - 20% | 41% - 50% | 21% - 30% | 50% | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 71% - 80% | Not started (0%) | 21% - 30% | 1% - 10% | 25% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 1% - 10% | 11% - 20% | 11% - 20% | 75% | 11% - 20%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | 25% | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 50% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 61% - 70% | 21% - 30% | 31% - 40% | 1% - 10% | 75% | 51% - 60%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 21% - 30% | 1% - 10% | 21% - 30% | Not started (0%) | 50% | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 41% - 50% | 1% - 10% | 51% - 60% | 31% - 40% | 75% | 11% - 20%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 11% - 20% | Not started (0%) | 21% - 30% | 1% - 10% | 25% | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 1% - 10% | 1% - 10% | Not started (0%) | 0% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Momentum Energy | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | Not within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Not within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Momentum Energy | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [9 empty] | Select Solutions has its strategy in place. A key variable is confirming delivery of the systems which will form the final part of our delivery plan.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Dependent on the finalisation of associated industry documentation. |  |  |  | Progressing through requirements for MC and ENM accreditation/registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Dependent on the finalisation of associated industry documentation.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [9 empty] | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role |  | Impacted by EQL merger and restructuring activity
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Resource assessment with respect to the MC role |  |  |  | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [9 empty] | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Delays experienced due to change in key system component. |  | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing | [9 empty] | At risk due to system procurement program slippage.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Delays experienced due to change in key system component. | System development is reliant on external vendor, delays in final market procedures will impact readiness activities | A significant "blue print process" has been completed highlighting requirements. Still understanding B2B changes. Consequently system procurement is challenged.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Delays experienced due to change in key system component. |  | Build phase was scheduled to start in February 2017. Build is now not likely to commence until May.
5.3 |  | The internal testing of market systems for your business | [9 empty] | Due in mid 2017, dependant on progress of system build.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [9 empty] | Due in mid 2017, dependant on progress of system build.
5.5 |  | The validation of performance of market systems during industry testing | [9 empty] | Due in mid 2017, dependant on progress of system build.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [9 empty] | This action dependent upon finalisation of system procurement.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [9 empty] | This action dependent upon finalisation of system procurement.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Momentum Energy | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [9 empty] | Dedicated resources and strong business focus on the systems delivery project.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Working with Exec on key dates
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Update plan with required dates and allocate resources.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Update plan with required dates and allocate resources.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Update plan with required dates and allocate resources. |  | Dedicated resources and strong business focus on the systems delivery project.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Embedded Networks
| 2017-04-03 |  |  | Embedded Networks Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Momentum Energy | Within schedule | Medium | [8 empty] | Detailed planning being developed
| Network Energy Services | Within schedule | Low | Preparing for Accreditation | [7 empty] | Getting prepared to implement all aspects
| Select Solutions | Not within schedule | Medium | The overall timeframes for these industry changes are tight. Select Solutions is working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs and procure a new system to form part of our accreditation for Type 4 small meters. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. IT system procurement is now well behind schedule. A significant numbers of resources is focussed on delivering this aspect of the project. Notwithstanding, meeting the milestone of industry testing is challenged. | [7 empty] | Risk relates to the current status of new system implementation
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Momentum Energy | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Network Energy Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Select Solutions | At risk | Low | At risk | Low | At risk | Low | At risk | Low | At risk | Low | At risk | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Momentum Energy | Network Energy Services | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 100% | 75%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 31% - 40% | 75% | 75%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 31% - 40% | 100% | 75%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Not started (0%) | 75% | 75%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Not started (0%) | 25% | 25%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 21% - 30% | 100% | 50%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 1% - 10% | 0% | 25%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 100% | 75%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | 100% | 25%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | 25% | 50%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 1% - 10% | 50% | 75%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Not started (0%) | 50% | 50%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 0% | 0%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 31% - 40% | 25% | 75%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 1% - 10% | 0% | 25%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | 0% | 0%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | 0% | 0%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | 0% | 0%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 50% | 0%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | 0% | 0%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Momentum Energy | Network Energy Services | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | At risk
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | At risk
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Not within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Not within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Not within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Not within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Not within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Not within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Not within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Momentum Energy | Network Energy Services | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Select Solutions has its strategy in place. A key variable is confirming delivery of the systems which will form the final part of our delivery plan.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities | [7 empty] | Progressing through requirements for MC and ENM accreditation/registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [7 empty] | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing | [7 empty] | At risk due to system procurement program slippage.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | System development is reliant on external vendor, delays in final market procedures will impact readiness activities |  | A significant "blue print process" has been completed highlighting requirements. Still understanding B2B changes. Consequently system procurement is challenged.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Build phase was scheduled to start in February 2017. Build is now not likely to commence until May.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Due in mid 2017, dependant on progress of system build.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Due in mid 2017, dependant on progress of system build.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Due in mid 2017, dependant on progress of system build.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | This action dependent upon finalisation of system procurement.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | This action dependent upon finalisation of system procurement.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Momentum Energy | Network Energy Services | Select Solutions | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Dedicated resources and strong business focus on the systems delivery project.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Dedicated resources and strong business focus on the systems delivery project.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Third Party
| 2017-04-03 |  |  | Third Party Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2017-04-03 | [5 empty] | Within schedule | Medium | The Vic Govt decision and the instruments have been announced. A formal notification including scope of OIC is expected Q1 2017. Industry Testing and the Transition and Cut-Over planning has commenced. AEMO notes that the collaborative approach requires industry participation and is undertaking to establish ‘focus groups’ to expedite the development of the detail required to effectively transition.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Medium
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | 11% - 20% | Within schedule | Workshops on 4 (Readiness) and 5 (Industry Testing) April to review second drafts of the Accreditation and Registration, and Industry Test Strategy and Plan. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies consistent with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 1% - 10% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 61% - 70% | Within schedule | Undertaking detailed planning for AEMO activities during the accreditation and registration phase based on final Qualification Procedure (ENM. MP, MDP) and MC Registration. Draft B2B e-hub accreditation process and application form released for industry feedback on 6 April. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule | Final determination for work package 2 published on 28 February 2017. AEMO held POC-PWG meeting on 6 March 2017 to discuss work package 3 contents and key dates |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updated B2B retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule | B2B Procedures Final Determination was published on 6 March 2017. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 11% - 20% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | 61% - 70% | Within schedule | First two sessions (out of 6) held on 28 November 2016. Next two held on 24 March 2017. Next session will be on qualification processes (to be scheduled). |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS (EN/MC) | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 81% - 99% | Within schedule | Initial build completed and released. Single change request underway per As Built Procedure |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 11% - 20% | Within schedule | Industry Testing planning is now underway |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B e-hub and MSATS | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 51% - 60% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | The internal testing of market systems for your business | [5 empty] | 1% - 10% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | Within schedule | Initial planning commenced, draft transition and cutover principles circulated for industry feedback on 6 April. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
[12 empty] | 41% - 50% | Retailer
[12 empty] | 51% - 60% | Distributor
[12 empty] | 61% - 70% | Meter Provider
[12 empty] | 71% - 80% | Meter Data Provider
[12 empty] | 81% - 99% | Metering Coordinator
[12 empty] | Completed (100%) | Embedded Network Manager
[12 empty] | N/A | Embedded Network Operator
Third Party B2B Participant
Within schedule
At risk
Not within schedule
N/A
[12 empty] | Completed | √
x
Low
Medium
High
N/A

## Harvey Balls 10% (hidden)
ü
Completed
| 100 | 90 | 80 | 70 |  | 60 | 50 | 40 | 30 | 20 | 10 | 0
| 0 | 10 | 20 | 30 |  | 40 | 50 | 60 | 70 | 80 | 90 | 100
WITHIN SCHEDULE | [12 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE
|  |  | ~0% |  | ~50%
|  |  | ~10% |  | ~60%
|  |  | ~20% |  | ~70%
|  |  | ~30% |  | ~80%
|  |  | ~40% |  | ~90%