## Market Readiness Report Page 1
42954
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2017-08-07
Overall Status |  | Commentary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | The overall project status remains amber - "at risk" of delivery by 1 December 2017 - primarily due to challenging program timeframes . Participants have highlighted challenging timeframes for system build and testing, registration and accreditation activities, and the number and complexity of commercial arrangements to be entered into. The overall project risk rating remains medium - with highlighted risk areas including a lack of alignment across industry processes including faults and emergency processes, jurisdictional safety regulations and treatment of embedded networks, and readiness of other participants. |  |  |  |  | High | Med | Low | #
[7 empty] | 3 | 7 | 4 | 0
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Network Manager |  | Third party e-hub
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place |  |  |  | #1
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with regulatory changes including jurisdictional regulations and requirements (e.g. safety) |  |  |  | #2 | [7 empty] | #2
2.3 |  | Operationally critical commercial contracts in place |  |  |  | #3 |  |  |  | #3 |  | #3
2.4 |  | Accreditation and registration activities completed |  |  |  | #4
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place |  |  |  | #5 | [5 empty] | #5 |  | #5
4.2 |  | Successfully validated critical business processes during industry testing |  |  |  | #7 | [5 empty] | #7 |  | #7
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing
5.2 |  | Successfully tested market systems capable of being moved into production |  |  |  | #6 |  | #6 |  |  |  | #6
5.3 |  | Performance of, and communication between, market systems validated during industry testing |  |  |  | #7 |  | #7 |  |  |  | #7
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place |  |  |  | #8 | [7 empty] | #8
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals)
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Network Manager |  | Third party e-hub
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdictional risk is a reflection of overall project risk. | [11 empty] | #9
NSW |  | Jurisdictional risk is a reflection of overall project risk.
QLD |  | Jurisdictional risk is a reflection of overall project risk.
SA |  | Jurisdictional risk is a reflection of overall project risk.
TAS |  | Jurisdictional risk is a reflection of overall project risk.
VIC |  | Jurisdictional risk is a reflection of overall project risk.

## HIDDEN 25% (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2017-08-07
Variances
Note # | Explanation of Variance |  |  | Mitigating Actions
1 | Variance reported by Participants: Development of detailed Implementation plans on schedule at risk as participants have identified a need to iterate plans for differing implementation approaches. |  |  | Retailers and DNSPs are meeting to align processes. The draft the Victorian government OIC has been released, participants are waiting for the final Victorian OIC.
2 | Variance reported by Participants: Updating internal policies on schedule at risk as participants are waiting for jurisdictional safety regulators to publish requirements and for clarity on the ENM role in Victoria and Queensland. Participants are also waiting for the final Vic government OIC . |  |  | Participants are engaging with jurisdictional bodies.
3 | Variance reported by Participants: Updating commercial arrangements on schedule is at risk due to volume and complexity of contracts that need to be entered into with industry parties. |  |  | Participants are increasing internal resources.
4 | Variance reported by Participants: Fulfilling registration and accreditation activities on schedule is at risk due compressed timeframes for all registration and accreditation activities. |  |  | Participants are increasing internal resources and commencing discussions with AEMO. [AEMO encourages early engagement with AEMO on registration and accreditation requirements - see POC Industry Accreditation & Registration Plan (http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Power-of-Choice/Readiness-Work-Stream)]
5 | Variance reported by Participants: Progress impacted by uncertainty in a number of areas including meter churn, faults and emergencies, jurisdictional requirements. Progress has been impacted by the Victorian Government deferral decision. |  |  | Participants are increasing internal resources, reviewing meter churn impacts under Package 3 and awaiting the final Victorian govt. OIC.
6 | Variance reported by Participants: System development at risk due to the complexity and number of changes required within tight timeframes for development and testing and delays from market system vendors. |  |  | Participants are increasing internal resources and working closely with market system vendors.
7 | Variance reported by Participants: Testing timelines are contingent on system design and build. |  |  | Participants are increasing internal resources and working closely with market system vendors.
8 | Variance reported by Participants: Transition and Cutover planning dependent on new connection processes, readiness of competitive MCs. Cutover plan for existing embedded networks yet to be developed. |  |  | Participants are engaging with the ITCFG. [http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Power-of-Choice/Readiness-Work-Stream/Industry-Transition-Cutover-Focus-Group]
9 | 2 out of the 7 intending Embedded Network Managers reporting have reported red ("not within schedule"). The main reason stated was that they were awaiting clarity on the different jurisdictional treatment of embedded networks. |  |  | Participants seeking feedback from jurisdictional bodies.
Notes
1. The count of open Risk and Issues is based on the POC Industry Risk Register as at 10/08/2017. 2. Explanation of Variance and Mitigating Actions above are based on Participants comments, AEMO's comments are included within square brackets [ ].
Key - Progress and Status | [5 empty] | Key - Risk Rating
Progress |  |  | Status
Harvey balls represent progress towards achieving the criterion |  |  | Colour indicates the readiness status |  |  | Rating
~0% |  | ~50% | Criterion is within agreed schedule and deliverable requirements |  |  | High
~10% |  | ~60% | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~20% |  | ~70% | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~30% |  | ~80% |  |  |  | See POC Industry Risk Register for open risks and issues:
~40% |  | ~90% | Criterion has been achieved |  | ü | POC Industry Register

## Retailer Reports
| 2017-08-07 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Retail | Within schedule | Medium | ActewAGL Retail is currently focused on System Integration Test, Industry test preparation and Operational readiness.A detailed project plan is in place and being tracked against in order to achieve compliance by the "go live" date.
| AGL Retailer Powerdirect | At risk | Medium | Industry testing for EN/MC completed sucessfully. Commercial activities are still in progress. Core B2B developments are complete and ready for bi-lateral testing. Bilateral testing scheduled to commence 17/7 with selected participants. AGL/Powerdirect on track for phase 3 cycle 1 industry testing. Project status remains yellow due to risks arising from commercial agreement completion. | [7 empty] | Risk rating remains at medium due to the number of parties involved, limited testing timeframes, significant commercial agreements that must be implemented and business transition and readiness activities.
| Alinta Energy | Within schedule | Medium | Over all the project is still progressing to plan. Metering Partner engagement progressing. Differences in processes between DBs is causing additional effort and uncertainty around interpretation at a more detailed level may require change or additional build and process development | [7 empty] | Operating in the Queensland market before the end of the year.
| Aurora Energy | At risk | Medium | Aurora Energy continues to manage a number of risks with regards to the implementation of the Power of Choice reforms by 1 December 2017. The most significant risk is the aggressive implementation timeline, reflected in Aurora Energy's 'at risk' project status. This risk is also impacting the ability of Aurora Energy's key vendors to meet POC timeframes. This includes, but is not limited to, a prospective Metering Coordinator, which will be required to establish advanced metering service capability in Tasmania where it currently does not exist.
| Energy Australia | At risk | Medium | We see siginficant risks associated with: the Vic Government decision to delay PoC; the lack of alignment on implementation approaches among participants; tighness of industry testing schedule; and the progress of industry coordinated activities, such as industry-wide readiness, BCP and Emergency Planning. | [7 empty] | The Program is making steady progress but has risks associated with the progress of industry coordinated activities, such as industry-wide readiness, BCP and Emergency Planning. | [5 empty] | Risks associated with industry coordinated activities still exist, such as BCP and Emergency Planning.
| Ergon Energy Queensland (retail) | At risk | Medium | The project risk rating remains at 'Medium' due to: - the volume of CIS system changes - the complexity, number and current progress of contracts that need to be negotiated with Initial MC / competitive MC - additional complexities and costs associated with delivering PoC metering changes in a regional setting - lack of changes to jurisdictional safety requirements which do not enable remote re-energisation. This will impact on the realisation of retailer and customer benefits. | [7 empty] | The project risk rating remains at 'medium' due to: - the volume of CIS system changes - the complexity, number and current progress of contracts that need to be negotiated with Initial MC / competitive MC - additional complexities and costs associated with delivering PoC metering changes in a regional setting - lack of changes to jurisdictional safety requirements which do not enable remote re-energisation. This will impact on the realisation of retailer and customer benefits.
| ERM Power Retail | At risk | Medium | ERM continues to report at risk for the PoC project, primarily due to remaining uncertainty in areas including 1) Meter Churn processes 2) Impact of these on commercial agreements 3) Impact of cancelling in-flight transfers that will force customers onto default rates and generate unnecessary work to re-instate these transfers.
| M2 Energy Pty Ltd | Within schedule | Medium | Project Scoping by Vendor is complete, and coding has commenced.. Vic related changes are a substantial risk. Business intention is to fully outsource MC role. Risk considered Medium as few vendors currently available for selection and none are accredited. M2 Energy is maintaining dialogue with potential vendors. | [7 empty] | Vic withdrawl from POC has introduced risk into System Scoping, and increased training and change management requirements.
| Macquarie Bank Limited | Within schedule | Low
| Mojo Power Pty Ltd | Within schedule | Medium | [8 empty] | Mojo in application process to be a retailer in Victoria
| Momentum Energy | At risk | Medium | Current risks are related to potential issues with development and implementation of system changes within given timeframes. There are dependencies on external vendors to develop required changes. There is also a lack of clarity from AEMO in terms of how the Victorian Distributors role will evolve related to MC. Also critical dependencies on external providers of MC role to meet their POC timeframes.
| Next Business Energy | Within schedule | Medium
| Origin Energy | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Program is currently reporting Amber however remains highly dependant on the readiness of other participants to be successful and 9 out of 11 Distributors reporting at risk. A high number of delivery risks continue to be monitored and mitigated for the duration of the project. Areas of concern include: Delivery • Uncertainty around the details of the VIC derogation extension may delay the delivery of the program (Origin has expressed concerns over proposed deviation from the overall B2B procedures); • Industry Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unclear and therefore impacting our planning and implementation of activities; participants updating own data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Awaiting delivery from AEMO of a completed Testing Plan inc. Test Data requirements for Market Trial Testing . If a Production Test Data cut is not agreed and published in the next few weeks, the Testing activities of the program will be impacted. Additionally, Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. • If safety regulations in each state (incl. ACT) does not allow MPs to energise a site, then New Connections timeframes will prolong by several days with risk of additional cost to customers. • Industry focus on compliance with the new obligations and lack of progress at jurisdictional level for supporting regulation changes, such as safety cases, right to entry etc. may result in poor customer experience. Cutover • Time frame for cutover is not practicable: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc.). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. This seems to suggest the aggregated risks may not be fully understood. Comms • Communications plan to affected parties (i.e. Electricians, Customers) is still not finalised; expectation that AEMO will lead on this activity. | [7 empty] | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. | [5 empty] | Areas of concern include: Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Program is currently reporting Amber however remains highly dependant on the readiness of other participants to be successful and 9 out of 11 Distributors reporting at risk. A high number of delivery risks continue to be monitored and mitigated for the duration of the project. Areas of concern include: Delivery • Uncertainty around the details of the VIC derogation extension may delay the delivery of the program (Origin has expressed concerns over proposed deviation from the overall B2B procedures); • Industry Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unclear and therefore impacting our planning and implementation of activities; participants updating own data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Awaiting delivery from AEMO of a completed Testing Plan inc. Test Data requirements for Market Trial Testing . If a Production Test Data cut is not agreed and published in the next few weeks, the Testing activities of the program will be impacted. Additionally, Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. • If QLD safety regulation does not allow MPs to energise a site, then New Connections timeframes will prolong by several days with risk of additional cost to customers. • Industry focus on compliance with the new obligations and lack of progress at jurisdictional level for supporting regulation changes, such as safety cases, right to entry etc. may result in poor customer experience. Cutover • Time frame for cutover is not practicable: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc.). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. This seems to suggest the aggregated risks may not be fully understood. Comms • Communications plan to affected parties (i.e. Electricians, Customers) is still not finalised; expectation that AEMO will lead on this activity.
| Pacific Hydro / Tango | At risk | High | The timing and outcomes of the following outstanding PoC activities have the potential to impact the build, test and implementation phases: 1. MSATS - As Built Consultation 2. B2B - Translation tool delivery and client side implementation & testing; potential new B2B schema changes prior to 1 Dec, and any Errata requiring process workarounds 3. Meter Churn Issues - recently raised and despite a paper being issued by AEMO, there are still concerns being raised. 4. Vic Government decision not to proceed with PoC. 5. Jurisdictional safety review of the remote Re-en/De-en process. 6. Internal Project delay for replacing current systems.
| People Energy Pty Ltd | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines.
| Pooled Energy | Within schedule | Medium | Project remains on track. Continuing to work through procedural and process changes. | [7 empty] | Project remains on track. Continuing to work through procedural and process changes.
| Powershop | At risk | Medium | [AEMO Note - Using 10 July 17 Report for Powershop]: System build requirements have been documented and scoped for effort and complexity. A delivery schedule and resourcing is being formulated to meet the 1 December 2017 timeframe. There may be a necessity for some non-volume transactions to be undertaken manually using MSATS for the initial period post implementation. Delays to releasing final schema specifications delayed activity significantly. | [7 empty] | System build requirements have been documented and scoped for effort and complexity. A delivery schedule and resourcing is being formulated to meet the 1 December 2017 timeframe. There may be a necessity for some non-volume transactions to be undertaken manually using MSATS for the initial period post implementation. Delays to releasing final schema specifications delayed activity significantly.
| Red Energy & Lumo Energy | At risk | High | Business and customer activity is very high at the targeted cut-over time. Inconsistent approaches across industry creates increased activity and raises risk (eg. new connections, meter churn, faults and emergencies, expected approaches to in-flight transactions). Victorian approach is understood but the detail and specifics is not yet finalised (Order in Council drafted but final version not released) Other jurisdictional consequential legislative amendments are not yet understood (and unseen) which is adding further risks to the overall project. Continued discussion at the industry forums regarding participants not being ready in various forms, is reducing our confidence in a positive customer experience in the move to metering competition. This is also highlighted in AEMO's assessment of the overall project having a high risk rating. The lack of clarity regarding what will be done to change the risk rating at the industry level is amplifying the risk. | [7 empty] | [Vic jurisdiction comment]: Lack of clarity regarding final OIC and nuances between approaches for each DNSP in Vic to standard processes has changed our Risk rating for Victoria. Draft OIC has initial MC contracts being available on 15 October rather than 1 September, further adding to uncertainty and risk
| Sumo Power | Within schedule | Medium | [8 empty] | Readiness of market participants
| Simply Energy | Within schedule | Low | Both the risks are somewhat resolved as "Faults and Emergencies" process has been clarified by most jurisdictions. Still waiting for the Final Order in Council, however it's a low risk now considering the draft has been provided with responses. | [13 empty] | Simply Energy has progressed as per it's internal plan of Power of Choice Program of Work and have prioritised B2M changes in order to commence testing for r35 schema, targetting Market Trial phase to commence industry testing.
| Stanwell Corporation Limited | Within schedule | Low | Project progressing as planned.
| WINConnect Pty LTD | At risk | Medium | Original policies and procedures have been developed on certain assumptions regarding the jursitictional differences in Vicotoria. The draft orders in council in Victoria indicates a separate approach to embedded networks to be adopted. Awaiting detail on that in order to finalise policies and procedures.
| Energy Locals | At risk | High | The comments below and those in our PWC survey response and interview demonstrate the limited resource we can put into POC as a startup. This is made especially difficult when the customer benefits of POC are not apparent (beyond what we already do for customers). There is huge uncertainty across the industry - will it take place on 1 Dec or won't it. That uncertainty in itself is expensive and is losing us time. We need AEMO to either light the fuse or put the matches away by the end of August to stand a chance of hitting 1 December.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Retail | Within schedule | Medium | Within schedule | Medium
| AGL Retailer Powerdirect | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Alinta Energy |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Aurora Energy | [8 empty] | At risk | Medium
| Energy Australia | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ergon Energy Queensland (retail) |  |  |  |  | At risk | Medium
| ERM Power Retail | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| M2 Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Macquarie Bank Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Mojo Power Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Momentum Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
Next Business Energy
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro / Tango |  |  | At risk | High | At risk | High | At risk | High |  |  | At risk | High
| People Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Pooled Energy |  |  | Within schedule | Medium
| Powershop |  |  | At risk | Medium | At risk | Medium |  |  |  |  | At risk | Medium
| Red Energy & Lumo Energy |  |  | At risk | High | At risk | High | At risk | High |  |  | At risk | High
| Sumo Power | [10 empty] | Within schedule | Medium
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Stanwell Corporation Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  |  |  | Within schedule | Low
| WINConnect Pty LTD |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Energy Locals |  |  | At risk | Medium | At risk | Medium
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | WINConnect Pty LTD | Energy Locals | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | 75% | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%) | 81% - 99% | Completed (100%) | 51% - 60% | 71% - 80% | 100% | 51% - 60% | 71% - 80% | 81% - 99% | Completed (100%) | Completed (100%) | 51% - 60%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 51% - 60% | 71% - 80% | 71% - 80% | 51% - 60% | 50% | 81% - 99% | 41% - 50% | 71% - 80% | 71% - 80% | 61% - 70% | 51% - 60% | 41% - 50% | 41% - 50% | N/A | 11% - 20% | 51% - 60% | 71% - 80% | 71% - 80% | 71% - 80% | 11% - 20%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 61% - 70% | Completed (100%) | 71% - 80% | 61% - 70% | 71% - 80% | 71% - 80% | 51% - 60% | 25% | 81% - 99% | 71% - 80% | 61% - 70% | 31% - 40% | 61% - 70% | 51% - 60% | 31% - 40% | 41% - 50% | 75% | 81% - 99% | 21% - 30% | 31% - 40% | 71% - 80% | 41% - 50% | 1% - 10%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 31% - 40% | 61% - 70% | 51% - 60% | 31% - 40% | 51% - 60% | 61% - 70% | 21% - 30% | 0% | 81% - 99% | 61% - 70% | 31% - 40% | 1% - 10% | 41% - 50% | 31% - 40% | 11% - 20% | 21% - 30% | N/A | Not started (0%) | Not started (0%) | 11% - 20% | 21% - 30% | 11% - 20% | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 21% - 30% | 51% - 60% | 21% - 30% | 31% - 40% | 51% - 60% | 41% - 50% | 31% - 40% | 0% | Not started (0%) | 61% - 70% | 31% - 40% | 31% - 40% | 21% - 30% | 21% - 30% | 11% - 20% | 11% - 20% | 25% | N/A | 11% - 20% | 41% - 50% | 11% - 20% | 41% - 50% | 31% - 40%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 41% - 50% | Completed (100%) | N/A | 31% - 40% | 51% - 60% | 61% - 70% | 61% - 70% | 25% | 61% - 70% | 91% - 99% | 61% - 70% | 41% - 50% | 61% - 70% | 51% - 60% | 41% - 50% | 61% - 70% | 25% | N/A | Not started (0%) | Completed (100%) | Completed (100%) | 71% - 80% | 51% - 60%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 11% - 20% | 51% - 60% | N/A | 1% - 10% | 1% - 10% | Not started (0%) | 11% - 20% | N/A | Not started (0%) | 11% - 20% | 51% - 60% | 1% - 10% | Not started (0%) | 1% - 10% | 1% - 10% | 11% - 20% | 0% | N/A | Not started (0%) | N/A | 11% - 20% | 71% - 80% | 51% - 60%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 81% - 99% | 11% - 20% | 51% - 60% | 61% - 70% | 71% - 80% | 71% - 80% | 51% - 60% | 50% | N/A | Completed (100%) | 61% - 70% | 61% - 70% | 51% - 60% | 51% - 60% | 21% - 30% | 61% - 70% | 0% | N/A | Completed (100%) | 41% - 50% | 41% - 50% | 71% - 80% | 31% - 40%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 1% - 10% | 1% - 10% | 41% - 50% | 51% - 60% | 41% - 50% | 21% - 30% | 51% - 60% | N/A | N/A | Completed (100%) | 61% - 70% | 51% - 60% | 31% - 40% | 51% - 60% | Not started (0%) | 61% - 70% | N/A | N/A | N/A | Not started (0%) | 41% - 50% | Completed (100%) | N/A
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 11% - 20% | 21% - 30% | 41% - 50% | 41% - 50% | 25% | Not started (0%) | 31% - 40% | 21% - 30% | 21% - 30% | 1% - 10% | Not started (0%) | Not started (0%) | 11% - 20% | 0% | N/A | Not started (0%) | Not started (0%) | Not started (0%) | 71% - 80% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 71% - 80% | 51% - 60% | 61% - 70% | 71% - 80% | 71% - 80% | 41% - 50% | 25% | 81% - 99% | 61% - 70% | 41% - 50% | 51% - 60% | 71% - 80% | 51% - 60% | 31% - 40% | 51% - 60% | 75% | 41% - 50% | 51% - 60% | 61% - 70% | 61% - 70% | 41% - 50% | 21% - 30%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed (100%) | 51% - 60% | 31% - 40% | 31% - 40% | 71% - 80% | 61% - 70% | 41% - 50% | 0% | 71% - 80% | 21% - 30% | 21% - 30% | 21% - 30% | 41% - 50% | 1% - 10% | 11% - 20% | 21% - 30% | 25% | 21% - 30% | 31% - 40% | 31% - 40% | 1% - 10% | 51% - 60% | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 21% - 30% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 11% - 20% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) |  | Not started (0%) | Not started (0%) | Completed (100%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | 81% - 90% | 81% - 90% | 61% - 70% | 81% - 99% | 81% - 99% | 51% - 60% | 50% | 71% - 80% | 31% - 40% | 61% - 70% | Completed (100%) | 71% - 80% | 61% - 70% | 51% - 60% | 71% - 80% | 75% | 51% - 60% | 71% - 80% | 61% - 70% | 81% - 99% | 61% - 70% | 11% - 20%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 31% - 40% | 71% - 80% | 81% - 90% | 31% - 40% | 51% - 60% | 81% - 99% | 41% - 50% | 50% | 41% - 50% | 31% - 40% | 31% - 40% | 61% - 70% | 51% - 60% | 31% - 40% | 31% - 40% | 61% - 70% | 0% | 21% - 30% | 61% - 70% | 11% - 20% | 51% - 60% | 61% - 70% | 11% - 20%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 31% - 40% | 71% - 80% | 1% - 10% | 31% - 40% | 11% - 20% | 21% - 30% | 21% - 30% | 0% | 41% - 50% | Not started (0%) | 51% - 60% | Not started (0%) | 21% - 30% | Not started (0%) | Not started (0%) | 51% - 60% | 0% | 1% - 10% | 51% - 60% | 11% - 20% | 21% - 30% | Not started (0%) | 1% - 10%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 11% - 20% | 21% - 30% | Not started (0%) | 1% - 10% | 11% - 20% | 11% - 20% | Not started (0%) | 0% | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | 11% - 20% | 0% | Not started (0%) | 11% - 20% | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) |  | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | 11% - 20% | 0% | Not started (0%) | 11% - 20% | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 11% - 20% | 31% - 40% | 11% - 20% | 21% - 30% | 31% - 40% | 1% - 10% | 11% - 20% | 25% | 71% - 80% | Not started (0%) | 21% - 30% | Not started (0%) | 21% - 30% | 11% - 20% | 1% - 10% | 41% - 50% | 0% | 11% - 20% | 51% - 60% | 11% - 20% | Not started (0%) | Not started (0%) | 1% - 10%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 21% - 30%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | WINConnect Pty LTD | Energy Locals | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Completed | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed | At risk | Completed | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | At risk
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed | Completed | Completed | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Completed | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Not within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | At risk | Within schedule | At risk | At risk | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | At risk | Not within schedule | Within schedule | At risk | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Not within schedule | At risk | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Completed | N/A | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | N/A | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | At risk | At risk | At risk | At risk | Within schedule | Within schedule | At risk | N/A | Within schedule | N/A | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | N/A | N/A | N/A | Within schedule | Within schedule | Within schedule | At risk
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Within schedule | At risk | At risk | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Not within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | At risk | Not within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed | Within schedule | At risk | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Not within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule |  | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Not within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Not within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Not within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | At risk | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | N/A | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | WINConnect Pty LTD | Energy Locals | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | High level impact assessment has been conducted. |  |  | A high-level assessment of necessary business operational process and systems changes is near 100% completion noting the detailed assessment supporting the high-level view is still incomplete. | Due to differing implementation approaches of participants, Reassessment of customer impacts is required at a DNSP level. | [7 empty] | Impact Assessment completed, but will need to be iterated pending consultation outcomes and changes. Procedure and meter type implication due to VIC derogation extension are not yet clear. Faults and Emergencies process not yet finalised | [5 empty] | Less impact due to derogation; will not be undertaking a MC role and will not require rapid transctions from day 1 | 95% complete |  |  | As a startup we need to terminate some of our staff to pay for POC. We're unwilling to do this until AEMO commits 100% to the December go live date.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Program established, Detailed plan in place and being tracked against. |  |  | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging. Additional changes to enable all other core operations post 1 December 2017 are being assessed. The aggressive timelines for systems build and testing, combined with contracting and establishment of an MC and the required implementation and testing combined systems is the basis of the 'at risk' status. | Re-development of DB specific implementation plans is required, due to variations in participant implementationa approaches. | As a retailer, EEQ is heavily reliant on contracted parties being ready from go-live date. | [7 empty] | At risk due to process and system delays. |  |  |  |  | Depends on the market cutover approach and handling inflight transactions |  |  |  | As above
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [8 empty] | A detailed assessment of the revised legal and regulatory is significantly developed. In its current form the detailed assessment has provided the basis of Aurora Energy preparedness to date. The assessment continues to be informed by on-going AEMO market procedure consultation although remaining uncertainty over rule and procedure operations ensures this is still considered 'at risk'. |  | Queensland jurisdictional safety requirements are yet to be addressed. |  | scheduled and commenced. |  |  | Retailer timeframes to assess and agree to the Ts&Cs of the LNSPs are extremely tight and require the same pool of resources needed elsewhere in the program | Awaiting further instruction from some market participants on specific requirements. | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines | Jurisdictional requirements for safety in relation to remote re-en/de-en in non-Vic jurisdictions unconfirmed. |  |  |  | Await final Victoria Order in Council and jurisdictional amendments to safety regulations and assessment of any potential changes required |  | Awaiting jurisdictional safety regulators to publish requirements |  |  | As above
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | Continuing | Aurora Energy has considered the wider and indirect regulatory implications of metering competition on business-as-usual activities (particularly given the existing regulatory framework was developed in the context of type 6 metering). |  | Jurisdictional changes to Meterology Part A have not yet been updated. |  | not yet scheduled. |  |  | Severe challenges with the level of effort required to translate system and process changes into business operational readiness |  | Policy changes/decisions still being derived | Vic Government decision on PoC and timing of regulatory changes to reflect the decision not to proceed with PoC. Potential variance of process by QLD DNSP not accepting Service Orders from an MC. | [7 empty] | Subject to confirmation on ENM roll in Victoria. | Requires items above to be completed first
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Awaiting executable MC contracts to be issued by the relevant parties. | Contract dlivery is now behind revised schedule. | . Commenced . RFP Issued . Draft Services Agreement available, RFP process progressing. . Review of (MM&C&I)Customer contracts, T&Cs continuing | Activity has commenced for customers and vendors as part of POC implementation. The major challenge is to develop and execute contractual arrangements with a Metering Coordinator, which will have to establish metering service capability in Tasmania where it currently does not exist. | Scheduled activties at risk due to complexities of numerous participants | Substantial progress has been made as additional resources have been allocated. MC contract is scheduled to be complete by the end of August. | The number of contracts and counter-parties put this item at risk. | not yet scheduled. |  |  | Dependency on partnering with registered MC(s) |  | Overall strategy has been developed and endorsed. Generic Meter provider contract drafted for new providers and contracts in play for current providers. | Requirements/services for various Service Providers yet to be finalised. Discussions with various Service Providers have commenced. Uncertainty as to which MCs will be ready for 1 Dec a major concern. |  |  | Awaiting for MC's to be accredited. Discussions have commenced | Internal management of this item |  | Final determination of Meter Churn (Package 3) procedures might require some amendments to the relavant commercial contracts and operational procedures, especially with contestable metering providers. |  |  | We've signed one contract with a MP/MDP and that provider has also added the MC role at our request. 3 others are at contract stage.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Preparing for Industry test. |  | . Contractual arrangements to support Accreditation requirements through a nominated MC . Certification scheduled as part of Industry Testing | Aurora Energy will be required to receive accreditation for using the B2B e-hub. The newly published B2B E-Hub Accreditation and Revocation process is currently being considered. The timeline and uncertainty for accreditation and registration activities of other participants (specifically, the Metering Coordinator role) also impacts on Aurora Energy's planning. Dialogue with the jurisdictional safety regulator has commenced. |  |  |  | unclear testing registration requirements and impacts at this time. Ehub application is delayed. |  |  | Volume of information required following initial assessment is higher than expected |  | Underway for new Market Roles | Despite 5.2, B2B accreditation is still required and for that purpose we still believe we will be in a position to complete in the required timeframe. |  |  |  | Internal management of this item |  |  |  |  | Confirmed that accreditation is only require for MC, MP, MDP and no other retailer requirements. Application has been submitted to AEMO
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Accrediatation materials review and application submitted. |  | . Certification scheduled as part of Industry Testing | Fulfilment of the accreditation obligations is now being considered following AEMO publishing final version of the 'B2B Accreditation and Revocation Process'. |  | Minimal requirements for a retailer. |  |  |  |  | Volume of information required following initial assessment is higher than expected |  | Planning and preparation in progress | Per 5.2 and the limited timeframes for internal testing and commencement of Market Trial. |  |  |  | Internal management of this item |  |  |  |  | As above
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Detailed assessment completed |  | Underway | This has commenced and will be finalised following with the detailed assessment of operational and systems changes. |  | FTE Impact anaylsis complete TST analysis ongoing |  | No resource changes at this time |  |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. Forecasted workload planning completed for key business areas and socialised to inform recruitment decisions. | Internal replanning drafted with resourcing requirements identified. |  |  |  | Internal management of this item | No additional staff operational required |  |  |  | Assessments to date show no additional ongoing resource, which is good because we'd need to busk outside Richmond station to pay for them.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Underway | The recruitment of specialist human resources to cater for the rule change is progressing as the need to fill key project roles arises. A key challenge is the availability of internal business subject matter experts to assist in change management. |  | Recruitment for a number of roles is currently underway. | [6 empty] | Policy changes/decisions identified. Recruitment for long lead time positions commenced. |  |  |  |  | Internal management of this item |  |  |  |  | N/A depending on 3.1
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [8 empty] | Training requirements are currently being assessed as part of the business process, change management and system planning. |  | Training Needs Analysis has been finalised. Training staff engaged and developing programs. Staff training scheduled for Oct-Nov |  | Waiting on testing environment to be released, staff have been briefed and aware of industry change |  |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing |  | Training requirements and resourcing determined and magnitude of change is understood, change planning started. Learning curriculum being finalised and training material development commenced. Confirmation of some market transactions and treatments still pending which may impact training timelines given constraints in place. | At risk due to 5.2/4.1. |  |  |  | Internal management of this item |  |  |  |  | Depends on section 1
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Awaiting advice on meter bridging in the case of meter faults. |  | Management of procedural differences adding to effort | All impacted service order, B2B & B2M and business processes have been identified. Assessment of current and future processes is underway to enable gap analysis and identify process and system changes. Possible future changes puts the delivery scope and timeline at risk. | Detailed process validation with individual Participants resulted in the requirement to redesign some solutions, with likely manual effort and customer impacts. | There remains a small number of outstanding business processes between market participants to be agreed. Negotiations continue to agree these processes to align systems and business processes. | The scope of change puts this item at risk. | commenced and in schedule |  |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension not yet clear. Faults and Emergencies process not yet finalised; | Re-assessing business process impacts still in progress due to change in approach for 1 Dec. |  |  |  |  | Back office service provider has assessed PoC impacts on BAU activity |  |  | Subject to confirmation of jursitictional differences. | Undertaken high level assessment. Full assessment required of existing and future business processes, plan and actions to close and resource allocation and responsibility.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Business Processes completed and Process Owners allocated. Validation continues to be done with MC's (depending on their maturity). Now under formal change control |  | Management of procedural differences adding to effort | Future business processes are currently being developed using the details from Work Package 1 and 2, as well as the B2B procedures. The timeline for implementation and on-going procedural uncertainty is the basis for Aurora Energy reporting 'at risk'. | As above | On track for completing documentation of work instructions for end of September | The scope of change puts this item at risk. |  |  |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension not yet clear. Faults and Emergencies process not yet finalised; Engagement with networks is planned to confirm smooth transition. | No longer within schedule due to system delay per 5.2 and 4.1. Potential process variances between jurisdictions/distributors and other service providers. | [8 empty] | Need to do 4.1 as pre requirement.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Scheduled to commence in next period. | Via phase 1 and bilateral testing with Jemena and Active Stream |  | Activity has not yet started. |  |  |  | not yet scheduled. |  |  | Delays from third parties are impacting our ability to participate in industry testing |  | Test planning commenced, detail on industry testing as yet unclear | At risk due to 5.2/4.1. | [8 empty] | Can't do that until accreditation received and system being ready for test.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | DB interpretation of procedures requires additional build. | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging systems. The aggressive timeframe impacts on the ability of Aurora Energy's key vendors (including, but not limited to, prospective Metering Coordinators) to deliver the required system changes. |  | System designs complete. System build complete. SIT testing underway. UAT to commence early September. |  | Vendor at 47% completion of overall project plan |  |  |  |  | Mass Market Design activities complete and Large Customers design in progress. Change requests being assessed and planned. | In addition to 4.1, identification of any interim system changes required to be compliant on 1 Dec also in progress. | [5 empty] | Business requirements Complete |  |  | System delivery being managed by Agility. Back up plan to use Translation tool has now been changed so that we will pursue the full solution in our billing system (Engage from Agility). Development is in progress by Agility for release in September.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Drop 2 of 6 in test. Drop 3 is tracking to plan. |  |  | Aurora Energy has engaged its key market system vendors. System build has commenced for essential market connectivity and system functionality for 1 December 2017. Further priority system functionality is in design phase. Systems changes will still be impacted by the any further changes to the B2B/B2M environment as part of Work Package 3. | Changes required to align with revised LNSP processes has delayed build & test | Build now complete Serveral Change Request under analysis |  | vendor at 15% of retail sys build plan |  |  | System development is reliant on external vendors, any delays in final market procedures will impact readiness activities. | Being run by external vendor | Build progressing on track | Reverted from 'Not within Schedule' given we are no longer looking at implementing PoC with new system for 1 Dec. Dependent on completed development and implementation of B2B Translation Tool, and any changes per 5.1. Uncertainty regarding B2B Errata process and timelines for potential schema updates. | [8 empty] | As per 5.1
5.3 |  | The internal testing of market systems for your business | [5 empty] | Cycle 2 of SIT in progress |  | Test planning and test case development almost complete. Planned to undertake in parallel with Market testing | Aurora Energy is implementing its test strategy and has commenced the initial phases of system testing. | As above | Assembly Testing Complete, SIT has commenced |  |  |  |  | The late delivery of our B2B code by the external provider doesn't allow enough time for internal testing |  | Testing is progressing on track. Risks remain around open changes eg Vic derogation. | As per 5.2 | [5 empty] | Commenced for B2M and B2B |  |  | As per 5.1
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Limited testing has been conducted in Pre-prod to date, will resume when pre-prod access is re-established. |  | commences 21st Aug. | Aurora Energy was unable to participate in AEMO's first round of testing due to no other participants being available. eHub connectivity will be tested in Phase 2 of AEMO's market interface testing. While Aurora Energy is currently on schedule to meet the timing of AEMO's market system testing opportunities, it is reliant on both key system vendors and other participants to perform testing and therefore continues to consider this to be 'at risk'. | As above | Smoke test' completed testing conectivity to MSTATs Pre-Prod Industry test Plan approved | [6 empty] | Small cohort available for cycle 1 industry testing due to industry participant readiness. A slow start is therefore expected. | As per 5.2 Agreement with test partners (particularly MCs) yet to be confirmed. | [5 empty] | Scheduled to commence as planned however some dependency on contestable metering providers (pending confirmation) |  |  | As per 5.1
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | Aurora Energy is planning to separately initiate performance testing, as distinct from market interface testing, scheduled for October 2017. Aurora Energy is reliant on key system vendors to perform performance testing and therefore continues to consider this to be 'at risk' | [8 empty] | Batch performance and sizing in progress | As per 5.2 |  |  |  | Target Rounds 2 and 3 of industry testing. |  | Scheduled to commence late August 2017 |  |  | As per 5.1
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Detailed planning in progress. |  |  | A Transition Plan will be completed once AEMO packages and commercial agreements with Metering Coordinator(s) are finalised. Aurora Energy has started discussions with TasNetworks regarding transition and cutover planning. |  | Cut-over oprtions paper being drafted. Deployment Lead has been recruited |  |  |  |  | Transition plans are dependent on timely delivery of earlier program stages |  | Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, cyclone, etc.). Transition & Cutover planning will take this into account. | Internal cutover planning commenced, based on output from ITCFG. |  |  |  | Transition and cut over working group outcomes are not yet finalised, as such, this is impacting the preparation of our business processes. Of particular concern are: - New connections process - initial MC contracts are not yet understood - readiness of competitive MCs | Depends on the market cutover approach and handling inflight transactions |  |  |  | Will start when 5.4 & 5.5 are complete
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [8 empty] | Aurora Energy has started discussions with TasNetworks regarding transition and cutover planning. | [8 empty] | Transition planning and scheduling cannot be accurately determined until Design & Build is completed. Bulk Data conversion for Meter Standing Data (MC/ENM role, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our Build / Test activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; | [9 empty] | Will start when 5.4 & 5.5 are complete
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | WINConnect Pty LTD | Energy Locals | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms, within the context of the timeframe and procedural uncertainty. | Ongoing meetings with DNSP's to align processes. | [7 empty] | Progressing with working assumptions. | [9 empty] | Request commitment from AEMO to 1 Dec date by 31 Aug. If not received, take a decision on 1 Sep over participation or otherwise.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Aurora Energy has implemented a program of work to effectively and efficiently work towards market compliance. | Implementing manual processes for December 1st which will be progressively implemented over the following quarter. | EEQ continues to work with delivery partners in go-live preparations | [16 empty] | As above
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Meeting with ACT Government conducted- no expected barriers at this point. NSW Govt is proving to be a challenge to engage. |  |  | Aurora Energy has implemented a program of work to interpret and implement the POC reforms that factors in the challenging timeframe and procedural uncertainty. Aurora Energy continues to engage with AEMO and other market participants to inform its assessment. |  | Ongoing discussions with the Department of Energy and Water Supply and participation in development of a national framework for remote re-energisation. At this stage it is unlikely that remote re-energisation will be available to retailers on 1 December 2017. | [7 empty] | Monitor jurisdictional saftey discussion. | [5 empty] | Internal assessments have commenced |  |  | As above
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Internal documents related to Cth legislation are listed by branch and business unit. Dates for update and review have been set. Codes of Practice being written for key areas. |  |  | Aurora Energy continues to liaise with the Tasmania Government and WorkSafe Tasmanian to identify jurisdictional requirements that require amendment to facilitate metering competition. | Actively participating in industry working group for developing industry re-en/de-en guideline. | AEMO and Department of Energy and Water Supply are currently addressing jurisdictional changes to Metrology Part A. | [7 empty] | Closely review and monitor Vic Government's progress of the OIC. Discussions with DBs ongoing. | [7 empty] | Clear guidance required from juiristictional bodies of the roll of the ENM in Victoria and QLD.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [6 empty] | Escalated via steering committee. Full time legal and additional business resources added |  | Aurora Energy is part way through a procurement process for securing a Metering Coordinator for small customers. |  | Ensure contingencies are in place to enable interim arrangements if required for commercial arrangements. Additional resources have been allocated. Initial MC Contract scheduled to be available in mid-August. | [6 empty] | Origin has onboarded additional Business and Technology resources | Engaging with MCs to obtain details about their planned offerings and draft terms and agreements. | [5 empty] | Mitigation plans have been put in place to expedite contractual obligations, and in case package 3 introduces any risks, manual workarounds have been workshopped considereing all possible scenarios. |  |  | Get list of accredited MCs from AEMO. Get crystal clear clarity from AEMO on role of MC (it currently differs according to who we talk to in the industry).
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy has submitted its accreditation application and is proceeding on the assumption that accreditation will be received. | [9 empty] | Dependent on AEMO delivery of B2B Translation Tool, and our implementation and testing. Draft B2B Accreditation Guide under review. | [8 empty] | Chase AEMO re our application
2.5 |  | The fulfilment of accreditation and registration obligations | [17 empty] | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | Aurora Energy has established the core group of its Testing team and will continue to expand its testing resources over the coming months.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [10 empty] | Currently recruiting more resources for the development and delivery of training | [7 empty] | Reallocation of resources to cover this activity.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | Application of Resources | Aurora Energy continues to invest considerable effort in participating in AEMO procedural consultation. Aurora Energy is proceeding on the basis of the currently available information and must continue to manage the risk of final procedures changing. | Ongoing DNSP and MC meetings. | [8 empty] | Reallocation of resources to cover this activity. | [7 empty] | Clear guidance required from juiristictional bodies of the roll of the ENM in Victoria and QLD.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Application of Resources |  | Additional DNSP specific processes under development | [8 empty] | Discussions with other participants ongoing.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [8 empty] | Aurora Energy is in the process of gathering detailed business and system requirements and engaging with key vendors. | [9 empty] | Assisting AEMO with testing of B2B Translation Tool. Reviewed draft Vic OIC. | [8 empty] | Use Translation tool approved for build by AEMO. Supplement with documentation for manual use of MSATS to perform market transactions and service orders. Partner with a another Agility supported T2 / T3 retailer to leverage work.
5.2 |  | The development and build of appropriate market systems for your business | [8 empty] | Aurora Energy continues to proactively manage its key market system vendors and has now taken delivery of key system code releases. | [9 empty] | Closely monitoring IEC/B2BWG/ASWG discussions and potential for additional B2B Errata/schema changes prior to 1 Dec.
5.3 |  | The internal testing of market systems for your business | [18 empty] | As per 5.2
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [18 empty] | As per 5.2
5.5 |  | The validation of performance of market systems during industry testing | [18 empty] | As per 5.2
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [8 empty] | Aurora Energy transition and cutover preparations are being supported by its attendance at AEMO cutover and planning workshops. | [8 empty] | Transition & Cutover planning will take this into account.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Retailer Participation
References:
[7 empty] | AEMO | http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Participant-information/Current-participants/Current-registration-and-exemption-lists
[7 empty] | AER | https://www.aer.gov.au/retail-markets/authorisations/public-register-of-authorised-retailers-and-authorisation-applications
[7 empty] | ESC | http://www.esc.vic.gov.au/project/energy/2075-licensing/
Retailer | On Aug 2017 Report? | On Jul 2017 Report? | On Jun 2017 Report? | On May 2017 Report? | On April 2017 Report? | On March 2017 Report?
1st Energy Pty Ltd | No | No | No | No | No | No
ActewAGL Retail | Yes | Yes | Yes | Yes | Yes | Yes
AGL | Yes | Yes | Yes | Yes | Yes | Yes
Alinta Energy | Yes | Yes | Yes | Yes | Yes | Yes
Aurora Energy | Yes | Yes | Yes | Yes | Yes | Yes
Blue NRG Pty Ltd | No | No | No | No | No | No
Click Energy Pty Ltd | No | No | No | No | No | No
Covau Pty Limited | No | No | No | No | No | No
COzero Energy Retail Pty Ltd | No | No | No | No | No | No
Diamond Energy Pty Ltd | No | No | No | No | No | No
Energy Locals Pty Ltd | Yes | No | No | No | No | No
EnergyAustralia | Yes | Yes | Yes | Yes | Yes | Yes
Enova Energy Pty Ltd | No | No | No | No | No | No
Ergon Energy Queensland (retail) | Yes | Yes | Yes | Yes | Yes (using March report) | Yes
ERM Power Retail Pty Ltd | Yes | Yes | Yes | Yes | No | No
Globird Energy Pty Ltd | No | No | No | No | No | No
Lumo Energy (reporting with Red Energy) | Yes | Yes | Yes | Yes | Yes | Yes
M2 Energy Pty Ltd | Yes | Yes | Yes (using May report) | Yes | Yes | Yes
Macquarie Bank Limited | Yes | Yes | Yes | No | No | No
Mojo Power Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes
Momentum Energy | Yes | Yes | Yes | Yes | Yes | Yes
Next Business Energy Pty Ltd | Yes | Yes | No | No | No | No
Online Power and Gas Pty Ltd | No | No | No | No | No | No
Onsite Energy Solutions Pty Ltd | No | No | No | No | No | No
Origin Energy | Yes | Yes | Yes | Yes | Yes | Yes
Pacific Hydro / Tango | Yes | Yes | Yes | Yes | Yes | Yes
People Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes
Pooled Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes | No
Powerdirect Pty Ltd (reporting with AGL) | Yes | Yes | Yes | No | No | No
Powershop Australia Pty Limited | Yes (using July report) | Yes | No | Yes (using April report) | Yes | No
Progressive Green Pty Ltd | No | No | No | No | No | No
Qenergy Limited | No | No | No | No | No | No
Red Energy | Yes | Yes | Yes | Yes | Yes | Yes
Sanctuary Energy Pty Ltd | No | No | No | No | No | No
Simply Energy | Yes | Yes | Yes | Yes | Yes | Yes
SparQ Pty Ltd (Sumo Power) | Yes | Yes (using June report) | Yes | No | No | No
Stanwell Corporation Limited (Stanwell Energy) | Yes | Yes | Yes | Yes | Yes | No
WINenergy Pty Ltd (WINenergy) | Yes | Yes | No | No | No | No

## Distributor Reports
| 2017-08-07 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule | Medium | For this reporting period the project remains heavily focussed on development and testing activities. AAD has commenced the test cycle 3 of 6. AAD is currently conducting workshops with retailers to establish detailed processes. AAD is now shifting its attention from procedural documents and commencing a detailed revision of all online materials and other supporting documentation. Total project progress is estimated at 49%. | [7 empty] | [Meter Provider]: Risk = Medium, AAD has recently received Type 3-4 accreditation and is continuing work on post PoC procedures and processes. [Meter Data Provider]: Risk = Medium, AAD has recently received Type 3-4 accreditation and is continuing work on post PoC procedures and processes. [Metering Coordinator]: Risk = Low, AAD has submitted the required information (for initial MC) to AEMO and is currently preparing a response to clarification questions. | [5 empty] | AAD has submitted the required information for accreditation as the initial MC for type 5, 6 and 7 metering installations and are responding to AEMO queries. Type 3-4 metering accreditation has now been received and AAD is continuing work on systems development to maintain compliance with the PoC reforms. The readiness of AAD to interface with the AEMO B2B eHub is a significant risk. In the absence of information, the system changes required to facilitate this new data flow is undefined. It is noted AEMO have 12 mths to develop this and Industry only have 3.5 mths to implement. There is a disparate timeframe for Industry to modify, test, put into production and this is noted as a major area of concern for AAD. AAD has noted that AEMO is making a "planning assumption" of go live on 4 December allowing for cutover activities to occur on the weekend of 2/3 December. AAD welcomes clarification on this point and is working to 1 December 2017 in the absence of formal notification of a delay.
| Ausgrid | At risk | Medium | We have established a number of formal ICT projects and assigned resources. A number of significant IT rebuilds are required in order to facilitate the new B2B, CATS and new minimum specification requirements. New interfaces for the customer are under development to assist our customers in operating in the POC space | [7 empty] | Issues noted above (section B) impact on all these categories.
| AusNet Services | Within schedule | Medium | On track for 1st December cutover and go-live. Other participant readiness across the NEM remains a risk, the majority of contributing concerns are not relevant within Victoria given metering exclusivity. | [7 empty] | Refer to overall comment.
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | At risk | Medium | CitiPower/Powercor is continuing to progress its build/test phase. Program timing remains challenging with no tolerance for delays or further requirement changes. CitiPower/Powercor has participated in industry planning for market trials and 1 December 2017 industry transition and cutover. We have hosted an information forum for retailers. We are available to meet one-one with any industry participant at their request. | [7 empty] | The Victorian Government has decided that distributors will be required to continue to install remotely read interval metering after 1 December 2017 compliant with the Victorian AMI functionality and service levels specifications and that existing and new/replacement AMI metering will be continue to be classified as Type 5 metering. In line with this decision and the draft Orders in Council published by the Victorian Government, CitiPower and Powercor will not be making any changes to how we classify either existing or new/replacement AMI meters in MSATS, nor any changes to our forward estimates, meter data validation and/or substitution methodologies. The Government Orders are yet to be finalised and a discussion paper on embedded networks yet to be published.
| Endeavour Energy | Within schedule | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures, which requires significant system and process changes over a period of only 6-7 months to design, develop and test. This short timeframe increases the risk on quality vendor delivery, however to date our vendors have made good progress against our schedule having provided periodic system functionality drops enabling us to commence testing. A key dependency for our PoC project, which is technical currency of our core system, has been successfully implemented. Another project risk is that different interpretations from each market participant of the Rules, procedures and jurisdictional obligations may result in an ineffective or unworkable processes between businesses. To mitigate this we are actively engaging with retailers and metering service providers to foster an open dialog on managing key processes. These engagements are proving beneficial as they are highlighting differences in our assumptions and approaches to some of the processes at an early point of the project. To help industry and to provide us better confidence that our solution will work effectively with other market participants we will be participating in the upcoming industry testing and additional bi-lateral testing with other participants. We are also actively participating in the various working groups including the PoC-WG, B2BWG, ITWG, RWG and SWG to ensure that AEMO procedures and B2B procedures supports the metering contestability and embedded networks rule changes in the most effective and cost efficient manner, and to only include transactions and obligations required for go live as a priority. | [7 empty] | [See project comment] | [5 empty] | This report is for Endeavour Energy as at 31 July 2017. Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5, 6 & 7 metering installations from 1 December 2017. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. The activities for the Market Systems testing and cutover are dependent on the development and build of the appropriate market system which is currently at risk.
| Energex Ltd. & Ergon Energy Corporation Ltd. | At risk | Medium | The Distribution project is tracking slightly behind its intended schedule. This is recoverable and the project will meet 1 December 17 compliance requirements due to a phased implementation approach. The project is undertaking its system integration testing and its industry test release in priority order. Similar to last month, the project's key focus remains on confirming assumptions with retailers and MCs on the mutual interpretation of B2B procedures. The project has sent all its assumptions to smaller retailers as well as the retailers with the biggest market share for feedback. Joint coordination across multiple parties remains a contentious issue, requiring a collective agreement to safely ensure continuity of service to customers. | [7 empty] | The project is currently 'At risk'. It is therefore undertaking a phased implementation approach with focus on the delivery of high priority transactions initially. Should build and test not progress exactly as planned due to compressed timeframes, manual work arounds remain a viable option for low priority transactions to meet 1 December 17 compliance.
| Essential Energy | At risk | High | Essential Energy's PoC program is progressing, with system changes on the critical path to deliver compliance by 1 December 2017. While timing remains very tight, the program is on track to deliver the majority of systems changes required to enable Essential Energy to commence B2B industry testing from 21 August 2017. Final release required for industry testing will be delivered to Essential Energy on 18 August; this release will be migrated to our industry testing environment once internal testing has been completed. | [7 empty] | [Distributor]: Risk = High, Risk rating remains at high due risks associated with systems delivery in preparation for industry testing from August 2017. Program schedule is tight and does not provide tolerance for any delays. Some business efficiency items deferred for delivery post 1 December. [Meter Provider]: Risk = Low. [Meter Data Provider]: Risk = Medium, Risk rating is classified as moderate for systems changes to support amended B2B framework, including to receive and process meter exchange information to enable timely publishing of final readings for Type 5 & 6 meters. | [5 empty] | Essential Energy will be an Initial MC, MDP and MP for Type 5 and 6 meter installations connected as at 1 December 2017. Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Networks | Within schedule | Medium | With 17 weeks to go-live on 1 December 2017, JEN is ready for industry testing and has been conducting bilateral testing with retailers prior to industry testing. The industry is currently working through risks associated with 1. A lack of end-to-end understanding of market operation and work practices between participants requires a workshop session facilitated by the industry program to resolve any procedural or build differences prior to industry testing; 2. Cutover and transition planning to complete in July to confirm there is no bow wave of transactions and go-live readiness criteria is defined; and 3. confirmation that all retailers who have customers of the JEN network are ready for 1-3 December 2017 go-live without manual intervention. Until these partner readiness risks are clarified within the industry program, the risk to the JEN Program will remain AMBER. | [7 empty] | With 17 weeks to go-live on 1 December 2017, JEN is ready for industry testing and has been conducting bilateral testing with retailers prior to industry testing. The industry is currently working through risks associated with 1. A lack of end-to-end understanding of market operation and work practices between participants requires a workshop session facilitated by the industry program to resolve any procedural or build differences prior to industry testing; 2. Cutover and transition planning to complete in July to confirm there is no bow wave of transactions and go-live readiness criteria is defined; and 3. confirmation that all retailers who have customers of the JEN network are ready for 1-3 December 2017 go-live without manual intervention. Until these partner readiness risks are clarified within the industry program, the risk to the JEN Program will remain AMBER.
| SA Power Networks | At risk | Medium | SAPN continue to face significant project challenges, particularly with regards to the development of the market system. At this point we still believe that we will be in a positon to achieve minimum market compliance. | [7 empty] | See overall project status comment
| TasNetworks | At risk | High | TasNetworks work program is to be ready for the 1st December 2017. The amount of change to be delivered in the timeframe is greater than anticipated as delivery timeframes are highly compressed. TasNetworks is taking a risk based approach on delivery which will have a flow on effect to processes and change management activities. Little time in the schedule to complete all business readiness activities before the 1st December. Some activities will need to be completed post 1st December, Market system software testing has commenced with some delays encountered with software delivery schedule.
| United Energy | Within schedule | Medium | Internal preparations continue to progress well. End-to-end integration testing has been completed successfully and the solution will be ready for industry and bi-lateral testing on 21 August. The risk rating reflects general concerns about industry readiness, and the cost and operational impact of any potential delay to the go-live date. | [7 empty] | UE operates in Victoria only. Jurisdictional status reflects overall position. Vic deferral details are yet to be formalised via changed Govt orders. | [5 empty] | Key concerns regarding UE (and industry) readiness are as follows: 1) The Victorian Government draft orders confirm the assumptions that 1: UE's role as MC for new meters after 1 Dec will be on the basis of existing regulated services, 2: New meters after 1 Dec will need to meet only the Vic AMI specifications and 3: New meters after 1 Dec will be classified as Type 5 MRIM, per current practice, and existing meters will remain Type 5 MRIM. Until the amended Orders are finalised, the possibility of unexpected requirements or obligations remains. However the likelihood of this has reduced following the publication of the draft orders. 2) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. UE's compliance in this area may also be dependent on existing child metering services being transitioned to meter providers on or by 1 Dec 2017, although this is partly dependent on the Vic Govt amended Orders (some parts of which have not yet been issued in draft form). If transition is required, it will be an activity over which UE does not have full control, particularly given UE's understanding that there are currently no accredited Embedded Network Managers in the market as at late July 2017. 3) UE is concerned that the lateness of procedures finalisation and the Victorian deferral details, plus the complexity and scale of testing with the increased number of market participants may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections and supply processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers. It is important that higher participation in readiness reporting and in the remaining testing phases is achieved for a robust 1 Dec 17 start. 4) UE is concerned that lack of readiness of some industry participants and/or poor results during industry testing may lead to the go-live being delayed from 1 Dec 2017 until some time in 2018. If this occurs, the cost incurred by UE to retain the appropriate project personnel during the delay will be significant. There will also be a negative impact on operational teams, with readiness preparations having to be interrupted and/or repeated, and recruitment of additional operational personnel being impacted.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule | Medium
| Ausgrid |  |  | At risk | Medium
| AusNet Services | [10 empty] | Within schedule | Medium
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | At risk | Medium
| Endeavour Energy |  |  | Within schedule | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | At risk | Medium
| Essential Energy |  |  | At risk | High
| Jemena Electricity Networks | [10 empty] | Within schedule | Medium
| SA Power Networks | [6 empty] | At risk | Medium
| TasNetworks | [8 empty] | At risk | High
| United Energy | [10 empty] | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | 81% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 61% - 70% | 81% - 99% | Completed (100%) | Completed (100%) | 81% - 99% | 81% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | 61% - 70% | Completed (100%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 61% - 70% | 81% - 99% | 81% - 99% | Completed (100%) | 81% - 99% | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 90% | 61% - 70% | 91% - 99%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 61% - 70% | 31% - 40% | 51% - 60% | 51% - 60% | 41% - 50% | 41% - 50% | 61% - 70% | Completed (100%) | 41% - 50% | 61% - 70% | 91% - 99%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 41% - 50% | 61% - 70% | 51% - 60% | 51% - 60% | 81% - 99% | 21% - 30% | 41% - 50% | 71% - 80% | 31% - 40% | 61% - 70% | 91% - 99%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 90% | 71% - 80% | 91% - 99%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 61% - 70% | 11% - 20% | 41% - 50% | 41% - 50% | 41% - 50% | 51% - 60% | 41% - 50% | 71% - 80% | 31% - 40% | 41% - 50% | 61% - 70%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 61% - 70% | 81% - 99% | Not started (0%) | 71% - 80% | 61% - 70% | 51% - 60% | Completed (100%) | 41% - 50% | 51% - 60% | Completed (100%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 31% - 40% | 41% - 50% | Not started (0%) | 81% - 99% | 31% - 40% | 11% - 20% | N/A | N/A | Not started (0%) | 11% - 20%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 31% - 40% | 21% - 30% | 31% - 40% | 11% - 20% | 21% - 30% | 11% - 20% | 1% - 10% | 51% - 60% | 11% - 20% | 11% - 20% | 51% - 60%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 51% - 60% | 61% - 70% | Completed (100%) | 81% - 99% | 81% - 99% | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | 51% - 60% | Completed (100%)
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 51% - 60% | 21% - 30% | Completed (100%) | 81% - 99% | 81% - 99% | 71% - 80% | 11% - 20% | Completed (100%) | 91% - 99% | 21% - 30% | Completed (100%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 31% - 40% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 90% | 81% - 99% | Completed (100%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 51% - 60% | 81% - 99% | 51% - 60% | 61% - 70% | 21% - 30% | 61% - 70% | 71% - 80% | Completed (100%) | 61% - 70% | 51% - 60% | Completed (100%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | 31% - 40% | 11% - 20% | 31% - 40% | 51% - 60% | 1% - 10% | 41% - 50% | 61% - 70% | 81% - 99% | 51% - 60% | 11% - 20% | 71% - 80%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10% | Not started (0%) | 61% - 70% | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | N/A | 31% - 40% | Not started (0%) | 1% - 10%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 21% - 30% | 1% - 10% | 31% - 40% | 31% - 40% | 21% - 30% | 21% - 30% | 11% - 20% | 71% - 80% | 61% - 70% | 11% - 20% | 61% - 70%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | 11% - 20% | Not started (0%) | 31% - 40% | 1% - 10% | 1% - 10% | 1% - 10%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Completed | Within schedule | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | At risk | Completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | At risk
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Completed | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule | Completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | At risk | Completed
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk | Completed
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Completed | Completed | Within schedule | At risk | At risk | Completed | Completed | Within schedule | Within schedule | Completed
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | Within schedule | At risk | At risk | At risk | At risk | Completed | At risk | Not within schedule | Completed
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | At risk | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | At risk | Not within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | The high level impact assessment is complete. Some gaps may be identified as part of the more detailed program of works to be carried out in the period through to December 2017. | Awaiting feedback from August AEMO Executive Forum |  |  |  | Business review of the Organisational Impact assessment is almost completed. |  |  | Completed | Further updates pending the consultation process on pack 3.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD is approximately half way through the third of six test cycles. Progress is ahead of schedule AAD is currently conducting workshops with market participants to continue progress on retailer specific items. | Awaiting feedback from August AEMO Executive Forum |  |  |  | The Business Readiness Framework has been finalised and has received formal approval. |  |  | Completed ( July 2017) | Implementation timeframe is compressed, a risk based approach is being applied across all program activities. Considerable reliance on the readiness of other local industry participants.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | AAD is currently working through initial MC contract drafting, legal aspects of market processes and ring fencing implications. | Final reviews in place |  |  |  | Ongoing activity - currently in progress by organisational specialists. |  |  | Monitor of changes from WP3 for impacts and changes | T&C's progressing according to schedule. | Given the deferral of competition in Victoria, United Energy has been proceeding on the basis of the following assumptions: 1: UE's role as MC for new meters after 1st of Dec will be on the basis of existing regulated services 2: New meters after 1 Dec will need to meet only the Vic AMI specifications. 3: New meters after 1 Dec will be classified as Type 5 MRIM, per current practice, and existing meters will remain Type 5 MRIM. These have been confirmed through the draft Order-in-Council issued in July 2017, but some risk will remain until the OIC details formally confirmed.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | AAD has commenced work on legal agreements relating to customer contracts, initial MC agreements with retailers, terms and conditions for provision of data/information to customers, etc. This work will continue until approximately September. | In progress. Will not be finalised until prototypes of user systems are available, commencing in August |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - the project is working with the internal regulatory team to ensure all regulatory requirements are met. |  |  | Within schedule; Work in progress with the business |  | This work is complete, but is based on the draft outcomes in the Vic Govt Order-in-Council. If the final orders differ from the positions presented to date, rework will be required which may impact readiness.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | As above. | Final drafting in progress with Legal team. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - amendments under consideration by each contract owner, updates will be made using existing procurement and contractual processes. Assessment of new agreements/contracts also ongoing. |  | On track to issue draft to retailers mid-August. Will be draft until OIC is finalised. | Within schedule; Work in progress with the business | T&C's progressing according to schedule. | Plans are in place to address the commercial implications, and resourcing is now in place. Work on the Initial MC Contract is nearing completion, based on the draft Order-in-Council documentation issued by the Vic Govt on 20 July. It is important that the Victorian Orders are formally concluded as a priority to ensure that the MC contract can be issued by the required date and is consistent with the National and Victorian arrangements. No other major commercial preparations are required.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | AAD has now submitted the required documentation to AEMO for B2B eHub accreditation. Application for accreditation as the initial MC has now been submitted to AEMO. AAD is now responding to clarification questions relating to the MC registration application. Type 4 accreditation has been received and AAD is working towards systems compliance with PoC requirements. | In progress. |  |  |  | The project is clear on the accreditation activities required for compliance and is well progressed with its associated obligations. |  | JEN eHub accreditation date has been confirmed by AEMO. | Within schedule; Work in progress with the business |  | Based on Vic Govt draft orders, UE continues to assume that accreditation as a Type 4 MDP is not required. Registration as MC and accreditation for use of e-Hub are required.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | As above. | In progress. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The project is clear on the accreditation activities required for compliance and is well progressed with its associated obligations. |  |  | Within schedule; Work in progress with the business |  | Accreditation for use of e-Hub and registration as MC for Type 5, 6 and 7 meters will be completed in accordance with AEMO requirements, and preparations are nearing completion. The "at risk" flag reflects the remaining uncertainty about accreditation as a Type 4 MDP (which UE is assuming is not required).
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | A detailed assessment of ongoing operational resource requirements has commenced (approximately 50 per cent complete) to ready the business for the transition and post PoC go-live activities. | Awaiting outcome of updated policies and work instructions to complete. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - Impact assessment currently under business review. |  |  | Within schedule; Work in progress with the business | Implementation timeframe is compressed, and program is not yet at a stage to fully assesss operational resource impacts and requirements.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Recruitment processes have now begun to fill these roles. | Relies on the above. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - Impact assessment currently under business review. |  | Not required for Jemena - out of scope. | Not Applicable |  | Operational backfill resources in place to allow subject matter experts to carry out testing. Planning underway for securing post-go-live operational resources
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Development of detailed training packages for industry and internal staff relating to network requirements has begun. | Relies on the above. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The training approach is progressing as planned, with training collateral in development. |  | All training has been scheduled with personnel for commencement in September. | Within schedule; Training needs analysis and development of training packages are in progress | Implementation timeframe is compressed, a risk based approach is being applied across all program activities. Considerable reliance on the readiness of other local industry participants. | Development of training strategy and training needs analysis is complete. Training materials and work instructions are under development and progressing well. Training delivery will commence in late October 2017.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Detailed workshops with retailers to develop systems and processes that are compatible with other external requirements are underway. | In concert with the changes ot policies, priocedures and work instructions. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | High priority 'to be' business processes are completed. Lower priority business processes are underway. |  | It is clear in discussions with industry participants that an end-to-end walkthrough of processes and the market operating model occurs in July 2017 at the latest. It is likely industry testing will fail if this does not occur. Jemena has been conducting 1:1 sessions to walk through processes and work practices with each Retailer who has customers on the JEN in the absence of this industry program activity occurring. | Completed (April 2017) | Implementation timeframe is compressed, a risk based approach is being applied across all program activities. Considerable reliance on the readiness of other local industry participants.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | As above. | In concert with the changes ot policies, priocedures and work instructions. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The high priority future state processes are completed, with low priority business processes underway. |  |  | Within schedule; Procedures are being updated to reflect changes from WP3 | Implementation timeframe is compressed, a risk based approach is being applied across all program activities. Considerable reliance on the readiness of other local industry participants.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not yet begun. | Not expected to start until mid-August 2017 | Industry testing only covers small subset of transactions. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Activities associated with the Test Approach are ongoing. The scope of August industry testing remains unclear and is perceived as retailer focused. Participation in industry testing will prove most valuable for our businesses if undertaken with participants within our jurisdiction, with whom we currently do business. Industry test is very transactional and will not effectively test all business processes, therefore it will need to be tested in UAT. |  |  | In line with SAPN delivery schedule | Validation of business process maybe done outside of industry testing and during UAT | Plans are in place to execute industry testing. However the current draft of B2B procedures includes the movement of currently enforceable details into a non-binding "guidance" category. The industry considers some of these details to be necessary for uniform, reliable end-to-end processing in the market. UE remains concerned that varying interpretations and inconsistencies between industry participants will become apparent during industry testing and may threaten its progress.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | AAD has a change request process underway for several minor amendments to system design. Changes are at various stages ranging from conceptual design through to development. | All solution designs are complete. |  | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | Requirement specifications and high priority designs are complete. Some of the lower priority and release 2 designs are still awaiting approval. The project's phased implementation approach ensures the achievement of compliance in release 1 and further efficiencies in release 2 which will occur post 1 December 2017. Risk of misalignment of assumptions between participants is evident as per discussions with various market participants during assumptions workshops. |  |  | Within schedule; Work in progress with the business |  | Based on Vic Govt advice that existing and new meters are to remain Type 5 MRIM, all solution impacts have been assessed.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | All initial code has been received by AAD. System updates relating to change requests (see above) are resulting in ongoing development efforts. | The implementation phase is nearing completion with final build tasks being completed in line with the testing schedule. |  | Critical path has little remaining contingency | See above comment | The build and test phase is progressing well but is slightly behind schedule. There is very little contingency remaining in the build schedule. Key Risk: changes in retailer / MC assumptions of the interpretation of the B2B procedures may impact the build schedule. | Agile delivery approach applied to system changes. Sprints required for market testing will be delivered just prior to commencement of market testing. |  | Critical path has little remaining contingency | Releases have been delayed from initial timeline, design complete and build activity underway. 2nd of 3 releases have been received. Systems build and testing timelines continue to be challenging. | Development and component testing of the core "market" solution that will support the MC changes is complete.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Internal testing is approximately 50% complete. AAD still holds concern for time constraints around retesting of blocked and failed tests already run. | Testing is underway. 15 testers are working across all solution components. Priority has been assigned to the Industry Test cases. |  | Note: Refer above. |  | Testing is currently tracking to schedule. However, testing timelines are compressed and therefore are 'at risk'. | Agile delivery approach applied to system changes. Sprints required for market testing will be delivered just prior to commencement of market testing. | JEN solution has been tested internally and bilaterally and is ready for industry testing with AEMO and Retailers. | Refer to Section 5.2 comment | Testing on release two is now underway, the timeline indicates that parallel testing will be required | End-to-end integration testing of the core "market" solution that will support the MC changes is complete and the solution is ready for industry testing. User acceptance testing will occur concurrent with industry testing.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not yet begun. | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is underway. | Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  | Successful completion of business to market testing was achieved on the 29 June 17. The production gateway will be tested with AEMO in September/October. |  | JEN is ready for 21 August 2017 minimum AEMO Market Testing. Full and complete bilateral testing is being arranged by Jemena directly with all Retailers who have customers on JEN to mitigate the PoC industry testing gap. | Refer to Section 5.2 comment; testing of market system interfaces will depend on the built solution above | TasNetworks intends to participate in industry towards the latter part of AEMO's proposed testing window | Limited bi-lateral testing of New Connections has been completed with one major retailer. On track to participate fully in industry and bi-lateral testing.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not yet begun. | Testing with market systems has not commenced. Test planning and preparation is complete. | Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  | We are concerned with the volume of retailers requesting to test with us in the early stage of cycle 1 market test. It is unclear if we have the number of resources required to participate in this testing without compromising the success of our own internal testing. Investigation of options is underway to determine the most beneficial option for us. i.e. higher execution of internal testing or participation in market testing with retailers that equate to a small volume of our market share. |  | The industry test plan performance testing is out of scope. We are unsure as to why this line item is in the report as there is no scheduled structured industry performance testing in AEMO's Industry Program Plan. | Within schedule; Phase 1 and Phase 2 Industry Testing complete | TasNetworks intends to participate in industry towards the latter part of AEMO's proposed testing window | Limited bi-lateral testing of New Connections has been completed with one major retailer. On track to participate fully in industry and bi-lateral testing.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | AAD is currently preparing transition and cutover plans. This includes actively participating in the ITCFG with AEMO and engaging with market participants to plan for jurisdictional specific measures. AAD is working with retailers to ensure readiness to go live on 1 December 2017. | Awaiting feedback from August AEMO Executive Forum, and working with internal stakeholders to understand impacts before completing planning |  | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | The AEMO transition and cutover workshops are very effective. Significant progress has now been achieved in this area. However please refer to the mitigant. Our project is keen to understand the position on Industry go /no go planning. |  | Transition planning is in progress internally and within industry collectively. It is important that AEMO facilitate the design and agreement of the go-live readiness criteria in July so that the industry is clear on what is required for 1-3 December 2017 go-live. | Within schedule; Work in progress with the business | This activity is under pressure due to the competing priorities and compressed timelines. This activity is also dependant on other market participants & industry planning readiness | Detailed cutover plan is nearing completion. Transitional preparations and documentation are well progressed.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | As above. | Not due yet. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Transition planning is tracking as scheduled. The Go Live Decision making framework has been formally approved. |  |  | Within schedule; Data conversion/migration planning started | Commenced data migration strategy and other preliminary planning activities. Preliminary assessment indicates cutover timeframes will exceed a day cutover window. | Preparation work is continuing. The first of two full dress rehearsals will be completed in mid-August 2017, prior to industry testing.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | AAD has established risk, issue and decision registers to track and mitigate gaps that are identified as progress is made.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Weekend work and additional test resources have been approved to mitigate the risks associated with slower than expected progress.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [15 empty] | On 20 July, the Vic Govt issued two draft orders that will be used to implement the deferal, and associated explanatory notes. UE assessed this documentation and provided feedback to the Vic Govt on 4 Aug. No major concerns were raised. UE continues to urge prompt finalisation of the changed Vic Govt Orders to ensure that no unexpected requirements or obligations are introduced. The DELWP position paper on embedded network child metering arrangements is expected on 7 Aug.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [15 empty] | As above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [15 empty] | UE continues to proceed on the basis of the draft orders issued on 20 July. Any changes to the draft materials may require change to the UE MC contract.
2.4 |  | An assessment of the required accreditation and registration activities | [15 empty] | As noted above, UE continues to urge prompt finalisation of the draft Vic Govt Orders so that accreditation requirements can be confirmed.
2.5 |  | The fulfilment of accreditation and registration obligations | [15 empty] | As above.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [14 empty] | Just in time waiting for MC to come onbaord, some internal process and final IT
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Requirements for additional testers and a business analyst has begun to mitigate risks associated with testing and delivery.
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing | [14 empty] | Validation of business process maybe done outside of industry testing and during UAT | To address concerns about varying interpretations of B2B procedures between industry participants, UE has developed an information pack and has directly engaged the key retailers in UE's patch. Intent is to execute bi-lateral testing with 25 retailers in UE patch, in addition to AEMO-led market trial tests. Testing with other participants will be supported by a "retailer handbook", which UE will issue prior to commencement of Industry Testing.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | See above comment | The Project has implemented a phased implementation approach.
5.2 |  | The development and build of appropriate market systems for your business | [6 empty] | All available resources have been assigned to the design & development tasks. |  |  | See above comment | The Project has implemented a phased implementation approach. | Working closely with vendor and business to ensure sprints are delivered on time and of high quality. Some non-market facing items deferred for delivery after 1 December 207. |  |  |  | Development and testing of flexible "management information" reports to support operational teams is scheduled to take place in late 2017. This work is not a dependency for 1 Dec go-live.
5.3 |  | The internal testing of market systems for your business | [11 empty] | Working closely with vendor and business to ensure sprints are delivered on time and of high quality. |  |  |  | Refer note above.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [10 empty] | Our organisation continues to urge AEMO to provide a transform capability as usual to mitigate go live risk.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2017-08-07 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | [AEMO Note - Using 10 July 17 Report for Active Stream]: The element of risk is elevating with the delay and/or deferral of the following items: - Package 3 - as built : delayed with inclusive items which need urgent clarification rather than been incorporated in a 6mth consultation process. i.e. Meter Churn, CR6300/800 etc. Feedback has been provided in the consultation process. - Clear communicated date of when the DB's treatment plan on how the Faults and Emergencies will be handled on site and subsequent Market communication of activities undertaken, will be available. Requesting AEMO to instruct the market that a consistent approach be rolled out across all jurisdictions. | [13 empty] | Active Stream is currently accredited and operating as a Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring Active Stream to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | At risk | Medium | The project remains amber within an aggressive schedule. Challenges remain against tight timeframes to complete developments and testing, ensure alignment with AEMO and participants for industry testing and define the business, people and cutover impacts. Gaining appropriate time and input with multiple parties for bialteral and commercial agreements provs to be challenging for all involved. Ongoing monitoring and mitigation plans for the management of projects risks and issues is being sustained.
| Ausgrid Business Services | At risk | Medium | The ICT and business projects are in final build and test stages. A number of significant IT rebuilds were required in order to facilitate the new B2B, CATS and new minimum specification requirements. Test scripts have been prepared to supplement Industry Testing. New interfaces for the customer are under development to assist our customers in operating in the POC space with the first phase release in UAT.
| intelliHUB Pty Ltd | Within schedule | Medium | [8 empty] | [Meter Provider]: Risk = Low [Meter Data Provider]: Risk = Low
| Metering Dynamics | At risk | Medium | Revised project delivery plans progressing well. The addition of experienced resources is bringing activities back within schedule. A number of jurisdictional differences continue to contribute to slow progress on MC commercial arrangements. | [7 empty] | Registration delays due to changing governance arrangements.
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Powermetric Metering Pty Ltd | At risk | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the aggressive POC implementation, industry testing and MC Registration timeframes place Powermetric POC development at a Medium risk.
| Select Solutions (EASTENMP, GLOBALM) | Within schedule | Medium | The summary project status and risk rating relating to the activities as Metering Coordinator. There are currently no substantial risks or issues impacting our existing Type 1-4 Large MP and MDP accreditations. There is limited time remaining for all participants to complete systems, process and people changes in readiness for Industry Testing. Select Solutions is working to the schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). There are substantial commercial agreement reviews and negotiations that are now commencing for all parties that has external risks to manage to ensure agreements are completed and executed prior to 1 December 2017. Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for MC Services.
| Spotless Advanced Metering | Within schedule | Low | Spotless Advanced Metering (SAM) has been developing a comprehensive metering business for approx 12 months. All plans, systems and process development is founded on PoC compliance and alignment with the PoC Go Live date of 1 Dec 17. | [7 empty] | Accrediation Audit scheduled to commence 7 August 2017
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on outstanding matters such as lack of clarity on Emergency Procedures, Meter Churn rules, and transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| intelliHUB Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metering Dynamics | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions (EASTENMP, GLOBALM) | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Spotless Advanced Metering | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
0
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 81% - 99% | 81% - 99% | Completed (100%) | 71% - 80% | 71% - 80% | 51% - 60% | 100% | Completed (100%) | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 71% - 80% | 81% - 99% | Completed (100%) | 71% - 80% | 51% - 60% | 61% - 70% | 100% | Completed (100%) | 81% - 99%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 61% - 70% | 81% - 99% | 81% - 99% | 61% - 70% | 71% - 80% | 11% - 20% | 100% | 81% - 90% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 81% - 99% | 61% - 70% | 21% - 30% | 61% - 70% | 31% - 40% | 71% - 80% | 11% - 20% | 75% | 81% - 90% | 51% - 60%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 61% - 70% | 31% - 40% | 51% - 60% | 81% - 99% | 21% - 30% | 51% - 60% | 11% - 20% | 50% | 81% - 90% | 31% - 40%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | 81% - 99% | Completed (100%) | 81% - 99% | 71% - 80% | 71% - 80% | 51% - 60% | 100% | 91% - 99% | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 81% - 99% | 21% - 30% | 21% - 30% | 41% - 50% | 51% - 60% | 51% - 60% | 11% - 20% | 75% | 81% - 90% | 51% - 60%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 61% - 70% | 51% - 60% | Completed (100%) | 71% - 80% | 71% - 80% | Completed (100%) | 100% | 61% - 70% | 61% - 70%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 61% - 70% | 31% - 40% | Completed (100%) | 41% - 50% | 71% - 80% | 71% - 80% | 75% | 61% - 70% | 41% - 50%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 11% - 20% | 11% - 20% | 21% - 30% | 61% - 70% | 11% - 20% | 41% - 50% | Not started (0%) | 25% | 71% - 80% | 21% - 30%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 71% - 80% | 51% - 60% | 81% - 99% | 71% - 80% | 51% - 60% | 31% - 40% | 100% | 81% - 99% | 71% - 80%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 99% | 61% - 70% | 11% - 20% | 61% - 70% | 31% - 40% | 51% - 60% | 21% - 30% | 50% | 81% - 99% | 41% - 50%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 21% - 30% | Not started (0%) | 31% - 40% | 1% - 10% | 11% - 20% | Not started (0%) | 25% | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 71% - 80% | 51% - 60% | Completed (100%) | 81% - 99% | 51% - 60% | 51% - 60% | 21% - 30% | 100% | 81% - 99% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 71% - 80% | 31% - 40% | 81% - 99% | 41% - 50% | 41% - 50% | 51% - 60% | 1% - 10% | 75% | 71% - 80% | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 71% - 80% | 11% - 20% | 11% - 20% | Not started (0%) | 21% - 30% | 11% - 20% | Not started (0%) | 25% | 41% - 50% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 41% - 50% | 1% - 10% | 1% - 10% | Not started (0%) | 11% - 20% | 11% - 20% | Not started (0%) | 0% | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | 0% | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 21% - 30% | 11% - 20% | 11% - 20% | Not started (0%) | 21% - 30% | 61% - 70% | Not started (0%) | 25% | 51% - 60% | 21% - 30%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 61% - 70% | Not started (0%) | 0% | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | At risk | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | Completed | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Finalising additional MC supporting documents arising from MC Application submission
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Dependent on Faults/Meter Churn , timely resolution or provisioning of answers from AEMO. |  | Working with ITCFG to understand impacts before completing planning |  |  | Implemetation plans to be revised in line with industry testing results.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Dependent on jurisdcitional determinations |  | Final reviews in place
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Dependent on jurisdcitional determinations |  | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Continuing uncertainty and changes in jurisdictional rules and interpretation of ring-fencing guideline requirements. |  |  | There are a number of new policies and procedures that are being documented as part of the MC Registration process with executive or senior level approval and signoff required as a dependancy for the MC Registration process.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | In progress. With Legal team. This is a significant logistical effort to negotiate agrements with each prospective party. |  | Complexity of contractual and commercial arrangements under POC is challenging. | Metering Coordinator contractual arrangements being finalised with several major retailers. |  | Substantial work has been completed to review and update all commercial agreements to ensure new services and transaction methods are included. There is a risk that any delays in planned negotiation timeframes will have impacts to arranagements for POC Go Live on 1 December 2017. This has been registered as part of our Risk Management framework.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | In progress and on-track. |  | In hand.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | In progress and on-track. |  | Applications submitted. ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. |  | Applications being finalised. Merger and corporate restructuring has delayed progress with revised governance processes. | Metering Coordinator registration application submitted to AEMO. |  | MC Registration submitted and progressing for completion in August 2017.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | MC resource requirements have been determined |  | Awaiting outcome of updated policies and work instructions to complete. |  | Corporate restructuring continues to add uncertainty to HR requirements analysis.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role; MC org chart in draft. |  | Relies on the above. |  | Impacted by recent merger and restructuring activity. |  |  | On Track to recruit additional MC resources as required to support Industry Transition and Go Live activities.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Training has commenced. |  | Relies on the above. |  | Due to change in key system components, flow on effect to training development and delivery timing. | Training to be developed inline with industry testing. |  | Change Management and Training Activities in progress.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions. |  | The volume of documents requiring approval and system integrator changes have delayed this work. |  |  | Documentation being prepared as part of MC Registration submitted and progressing for completion in August 2017.
4.3 |  | The validation of business processes during industry testing | [7 empty] | Not expected to start until 21 August 2017 |  |  | Industry testing not completed. |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | System impacts have been assessed in detail. The overall solution design is complete. |  | Key system architecture and system integrator changes. | Techical specifications under review.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | The implementation phase is nearing completion with final build tasks being completed in line with the testing schedule. |  | Change in systems approach has delayed progress in build activities. |  |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Testing is underway. 15 testers are working across all solution components. Priority has been assigned to the Industry Test cases. |  | Delays to systems build has impacted availability for testing. |  |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is underway. |  | Delays to systems build has impacted availability for testing. |  |  | We are on track to participate in Industry Testing activities as planned.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Testing with market systems has not commenced. Test planning and preparation is complete. |  |  |  |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Working with ITCFG to understand impacts before completing planning |  | Dependant on internal and market planning activities and decisions. |  |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Not yet due. |  |  |  |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Dedicated resource working on MC engagement and application
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [9 empty] | Further reviews of jurisdictional and ring-fencing requirements. Discussions and clarification with regulators.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [9 empty] | Continuing analysis of commercial requirements between parties. |  |  | Substantial customer and industry engagement has commenced and agreements are progressing and being monitored in our governance framework as key project risk.
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | Requirements being discussed with AEMO.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [9 empty] | Key assumptions being identified to allow progress.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [9 empty] | Work progressing, additional staff being recruited.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [9 empty] | Resources in training and development stream have started.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [9 empty] | Revised plan now in place for enhancing current systems. Process changes being updated accordingly.
4.3 |  | The validation of business processes during industry testing | [12 empty] | We are on track to participate in Industry Testing activities as planned and will also be engaging additional parties for Bilaterial Testing with our industry customers and peers.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | Revised plan in place for current systems. Systems impacts being updated accordingly.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Additional resources being secured to bring back on schedule
5.3 |  | The internal testing of market systems for your business | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule
5.5 |  | The validation of performance of market systems during industry testing | [12 empty] | We are on track to participate in Industry Testing activities as planned and will also be engaging additional parties for Bilaterial Testing with our industry customers and peers.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  | Focus on key deliverables for transition and cutover. ITCFG member. |  |  | Additional transition and cutover planning activities will be completed before the end of the Industry Testing and Market Trials.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [12 empty] | Additional transition and cutover planning activities will be completed before the end of the Industry Testing and Market Trials.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
| 2017-08-07 |  |  | Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | [AEMO Note - Using 10 July 17 Report for Active Stream]: The element of risk is elevating with the delay and/or deferral of the following items: - Package 3 - as built : delayed with inclusive items which need urgent clarification rather than been incorporated in a 6mth consultation process. i.e. Meter Churn, CR6300/800 etc. Feedback has been provided in the consultation process. - Clear communicated date of when the DB's treatment plan on how the Faults and Emergencies will be handled on site and subsequent Market communication of activities undertaken, will be available. Requesting AEMO to instruct the market that a consistent approach be rolled out across all jurisdictions. | [13 empty] | Active Stream is currently accredited and operating as a Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring Active Stream to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | At risk | Medium | The project remains amber within an aggressive schedule. Challenges remain against tight timeframes to complete developments and testing, ensure alignment with AEMO and participants for industry testing and define the business, people and cutover impacts. Gaining appropriate time and input with multiple parties for bialteral and commercial agreements provs to be challenging for all involved. Ongoing monitoring and mitigation plans for the management of projects risks and issues is being sustained.
| Ausgrid Business Services | At risk | Medium | The ICT and business projects are in final build and test stages. A number of significant IT rebuilds were required in order to facilitate the new B2B, CATS and new minimum specification requirements. Test scripts have been prepared to supplement Industry Testing. New interfaces for the customer are under development to assist our customers in operating in the POC space with the first phase release in UAT.
| intelliHUB Pty Ltd | Within schedule | Medium | [8 empty] | Delay experienced in UAT testing of CATS MC compliant system. Vendor is Brave Energy
| Metering Dynamics | At risk | Medium | Revised project delivery plans progressing well. The addition of experienced resources is bringing activities back within schedule. A number of jurisdictional differences continue to contribute to slow progress on MC commercial arrangements. | [7 empty] | Registration delays due to changing governance arrangements.
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Powermetric Metering Pty Ltd | At risk | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the aggressive POC implementation, industry testing and MC Registration timeframes place Powermetric POC development at a Medium risk.
| Select Solutions (EASTENMP, GLOBALM) | Within schedule | Medium | The summary project status and risk rating relating to the activities as Metering Coordinator. There are currently no substantial risks or issues impacting our existing Type 1-4 Large MP and MDP accreditations. There is limited time remaining for all participants to complete systems, process and people changes in readiness for Industry Testing. Select Solutions is working to the schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). There are substantial commercial agreement reviews and negotiations that are now commencing for all parties that has external risks to manage to ensure agreements are completed and executed prior to 1 December 2017. Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for MC Services.
| Spotless Advanced Metering | Within schedule | Low | Spotless Advanced Metering (SAM) has been developing a comprehensive metering business for approx 12 months. All plans, systems and process development is founded on PoC compliance and alignment with the PoC Go Live date of 1 Dec 17. | [7 empty] | Application for Registration as a MC submitted to AEMO
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on outstanding matters such as lack of clarity on Emergency Procedures, Meter Churn rules, and transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| intelliHUB Pty Ltd | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium
| Metering Dynamics | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions (EASTENMP, GLOBALM) | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Spotless Advanced Metering | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
0
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 81% - 99% | 81% - 99% | Completed (100%) | 71% - 80% | 71% - 80% | 51% - 60% | 100% | Completed (100%) | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 71% - 80% | 81% - 99% | Completed (100%) | 71% - 80% | 51% - 60% | 61% - 70% | 100% | Completed (100%) | 81% - 99%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 61% - 70% | 81% - 99% | 81% - 99% | 61% - 70% | 71% - 80% | 11% - 20% | 100% | 81% - 90% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 81% - 99% | 61% - 70% | 21% - 30% | 61% - 70% | 31% - 40% | 71% - 80% | 11% - 20% | 75% | 81% - 90% | 51% - 60%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 61% - 70% | 31% - 40% | 51% - 60% | 81% - 99% | 21% - 30% | 51% - 60% | 11% - 20% | 50% | 81% - 90% | 31% - 40%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | 81% - 99% | Completed (100%) | 81% - 99% | 71% - 80% | 71% - 80% | 51% - 60% | 100% | 91% - 99% | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 81% - 99% | 21% - 30% | 21% - 30% | 41% - 50% | 51% - 60% | 51% - 60% | 11% - 20% | 75% | 81% - 90% | 51% - 60%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 61% - 70% | 51% - 60% | Completed (100%) | 71% - 80% | 71% - 80% | Completed (100%) | 100% | 61% - 70% | 61% - 70%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 61% - 70% | 31% - 40% | Completed (100%) | 41% - 50% | 71% - 80% | 71% - 80% | 75% | 61% - 70% | 41% - 50%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 11% - 20% | 11% - 20% | 21% - 30% | 61% - 70% | 11% - 20% | 41% - 50% | Not started (0%) | 25% | 71% - 80% | 21% - 30%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 71% - 80% | 51% - 60% | 81% - 99% | 71% - 80% | 51% - 60% | 31% - 40% | 100% | 81% - 99% | 71% - 80%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 99% | 61% - 70% | 11% - 20% | 61% - 70% | 31% - 40% | 51% - 60% | 21% - 30% | 50% | 81% - 99% | 41% - 50%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 21% - 30% | Not started (0%) | 31% - 40% | 1% - 10% | 11% - 20% | Not started (0%) | 25% | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 71% - 80% | 51% - 60% | Completed (100%) | 81% - 99% | 51% - 60% | 51% - 60% | 21% - 30% | 100% | 81% - 99% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 71% - 80% | 31% - 40% | 81% - 99% | 41% - 50% | 41% - 50% | 51% - 60% | 1% - 10% | 75% | 71% - 80% | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 71% - 80% | 11% - 20% | 11% - 20% | Not started (0%) | 21% - 30% | 11% - 20% | Not started (0%) | 25% | 41% - 50% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 41% - 50% | 1% - 10% | 1% - 10% | Not started (0%) | 11% - 20% | 11% - 20% | Not started (0%) | 0% | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | 0% | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 21% - 30% | 11% - 20% | 11% - 20% | Not started (0%) | 21% - 30% | 61% - 70% | Not started (0%) | 25% | 51% - 60% | 21% - 30%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 61% - 70% | Not started (0%) | 0% | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | At risk | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | Completed | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Finalising additional MC supporting documents arising from MC Application submission
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Dependent on Faults/Meter Churn , timely resolution or provisioning of answers from AEMO. |  | Working with ITCFG to understand impacts before completing planning |  |  | Implemetation plans to be revised in line with industry testing results.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Dependent on jurisdcitional determinations |  | Final reviews in place
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Dependent on jurisdcitional determinations |  | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Continuing uncertainty and changes in jurisdictional rules and interpretation of ring-fencing guideline requirements. |  |  | There are a number of new policies and procedures that are being documented as part of the MC Registration process with executive or senior level approval and signoff required as a dependancy for the MC Registration process.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | In progress. With Legal team. This is a significant logistical effort to negotiate agrements with each prospective party. |  | Complexity of contractual and commercial arrangements under POC is challenging. | Metering Coordinator contractual arrangements being finalised with several major retailers. |  | Substantial work has been completed to review and update all commercial agreements to ensure new services and transaction methods are included. There is a risk that any delays in planned negotiation timeframes will have impacts to arranagements for POC Go Live on 1 December 2017. This has been registered as part of our Risk Management framework.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | In progress and on-track. |  | In hand.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | In progress and on-track. |  | Applications submitted. ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. |  | Applications being finalised. Merger and corporate restructuring has delayed progress with revised governance processes. | Metering Coordinator registration application submitted to AEMO. |  | MC Registration submitted and progressing for completion in August 2017.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | MC resource requirements have been determined |  | Awaiting outcome of updated policies and work instructions to complete. |  | Corporate restructuring continues to add uncertainty to HR requirements analysis.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role; MC org chart in draft. |  | Relies on the above. |  | Impacted by recent merger and restructuring activity. |  |  | On Track to recruit additional MC resources as required to support Industry Transition and Go Live activities.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Training has commenced. |  | Relies on the above. |  | Due to change in key system components, flow on effect to training development and delivery timing. | Training to be developed inline with industry testing. |  | Change Management and Training Activities in progress.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions. |  | The volume of documents requiring approval and system integrator changes have delayed this work. |  |  | Documentation being prepared as part of MC Registration submitted and progressing for completion in August 2017.
4.3 |  | The validation of business processes during industry testing | [7 empty] | Not expected to start until 21 August 2017 |  |  | Industry testing not completed. |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | System impacts have been assessed in detail. The overall solution design is complete. |  | Key system architecture and system integrator changes. | Techical specifications under review.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | The implementation phase is nearing completion with final build tasks being completed in line with the testing schedule. |  | Change in systems approach has delayed progress in build activities. |  |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Testing is underway. 15 testers are working across all solution components. Priority has been assigned to the Industry Test cases. |  | Delays to systems build has impacted availability for testing. |  |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is underway. |  | Delays to systems build has impacted availability for testing. |  |  | We are on track to participate in Industry Testing activities as planned.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Testing with market systems has not commenced. Test planning and preparation is complete. |  |  |  |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Working with ITCFG to understand impacts before completing planning |  | Dependant on internal and market planning activities and decisions. |  |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Not yet due. |  |  |  |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Dedicated resource working on MC engagement and application
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [9 empty] | Further reviews of jurisdictional and ring-fencing requirements. Discussions and clarification with regulators.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [9 empty] | Continuing analysis of commercial requirements between parties. |  |  | Substantial customer and industry engagement has commenced and agreements are progressing and being monitored in our governance framework as key project risk.
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | Requirements being discussed with AEMO.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [9 empty] | Key assumptions being identified to allow progress.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [9 empty] | Work progressing, additional staff being recruited.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [9 empty] | Resources in training and development stream have started.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [9 empty] | Revised plan now in place for enhancing current systems. Process changes being updated accordingly.
4.3 |  | The validation of business processes during industry testing | [12 empty] | We are on track to participate in Industry Testing activities as planned and will also be engaging additional parties for Bilaterial Testing with our industry customers and peers.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | Revised plan in place for current systems. Systems impacts being updated accordingly.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Additional resources being secured to bring back on schedule
5.3 |  | The internal testing of market systems for your business | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule
5.5 |  | The validation of performance of market systems during industry testing | [12 empty] | We are on track to participate in Industry Testing activities as planned and will also be engaging additional parties for Bilaterial Testing with our industry customers and peers.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  | Focus on key deliverables for transition and cutover. ITCFG member. |  |  | Additional transition and cutover planning activities will be completed before the end of the Industry Testing and Market Trials.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [12 empty] | Additional transition and cutover planning activities will be completed before the end of the Industry Testing and Market Trials.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Embedded Networks
| 2017-08-07 |  |  | Embedded Networks Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Ausgrid Business Services | At risk | Medium | The ICT and business projects are in final build and test stages. A number of significant IT rebuilds were required in order to facilitate the new B2B, CATS and new minimum specification requirements. Test scripts have been prepared to supplement Industry Testing. New interfaces for the customer are under development to assist our customers in operating in the POC space with the first phase release in UAT.
| Energy & Plant Management Pty Limited | Within schedule | Low | Preparing for accreditation. Attended Pre-Application Meeting 4/8/17 ENM Accreditation Application Forms submitted 7/8/17
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Momentum Energy | At risk | Medium | Current risks are related to potential issues with development and implementation of system changes within given timeframes. There are dependencies on external vendors to develop required changes. There is also a lack of clarity from AEMO in terms of how the Victorian Distributors role will evolve related to MC. Also critical dependencies on external providers of MC role to meet their POC timeframes.
| Network Energy Services | Within schedule | Low | Submitted accreditation application | [7 empty] | Getting prepared to implement all aspects
| Watts Energy Pty Ltd | Within schedule | Medium
| WINConnect Pty LTD | At risk | Medium | Original policies and procedures have been developed on certain assumptions regarding the jursitictional differences in Vicotoria. The draft orders in council in Victoria indicates a separate approach to embedded networks to be adopted. Awaiting detail on that in order to finalise policies and procedures. | [7 empty] | Awaiting feedback from Victorian Department on applicability of ENM in Victoria
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Energy & Plant Management Pty Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Metropolis Metering Services Pty Ltd | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium
| Momentum Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Network Energy Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Watts Energy Pty Ltd |  |  |  |  | Within schedule | Medium
| WINConnect Pty LTD | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium |  |  | Not within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Metropolis Metering Services Pty Ltd | Momentum Energy | Network Energy Services | Watts Energy Pty Ltd | WINConnect Pty LTD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 81% - 99% | 61% - 70% | 71% - 80% | 71% - 80% | 100% | 61% - 70% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 21% - 30% | 51% - 60% | 71% - 80% | 100% | 51% - 60% | 71% - 80%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 21% - 30% | 71% - 80% | 61% - 70% | 100% | 61% - 70% | 41% - 50%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 21% - 30% | 21% - 30% | 71% - 80% | 31% - 40% | 100% | 51% - 60% | 11% - 20%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 51% - 60% | 41% - 50% | 51% - 60% | 31% - 40% | 25% | 11% - 20% | 41% - 50%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | 61% - 70% | 71% - 80% | 61% - 70% | 100% | 61% - 70% | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 21% - 30% | 1% - 10% | 51% - 60% | 51% - 60% | 50% | 31% - 40% | 71% - 80%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 81% - 99% | 71% - 80% | 61% - 70% | 100% | 41% - 50% | 71% - 80%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 61% - 70% | 71% - 80% | 61% - 70% | 100% | 51% - 60% | Completed (100%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 21% - 30% | 41% - 50% | 41% - 50% | 21% - 30% | 50% | 1% - 10% | 71% - 80%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 51% - 60% | 71% - 80% | 51% - 60% | 41% - 50% | 100% | 31% - 40% | 41% - 50%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 11% - 20% | 11% - 20% | 51% - 60% | 21% - 30% | 100% | 11% - 20% | 51% - 60%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 1% - 10% | 11% - 20% | Not started (0%) | 0% | Not started (0%) | Completed (100%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | 51% - 60% | 51% - 60% | 61% - 70% | 75% | 31% - 40% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 99% | 41% - 50% | 51% - 60% | 31% - 40% | 50% | 11% - 20% | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 11% - 20% | 1% - 10% | 11% - 20% | 51% - 60% | 50% | Not started (0%) | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 1% - 10% | Not started (0%) | 11% - 20% | 11% - 20% | 50% | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | 1% - 10% | 11% - 20% | Not started (0%) | 0% | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 11% - 20% | 41% - 50% | 61% - 70% | 21% - 30% | 75% | 11% - 20% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | 11% - 20% | 61% - 70% | Not started (0%) | 25% | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Metropolis Metering Services Pty Ltd | Momentum Energy | Network Energy Services | Watts Energy Pty Ltd | WINConnect Pty LTD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Metropolis Metering Services Pty Ltd | Momentum Energy | Network Energy Services | Watts Energy Pty Ltd | WINConnect Pty LTD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Finalising additional MC supporting documents arising from MC Application submission
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Working with ITCFG to understand impacts before completing planning |  | Implemetation plans to be revised in line with industry testing results.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Final reviews in place |  |  | Retailer timeframes to assess and agree to the Ts&Cs of the LNSPs are extremely tight and require the same pool of resources needed elsewhere in the program
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | In progress. Will not be finalised until design and early prototypes of user systems are available. |  |  | Severe challenges with the level of effort required to translate system and process changes into business operational readiness |  |  | Subject to confirmation on ENM roll in Victoria.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | In progress. With Legal team. This is a significant logistical effort to negotiate agrements with each prospective party. |  | Metering Coordinator contractual arrangements being finalised with several major retailers. | Dependency on partnering with registered MC(s)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | In hand. |  |  | Volume of information required following initial assessment is higher than expected
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Applications submitted. ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. |  | Metering Coordinator registration application submitted to AEMO. | Volume of information required following initial assessment is higher than expected
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Awaiting outcome of updated policies and work instructions to complete.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Relies on the above.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Relies on the above. |  | Training to be developed inline with industry testing. | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | In concert with the changes ot policies, priocedures and work instructions. | [5 empty] | Subject to confirmation of jursitictional differences.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | In concert with the changes ot policies, priocedures and work instructions. |  |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not expected to start until 21 August 2017 |  | Industry testing not completed. | Delays from third parties are impacting our ability to participate in industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | System impacts have been assessed in detail. The overall solution design is complete. |  | Techical specifications under review.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | The implementation phase is nearing completion with final build tasks being completed in line with the testing schedule. |  |  | System development is reliant on external vendors, any delays in final market procedures will impact readiness activities.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Testing is underway. 15 testers are working across all solution components. Priority has been assigned to the Industry Test cases. |  |  | The late delivery of our B2B code by the external provider doesn't allow enough time for internal testing
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is underway.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Testing with market systems has not commenced. Test planning and preparation is complete.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Working with ITCFG to understand impacts before completing planning |  |  | Transition plans are dependent on timely delivery of earlier program stages
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not yet due.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Metropolis Metering Services Pty Ltd | Momentum Energy | Network Energy Services | Watts Energy Pty Ltd | WINConnect Pty LTD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Dedicated resource working on MC engagement and application
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [11 empty] | Clear guidance required from juiristictional bodies of the roll of the ENM in Victoria and QLD.
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [11 empty] | Clear guidance required from juiristictional bodies of the roll of the ENM in Victoria and QLD.
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | All available resources have been assigned to the design & development tasks.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Member on ITCFG
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Third Party
| 2017-08-07 |  |  | Third Party Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2017-08-07 | [5 empty] | Within schedule | Medium | PWC Survey demonstrates a number of risks that and other related items that have been articulated to AEMO which has been transferred to the contingency planning and another list for clarification and accountability purposes. The aim is to de-risk the industry program. All Industry participants are responsible for the outcomes of these activities. Key activities requiring industry input include: • Contingency planning being conducted by RWG • Staged approach to effective date being examined by the ITCFG The Draft Industry Transition and Cutover plan has been completed. The first MC registration has been completed and more are underway.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Medium
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies consistent with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 41% - 50% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updated B2B retail electricity market procedures and associated documentation | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | 51% - 60% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 51% - 60% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS (EN/MC) | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B e-hub and MSATS | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 90% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | The internal testing of market systems for your business | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 1% - 10% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 41% - 50% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
[12 empty] | 41% - 50% | Retailer
[12 empty] | 51% - 60% | Distributor
[12 empty] | 61% - 70% | Meter Provider
[12 empty] | 71% - 80% | Meter Data Provider
[12 empty] | 81% - 90% | Metering Coordinator
[12 empty] | 91% - 99% | Embedded Network Manager
[12 empty] | Completed (100%) | Embedded Network Operator
[12 empty] | N/A | Third Party B2B Participant
Within schedule
At risk
Not within schedule
N/A
[12 empty] | Completed | √
x
Low
Medium
High
N/A

## Harvey Balls 10% (hidden)
ü
Completed
| 100 | 90 | 80 | 70 |  | 60 | 50 | 40 | 30 | 20 | 10 | 0
| 0 | 10 | 20 | 30 |  | 40 | 50 | 60 | 70 | 80 | 90 | 100
WITHIN SCHEDULE | [12 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE
|  |  | ~0% |  | ~50%
|  |  | ~10% |  | ~60%
|  |  | ~20% |  | ~70%
|  |  | ~30% |  | ~80%
|  |  | ~40% |  | ~90%