## Market Readiness Report Page 1
42926
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2017-07-10
Overall Status |  | Commentary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | The overall project status remains amber - "at risk" of delivery by 1 December 2017 - primarily due to challenging program timeframes. Participants have highlighted challenging timeframes for system build and testing, registration and accreditation activities, and the number and complexity of commercial arrangements to be entered into. Highlighted risk areas include uncertainty associated with the Victorian Government deferral decision, faults and emergency processes, meter churn, jurisdiction safety regulations and transition approach. The overall project risk rating has been decreased to medium - with participants having more confidence that their systems will be in place in time, however participants continue to express concerns regarding other participants' readiness. |  |  |  |  | High | Med | Low | #
[7 empty] | 4 | 3 | 3 | 1
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Network Manager |  | Third party e-hub
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place |  |  |  | #1
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with regulatory changes including jurisdictional regulations and requirements (e.g. safety) |  |  |  | #2 | [7 empty] | #2
2.3 |  | Operationally critical commercial contracts in place |  |  |  | #3 |  |  |  | #3 |  | #3 |  | #3
2.4 |  | Accreditation and registration activities completed |  |  |  | #4 |  |  |  | #4 |  | #4
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place |  |  |  | #5 |  |  |  | #5 |  | #5 |  | #5
4.2 |  | Successfully validated critical business processes during industry testing
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing
5.2 |  | Successfully tested market systems capable of being moved into production |  |  |  | #6 |  | #6 |  | #6 |  | #6
5.3 |  | Performance of, and communication between, market systems validated during industry testing |  |  |  | #7 |  | #7 |  | #7 |  | #7
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place |  |  |  | #8 | [7 empty] | #8
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals)
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Network Manager |  | Third party e-hub
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdictional risk is a reflection of overall project risk.
NSW |  | Jurisdictional risk is a reflection of overall project risk.
QLD |  | Jurisdictional risk is a reflection of overall project risk.
SA |  | Jurisdictional risk is a reflection of overall project risk.
TAS |  | Jurisdictional risk is a reflection of overall project risk.
VIC |  | Jurisdictional risk is a reflection of overall project risk.

## HIDDEN 25% (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2017-07-10
Variances
Note # | Explanation of Variance |  |  | Mitigating Actions
1 | Variance reported by Participants: Development of detailed Implementation plans on schedule at risk as participants are still waiting for the VIC derogation extension details, and have identified a need to iterate plans for differing implementation approaches. |  |  | Participants are awaiting the Victorian government OIC.
2 | Variance reported by Participants: Updating internal policies on schedule at risk as participants are waiting for the Victorian Government to release the VIC derogation extension details, for jurisdictional safety regulators to publish requirements and for clarity on the ENM role in Victoria and Queensland. |  |  | Participants are engaging with jurisdictional bodies.
3 | Variance reported by Participants: Updating commercial arrangements on schedule is at risk due to volume and complexity of contracts that need to be entered into with industry parties. |  |  | Participants are increasing internal resources.
4 | Variance reported by Participants: Fulfilling registration and accreditation activities on schedule is at risk due compressed timeframes for all registration and accreditation activities. |  |  | Participants are increasing internal resources and commencing discussions with AEMO. [AEMO encourages early engagement with AEMO on registration and accreditation requirements - see POC Industry Accreditation & Registration Plan (http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Power-of-Choice/Readiness-Work-Stream)]
5 | Variance reported by Participants: Progress impacted by uncertainty in a number of areas including meter churn, faults and emergencies, jurisdictional requirements. Progress has been impacted by the Victorian Government deferral decision. |  |  | Participants are increasing internal resources, reviewing meter churn impacts under Package 3 and awaiting the Victorian govt. OIC.
6 | Variance reported by Participants: System development at risk due to the complexity and number of changes required within tight timeframes for development and testing. Dependency on VIC derogation details, package 3 consultation and faults & emergencies processes also noted. |  |  | Participants are increasing internal resources and working closely with market system vendors.
7 | Variance reported by Participants: Testing timelines are contingent on system design and build. |  |  | Participants are increasing internal resources and working closely with market system vendors.
8 | Variance reported by Participants: Transition and Cutover planning dependent on new connection processes, readiness of competitive MCs. Cutover plan for existing embedded networks yet to be developed. |  |  | Participants are engaging with the ITCFG. [http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Power-of-Choice/Readiness-Work-Stream/Industry-Transition-Cutover-Focus-Group]
Notes
1. The count of open Risk and Issues is based on the POC Industry Risk Register as at 14/07/2017. 2. Explanation of Variance and Mitigating Actions above are based on Participants comments, AEMO's comments are included within square brackets [ ].
Key - Progress and Status | [5 empty] | Key - Risk Rating
Progress |  |  | Status
Harvey balls represent progress towards achieving the criterion |  |  | Colour indicates the readiness status |  |  | Rating
~0% |  | ~50% | Criterion is within agreed schedule and deliverable requirements |  |  | High
~10% |  | ~60% | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~20% |  | ~70% | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~30% |  | ~80% |  |  |  | See POC Industry Risk Register for open risks and issues:
~40% |  | ~90% | Criterion has been achieved |  | ü | POC Industry Register

## Retailer Reports
| 2017-07-10 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Retail | Within schedule | Medium | ActewAGL Retail has completed a high level impact assessment of the changes required by PoC on its business operations and systems, requirements have been baselined, business processes and detailed system design completed, system build and test in progress. A detailed project plan is in place and being tracked against in order to achieve compliance by the "go live" date.
| AGL Retailer Powerdirect | At risk | Medium | Industry testing for EN/MC completed sucessfully. Commercial activities are still in progress. Core B2B developments are complete and ready for bi-lateral testing. Bilateral testing scheduled to commence 17/7 with selected participants. AGL/Powerdirect on track for phase 3 cycle 1 industry testing. Project status remains yellow due to risks arising from commercial agreement completion. | [7 empty] | Risk rating remains at medium due to the number of parties involved, limited testing timeframes, significant commercial agreements that must be implemented and business transition and readiness activities.
| Alinta Energy | Within schedule | Medium | Over all the project is still progressing to plan. IMetering Partner engagement progressing, however there is no certainty around who will be ready at 1/12 Fault and Emmergency responses from the DBs will govern the Requirments Retailers and their MCs will have for Go-Live Interpretation of Proceedures by the DBs may require additional system and process changes. | [7 empty] | Operating in the Queensland market before the end of the year. Looking to participate in industry testing for QLD MM in Cycle 2.
| Aurora Energy | At risk | Medium | Aurora Energy continues to manage a number of risks with regards to the implementation of the Power of Choice reforms by 1 December 2017. The most significant risk is the aggressive implementation timeline, reflected in Aurora Energy's 'at risk' project status. This risk is also impacting the ability of Aurora Energy's key vendors to meet POC timeframes. This includes, but is not limited to, a prospective Metering Coordinator, which will be required to establish advanced metering service capability in Tasmania where it currently does not exist.
| Energy Australia | At risk | Medium | We see siginficant risks associated with: the Vic Government decision to delay PoC; the lack of alignment on implementation approaches among participants; tighness of industry testing schedule; and the progress of industry coordinated activities, such as industry-wide readiness, BCP and Emergency Planning. | [7 empty] | The Program is making steady progress but has risks associated with the progress of industry coordinated activities, such as industry-wide readiness, BCP and Emergency Planning. [VIC specific comment]: The Vic decision to delay competition in metering has had a significant impact on DB alignment to B2B guidelines, which have not been addressed at an industry level. The resulting variances place a high level of risk on the project. | [5 empty] | Risks associated with industry coordinated activities still exist, such as BCP and Emergency Planning.
| Ergon Energy Queensland (retail) | At risk | High | The project risk rating has been increased to 'high' due to: - the timelines associated with system changes - the complexity, number and current progress of contracts that need to be negotiated with Initial MC / competitive MC - additional complexities and costs associated with delivering PoC metering changes in a regional setting with no effective competition - jurisdictional safety requirements which do not enable remote re-energisation. This will impact on the realisation of retailer and customer benefits. | [7 empty] | The project risk rating has been increased to 'high' due to: - the timelines associated with system changes - the complexity, number and current progress of contracts that need to be negotiated with Initial MC / competitive MC - additional complexities and costs associated with delivering PoC metering changes in a regional setting with no effective competition - jurisdictional safety requirements which do not enable remote re-energisation. This will impact on the realisation of retailer and customer benefits.
| ERM Power Retail | At risk | Medium | In addition to the reasons ERM Power Retail have previously provided for our Power of Choice program overall project risk rating of At Risk / Medium, the lack of certainty around the timing of the systems cutover and the conflict between the discussed weekend cutover and the official Power of Choice start date introduce additional risk to the overall industry wide program of work.
| M2 Energy Pty Ltd | Within schedule | Medium | Project Scoping by Vendor is complete, and coding has commenced.. Vic related changes are a substantial risk. Business intention is to fully outsource MC role. Risk considered Medium as few vendors currently available for selection and none are accredited. M2 Energy is maintaining dialogue with potential vendors. | [7 empty] | Vic withdrawl from POC has introduced risk into System Scoping, and increased training and change management requirements.
| Macquarie Bank Limited | Within schedule | Low
| Mojo Power Pty Ltd | Within schedule | Medium | [8 empty] | Treatment of VIC AMI by market. Mojo in application process to be a retailer in Victoria.
| Momentum Energy | At risk | Medium | Current risks are related to potential issues with development and implementation of system changes within given timeframes. There are dependencies on external vendors to develop required changes. There is also a lack of clarity from AEMO in terms of how the Victorian Distributors role will evolve related to MC. Also critical dependencies on external providers of MC role to meet POC timeframes.
| Next Business Energy | Within schedule | Medium
| Origin Energy | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Program is currently reporting Amber however remains highly dependant on the readiness of other participants to be successful and 9 out of 11 Distributors reporting at risk. A high number of delivery risks continue to be monitored and mitigated for the duration of the project. Areas of concern include: Delivery • Uncertainty around the details of the VIC derogation extension may delay the delivery of the program (Origin has expressed concerns over proposed deviation from the overall B2B procedures); • Industry Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unclear and therefore impacting our planning and implementation of activities; participants updating own data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Awaiting delivery from AEMO of a completed Testing Plan inc. Test Data requirements for Market Trial Testing . If a Production Test Data cut is not agreed and published in the next few weeks, the Testing activities of the program will be impacted. Additionally, Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. • If safety regulations in each state (incl. ACT) does not allow MPs to energise a site, then New Connections timeframes will prolong by several days with risk of additional cost to customers. • Industry focus on compliance with the new obligations and lack of progress at jurisdictional level for supporting regulation changes, such as safety cases, right to entry etc. may result in poor customer experience. Cutover • Time frame for cutover is not practicable: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc.). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. This seems to suggest the aggregated risks may not be fully understood. Comms • Communications plan to affected parties (i.e. Electricians, Customers) is still not finalised; expectation that AEMO will lead on this activity. | [7 empty] | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. | [5 empty] | Areas of concern include: Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Program is currently reporting Amber however remains highly dependant on the readiness of other participants to be successful and 9 out of 11 Distributors reporting at risk. A high number of delivery risks continue to be monitored and mitigated for the duration of the project. Areas of concern include: Delivery • Uncertainty around the details of the VIC derogation extension may delay the delivery of the program (Origin has expressed concerns over proposed deviation from the overall B2B procedures); • Industry Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unclear and therefore impacting our planning and implementation of activities; participants updating own data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Awaiting delivery from AEMO of a completed Testing Plan inc. Test Data requirements for Market Trial Testing . If a Production Test Data cut is not agreed and published in the next few weeks, the Testing activities of the program will be impacted. Additionally, Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. • If QLD safety regulation does not allow MPs to energise a site, then New Connections timeframes will prolong by several days with risk of additional cost to customers. • Industry focus on compliance with the new obligations and lack of progress at jurisdictional level for supporting regulation changes, such as safety cases, right to entry etc. may result in poor customer experience. Cutover • Time frame for cutover is not practicable: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc.). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. This seems to suggest the aggregated risks may not be fully understood. Comms • Communications plan to affected parties (i.e. Electricians, Customers) is still not finalised; expectation that AEMO will lead on this activity.
| Pacific Hydro / Tango | At risk | High | The timing and outcomes of the following outstanding PoC activities have the potential to impact the build, test and implementation phases: 1. MSATS - As Built Consultation 2. B2B - Translation tool technical details yet to be confirmed 3. Meter Churn Issues - recently raised and despite a paper being issued by AEMO, there are still concerns being raised. 4. Vic Government decision not to proceed with PoC. 5. Jurisdictional safety review of the remote Re-en/De-en process. There is also an issue with other Market changes, e.g. Retail Transfer Errors to take effect 3 August 2017, being introduced within the PoC delivery timeframe. 6. Internal Project delay for replacing current systems.
| People Energy | At risk | Medium | The overall project is at a medium risk due to constrained timelines for delivery against overall AEMO Delivery Timelines.VIC withdrawl from POC has introduced risk into System Scoping, Process changes and increased training.
| Pooled Energy | Within schedule | Medium | Project remains on track. Continuing to work through procedural and process changes. | [7 empty] | Project remains on track. Continuing to work through procedural and process changes.
| Red Energy & Lumo Energy | At risk | High | Business and customer activity is very high at the targeted cut-over time. Inconsistent approaches across industry creates increased activity and raises risk (eg. new connections, meter churn, faults and emergencies, expected approaches to in-flight transactions). Victorian approach is understood but the detail and specifics is not yet known (Order in Council not released) Other jurisdictional consequential legislative amendments are not yet understood (and unseen) which is adding further risks to the overall project. Continued discussion at the industry forums regarding participants not being ready in various forms, is reducing our confidence in a positive customer experience in the move to metering competition. This is also highlighted in AEMO's assessment of the overall project having a high risk rating. The lack of clarity regarding what will be done to change the risk rating at the industry level is amplifying the risk.
| Sumo Power |  |  | [AEMO Note - Only progress was provided on report - see details below]
| Simply Energy | Within schedule | Medium | The program has identified two keys risks: 1. Faults and Emergencies Process not confirmed by Distribution Businesses. 2. VIC Govt decision of deferral of metering competition has opened a few questions that's impacting our design and build, e.g. new connections process in VIC; Plan of approach for VICAMI meters post go-live (type 5 vs type 4 issue), etc. | [13 empty] | Simply Energy has progressed as per it's internal plan of Power of Choice Program of Work and have prioritised B2M changes in order to commence testing for r35 schema, targetting Market Trial phase to commence industry testing.
| Stanwell Corporation Limited | Within schedule | Low | Project progressing as planned.
| WINconect Pty Ltd | Within schedule | Low | Uncertainty about the implication of Victorian order in council relating to adoptions of POC changes. Practical implications for application of AER's NSP Exemption guidelines might be significant. Further uncertanty about application of ENM role in juristircitons that still require legislative arrangements to facilitate conteisibillity (QLD).
| Powershop | At risk | Medium | System build requirements have been documented and scoped for effort and complexity. A delivery schedule and resourcing is being formulated to meet the 1 December 2017 timeframe. There may be a necessity for some non-volume transactions to be undertaken manually using MSATS for the initial period post implementation. Delays to releasing final schema specifications delayed activity significantly. | [7 empty] | System build requirements have been documented and scoped for effort and complexity. A delivery schedule and resourcing is being formulated to meet the 1 December 2017 timeframe. There may be a necessity for some non-volume transactions to be undertaken manually using MSATS for the initial period post implementation. Delays to releasing final schema specifications delayed activity significantly.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Retail | Within schedule | Medium | Within schedule | Medium
| AGL Retailer Powerdirect | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Alinta Energy |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Aurora Energy | [8 empty] | At risk | Medium
| Energy Australia | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | High
| Ergon Energy Queensland (retail) |  |  |  |  | At risk | High
| ERM Power Retail | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| M2 Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Macquarie Bank Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Mojo Power Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Momentum Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
Next Business Energy
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro / Tango |  |  | At risk | High | At risk | High | At risk | High |  |  | At risk | High
| People Energy |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | At risk | Medium
| Pooled Energy |  |  | Within schedule | Medium
| Red Energy & Lumo Energy |  |  | At risk | High | At risk | High | At risk | High |  |  | At risk | High
Sumo Power
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Stanwell Corporation Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  |  |  | Within schedule | Low
| WINconect Pty Ltd |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Powershop |  |  | At risk | Medium | At risk | Medium |  |  |  |  | At risk | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy | Pooled Energy | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | WINconect Pty Ltd | Powershop | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Completed (100%) | 100% | 71% - 80% | 81% - 99% | 71% - 80% | Completed (100%) | 50% | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%) | 81% - 99% | Completed (100%) | 41% - 50% | 51% - 60% | 51% - 60% | 41% - 50% | 81% - 99% | Completed (100%) | 71% - 80% | 100%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | Completed (100%) | 100% | 41% - 50% | 71% - 80% | 61% - 70% | 41% - 50% | 50% | 81% - 99% | 41% - 50% | 71% - 80% | 71% - 80% | 61% - 70% | 51% - 60% | 31% - 40% | 31% - 40% | 11% - 20% | Not started (0%) | 71% - 80% | 71% - 80% | 71% - 80% | N/A
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 51% - 60% | Completed (100%) | 50% | 51% - 60% | 71% - 80% | 71% - 80% | 41% - 50% | 25% | 81% - 99% | 61% - 70% | 51% - 60% | 41% - 50% | 61% - 70% | 51% - 60% | 21% - 30% | Not started (0%) | 81% - 99% | Not started (0%) | 21% - 30% | 71% - 80% | 41% - 50% | 75%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 11% - 20% | 51% - 60% | 50% | 21% - 30% | 51% - 60% | 41% - 50% | 11% - 20% | 0% | 81% - 99% | 61% - 70% | 31% - 40% | 1% - 10% | 41% - 50% | 11% - 20% | 1% - 10% | 21% - 30% | Not started (0%) | Not started (0%) | 1% - 10% | 1% - 10% | 11% - 20% | N/A
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 21% - 30% | 51% - 60% | 25% | 31% - 40% | 41% - 50% | 11% - 20% | 21% - 30% | 0% | Not started (0%) | 61% - 70% | 31% - 40% | 31% - 40% | 11% - 20% | 11% - 20% | 1% - 10% | 11% - 20% |  | Not started (0%) | 31% - 40% | Not started (0%) | 41% - 50% | 25%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 31% - 40% | Completed (100%) | N/A | 31% - 40% | 51% - 60% | 1% - 10% | 61% - 70% | 25% | 51% - 60% | 71% - 80% | 71% - 80% | 41% - 50% | 61% - 70% | 51% - 60% | 31% - 40% | 21% - 30% |  | N/A | Completed (100%) | Completed (100%) | 71% - 80% | 25%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 11% - 20% | 41% - 50% | N/A | 1% - 10% | 1% - 10% | Not started (0%) | 1% - 10% | N/A | Not started (0%) | Not started (0%) | 51% - 60% | 1% - 10% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) |  | N/A | N/A | Not started (0%) | 71% - 80% | 0%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 81% - 99% | 11% - 20% | 50% | 61% - 70% | 71% - 80% | 41% - 50% | 31% - 40% | 25% | N/A | Completed (100%) | 51% - 60% | 61% - 70% | 51% - 60% | 41% - 50% | 11% - 20% | 51% - 60% |  | Not started (0%) | 31% - 40% | 41% - 50% | 71% - 80% | 0%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 25% | 51% - 60% | 41% - 50% | 1% - 10% | 41% - 50% | N/A | N/A | Completed (100%) | N/A | 51% - 60% | 31% - 40% | 51% - 60% | Not started (0%) | 41% - 50% |  | N/A | Not started (0%) | 41% - 50% | Completed (100%) | N/A
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | 0% | 11% - 20% | 21% - 30% | 31% - 40% | 41% - 50% | 0% | Not started (0%) | 31% - 40% | 21% - 30% | 21% - 30% | 1% - 10% | Not started (0%) | Not started (0%) | 11% - 20% |  | Not started (0%) | Not started (0%) | Not started (0%) | 41% - 50% | 0%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 71% - 80% | 25% | 61% - 70% | 71% - 80% | 71% - 80% | 31% - 40% | 25% | 81% - 99% | 41% - 50% | 41% - 50% | 51% - 60% | 71% - 80% | 21% - 30% | 21% - 30% | 31% - 40% | 31% - 40% | Not started (0%) | 61% - 70% | 61% - 70% | 41% - 50% | 75%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 99% | 51% - 60% | 0% | 31% - 40% | 71% - 80% | 31% - 40% | 31% - 40% | 0% | 71% - 80% | 21% - 30% | 11% - 20% | 21% - 30% | 41% - 50% | Not started (0%) | 11% - 20% | 11% - 20% | 1% - 10% | Not started (0%) | 21% - 30% | Not started (0%) | 51% - 60% | 25%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 11% - 20% | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | 0%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | 71% - 80% | 100% | 61% - 70% | 81% - 99% | 81% - 99% | 41% - 50% | 50% | 71% - 80% | 31% - 40% | 51% - 60% | Completed (100%) | 71% - 80% | 51% - 60% | 41% - 50% | 1% - 10% | 31% - 40% | 61% - 70% | 51% - 60% | 81% - 99% | 61% - 70% | 75%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 11% - 20% | 61% - 70% | 75% | 21% - 30% | 41% - 50% | 21% - 30% | 41% - 50% | 50% | 41% - 50% | 21% - 30% | 31% - 40% | 61% - 70% | 21% - 30% | 21% - 30% | 21% - 30% | Not started (0%) | 21% - 30% | 11% - 20% | 1% - 10% | 51% - 60% | 61% - 70% | 0%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 1% - 10% | 61% - 70% | 0% | 11% - 20% | 11% - 20% | Not started (0%) | 11% - 20% | 0% | 41% - 50% | Not started (0%) | 31% - 40% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | 21% - 30% | Not started (0%) | 0%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | 11% - 20% | 0% | 1% - 10% | 11% - 20% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | 0%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | 0% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | 11% - 20% | 0% | 1% - 10% | 21% - 30% | Not started (0%) | 11% - 20% | 25% | 71% - 80% | Not started (0%) | 21% - 30% | Not started (0%) | 21% - 30% | 1% - 10% | 1% - 10% | Not started (0%) | 11% - 20% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | 0%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | 0% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy | Pooled Energy | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | WINconect Pty Ltd | Powershop | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Completed | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed | At risk | Completed | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed | Completed | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | N/A
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Completed | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | At risk | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule |  | Within schedule | Within schedule | At risk | N/A
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | At risk | At risk | Within schedule | At risk | At risk | Not within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Not within schedule | At risk | Within schedule | N/A |  | At risk | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A |  | Within schedule | Completed | Within schedule | At risk
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | N/A |  | N/A | Within schedule | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | N/A |  | Within schedule | Within schedule |  | At risk
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | N/A | Within schedule | N/A | Within schedule | Within schedule | At risk | Within schedule | Within schedule | N/A |  | Within schedule | Within schedule | Within schedule | N/A
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A |  | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Within schedule | Within schedule | At risk | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Not within schedule | At risk | Within schedule | At risk |  | At risk | Within schedule | Within schedule | At risk
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Not within schedule | At risk | Within schedule | At risk |  | At risk | Within schedule | Within schedule | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | At risk | Not within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Completed | Within schedule | At risk | At risk | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | At risk | Within schedule | At risk |  | Within schedule | Within schedule | Within schedule | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Not within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | At risk | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | At risk | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk |  | Within schedule | Within schedule | At risk | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy | Pooled Energy | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | WINconect Pty Ltd | Powershop | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | High level impact assessment has been conducted. |  |  | A high-level assessment of necessary business operational process and systems changes is near completion. | Due to differing implementation approaches of participants, Reassessment of customer impacts is required at a DNSP level. | [7 empty] | Impact Assessment completed, but will need to be iterated pending consultation outcomes and changes. Procedure and meter type implication due to VIC derogation extension are not yet clear. Faults and Emergencies process not yet finalised
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Program established. Detailed plan in place and being tracked against. |  |  | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging. Additional changes to enable all other core operations post 1 December 2017 are being assessed. The aggressive timelines for systems build and testing, combined with contracting and establishment of an MC and the required implementation and testing combined systems is the basis of the 'at risk' status. | Re-development of DB specific implementation plans is required, due to variations in participant implementationa approaches. | As a retailer, EEQ is heavily reliant on contracted parties being ready from go-live date.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | The ACT Government is reviewing the ACT regulatory framework. |  |  | A detailed assessment of the revised legal and regulatory is significantly developed. In its current form the detailed assessment has provided the basis of Aurora Energy preparedness to date. The assessment continues to be informed by on-going AEMO market procedure consultation although remaining uncertainty over rule and procedure operations ensures this is still considered 'at risk'. |  | Queensland jurisdictional safety requirements are yet to be addressed. |  | scheduled and commenced. |  |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines | Jurisdictional requirements for safety in relation to remote re-en/de-en unconfirmed. |  |  | Await Victoria Order in Council and assessment of any potential changes required for Victoria |  | Awaiting jurisdictional safety regulators to publish requirements |  | Waiting for guidance on ENM role in Victorian and Queensland.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | Underway | Preliminary advice has been sought with regards to regulatory compliance. A key challenge for Aurora Energy is to consider the wider/indirect regulatory implications of metering competition on business-as-usual activities (particularly given the existing regulatory framework was developed in the context of type 6 metering). |  | Queensland jurisdictional safety requirements are yet to be addressed. |  | not yet scheduled. |  |  | Dependency on participation in industry testing |  | Policy changes/decisions still being derived | Vic Government decision on PoC and timing of regulatory changes to reflect the decision not to proceed with PoC. | [6 empty] | Waiting for guidance on ENM role in Victorian and Queensland.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Awaiting MC contracts to be issued by the relevant parties. | Flagging risk due to the number of commercial agreements required. | Commenced RFP Issued Draft Services Agreemnt avaiable Review of (MM&C&I)Customer contracts underway | Activity has commenced for customers and vendors as part of POC implementation. The major challenge is to develop and execute contractual arrangements with a Metering Coordinator, which will have to establish metering service capability in Tasmania where it currently does not exist. | Scheduled activties at risk due to complexities of numerous participants | These processes have commenced. Significant complexity due to lack of precedent in negotiating agreements of this nature. Contracts not progressing as planned. | The number of contracts and counter-parties put this item at risk. | not yet scheduled. |  |  | Dependency on partnering with registered MC(s) |  | Overall strategy has been developed and endorsed. Generic Meter provider contract drafted for new providers and contracts in play for current providers. | Requirements/services for various Service Providers yet to be finalised. Discussions with various Service Providers have commenced. Uncertainty as to which MCs will be ready for 1 Dec a major concern. |  |  | Internal management of this item |  | Meter Churn (Package 3 outcome) is causing some issues in finalising high level agreements. |  |  | Awaiting for MC's to be accredited. Discussions have commenced
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Assessment of accreditation activities complete. Preparing for Industry test. |  | Contractual arrangements to support Accreditation requirements through a nominated MC Certification scheduled as part of Industry Testing | Aurora Energy will be required to receive accreditation for using the B2B e-hub. The newly published B2B E-Hub Accreditation and Revocation process is currently being considered. The timeline and uncertainty for accreditation and registration activities of other participants (specifically, the Metering Coordinator role) also impacts on Aurora Energy's planning. Dialogue with the jurisdictional safety regulator has commenced. |  |  |  | unclear testing registration requirements and impacts at this time. Ehub application is delayed. |  |  |  |  | Underway for new Market Roles | Despite 5.2, B2B accreditation is still required and for that purpose we still believe we will be in a position to complete in the required timeframe. |  |  | Internal management of this item
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Accreditation materials reviewed and application submitted. |  | Certification scheduled as part of Industry Testing | Fulfilment of the accreditation obligations is now being considered following AEMO publishing final version of the 'B2B Accreditation and Revocation Process'. | [8 empty] | Planning and preparation in progress | B2B e-Hub accreditation application submitted to AEMO Support Hub. |  |  | Internal management of this item
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Detailed assessment in progress and will complete within the next week. |  | Operating model development underway | This has commenced and will be finalised following with the detailed assessment of operational and systems changes. |  |  |  | not yet scheduled. |  |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines | At risk - Internal replanning in progress, including redeployment of resources due to 5.2. |  |  | Internal management of this item
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Operating model development underway | The recruitment of specialist human resources to cater for the rule change is progressing as the need to fill key project roles arises. A key challenge is the availability of internal business subject matter experts to assist in change management. | [8 empty] | Policy changes/decisions identified | Additional PoC resources on board. |  |  | Internal management of this item
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [8 empty] | Training requirements are currently being assessed as part of the business process, change management and system planning. |  | Training Needs Analysis draft complete. Staff training scheduled for Oct-Nov |  | not yet scheduled. |  |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing |  | Training requirements and resourcing determined and magnitude of change is understood, change planning started |  |  |  | Internal management of this item
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Nearing completion - additional workshop scheduled to complete with NSW DB's. |  | Continuing | All impacted service order, B2B & B2M and business processes have been identified. Assessment of current and future processes is underway to enable gap analysis and identify process and system changes. Possible future changes puts the delivery scope and timeline at risk. | Detailed process validation with individual Participants resulted in the requirement to redesign some solutions, with likely manual effort and customer impacts. | The significance of the changes to our billing system and the added complexity of developing a mechanism to address non-PoC areas not subject to the provisions in Chapter 7 of the NER (isolated networks) is challenging in the timeframes. EEQ is also reliant on contracted parties being ready for go-live. Additional complexities and time constraints also as a result of negotiating ring fencing strategy / waivers with the AER which is also impacting contract negotiations. | The scope of change puts this item at risk. | commenced and in schedule |  |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension not yet clear. Faults and Emergencies process not yet finalised; | No longer within schedule, regression due to 5.2 with likelihood of having to use current system post 1 Dec, internal replanning in progress. |  |  |  |  | VIC decision has posed some risk in detailing internal processes; Faults and Emergencies process is not confirmed by the Distribution businesses, posing a bigger risk on retailers to implement end to end process.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Majority of processes reviewed and finalised - awaiting workshop with NSW DB's to complete. |  | Commenced | Future business processes are currently being developed using the details from Work Package 1 and 2, as well as the B2B procedures. The timeline for implementation and on-going procedural uncertainty is the basis for Aurora Energy reporting 'at risk'. | As above |  | The scope of change puts this item at risk. |  |  |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension not yet clear. Faults and Emergencies process not yet finalised; Engagement with networks is planned to confirm smooth transition. | No longer within schedule due to system delay per 5.2 and 4.1. Pending outcome of design workshops for B2B Translation Tool. This is further complicated by the Vic Government decision not to proceed with PoC. |  |  |  |  | VIC decision has posed some risk in detailing internal processes; Faults and Emergencies process is not confirmed by the Distribution businesses, posing a bigger risk on retailers to implement end to end process.
4.3 |  | The validation of business processes during industry testing | [8 empty] | Activity has not yet started. |  |  |  | not yet scheduled. |  |  |  |  | Test planning commenced, detail on industry testing as yet unclear | At risk due to 5.2/4.1. |  |  |  |  | Due to commence in July 2017 |  | Not yet started testing fro ENM role.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Vendor is looking for final arrangements out of the victorian derrogation and meter classification to finalise requirements and design documents DB interpretation of proceedures may require additional work. | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging systems. The aggressive timeframe impacts on the ability of Aurora Energy's key vendors (including, but not limited to, prospective Metering Coordinators) to deliver the required system changes. | Likelihood of rework after detailed process analysis with other participants. | System designs complete. System build commenced. |  | Vendor at 47% completion of overall project plan |  |  | System development is reliant on external vendor, any delays in final market procedures will impact readiness activities. |  | Detailed impact assessment of system changes has completed. Review of updated B2B procedures in progress. VIC derogation extension impact assessment ongoing. Schema version considered for B2B will be R36 and B2M will be R35. Transaction Acknowledgment to match the version of the request | Pending outcome of design workshops for B2B Translation Tool. This is further complicated by the Vic Government decision not to proceed with PoC. |  |  |  |  | Business requirements Complete
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | The first of a number of builds has been delivered. |  | Almost Complete. | Aurora Energy has engaged its key market system vendors. System build has commenced for essential market connectivity and system functionality for 1 December 2017. Further priority system functionality is in design phase. Systems changes will still be impacted by the any further changes to the B2B/B2M environment as part of Work Package 3. | Non-alignment to B2B guidelines has not been addressed at an industry level, which results in risk to outcomes of industry test and risk of rework to system changes. |  |  | vendor at 15% of retail sys build plan |  |  |  |  | Systems development in progress | Internal Project delivering new system (replacing current systems) has been delayed, directly impacting PoC. |  |  |  |  | Solution Design workshops have commenced with vendors, functional specs underway
5.3 |  | The internal testing of market systems for your business | [5 empty] | Acceptance testing of the first build is in progress. SIT will commence as planned this week. |  |  | Aurora Energy has completed a test strategy, on-boarded test resources is in the process of preparing test cases, and has started the initial phases of stystem testing. | As above | [7 empty] | Test resources onboarded and test planning started | As per 5.2 |  |  |  |  | Commenced for B2M
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | Aurora Energy was unable to participate in AEMO's first round of testing due to no other participants being available. eHub connectivity will be tested in Phase 2 of AEMO's market interface testing. While Aurora Energy is currently on schedule to meet the timing of AEMO's market system testing opportunities, it is reliant on both key system vendors and other participants to perform testing and therefore continues to consider this to be 'at risk'. | As above | [7 empty] | Test resources onboarded and test planning started | As per 5.2 |  |  |  |  | Scheduled to commence in August 2017 |  | Not yet started testing fro ENM role.
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | Aurora Energy is planning to separately initiate performance testing, as distinct from market interface testing, scheduled for October 2017. Aurora Energy is reliant on key system vendors to perform performance testing and therefore continues to consider this to be 'at risk' | AEMO Industry Test Strategy calls performance testing out of scope. AEMO has indicated it will complete performance testing internally and will not provided outcomes to Participants. | [7 empty] | Test resources onboarded and test planning started | As per 5.2 |  |  | Target 2 and 3 round of industry testing. |  | Scheduled to commence in August 2017 |  | Not yet started testing fro ENM role.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Commenced | A Transition Plan will be completed once AEMO packages and commercial agreements with Metering Coordinator(s) are finalised. Aurora Energy has started discussions with TasNetworks regarding transition and cutover planning. | EA Transition and Cutover planning progressing. Residual risks still exist around B2B items out of scope for AEMO (such as Fault management, Emergency Procedures & Faults etc) and Market contingency planning. | [5 empty] | Transition plans are dependent on timely delivery of earlier program stages |  | Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, cyclone, etc.). Transition & Cutover planning will take this into account. | Internal cutover planning commenced, based on output from ITCFG. |  |  | Transition and cut over working group outcomes are not yet finalised, as such, this is impacting the preparation of our business processes. Of particular concern are: - New connections process - initial MC contracts are not yet understood - readiness of competitive MCs |  |  |  | Uncertainly over process for bulk role change of existin embedded networks before 1 December 2017.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [8 empty] | Aurora Energy has started discussions with TasNetworks regarding transition and cutover planning. | [8 empty] | Transition planning and scheduling cannot be accurately determined until Design & Build is completed. Bulk Data conversion for Meter Standing Data (MC/ENM role, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our Build / Test activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; | [7 empty] | Awaiting guidance on cut over plan for existing embedded netwokrs.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power Pty Ltd | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy | Pooled Energy | Red Energy & Lumo Energy | Sumo Power | Simply Energy | Stanwell Corporation Limited | WINconect Pty Ltd | Powershop | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms, within the context of the timeframe and procedural uncertainty. | [8 empty] | Progressing with working assumptions.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Aurora Energy has implemented a program of work to effectively and efficiently work towards market compliance.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | ActewAGL remains concerned at the lack of jurisdictional safety information. This is of particular relevance when looking at remote re-ens and de-ens given we are yet to be informed as to whether or not they will be allowed. Commonwealth legal framework is reviewed and on track. |  |  | Aurora Energy has implemented a program of work to interpret and implement the POC reforms that factors in the challenging timeframe and procedural uncertainty. |  | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office. At this stage it is unlikely that remote re-energisation will be available to retailers on 1 December 2017. | [7 empty] | Monitor jurisdictional saftey discussion. |  |  |  |  | Internal assessments have commenced
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Internal documents related to Cth legislation are listed by business unit. Dates for update and review have been set. |  |  | Aurora Energy is liaising with the Tasmanian Government to identify jurisdictional requirements that require amendment to facilitate metering competition. |  | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office. Lack of jursidictional changes represents a risk to EEQ. AEMO is currently addressing jurisdictional changes to Metrology Part A. | [7 empty] | Closely monitor Vic Government's progress on this matter. Meetings with VicDBs and documentation of planned transaction processes received and under review.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [6 empty] | Escalated and added resource to commercial preparations. |  | Aurora Energy is part way through a procurement proecss for securing a Metering Coordinator for small customers. |  | Ensure contingencies are in place. | [6 empty] | Origin has onboarded additional Business and Technology resources | Engaging with MCs to obtain details about their planned offerings and draft terms and agreements. |  |  |  |  | Package 3 scope should hopefully resolve the issues raised by the industry, however we're awaiting for the outcome.
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy has submitted its accredition application and is proceeding on the assumption that accreditation will be received. | [9 empty] | Dependent on AEMO delivery of B2B Translation Tool, and our implementation and testing. Design workshops completed and AEMO should be highly commended with the technical solution and detail provided.
2.5 |  | The fulfilment of accreditation and registration obligations | [17 empty] | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | Aurora Energy has establisehd the core group of its Testing team and will continue to expand its testing resoruces over the coming months.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [8 empty] | Aurora Energy continues to invest considerable effort in participating in AEMO procedural consultation. Aurora Energy is proceeding on the basis of the currently available information and must continue to manage the risk of final procedures changing. |  | Increasing internal resources to the project. Series of Assumptions Workshops with associated market participants continuing to ensure alignment of systems and market messaging. | [12 empty] | Awaiting VIC Order in Council; Distribution businesses to provide their positions as soon as possible especially around the faults and emergencies processes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [23 empty] | Awaiting VIC Order in Council; Distribution businesses to provide their positions as soon as possible especially around the faults and emergencies processes.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [8 empty] | Aurora Energy is in the process of gathering detailed business and system requirements and engaging with key vendors. | [9 empty] | Engaging with other small retailers and AEMO directly. Proof of Concepts for technical implementation of Translation Tool undertaken successfully. Closely monitoring Vic Government's progress on the regulatory changes.
5.2 |  | The development and build of appropriate market systems for your business | [8 empty] | Aurora Energy continutes to proactively manage its key market system vendors. | [9 empty] | Replanning in progress, with the view of being market compliant for 1 Dec by using the B2B Translation Tool.
5.3 |  | The internal testing of market systems for your business | [18 empty] | As per 5.2
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [18 empty] | As per 5.2
5.5 |  | The validation of performance of market systems during industry testing | [18 empty] | As per 5.2
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [17 empty] | Transition & Cutover planning will take this into account.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Retailer Participation
References:
[6 empty] | AEMO | http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Participant-information/Current-participants/Current-registration-and-exemption-lists
[6 empty] | AER | https://www.aer.gov.au/retail-markets/authorisations/public-register-of-authorised-retailers-and-authorisation-applications
[6 empty] | ESC | http://www.esc.vic.gov.au/project/energy/2075-licensing/
Retailer | On Jul 2017 Report? | On Jun 2017 Report? | On May 2017 Report? | On April 2017 Report? | On March 2017 Report?
1st Energy Pty Ltd | No | No | No | No | No
ActewAGL Retail | Yes | Yes | Yes | Yes | Yes
AGL | Yes | Yes | Yes | Yes | Yes
Alinta Energy | Yes | Yes | Yes | Yes | Yes
Aurora Energy | Yes | Yes | Yes | Yes | Yes
Blue NRG Pty Ltd | No | No | No | No | No
Click Energy Pty Ltd | No | No | No | No | No
Covau Pty Limited | No | No | No | No | No
COzero Energy Retail Pty Ltd | No | No | No | No | No
Diamond Energy Pty Ltd | No | No | No | No | No
Energy Locals Pty Ltd | No | No | No | No | No
EnergyAustralia | Yes | Yes | Yes | Yes | Yes
Enova Energy Pty Ltd | No | No | No | No | No
Ergon Energy Queensland (retail) | Yes | Yes | Yes | Yes (using March report) | Yes
ERM Power Retail Pty Ltd | Yes | Yes | Yes | No | No
Globird Energy Pty Ltd | No | No | No | No | No
Lumo Energy (reporting with Red Energy) | Yes | Yes | Yes | Yes | Yes
M2 Energy Pty Ltd | Yes | Yes (using May report) | Yes | Yes | Yes
Macquarie Bank Limited | Yes | Yes | No | No | No
Mojo Power Pty Ltd | Yes | Yes | Yes | Yes | Yes
Momentum Energy | Yes | Yes | Yes | Yes | Yes
Next Business Energy Pty Ltd | Yes | No | No | No | No
Online Power and Gas Pty Ltd | No | No | No | No | No
Onsite Energy Solutions Pty Ltd | No | No | No | No | No
Origin Energy | Yes | Yes | Yes | Yes | Yes
Pacific Hydro / Tango | Yes | Yes | Yes | Yes | Yes
People Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes
Pooled Energy Pty Ltd | Yes | Yes | Yes | Yes | No
Powerdirect Pty Ltd (reporting with AGL) | Yes | Yes | No | No | No
Powershop Australia Pty Limited | Yes | No | Yes (using April report) | Yes | No
Progressive Green Pty Ltd | No | No | No | No | No
Qenergy Limited | No | No | No | No | No
Red Energy | Yes | Yes | Yes | Yes | Yes
Sanctuary Energy Pty Ltd | No | No | No | No | No
Simply Energy | Yes | Yes | Yes | Yes | Yes
SparQ Pty Ltd (Sumo Power) | Yes (using June report) | Yes | No | No | No
Stanwell Corporation Limited (Stanwell Energy) | Yes | Yes | Yes | Yes | No
WINenergy Pty Ltd (WINenergy) | Yes | No | No | No | No

## Distributor Reports
| 2017-07-10 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule | Medium | For this reporting period the project remains heavily focussed on development and testing activities. AAD has commenced the test cycle 2 of 6. Review and revision of documentation continues and is approximately 47% complete. AAD is now shifting its attention from procedural documents and commencing a detailed revision of all online materials and other supporting documentation. In depth workshops are commencing with retailers active in the ACT market to establish a coordinated transition plan. Total project progress is estimated at 37%. | [7 empty] | [Initial MC comment]: AAD has submitted the required information (for initial MC) to AEMO and is awaiting a response. [Risk rating: Low] | [5 empty] | Accreditation transfer and registration starting 2 March is a risk area and it is noted that AEMO will still be developing systems and processes at the time industry is required to start this process. AAD has now submitted the required information for accreditation as the initial MC for type 5, 6 and 7 metering installations. The B2B eHub requirements have been released and AAD has provided the required documentation to AEMO. The readiness of AAD to interface with the AEMO B2B eHub is a significant risk. In the absence of information, the system changes required to facilitate this new data flow is undefined. It is noted AEMO have 12 mths to develop this and Industry only have 3.5 mths to implement. There is a disparate timeframe for Industry to modify, test, put into production and this is noted as a major area of concern for AAD. AAD has noted that AEMO is making a "planning assumption" of go live on 4 December allowing for cutover activities to occur on the weekend of 2/3 December. AAD welcomes clarification on this point and is working to 1 December 2017 in the absence of formal notification of a delay.
| Ausgrid | At risk | Medium | We have established a number of formal ICT projects and assigned resources. A number of significant IT rebuilds are required in order to facilitate the new B2B, CATS and new minimum specification requirements. New interfaces for the customer are under development to assist our customers in operating in the POC space | [7 empty] | Issues noted above (section B) impact on all these categories.
| AusNet Services | Within schedule | Medium | On track for 1st December cutover and go-live. Both the project status and risk profile have improved over the last month. This is due to the fact that a number of Industry wide issues have now have a path to resolution (EVM, Industry Transition, Industry Testing). Internal program continues to progress well. Other participant readiness is increasingly at risk. AusNet Services has significant dependencies on other participants, which may cause our risk to increase again in future months. | [7 empty] | Refer to overall comment.
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | At risk | Medium | CitiPower/Powercor is continuing to progress its build/test phase and successfully participated in Phase 1 industry testing. CitiPower/Powercor is also actively participating in industry planning for market trials and 1 December 2017 industry transition and cutover. A review was undertaken following the finalisation of market procedures and business requirements which identified a significantly greater development effort than originally forecasted and planned. Our system development & testing program has been considerably increased and replanned to achieve readiness for market trials and a 1 December 2017 go-live compliance. Program timing is challenging with no tolerance for delays or further requirement changes. | [7 empty] | The Victorian Government has decided that distributors will be required to continue to install remotely read interval metering after 1 December 2017 compliant with the Victorian AMI functionality and service levels specifications and that existing and new/replacement AMI metering will be continue to be classified as Type 5 metering. In line with this decision, CitiPower and Powercor will not making any changes to the how we classify either existing or new/replacement AMI meters in MSATS, nor any changes to our meter data validation and/or substitution methodologies. Victorian deferral arrangements are yet to be finalised in Government Orders.
| Endeavour Energy | At risk | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures. The B2B procedures requires significant system and process changes, however there is only 6-7 months to design and develop and to test with the market to achieve accreditation. This short timeframe increases the risk on quality vendor delivery. It is noted that registration as a B2B e-Hub Participants is required before the B2B e-Hub can be used. This registration process is also at risk as there is a dependency to demonstrate system compliance with the B2B procedures. AEMO facilitated a workshop on the meter churn process for participants to highlight issues and more efficient process options. AEMO later clarified that there will be no changes to the procedures for the meter churn process. In addition the MSATS procedure does not allow the existing MP or MDP to object where there is only a change in the MC. This puts Enedeavour Energy in a position where we have no choice but to provide MP and MDP services when a contestable MC is appointed to a NMI. This means that Enedeavour Energy, through no fault of its own, may be noncomplaint with the rules and the ringfencing guideline. The final determination for the "as built" consultation for AEMO procedures will not be published until 30 November 2017 which leaves no time to implement any changes for market start on 1 December 2017. To mitigate this we are actively participating in the various working groups including the PoC-WG, B2BWG, ITWG, RWG and SWG to ensure that AEMO procedures and B2B procedures supports the metering contestability and embedded networks rule changes in the most effective and cost efficient manner, and to only include transactions and obligations required for go live as a priority. We intend to seek clarification from the AER about our obligations with regards to the meter churn process. | [7 empty] | See above comment | [5 empty] | This report is for Endeavour Energy as at 30 June 2017. Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5, 6 & 7 metering installations from 1 December 2017. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. The activities for the Market Systems testing and cutover are dependent on the development and build of the appropriate market system which is currently at risk.
| Energex Ltd. & Ergon Energy Corporation Ltd. | At risk | Medium | The Distribution project is tracking slightly behind its intended schedule. This is recoverable and the project will meet 1 December 17 compliance requirements due to a phased implementation approach. The project has commenced its build and test phase and is progressing the system integration testing in priority order. Similar to last month, the projects key focus remains on confirming assumptions with retailers and MC’s on the mutual interpretation of B2B procedures. Joint coordination across multiple parties’ remains a contentious issue, requiring a collective agreement to safety ensure continuity of service to customers. | [7 empty] | The magnitude of change in the final version of the B2B Procedures was larger than expected. The project is currently 'At risk'. It is therefore undertaking a phased implementation approach with focus on the delivery of high priority transactions initially. Should build and test not progress exactly as planned due to compressed timeframes, manual work arounds remain a viable option for low priority transactions to meet 1 December 17 compliance.
| Essential Energy | At risk | High | Essential Energy's PoC program is progressing, with system changes on the critical path to deliver compliance by 1 December 2017. Timing is very tight deliver required systems changes to enable Essential Energy to participate in B2B industry testing from August 2017, with no tolerance for delays. Essential Energy is working closely with vendors to ensure required systems are delivered on time with internal testing completed in readiness for industry testing. Additional resources have been assigned to assist in supporting program delivery. | [7 empty] | [Distributor]: Risk rating upgraded to high due risks associated with systems delivery in preparation for industry testing from August 2017. Program schedule is tight and does not provide tolerance for any delays. [Meter Provider]: Risk rating low [Meter Data Provider]: Risk rating is classified as moderate for systems changes to support amended B2B framework, including to receive and process meter exchange information to enable timely publishing of final readings for Type 5 & 6 meters. | [5 empty] | Essential Energy will be an Initial MC, MDP and MP for Type 5 and 6 meter installations connected as at 1 December 2017. Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Networks | Within schedule | Medium | With 5 months to go-live on 1 December 2017, JEN is ready for bilateral testing and for industry testing. The industry is currently working through risks associated with 1. A lack of end-to-end understanding of market operation and work practices between participants requires a workshop session facilitated by the industry program to resolve any procedural or build differences prior to industry testing; 2. Cutover and transition planning to complete in July to confirm there is no bow wave of transactions and go-live readiness criteria is defined; and 3. confirmation that all retailers who have customers of the JEN network are ready for 1-3 December 2017 go-live without manual intervention. Until these partner readiness risks are clarified within the industry program, the risk to the JEN Program will remain AMBER. | [7 empty] | With 5 months to go-live on 1 December 2017, JEN is ready for bilateral testing and for industry testing. The industry is currently working through risks associated with 1. A lack of end-to-end understanding of market operation and work practices between participants requires a workshop session facilitated by the industry program to resolve any procedural or build differences prior to industry testing; 2. Cutover and transition planning to complete in July to confirm there is no bow wave of transactions and go-live readiness criteria is defined; and 3. confirmation that all retailers who have customers of the JEN network are ready for 1-3 December 2017 go-live without manual intervention. Until these partner readiness risks are clarified within the industry program, the risk to the JEN Program will remain AMBER.
| SA Power Networks | At risk | Medium | SAPN working towards ensuring minimum market compliance will be met. SAPN are facing significant challenges due to the limited market timeframes, this is impacting the development and build phase of our internal system, which will result in delays to our final state internal business capability. | [7 empty] | Refer to overall project status and Section 5.2
| TasNetworks | At risk | High | TasNetworks work progrm is to be ready for the 1st December 2017. The amount of change to be delivered in the timeframe is greater than anticipated as delivery timeframes are highly compressed. TasNetworks is undertaking a replanning exercise and taking a risk based approach on delivery which will have a flow on effect to processes and change management activities. The uncertainty about who the other market participants will be, in Tasmania, is leaving little time to complete all business readiness activities before the 1st December. Market system software testing has commenced.
| United Energy | Within schedule |  | Internal preparations continue to progress well. The core solution has been developed, and end-to-end integration testing is proceeding smoothly. The risk rating reflects the pending finalisation of the changed Vic Govt Order-in-council, general concerns about industry readiness, and the cost and operational impact of any potential delay to the go-live date. | [7 empty] | UE operates in Victoria only. Jurisdictional status reflects overall position. | [5 empty] | Key concerns regarding UE (and industry) readiness are as follows: 1) The Victorian Government has advised that 1: UE's role as MC for new meters after 1 Dec will be on the basis of existing regulated services, 2: New meters after 1 Dec will need to meet only the Vic AMI specifications and 3: New meters after 1 Dec will be classified as Type 5 MRIM, per current practice, and existing meters will remain Type 5 MRIM. On 5 June, the Vic Govt issued an 'AMI Order amendments outline document', which describes the specific changes and the Orders to which they apply. UE provided feedback accordingly and is awaiting the draft Order (now expected mid-July 2017). Until the amended Orders are finalised, the possibility of unexpected requirements or obligations remains. 2) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. UE's compliance in this area may also be dependent on existing child metering services being transitioned to meter providers on or by 1 Dec 2017, although this is yet to be confirmed and is partly dependent on the Vic Govt amended Orders. If transition is required, it will be an activity over which UE does not have full control, particularly given UE's understanding that there are currently no accredited Embedded Network Managers in the market as at mid July 2017. 3) UE is concerned that the lateness of procedures finalisation and the Victorian deferral details, plus the complexity and scale of testing with the increased number of market participants may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections and supply processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers. It is important that higher participation in readiness reporting and in the remaining testing phases is achieved for a robust 1 Dec 17 start. 4) UE is concerned that lack of readiness of some industry participants and/or poor results during industry testing may lead to the go-live being delayed from 1 Dec 2017 until some time in 2018. If this occurs, the cost incurred by UE to retain the appropriate project personnel during the delay will be significant. There will also be a negative impact on operational teams, with readiness preparations having to be interrupted and/or repeated, and recruitment of additional operational personnel being impacted.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule | Medium
| Ausgrid |  |  | At risk | Medium
| AusNet Services | [10 empty] | Within schedule | Medium
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | At risk | Medium
| Endeavour Energy |  |  | At risk | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | At risk | Medium
| Essential Energy |  |  | At risk | High
| Jemena Electricity Networks | [10 empty] | Within schedule | Medium
| SA Power Networks | [6 empty] | At risk | Medium
| TasNetworks | [8 empty] | At risk | High
| United Energy | [10 empty] | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | 81% - 99% | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 61% - 70% | 81% - 99% | Completed (100%) | Completed (100%) | 81% - 99% | 81% - 99% | 71% - 80% | Completed (100%) | 81% - 99% | 51% - 60% | Completed (100%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 51% - 60% | 81% - 99% | 71% - 80% | Completed (100%) | 81% - 99% | 61% - 70% | Completed (100%) | Completed (100%) | 81% - 99% | 41% - 50% | 81% - 99%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 41% - 50% | 21% - 30% | 51% - 60% | 41% - 50% | 41% - 50% | 41% - 50% | 61% - 70% | Completed (100%) | 31% - 40% | 31% - 40% | 81% - 99%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 31% - 40% | 51% - 60% | 41% - 50% | 51% - 60% | 61% - 70% | 21% - 30% | 31% - 40% | 61% - 70% | 21% - 30% | 21% - 30% | 71% - 80%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | 81% - 99% | Completed (100%) | 51% - 60% | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | 21% - 30% | 71% - 80% | 81% - 99%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 61% - 70% | 1% - 10% | 31% - 40% | Not started (0%) | 21% - 30% | 51% - 60% | 21% - 30% | 71% - 80% | 1% - 10% | 21% - 30% | 41% - 50%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 51% - 60% | 81% - 99% | Not started (0%) | 71% - 80% | 61% - 70% | 21% - 30% | Completed (100%) | 31% - 40% | 21% - 30% | Completed (100%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 31% - 40% | 31% - 40% | Not started (0%) | 71% - 80% | 31% - 40% | Not started (0%) | N/A | 1% - 10% | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 21% - 30% | 21% - 30% | 21% - 30% | Not started (0%) | 21% - 30% | 11% - 20% | Not started (0%) | 51% - 60% | 1% - 10% | 1% - 10% | 41% - 50%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 41% - 50% | 51% - 60% | Completed (100%) | 81% - 99% | 81% - 99% | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | 41% - 50% | Completed (100%)
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 41% - 50% | 11% - 20% | Completed (100%) | 81% - 99% | 81% - 99% | 71% - 80% | 1% - 10% | 71% - 80% | 81% - 99% | 11% - 20% | Completed (100%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 31% - 40% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 99% | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | 41% - 50% | 81% - 99% | Completed (100%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 31% - 40% | 21% - 30% | 41% - 50% | 41% - 50% | 1% - 10% | 41% - 50% | 41% - 50% | Completed (100%) | 21% - 30% | 31% - 40% | Completed (100%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | 1% - 10% | 1% - 10% | 21% - 30% | 31% - 40% | Not started (0%) | 31% - 40% | 21% - 30% | 81% - 99% | 21% - 30% | 1% - 10% | 51% - 60%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | 61% - 70% | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | N/A | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 11% - 20% | 1% - 10% | 21% - 30% | 11% - 20% | 1% - 10% | 21% - 30% | 1% - 10% | 71% - 80% | 11% - 20% | 1% - 10% | 11% - 20%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | 21% - 30% | Not started (0%) | 1% - 10% | 1% - 10%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | At risk | Completed | Completed | Completed | Within schedule | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk | Completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | At risk
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | At risk
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Completed | Within schedule | At risk | Completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | At risk | Completed
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Completed
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Completed | Completed | Within schedule | At risk | At risk | Completed | Completed | Within schedule | Within schedule | Completed
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | Within schedule | At risk | At risk | At risk | At risk | Completed | At risk | At risk | Completed
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | At risk | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | The high level impact assessment is complete. Some gaps may be identified as part of the more detailed program of works to be carried out in the period through to December 2017. |  |  |  |  | High-level scope and requirements documents have received business approval. Future state processes for Priority Services have also received business approval. Business review of the Organisation Impact assessment has commenced. |  |  |  | Further updates pending the consultation process on pack 3.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD has commenced the second of six test cycles. Progress is slower than expected and AAD is ramping up resources with the addition of up to two more testers and the commencement of weekend work. Business processes and procedures are approximately 47% complete and focus has now shifted to online materials and other supporting documentation. |  |  |  |  | The Business Readiness Framework has been finalised and is currently in the process of gaining formal approval. |  |  | Continuous monitoring of established plans | Timelines are compressing and a risk based approach being taken for work that needs to be done. There is also a reliance on other industry participants being ready.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | A high level assessment of the legal obligations will continue throughout the project as AEMO finalises the program requirements. | Final reviews in place |  |  |  | Ongoing activity - currently under review by organisational specialists. |  |  | Monitor of changes from WP3 for impacts and changes | Progressing T&C's | The Vic Govt. has advised that: 1: UE's role as MC for new meters after 1st of Dec will be on the basis of existing regulated services 2: New meters after 1 Dec will need to meet only the Vic AMI specifications. 3: New meters after 1 Dec will be classified as Type 5 MRIM, per current practice, and existing meters will remain Type 5 MRIM. However this item cannot be considered complete until the Vic Govt Order-in-council has been finalised.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | During the period February - April 2017 AAD has commenced work on legal agreements relating to customer contracts, initial MC agreements with retailers, terms and conditions for provision of data/information to customers, etc. This work will continue until approximately September. | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - the project is working with the internal regulatory team to ensure all regulatory requirements are met. |  |  | In progress |  | This work is complete, but is based on the outcomes expected in the Vic Govt Order-in-Council. If these differ from the positions presented to date, rework will be required which may impact readiness.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | As above. | Drafting in progress with Legal team. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - amendments under consideration by each contract owner, updates will be made using existing procurement and contractual processes. Assessment of new agreements/contracts also ongoing. |  | The draft OIC notes suggest that MC contract T&Cs are not required before 1 December for Victorian Distributors. Awaiting clarification. | In progress | DNSP T&C's | Plans are in place to address the commercial implications, and resourcing is now in place. Work on the Initial MC Contract (required by 1 Sep) is nearing completion. Assuming the Vic Govt Order-in-Council reflects the advice received to date. It is important that the Victorian Orders are finalised in July or early August to ensure that the 1 Sept MC contract is consistent with the National and Vicotiran arrangements. No other major commercial preparations are required.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | AAD has now submitted the required documentation to AEMO for B2B eHub accreditation. Application for accreditation as the initial MC has now been submitted to AEMO and AAD is awaiting a response. | In progress. |  | Note: Following the state government decision to defer the introduction of metering competion in Victoria, CitiPower and Powercor will need to further assess our accrediation and registrations requirements. |  | The project is clear on the accreditation activities required for compliance and is well progressed with its associated obligations. |  | Waiting for AEMO to confirm JEN eHub accreditation date. | In progress |  | Based on Vic Govt advice that existing and new meters are to remain Type 5 MRIM, it is assumed that accreditation as a Type 4 MDP is not required for UE. Once this is confirmed via the Vic Govt Order amendments, this work item will be marked as complete. Accreditation for use of e-Hub is required and preparations are underway.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | As above. | In progress. |  | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | The project is clear on the accreditation activities required for compliance and is well progressed with its associated obligations. |  |  | In progress |  | Accreditation for use of e-Hub and registration as MC for Type 5, 6 and 7 meters will be completed in accordance with AEMO requirements. The "at risk" flag reflects the remaining uncertainty about accreditation as a Type 4 MDP (which UE is assuming is not required).
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | AAD is recruiting additional resources to back fill operational roles in anticipation of future testing requirements commencing late June 2017. In addition, a detailed assessment of ongoing operational resource requirements has commenced (approximately 50 per cent complete) to ready the business for the transition and post PoC go-live activities. | Awaiting outcome of updated policies and work instructions to complete. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - Impact assessment currently under business review. |  |  | In progress | Timelines are compressing and decisions on operational roles will be made later in the program
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | AAD is currently recruiting additional people to fulfil the operational duties affected by project specific activities. Other recruitment requirements are being assessed as above. | Relies on the above. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - Impact assessment currently under business review. |  | Not required for Jemena - out of scope. | No major change from previous status |  | Not required until late 2017
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | The development of a training package to detail the changes to metering roles for internal and external parties has begun. | Relies on the above. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The training approach is progressing as planned, with training collateral in development. |  | On track. | No major change from previous status | Timelines are compressing and a risk based approach is being taken on what work that needs to be done. There is also a reliance on other industry participants being ready. | Development of training strategy and training needs analysis is complete. Training materials and work instructions are under development. Training delivery will commence in late October 2017.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Detailed reviews of AAD documentation has begun and resourcing for the changes has been completed. AAD is now in the process of carrying out the required reviews, consultation, workshops, etc. required to design and implement the required changes. Detailed workshops with retailers have begun to develop systems and processes that are compatible with other external requirements. | In concert with the changes ot policies, priocedures and work instructions. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | High priority To be business processes are completed. Lower priority business processes are underway. |  | It is clear in discussions with industry participants that an end-to-end walkthrough of processes and the market operating model occurs in July 2017 at the latest. It is likely industry testing will fail if this does not occur. Jemena has been arranging 1:1 sessions to walk through processes and work practices with each Retailer who has customers on the JEN in the absence of this industry program activity occurring. | Completed (April 2017) | Timelines are compressing and a risk based approach being taken on work that needs to be done. There is also a reliance on other industry participants being ready.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | As above. | In concert with the changes ot policies, priocedures and work instructions. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The high priority future state processes are completed, with low priority business processes underway. |  |  | In line with SAPN program delivery schedule | Timelines are compressing and a risk based approach being taken on work that needs to be done. Reliant on other industry participants being ready as well.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not yet begun. | Not expected to start until mid-August 2017 | Industry testing only covers small subset of transactions. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Activities associated with the Test Approach are ongoing. The scope of August industry testing remains unclear and is perceived as retailer focused. Participation in industry testing will only prove valuable for our businesses if undertaken with participants within our jurisdiction, of whom we currently do business with. Confirmation of industry testing scope is required as soon as possible to ensure we are equipped and ready to participate on the advised date. |  |  | Not started; In line with SAPN delivery schedule | Timelines are compressed | Plans are in place to execute industry testing. However the current draft of B2B procedures includes the movement of currently enforceable details into a non-binding "guidance" category. The industry considers some of these details to be necessary for uniform, reliable end-to-end processing in the market. UE remains concerned that varying interpretations and inconsistencies between industry participants will become apparent during industry testing and may threaten its progress.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | AAD has only two outstanding system requirements yet to be incorporated into designs and documentation. | System impacts have been assessed in detail. The overall solution design is complete. |  | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | Requirement specifications and high priority designs are complete. Some of the lower priority and release 2 designs are still awaiting approval. The projects phased implementation approach ensures the achievement of compliance in release 1 and further efficiencies in release 2 to occur post 1 December 2017. Risk of misalignment of assumptions between participants is evident as per discussions with various market participants during assumptions workshops. |  |  | No major change from previous status |  | Based on Vic Govt advice that existing and new meters are to remain Type 5 MRIM, all solution impacts have been assessed.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | All initial code changes have been received by AAD and system testing is in cycle 2 of 6. | The implementation phase is underway. Build activities are well advanced. Delivery schedule has been finalised. |  | Note: Program revision of critical path delivery for system changes has been completed. | See above comment | The build and test phase is progressing well. There is very little contingency remaining in the build schedule. Key Risk: changes in retailer / MC assumptions of the interpretation of the B2B procedures may impact the build schedule. | Agile delivery approach now being applied to system changes. Sprints required for market testing will be delivered just prior to commencement of market testing. |  | Prioritising internal system development/ build requirements to ensure market compliance. Extended work required post 1 December. | Releases have been delayed from initial timeline, design complete and build activity underway. 1st of 3 releases have been received. Systems build and testing timelines continue to be challenging. | Development and component testing of the core "market" solution that will support the MC changes is complete.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Test cycle 2 is underway however, progress is slower than expected. Additional resources for testing are being sought. | Early testing of market systems commenced. |  | Note: Refer above. |  | Testing is currently tracking to schedule. However, testing timelines are compressed and therefore are 'At risk'. | Agile delivery approach now being applied to system changes. Sprints required for market testing will be delivered just prior to commencement of market testing. | JEN solution has been tested and is ready for bilateral testing with AEMO and Retailers. | No major change from previous status | Testing on release one is now underway | System component testing is complete. Integration testing is underway and proceeding smoothly with relatively low defect rates.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  | Successful completion of business to market testing was achieved on the 29th June 17. |  | JEN is ready for 21 August 2017 minimum AEMO Market Testing. Full and complete bilateral testing is being arranged by Jemena directly with all Retailers who have customers on JEN to mitigate the PoC industry testing gap. | No major change from previous status | TasNetworks to participate in industry towards the latter part of AEMO's proposed testing window | Plans in place and resourcing agreed. Not yet due.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  | Further clarity on the scope of August Industry testing would facilitate this validation. Market and Industry test needs to prove that the industry will work on 1 December 17. At this stage our view is that: 1) The test scenarios are not comprehensive enough. 2) Do not have enough coverage of all high volume and priority transactions. 3) Are too retailer focused. All participants need to be able to participate. 4) Test data is not sufficiently defined. It is deeply concerning that no MC's are registered to participate in market trials. |  | The industry test plan performance testing is out of scope. We are unsure as to why this line item is in the report as there is no scheduled structured industry performance testing in AEMO's Industry Program Plan. | Monitor of changes from WP3 for impacts and changes | TasNetworks to participate in industry towards the latter part of AEMO's proposed testing window | Plans in place and resourcing agreed. Not yet due.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | AAD is currently preparing transition and cutover plans. This includes actively participating in the ITCFG with AEMO and engaging with market participants to plan for jurisdictional specific measures. AAD is working with retailers to ensure readiness to go live on 1 December 2017. | Working with various groups to understand impacts before completing planning |  | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | The AEMO transition and cutover workshops are very effective. Significant progress has now been achieved in this area. However, please see the mitigant. |  | Transition planning is in progress internally and within industry collectively. It is important that AEMO facilitate the design and agreement of the go-live readiness criteria in July so that the industry is clear on what is required for 1-3 December 2017 go-live. | Phase 1 Industry testing in progress | This activity is under pressure due to the competing priorities and compressed timelines. This activity is also dependant on other market participants & industry planning readiness | Early preparation work is underway.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | As above. | Not due yet. |  | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Transition planning is tracking as scheduled. The Go Live Decision making framework is awaiting business approval. |  |  | In line with SAPN delivery schedule | Commenced data migration strategy and other preliminary planning activities. Preliminary assessment indicates cutover timeframes will exceed a day cutover window. | Early preparation work is underway.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | AAD has established risk, issue and decision registers to track and mitigate gaps that are identified as progress is made. |  |  |  |  | Engagement of additional resources has commenced on this piece of work.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Weekend work and additional test resources have been approved to mitigate the risks associated with slower than expected progress.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [15 empty] | On 5 June, the Vic Govt issued an 'AMI Order amendments outline document', which describes the specific changes and the Orders to which they apply. UE assessed this document and provided feedback to the Vic Govt. UE continues to urge prompt finalisation of the changed Vic Govt Orders to ensure that no unexpected requirements or obligations are introduced.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [15 empty] | As above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [15 empty] | UE continues to proceed based on Vic Govt advice that DB-provided metering will remain a regulated service. It is also assumed that the current Victorian policy blocking customer opt-out will remain in place.
2.4 |  | An assessment of the required accreditation and registration activities | [15 empty] | As noted above, UE continues to urge prompt finalisation of the changed Vic Govt Orders so that accreditation requirements can be confirmed.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | See above comment | [5 empty] | As above.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Requirements for additional testers and a business analyst has begun to mitigate risks associated with testing and delivery.
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing | [14 empty] | Validation of business process maybe done outside of industry testing | To address concerns about varying interpretations of B2B procedures between industry participants, UE has developed an information pack and has been directly engaging the key retailers in UE's patch. This will continue in the period prior to industry testing commencing. As at 10 July, 9 retailers covering ~94% of customers in UE patch have been engaged. Intent is to execute bi-lateral testing with 25 retailers in UE patch, in addition to AEMO-led market trial tests.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | See above comment | The Project is reviewing several mitigation strategies; significantly a phased implementation approach.
5.2 |  | The development and build of appropriate market systems for your business | [6 empty] | All available resources have been assigned to the design & development tasks. |  |  | See above comment | The Project has implemented a phased implementation approach. | Working closely with vendor and business to ensure sprints are delivered on time and of high quality. |  |  |  | Development and testing of flexible "management information" reports to support operational teams is scheduled to take place in late 2017. This work is not a dependency for 1 Dec go-live.
5.3 |  | The internal testing of market systems for your business | [11 empty] | Working closely with vendor and business to ensure sprints are delivered on time and of high quality. |  |  |  | As above.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing | [10 empty] | Our organisation is keen to provide scenarios to ensure coverage.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [10 empty] | Our organisation continues to urge AEMO to provide a transform capability as usual to mitigate go live risk.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2017-07-10 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | The element of risk is elevating with the delay and/or deferral of the following items: - Package 3 - as built : delayed with inclusive items which need urgent clarification rather than been incorporated in a 6mth consultation process. i.e. Meter Churn, CR6300/800 etc. Feedback has been provided in the consultation process. - Clear communicated date of when the DB's treatment plan on how the Faults and Emergencies will be handled on site and subsequent Market communication of activities undertaken, will be available. Requesting AEMO to instruct the market that a consistent approach be rolled out across all jurisdictions. | [13 empty] | Active Stream is currently accredited and operating as a Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring Active Stream to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | At risk | Medium | Overall project remains amber but steady within an aggressive schedule. Key challenges remain around tight timeframes, aggressive testing schedule and need to further define business, people and cutover impacts. Also facing challenges in the areas of bilateral and commercial agreements with multiple parties due to the tight timelines. Ongoing monitoring and mitigation plans in place to manage and resolve project risks / issues.
| Ausgrid Business Services | At risk | Medium | The ICT and business projects are underway. A number of significant IT rebuilds are required in order to facilitate the new B2B, CATS and new minimum specification requirements. Test script development is well advanced. New interfaces for the customer are under development to assist our customers in operating in the POC space
| intelliHUB Pty Ltd | Within schedule | Medium
| Metering Dynamics | At risk | Medium | Revised delivery plans based on current systems now progressing well. Progress being made to bring activities back within schedule. A number of jurisdictional differences continue to contribute to slow progress on MC commercial arrangements. | [7 empty] | Current systems changes are progressing
| Powermetric Metering Pty Ltd | At risk | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the aggressive POC implementation, industry testing and MC Registration timeframes place Powermetric POC development at a Medium risk. Further, continued uncertainty of individual distribution business management of Faults and Emergency situations (where a contestable asset is installed at a customer premise) is concerning and clarification is sought by AEMO without delay.
| Select Solutions (EASTENMP, GLOBALM) | At risk | Medium | There is limited time remaining for all participants to complete systems, process and people changes in readiness for Industry Testing. Select Solutions is working to the schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). There are substantial commercial agreement reviews and negotiations that are now commencing for all parties that has external risks to manage to ensure agreements are completed and executed prior to 1 December 2017. Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for MC Services and Type 4 small meters. The main risks are associated with our readiness for Type 4 small customer to meet the industry testing phase in August 2017. We do not currently see substantial issues impacting our Type 1-4 Large customer accreditation. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. Substantial additional new dedicated POC project resources have now been mobilised to drive the changes required as part of this program of works. | [7 empty] | Risk relates to the remaining timeframe to complete existing systems modifications and industry testing.
| Spotless Advanced Metering | Within schedule | Low | Spotless Advanced Metering (SAM) has been developing a comprehensive metering business for approx 12 months. All plans, systems and process development is founded on PoC compliance and alignment with the PoC Go Live date of 1 Dec 17.
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on outstanding matters such as lack of clarity on Emergency Procedures, Meter Churn rules, and transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| intelliHUB Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metering Dynamics | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions (EASTENMP, GLOBALM) | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Spotless Advanced Metering | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 81% - 99% | 81% - 99% | Completed (100%) | 51% - 60% | 41% - 50% | 75% | Completed (100%) | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 71% - 80% | 81% - 99% | Completed (100%) | 41% - 50% | 61% - 70% | 75% | Completed (100%) | 81% - 99%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 61% - 70% | 81% - 99% | 81% - 99% | 41% - 50% | 11% - 20% | 75% | 71% - 80% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 81% - 99% | 51% - 60% | 21% - 30% | 61% - 70% | 21% - 30% | 11% - 20% | 75% | 71% - 80% | 31% - 40%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 61% - 70% | 31% - 40% | 11% - 20% | 81% - 99% | 11% - 20% | 1% - 10% | 50% | 71% - 80% | 31% - 40%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | 71% - 80% | Completed (100%) | 81% - 99% | 71% - 80% | 41% - 50% | 75% | 81% - 99% | 81% - 99%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 81% - 99% | 1% - 10% | 11% - 20% | 41% - 50% | 41% - 50% | 1% - 10% | 25% | 71% - 80% | 11% - 20%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 51% - 60% | 51% - 60% | Completed (100%) | 21% - 30% | 41% - 50% | 75% | 61% - 70% | 21% - 30%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 51% - 60% | 31% - 40% | Completed (100%) | 31% - 40% | 21% - 30% | 25% | 51% - 60% | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 11% - 20% | 11% - 20% | 21% - 30% | 61% - 70% | 11% - 20% | Not started (0%) | 50% | 71% - 80% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 71% - 80% | 51% - 60% | 81% - 99% | 41% - 50% | 21% - 30% | 75% | 81% - 99% | 71% - 80%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 99% | 61% - 70% | 11% - 20% | 61% - 70% | 31% - 40% | 21% - 30% | 50% | 81% - 99% | 41% - 50%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | 31% - 40% | Not started (0%) | Not started (0%) | 25% | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 71% - 80% | 41% - 50% | Completed (100%) | 81% - 99% | 51% - 60% | 21% - 30% | 100% | 81% - 99% | 41% - 50%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 71% - 80% | 21% - 30% | 21% - 30% | 41% - 50% | 21% - 30% | 1% - 10% | 75% | 61% - 70% | 31% - 40%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 71% - 80% | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10% | Not started (0%) | 25% | 21% - 30% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 41% - 50% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 75% | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 21% - 30% | 11% - 20% | 11% - 20% | Not started (0%) | 1% - 10% | Not started (0%) | 25% | N/A | 11% - 20%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | At risk | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | At risk | Within schedule | Completed | At risk | Within schedule | At risk | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | Completed | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | Not within schedule | Within schedule | At risk | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Finalising a number of MC requirements |  | Dependencies on other related initiatives have slowed progress on finalising impact assessment.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Dependent on Faults/Meter Churn , timely resolution or provisioning of answers from AEMO. |  | Working with ITCFG to understand impacts before completing planning |  | Impacts from system integrator departing have been managed. Revised implementation plan now in place.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Dependent on jurisdcitional determinations |  | Final reviews in place
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Dependent on jurisdcitional determinations |  | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Continuing uncertainty and changes in jurisdictional rules. |  | There are a number of new policies and procedures that are being documented as part of the MC Registration process with executive or senior level approval and signoff required as a dependancy for the MC Registration process.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | In progress. With Legal team. This is a significant logistical effort to negotiate agrements with each propsective party. |  | Complexity of contractual and commercial arrangements under POC. |  | Substantial work has been completed to review and update all commercial agreements to ensure new services and transaction methods are included. There is a risk that any delays in planned negotiation timeframes will have impacts to arranagements for POC Go Live on 1 December 2017. This has been registered as part of our Risk Management framework.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | In progress and on-track. |  | In hand. |  |  |  | Progressing through requirements for MC registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | In progress and on-track. |  | Applications submitted. ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. |  | Applications being finalised. Merger and corporate restructuring has delayed progress with revised governance processes. |  | Progressing through requirements for MC registration. Schedule challenged.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | MC resource requirements have been determined |  | Awaiting outcome of updated policies and work instructions to complete. |  | Corporate restructuring continues to add uncertainty to HR requirements analysis. |  | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role; MC org chart in draft. |  | Relies on the above. |  | Impacted by recent merger and restructuring activity. |  | Primary changes relate to resourcing around MC function. This work is being progressed but is currently behind schedule.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Training has commenced. |  | Relies on the above. |  | Due to change in key system components, flow on effect to training development and delivery timing. |  | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions. |  | Key system architecture and system integrator changes impacting on business processes. |  | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions. |  | Key system architecture and system integrator changes have delayed this work. |  | We continue to work within the AEMO POC Registration, Accreditation and Go Live timeframes.
4.3 |  | The validation of business processes during industry testing | [7 empty] | Not expected to start until mid-August 2017 |  |  |  | We are now planning the detailed end-to-end testing scenarios in preparation for Industry Testing and additional end-to-end testing with industry peers.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | System impacts have been assessed in detail. The overall solution design is complete. |  | Key system architecture and system integrator changes. |  | Detailed impact assessment and requirements baslines have been documented to align with the currently documented industry changes. Any change to these systems, processes or procedures will immediately raise a new risk and potential issue to our program.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | The implementation phase is underway. Build activities are well advanced. Delivery schedule has been finalised. |  | Change in systems approach has reduced progress in build activities. |  | There is pressure on the timeframe to complete and test all changes before Industry Testing commences in August 2017.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Early testing of market systems commenced. |  | Delays to systems build has impacted availability for testing. |  | There is pressure on the timeframe to complete and test all changes before Industry Testing commences in August 2017.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Not at the stage of testing market systems. |  | Delays to systems build has impacted availability for testing.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Not at the stage of testing market systems.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Working with ITCFG to understand impacts before completing planning |  | Dependant on internal and market planning activities and decisions. |  | This action dependent upon finalisation of process and system changes
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Not yet due. |  |  |  | This action dependent upon finalisation of system changes
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Dedicated resource working on MC engagement and application |  | Increasing executive awareness and support for progressing key activities |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG |  | Progress being made to bring work back on schedule. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [9 empty] | Further reviews of jurisdictional information and discussions with regulators. |  | This risk has been documented and is being managed as part of our Risk Management process and our POC Steering Committee has been engaed to ensure the document signoff process can be completed within the required timeframes.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [9 empty] | Continuing analysis of commercial requirements between parties. |  | Substantial customer and industry engagement has commenced and agreements are progressing.
2.4 |  | An assessment of the required accreditation and registration activities | [11 empty] | New dedicated resources have been assigned to our POC Project including our accreditation and registration activities.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | Requirements being discussed with AEMO. |  | New dedicated resources have been assigned to our POC Project including our accreditation and registration activities.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [9 empty] | Key assumptions being identified to allow progress.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [9 empty] | Work progressing, remains at risk |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [9 empty] | Increasing resources in training and development stream
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [9 empty] | Revised plan in place for current systems. Process impacts being updated accordingly.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [9 empty] | Revised plan in place for current systems. Process impacts being updated accordingly.
4.3 |  | The validation of business processes during industry testing | [11 empty] | We have engaged with a number of industry participants in preparation for end-to-end peer testing.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | Revised plan in place for current systems. Systems impacts being updated accordingly.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Additional resources being secured to bring back on schedule |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase. Some optional scope items have been deferred or excluded to ensure the core requirements to address compliance and business operations are delivered for Industry Testing and Accreditation activities.
5.3 |  | The internal testing of market systems for your business | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase. Some optional scope items have been deferred or excluded to ensure the core requirements to address compliance and business operations are delivered for Industry Testing and Accreditation activities.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule |  | Market Gateway systems have been modified in preparation for e-Hub accreditation and testing processes.
5.5 |  | The validation of performance of market systems during industry testing | [11 empty] | Market Gateway systems have been modified in preparation for e-Hub accreditation and testing processes.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  | Focus on key deliverables for transition and cutover. ITCFG member. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [11 empty] | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
| 2017-07-10 |  |  | Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | The element of risk is elevating with the delay and/or deferral of the following items: - Package 3 - as built : delayed with inclusive items which need urgent clarification rather than been incorporated in a 6mth consultation process. i.e. Meter Churn, CR6300/800 etc. Feedback has been provided in the consultation process. - Clear communicated date of when the DB's treatment plan on how the Faults and Emergencies will be handled on site and subsequent Market communication of activities undertaken, will be available. Requesting AEMO to instruct the market that a consistent approach be rolled out across all jurisdictions. | [13 empty] | Active Stream is currently accredited and operating as a Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring Active Stream to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | At risk | Medium | Overall project remains amber but steady within an aggressive schedule. Key challenges remain around tight timeframes, aggressive testing schedule and need to further define business, people and cutover impacts. Also facing challenges in the areas of bilateral and commercial agreements with multiple parties due to the tight timelines. Ongoing monitoring and mitigation plans in place to manage and resolve project risks / issues.
| Ausgrid Business Services | At risk | Medium | The ICT and business projects are underway. A number of significant IT rebuilds are required in order to facilitate the new B2B, CATS and new minimum specification requirements. Test script development is well advanced. New interfaces for the customer are under development to assist our customers in operating in the POC space
| intelliHUB Pty Ltd | Within schedule | Medium
| Metering Dynamics | At risk | Medium | Revised delivery plans based on current systems now progressing well. Progress being made to bring activities back within schedule. A number of jurisdictional differences continue to contribute to slow progress on MC commercial arrangements. | [7 empty] | Registration delays due to changing governance arrangements.
| Powermetric Metering Pty Ltd | At risk | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the aggressive POC implementation, industry testing and MC Registration timeframes place Powermetric POC development at a Medium risk. Further, continued uncertainty of individual distribution business management of Faults and Emergency situations (where a contestable asset is installed at a customer premise) is concerning and clarification is sought by AEMO without delay.
| Select Solutions (EASTENMP, GLOBALM) | At risk | Medium | There is limited time remaining for all participants to complete systems, process and people changes in readiness for Industry Testing. Select Solutions is working to the schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). There are substantial commercial agreement reviews and negotiations that are now commencing for all parties that has external risks to manage to ensure agreements are completed and executed prior to 1 December 2017. Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for MC Services and Type 4 small meters. The main risks are associated with our readiness for Type 4 small customer to meet the industry testing phase in August 2017. We do not currently see substantial issues impacting our Type 1-4 Large customer accreditation. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. Substantial additional new dedicated POC project resources have now been mobilised to drive the changes required as part of this program of works. | [7 empty] | Risk relates to the remaining timeframe to complete existing systems modifications and industry testing.
| Spotless Advanced Metering | Within schedule | Low | Spotless Advanced Metering (SAM) has been developing a comprehensive metering business for approx 12 months. All plans, systems and process development is founded on PoC compliance and alignment with the PoC Go Live date of 1 Dec 17.
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on outstanding matters such as lack of clarity on Emergency Procedures, Meter Churn rules, and transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| intelliHUB Pty Ltd | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Metering Dynamics | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions (EASTENMP, GLOBALM) | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Spotless Advanced Metering | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 81% - 99% | 81% - 99% | Completed (100%) | 51% - 60% | 41% - 50% | 75% | Completed (100%) | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 71% - 80% | 81% - 99% | Completed (100%) | 41% - 50% | 61% - 70% | 75% | Completed (100%) | 81% - 99%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 61% - 70% | 81% - 99% | 81% - 99% | 41% - 50% | 11% - 20% | 75% | 71% - 80% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 81% - 99% | 51% - 60% | 21% - 30% | 61% - 70% | 21% - 30% | 11% - 20% | 75% | 71% - 80% | 31% - 40%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 61% - 70% | 31% - 40% | 11% - 20% | 81% - 99% | 11% - 20% | 1% - 10% | 50% | 71% - 80% | 31% - 40%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | 71% - 80% | Completed (100%) | 81% - 99% | 71% - 80% | 41% - 50% | 75% | 81% - 99% | 81% - 99%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 81% - 99% | 1% - 10% | 11% - 20% | 41% - 50% | 41% - 50% | 1% - 10% | 25% | 71% - 80% | 11% - 20%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 51% - 60% | 51% - 60% | Completed (100%) | 21% - 30% | 41% - 50% | 75% | 61% - 70% | 21% - 30%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 51% - 60% | 31% - 40% | Completed (100%) | 31% - 40% | 21% - 30% | 25% | 51% - 60% | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 11% - 20% | 11% - 20% | 21% - 30% | 61% - 70% | 11% - 20% | Not started (0%) | 50% | 71% - 80% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 71% - 80% | 51% - 60% | 81% - 99% | 41% - 50% | 21% - 30% | 75% | 81% - 99% | 71% - 80%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 99% | 61% - 70% | 11% - 20% | 61% - 70% | 31% - 40% | 21% - 30% | 50% | 81% - 99% | 41% - 50%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | 31% - 40% | Not started (0%) | Not started (0%) | 25% | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 71% - 80% | 41% - 50% | Completed (100%) | 81% - 99% | 51% - 60% | 21% - 30% | 100% | 81% - 99% | 41% - 50%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 71% - 80% | 21% - 30% | 21% - 30% | 41% - 50% | 21% - 30% | 1% - 10% | 75% | 61% - 70% | 31% - 40%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 71% - 80% | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10% | Not started (0%) | 25% | 21% - 30% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 41% - 50% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 75% | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 21% - 30% | 11% - 20% | 11% - 20% | Not started (0%) | 1% - 10% | Not started (0%) | 25% | N/A | 11% - 20%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | At risk | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | At risk | Within schedule | Completed | At risk | Within schedule | At risk | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | Completed | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | Not within schedule | Within schedule | At risk | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Finalising a number of MC requirements |  | Dependencies on other related initiatives have slowed progress on finalising impact assessment.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Dependent on Faults/Meter Churn , timely resolution or provisioning of answers from AEMO. |  | Working with ITCFG to understand impacts before completing planning |  | Impacts from system integrator departing have been managed. Revised implementation plan now in place.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Dependent on jurisdcitional determinations |  | Final reviews in place
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Dependent on jurisdcitional determinations |  | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Continuing uncertainty and changes in jurisdictional rules. |  | There are a number of new policies and procedures that are being documented as part of the MC Registration process with executive or senior level approval and signoff required as a dependancy for the MC Registration process.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | In progress. With Legal team. This is a significant logistical effort to negotiate agrements with each propsective party. |  | Complexity of contractual and commercial arrangements under POC. |  | Substantial work has been completed to review and update all commercial agreements to ensure new services and transaction methods are included. There is a risk that any delays in planned negotiation timeframes will have impacts to arranagements for POC Go Live on 1 December 2017. This has been registered as part of our Risk Management framework.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | In progress and on-track. |  | In hand. |  |  |  | Progressing through requirements for MC registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | In progress and on-track. |  | Applications submitted. ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. |  | Applications being finalised. Merger and corporate restructuring has delayed progress with revised governance processes. |  | Progressing through requirements for MC registration. Schedule challenged.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | MC resource requirements have been determined |  | Awaiting outcome of updated policies and work instructions to complete. |  | Corporate restructuring continues to add uncertainty to HR requirements analysis. |  | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role; MC org chart in draft. |  | Relies on the above. |  | Impacted by recent merger and restructuring activity. |  | Primary changes relate to resourcing around MC function. This work is being progressed but is currently behind schedule.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Training has commenced. |  | Relies on the above. |  | Due to change in key system components, flow on effect to training development and delivery timing. |  | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions. |  | Key system architecture and system integrator changes impacting on business processes. |  | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | In concert with the changes ot policies, priocedures and work instructions. |  | Key system architecture and system integrator changes have delayed this work. |  | We continue to work within the AEMO POC Registration, Accreditation and Go Live timeframes.
4.3 |  | The validation of business processes during industry testing | [7 empty] | Not expected to start until mid-August 2017 |  |  |  | We are now planning the detailed end-to-end testing scenarios in preparation for Industry Testing and additional end-to-end testing with industry peers.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | System impacts have been assessed in detail. The overall solution design is complete. |  | Key system architecture and system integrator changes. |  | Detailed impact assessment and requirements baslines have been documented to align with the currently documented industry changes. Any change to these systems, processes or procedures will immediately raise a new risk and potential issue to our program.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | The implementation phase is underway. Build activities are well advanced. Delivery schedule has been finalised. |  | Change in systems approach has reduced progress in build activities. |  | There is pressure on the timeframe to complete and test all changes before Industry Testing commences in August 2017.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Early testing of market systems commenced. |  | Delays to systems build has impacted availability for testing. |  | There is pressure on the timeframe to complete and test all changes before Industry Testing commences in August 2017.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Not at the stage of testing market systems. |  | Delays to systems build has impacted availability for testing.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Not at the stage of testing market systems.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Working with ITCFG to understand impacts before completing planning |  | Dependant on internal and market planning activities and decisions. |  | This action dependent upon finalisation of process and system changes
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Not yet due. |  |  |  | This action dependent upon finalisation of system changes
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | Dedicated resource working on MC engagement and application |  | Increasing executive awareness and support for progressing key activities |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG |  | Progress being made to bring work back on schedule. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [9 empty] | Further reviews of jurisdictional information and discussions with regulators. |  | This risk has been documented and is being managed as part of our Risk Management process and our POC Steering Committee has been engaed to ensure the document signoff process can be completed within the required timeframes.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [9 empty] | Continuing analysis of commercial requirements between parties. |  | Substantial customer and industry engagement has commenced and agreements are progressing.
2.4 |  | An assessment of the required accreditation and registration activities | [11 empty] | New dedicated resources have been assigned to our POC Project including our accreditation and registration activities.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | Requirements being discussed with AEMO. |  | New dedicated resources have been assigned to our POC Project including our accreditation and registration activities.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [9 empty] | Key assumptions being identified to allow progress.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [9 empty] | Work progressing, remains at risk |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [9 empty] | Increasing resources in training and development stream
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [9 empty] | Revised plan in place for current systems. Process impacts being updated accordingly.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [9 empty] | Revised plan in place for current systems. Process impacts being updated accordingly.
4.3 |  | The validation of business processes during industry testing | [11 empty] | We have engaged with a number of industry participants in preparation for end-to-end peer testing.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | Revised plan in place for current systems. Systems impacts being updated accordingly.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Additional resources being secured to bring back on schedule |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase. Some optional scope items have been deferred or excluded to ensure the core requirements to address compliance and business operations are delivered for Industry Testing and Accreditation activities.
5.3 |  | The internal testing of market systems for your business | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase. Some optional scope items have been deferred or excluded to ensure the core requirements to address compliance and business operations are delivered for Industry Testing and Accreditation activities.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule |  | Market Gateway systems have been modified in preparation for e-Hub accreditation and testing processes.
5.5 |  | The validation of performance of market systems during industry testing | [11 empty] | Market Gateway systems have been modified in preparation for e-Hub accreditation and testing processes.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  | Focus on key deliverables for transition and cutover. ITCFG member. |  | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [11 empty] | New dedicated resources have been assigned to our POC Project and will ramp up towards August Industry Testing phase.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Embedded Networks
| 2017-07-10 |  |  | Embedded Networks Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Ausgrid Business Services | At risk | Medium | The ICT and business projects are underway. A number of significant IT rebuilds are required in order to facilitate the new B2B, CATS and new minimum specification requirements. Test script development is well advanced. New interfaces for the customer are under development to assist our customers in operating in the POC space
| Energy & Plant Management Pty Limited | Within schedule | Low | Preparing for accreditation
| Momentum Energy | At risk | Medium | Current risks are related to potential issues with development and implementation of system changes within given timeframes. There are dependencies on external vendors to develop required changes. There is also a lack of clarity from AEMO in terms of how the Victorian Distributors role will evolve related to MC. Also critical dependencies on external providers of MC role to meet POC timeframes. | [7 empty] | Whilst our ENM accreditation application is in progress, our participation in industry testing is dependent on us being granted a Participant ID.
| Network Energy Services | Within schedule | Low | Submitted accreditation application | [7 empty] | Getting prepared to implement all aspects
| WINconect Pty Ltd | Within schedule | Low | Uncertainty about the implication of Victorian order in council relating to adoptions of POC changes. Practical implications for application of AER's NSP Exemption guidelines might be significant. Further uncertanty about application of ENM role in juristircitons that still require legislative arrangements to facilitate conteisibillity (QLD).
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Energy & Plant Management Pty Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Momentum Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Network Energy Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| WINconect Pty Ltd |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Momentum Energy | Network Energy Services | WINconect Pty Ltd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 81% - 99% | 61% - 70% | 71% - 80% | 100% | 71% - 80%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 21% - 30% | 71% - 80% | 100% | 71% - 80%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 21% - 30% | 51% - 60% | 100% | 41% - 50%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 21% - 30% | 21% - 30% | 31% - 40% | 100% | 11% - 20%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 11% - 20% | 41% - 50% | 31% - 40% | 25% | 41% - 50%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | 61% - 70% | 71% - 80% | 100% | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 11% - 20% | 1% - 10% | 51% - 60% | 50% | 71% - 80%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 81% - 99% | 51% - 60% | 100% | 71% - 80%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 61% - 70% | N/A | 100% | Completed (100%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 21% - 30% | 41% - 50% | 21% - 30% | 50% | 41% - 50%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 51% - 60% | 71% - 80% | 41% - 50% | 100% | 41% - 50%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 11% - 20% | 11% - 20% | 11% - 20% | 100% | 51% - 60%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | 0% | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | 51% - 60% | 51% - 60% | 75% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 21% - 30% | 41% - 50% | 31% - 40% | 50% | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 1% - 10% | 1% - 10% | 31% - 40% | 50% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | 0% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 11% - 20% | 41% - 50% | 21% - 30% | 75% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | 11% - 20% | Not started (0%) | 25% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Momentum Energy | Network Energy Services | WINconect Pty Ltd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | Within schedule | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | At risk | Within schedule | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | N/A | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Within schedule | At risk | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | Within schedule | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Momentum Energy | Network Energy Services | WINconect Pty Ltd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Finalising a number of MC requirements
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Working with ITCFG to understand impacts before completing planning
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Final reviews in place |  |  |  | Waiting for guidance on ENM role in Victorian and Queensland.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Dependency on participation in industry testing |  | Waiting for guidance on ENM role in Victorian and Queensland.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | In progress. With Legal team. This is a significant logistical effort to negotiate agrements with each propsective party. |  | Dependency on partnering with registered MC(s)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | In hand.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Applications submitted. ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Awaiting outcome of updated policies and work instructions to complete.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Relies on the above.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Relies on the above. |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | In concert with the changes ot policies, priocedures and work instructions.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | In concert with the changes ot policies, priocedures and work instructions. |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not expected to start until mid-August 2017 |  |  |  | Not yet started testing fro ENM role.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | System impacts have been assessed in detail. The overall solution design is complete. |  | System development is reliant on external vendor, any delays in final market procedures will impact readiness activities.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | The implementation phase is underway. Build activities are well advanced. Delivery schedule has been finalised.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Early testing of market systems commenced.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not at the stage of testing market systems. |  |  |  | Not yet started testing fro ENM role.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not at the stage of testing market systems. |  |  |  | Not yet started testing fro ENM role.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Working with ITCFG to understand impacts before completing planning |  | Transition plans are dependent on timely delivery of earlier program stages |  | Uncertainly over process for bulk role change of existin embedded networks before 1 December 2017.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not yet due. |  |  |  | Awaiting guidance on cut over plan for existing embedded netwokrs.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Momentum Energy | Network Energy Services | WINconect Pty Ltd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Dedicated resource working on MC engagement and application
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | All available resources have been assigned to the design & development tasks.
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Member on ITCFG
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Third Party
| 2017-07-10 |  |  | Third Party Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2017-07-10 | [5 empty] | Within schedule | Medium | PWC have commenced their survey of industry readiness and begun planning for one-on-one interviews with participants who've nominated to take part in the process. The Vic Govt has verbalised that they are within a couple of weeks of releasing a draft of the Order in Council and will undertake a brief consultation on the draft. Readiness remains the main focus of AEMO and the broader industry. AEMO in collaboration with industry have completed planning for the transition of market services within in accordance with the current Rules. AEMO notes that progress with this focus group is on schedule and acknowledges the input by participants in this important activity. AEMO encourages registration and accreditation by all participants requiring to do so to commence as soon as is practicable.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Medium | AEMO risk rating relates to uncertainty of the detail within proposed Victorian Order in Council. AEMO notes that the imminent commencement of market trials leaves no contingency to deal with any incosistancy. Treatment of this risk relies on the drafting being made availlable as soon as possible.
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | 51% - 60% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies consistent with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updated B2B retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 41% - 50% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS (EN/MC) | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B e-hub and MSATS | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | The internal testing of market systems for your business | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 1% - 10% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 11% - 20% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
[12 empty] | 41% - 50% | Retailer
[12 empty] | 51% - 60% | Distributor
[12 empty] | 61% - 70% | Meter Provider
[12 empty] | 71% - 80% | Meter Data Provider
[12 empty] | 81% - 99% | Metering Coordinator
[12 empty] | Completed (100%) | Embedded Network Manager
[12 empty] | N/A | Embedded Network Operator
Third Party B2B Participant
Within schedule
At risk
Not within schedule
N/A
[12 empty] | Completed | √
x
Low
Medium
High
N/A

## Harvey Balls 10% (hidden)
ü
Completed
| 100 | 90 | 80 | 70 |  | 60 | 50 | 40 | 30 | 20 | 10 | 0
| 0 | 10 | 20 | 30 |  | 40 | 50 | 60 | 70 | 80 | 90 | 100
WITHIN SCHEDULE | [12 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE
|  |  | ~0% |  | ~50%
|  |  | ~10% |  | ~60%
|  |  | ~20% |  | ~70%
|  |  | ~30% |  | ~80%
|  |  | ~40% |  | ~90%