## Market Readiness Report Page 1
43017
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2017-10-09
Overall Status |  | Commentary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | The overall project status remains amber - "at risk" of delivery by 1 December 2017 with a medium risk rating. Participants have noted that whilst many program risks have now been addressed, concerns still exist around other participants’ readiness and the lack of registered Metering Coordinators. Participants have also highlighted ongoing challenging timeframes for system build and testing, registration and accreditation activities, and the number and complexity of commercial arrangements to be entered into. |  |  |  |  | High | Med | Low | #
[7 empty] | 2 | 7 | 2 | 3
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Network Manager |  | Third party e-hub
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with regulatory changes including jurisdictional regulations and requirements (e.g. safety) |  |  |  | #1 | [7 empty] | #1
2.3 |  | Operationally critical commercial contracts in place |  |  |  | #2 |  |  |  | #2 |  | #2
2.4 |  | Accreditation and registration activities completed
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place |  |  |  | #3 | [5 empty] | #3 |  | #4
4.2 |  | Successfully validated critical business processes during industry testing |  |  |  | #5
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing
5.2 |  | Successfully tested market systems capable of being moved into production |  |  |  | #4 |  | #4 | [5 empty] | #4
5.3 |  | Performance of, and communication between, market systems validated during industry testing |  |  |  | #5 |  | #5 | [5 empty] | #5
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place |  |  |  | #6
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals) | [11 empty] | #6
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Network Manager |  | Third party e-hub
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdictional risk is a reflection of overall project risk.
NSW |  | Jurisdictional risk is a reflection of overall project risk.
QLD |  | Jurisdictional risk is a reflection of overall project risk.
SA |  | Jurisdictional risk is a reflection of overall project risk.
TAS |  | Jurisdictional risk is a reflection of overall project risk.
VIC |  | Jurisdictional risk is a reflection of overall project risk.

## HIDDEN 25% (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2017-10-09
Variances
Note # | Explanation of Variance |  |  | Mitigating Actions
1 | Variance reported by Participants: Updating internal policies on schedule at risk as participants are waiting for jurisdictional safety regulators to publish requirements (re-en and de-en) – particularly in NSW. Participants are also waiting for the final Vic government OIC and clarity on the ENM role in Victoria. |  |  | Participants are engaging with jurisdictional bodies. [The final Victorian government OIC was published on 10 October: www.gazette.vic.gov.au.]
2 | Variance reported by Participants: Updating commercial arrangements on schedule is at risk due to volume and complexity of contracts that need to be entered into with industry parties. The slow progress of MC registration has also been raised as a risk. |  |  | Participants are increasing internal resources and considering contingency options (such as the staged transition approach).
3 | Variance reported by Participants: Updating and finalising business processes on schedule is at risk due to #1 (lack of clarity in processes including remote re-en and de-en) and #2 (dependency on metering partners) Intending ENMs have also highlighted concerns with the ENM NMI discovery process. |  |  | Participants continuing to engage with each other and relevant jurisdictional bodies. Intending ENMs engaging with AEMO and the AER.
4 | Variance reported by Participants: System development at risk due to the complexity and number of changes required within tight timeframes for development and testing and delays from external market system vendors. |  |  | Participants are increasing internal resources and working closely with market system vendors.
5 | Variance reported by Participants: Testing timelines are contingent on system design and build and are compressed. Concerns with scope of testing, and late or no participation in industry or bi-lateral testing. |  |  | [Market Trial cycle 2 completed on 6/10, with 36 companies taking part, 67% execution was achieved. No major defects identified, 24 minor defects assigned to AEMO. Cycle 3 commencing 16/10 with 5 additional retailers to commence testing]
6 | Variance reported by Participants: Transition and Cutover planning are dependent on timely delivery of earlier program stages and industry transition and cutover planning. |  |  | [AEMO has published version 1.1 of the POC Industry Transition & Cutover Plan The ITCFG are currently focused on dress rehearsal arrangements prior to the commence of system cutover activities on 30 November]
Notes
1. Please refer to the POC Industry Readiness Reporting Plan for more details on the Readiness Report process: http://www.aemo.com.au/-/media/Files/Electricity/NEM/Power-of-Choice/B2B/AEMO-POC-Industry-Readiness-Reporting-Plan-v20.pdf 2. The count of open Risk and Issues is based on the POC Industry Risk Register as at 11/10/2017. 3. Explanation of Variance and Mitigating Actions above are based on Participants comments, AEMO's comments are included within square brackets [ ].
Key - Progress and Status | [5 empty] | Key - Risk Rating
Progress |  |  | Status
Harvey balls represent progress towards achieving the criterion |  |  | Colour indicates the readiness status |  |  | Rating
~0% |  | ~50% | Criterion is within agreed schedule and deliverable requirements |  |  | High
~10% |  | ~60% | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~20% |  | ~70% | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~30% |  | ~80% |  |  |  | See POC Industry Risk Register for open risks and issues:
~40% |  | ~90% | Criterion has been achieved |  | ü | POC Industry Register

## Retailer Reports
| 2017-10-09 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Retail | Within schedule | Medium | ActewAGL Retail is currently focused on UAT/Regression Testing, Industry test and Operational readiness.A detailed project plan is in place and being tracked against in order to achieve compliance by the "go live" date.
| AGL Retailer Powerdirect | At risk | Medium | Cycle 2 market trials completed. Commercial activities are still in progress. Final lower priority developments are now being completed. Work instruction updates are in progress. A training plan has been developed and training modules are being prepared. Release plan prepared. Performance test plan developed. Focus now on MC mobilisation, process refinement and system configuration for go-live. Project status remains yellow due to key risks in finalising commercial agreements and MC mobilisation activities in readiness for go-live | [7 empty] | Risk rating remains at medium due to the number of parties involved, limited testing timeframes for end to end testing, commercial agreements finalisation and business transition and readiness activities. Industry process issues such as change of role (CR6800), fault management communications and metering locks continue to consume effort and remain a key risk for Power of Choice post go-live.
| Alinta Energy | At risk | Medium | Metering Partner engagement behind schedule Risk that MCs will not be accredited in time Work is continuing to operationalise the PoC changes | [7 empty] | MC engagement behind schedule.
| Aurora Energy | At risk | Medium | Aurora Energy continues to manage a number of risks with regards to the implementation of the Power of Choice reforms by 1 December 2017. The most significant risk is the aggressive implementation timeline, reflected in Aurora Energy's 'at risk' project status. This risk is also impacting the ability of Aurora Energy's key vendors to meet POC timeframes. This includes, but is not limited to, its selected Metering Coordinator, which is required to establish advanced metering service capability in Tasmania where it currently does not exist.
| Energy Australia | At risk | Medium | We see significant risks associated with: late participation by some participants in industry and bi-lateral testing. Delays in some industry documentation is causing some concern. The introduction of the staged new connections process is welcomed however, there are concerns that participants are not necessarily aligned in interpretation of this process. | [7 empty] | The Program is making steady progress but has risks associated with the progress of industry coordinated activities, such as industry-wide readiness, BCP and Emergency Planning. The Vic decision to delay competition in metering has had a significant impact on implementation of B2B processes, while these have been largely resolved, there are residual impacts to the schedule. | [5 empty] | Risks associated with industry coordinated activities still exist, such as BCP, Communications Planning and Emergency Planning.
| Ergon Energy Queensland (retail) | At risk | Medium | Ergon Energy continues to manage a number of system, process and people risks to deliver to the aggressive timeframe of the 1 December 2017. EEQ is focussed on ensuring customers are not impacted in a negative way. From a system perceptive, clarity is required on the overall readiness assessment of AEMO and the market. In particular where many participants are showing amber/red, recent industry testing defects and uncertainty around accreditation of participants throughout the market. Transitions Planning and revised Business Continuity Plan (BCP) has added additional requirement to the Project to mitigate risk that may add additional resources and costs. Deployment Planning and associated in-flight transitions approach is being developed but could add additional risk to cut-over due to the tight timeframe. Change management is being reassessed and an increased focus to ensure business readiness. | [7 empty] | Ergon Energy continues to manage a number of system, process and people risks to deliver to the aggressive timeframe of the 1 December 2017. EEQ is focussed on ensuring customers are not impacted in a negative way. From a system perceptive, clarity is required on the overall readiness assessment of AEMO and the market. In particular where many participants are showing amber/red, recent industry testing defects and uncertainty around accreditation of participants throughout the market. Transitions Planning and revised Business Continuity Plan (BCP) has added additional requirement to the Project to mitigate risk that may add additional resources and costs. Deployment Planning and associated in-flight transitions approach is being developed but could add additional risk to cut-over due to the tight timeframe. Change management is being reassessed and an increased focus to ensure business readiness.
| ERM Power Retail | At risk | Medium | ERM continues to report at risk for the PoC project, primarily due to remaining uncertainty in areas including 1) Meter Churn processes 2) Impact of these on commercial agreements Many previous uncertainties have been resolved, reducing (but not eliminating) risk.
| M2 Energy Pty Ltd | Within schedule | Medium | Project Scoping and coding by Vendor is complete, and testing has commenced. Business intention is to fully outsource MC role. Risk considered Medium moving to High as 1 MC accredited, who is a retail competitor. M2 Energy is maintaining dialogue with potential MCs who are in process of accreditation.. | [7 empty] | Vic withdrawal from POC has introduced risk into System Scoping, and increased training and change management requirements.
| Macquarie Bank Limited | Within schedule | Low
| Mojo Power | Within schedule | Medium | [8 empty] | Mojo in application for licence to enter Victoria.
| Momentum Energy | At risk | Medium | Material risks are related to probable issues with development and implementation of system changes within given timeframes. There are dependencies on external vendors to develop required changes and merge codes for B2B and B2M market transactions. Also critical dependencies on external providers of MC role to meet their POC timeframes.
| Next Business Energy | Within schedule | Low | NBE is tracking well with internal processes almost complete for post POC implementation. NBE also intends to adopt the staged approach to POC implementation to mitigate risk associated with delays in receiving, reviewing and implementing MC contracts which have not been received by all MC/MDPs despite repeated requests.
| Origin Energy | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Program is currently reporting Amber however remains highly dependant on the readiness of other participants to be successful and 9 out of 11 Distributors reporting at risk. A significant number of delivery risks continue to be monitored and mitigated for the duration of the project. Areas of concern include: Delivery • Origin believes that Phase 3 Market Testing is not mandatory, and has no quality hurdle for exit e.g. % of end to end scenarios completed. Cutover • There is no Go / No go option based on overall participant readiness e.g. successful completion of Market Testing. • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; | [7 empty] | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines.
| Pacific Hydro / Tango | At risk | High | The timing and outcomes of the following outstanding PoC activities have the potential to impact the build, test and implementation phases: 1. MSATS - As Built Consultation 2. B2B - Translation tool delivery and client side implementation & testing; potential new B2B schema changes prior to 1 Dec, and any Errata requiring process workarounds 3. Meter Churn Issues - recently raised and despite a paper being issued by AEMO, there are still concerns being raised. 4. Vic Government decision not to proceed with PoC. 5. Jurisdictional safety review of the remote Re-en/De-en process. 6. Internal Project delay for replacing current systems.
| People Energy Pty Ltd | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines.
| Pooled Energy | Within schedule | Medium | Project status remains within schedule with a medium risk rating. We are continuing to work through procedural and process changes. Pooled Energy is awaiting a number of related commercial agreements and updates and progress is dependent on external providers meeting timelines. | [7 empty] | As above - Pooled Energy operates in NSW only currently.
| Powershop | Within schedule | Medium | [AEMO Note - Using 11-Sep-17 Report for Powershop]: Powershop's development team is currently building the functionality to support POC
| Red Energy & Lumo Energy | At risk | Medium | Consistent concerns: - Business and customer activity is very high at the targeted cut-over time. Inconsistent approaches across industry creates increased activity and raises risk (eg. new connections, meter churn, faults and emergencies, expected approaches to in-flight transactions). - Other jurisdictional consequential legislative amendments are not yet understood (and some jurisdictions unseen) which is adding further risks to the overall project. We have reduced our overall risk rating as some previous risks and concerns have been mitigated. | [13 empty] | We remain concerned with the progress of MC registration.
| Simply Energy | Within schedule | Low | NSW Govt. email sent on the 4th of October that may have an impact on the readiness if the new suite of procedures require system or process changes effective 1st December 2017. | [13 empty] | Simply Energy has commenced Market Trial and is on track as per the schedule with no major defects identified in cycle 2 of Phase 3.
| Stanwell Corporation Limited | Within schedule | Low | Project progressing as planned.
| Sumo Power | Within schedule | Medium | [AEMO Note - Using 11-Sep-17 Report for Sumo Power] | [7 empty] | Readiness of market participants
| WINconnect Pty LTD | At risk | Medium | Working through clarification on market design and ENM discovery procedure in MSATS. | [13 empty] | Require guidance from AEMO as to process for ENM discover of MSATS to initiate the customer churn process. The ENM is not to be listed against a EN parent in MSATS. Require confirmation on validation in MSATS to ensure only appointed ENMs can perform CR against certain parent NMIS.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Retail | Within schedule | Medium | Within schedule | Medium
| AGL Retailer Powerdirect | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Alinta Energy |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Aurora Energy | [8 empty] | At risk | Medium
| Energy Australia | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ergon Energy Queensland (retail) |  |  |  |  | At risk | Medium
| ERM Power Retail | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| M2 Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Macquarie Bank Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Mojo Power |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Momentum Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Next Business Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro / Tango |  |  | At risk | High | At risk | High | At risk | High |  |  | At risk | High
| People Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Pooled Energy |  |  | Within schedule | Medium
| Powershop |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Red Energy & Lumo Energy |  |  | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Stanwell Corporation Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  |  |  | Within schedule | Low
| Sumo Power | [10 empty] | Within schedule | Medium
| WINconnect Pty LTD |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo Power | WINconnect Pty LTD | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | 75% | Completed (100%) | Completed (100%) | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 71% - 80% | 100% | 81% - 99% | 81% - 99% | Completed (100%) | 71% - 80% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 81% - 99% | 71% - 80% | 51% - 60% | 50% | 91% - 99% | 71% - 80% | 71% - 80% | 61% - 70% | 71% - 80% | 51% - 60% | 71% - 80% | 51% - 60% | 0% | 81% - 99% | 81% - 99% | 81% - 99% | 61% - 70% | 71% - 80%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 71% - 80% | Completed (100%) | Completed (100%) | 71% - 80% | 71% - 80% | 81% - 99% | 51% - 60% | 25% | 91% - 99% | 71% - 80% | 71% - 80% | 51% - 60% | 71% - 80% | 61% - 70% | 61% - 70% | 41% - 50% | 75% | 81% - 99% | 71% - 80% | 71% - 80% | 21% - 30% | 41% - 50%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 61% - 70% | 71% - 80% | 91% - 99% | 31% - 40% | 61% - 70% | 71% - 80% | 41% - 50% | 0% | 91% - 99% | 61% - 70% | 61% - 70% | 61% - 70% | 51% - 60% | 41% - 50% | 41% - 50% | 31% - 40% | 0% | 31% - 40% | 71% - 80% | 31% - 40% | Not started (0%) | 11% - 20%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 61% - 70% | 71% - 80% | 91% - 99% | 61% - 70% | 61% - 70% | 71% - 80% | 41% - 50% | 0% | 21% - 30% | 71% - 80% | 61% - 70% | 11% - 20% | 41% - 50% | 51% - 60% | 31% - 40% | 21% - 30% | 25% | N/A | 71% - 80% | 11% - 20% | 11% - 20% | 41% - 50%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 31% - 40% | 71% - 80% | Completed (100%) | 71% - 80% | 25% | 91% - 99% | 81% - 99% | 81% - 90% | 41% - 50% | 71% - 80% | 51% - 60% | 61% - 70% | 61% - 70% | 50% | N/A | Completed (100%) | Completed (100%) | Not started (0%) | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Completed (100%) | 71% - 80% | 51% - 60% | 1% - 10% | 51% - 60% | Completed (100%) | 11% - 20% | N/A | 91% - 99% | 11% - 20% | 81% - 90% | Not started (0%) | Not started (0%) | 1% - 10% | 41% - 50% | 31% - 40% | 0% | N/A | N/A | 61% - 70% | Not started (0%) | 71% - 80%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 81% - 99% | Completed (100%) | 91% - 99% | 61% - 70% | 71% - 80% | 81% - 99% | 61% - 70% | 50% | N/A | Completed (100%) | 81% - 90% | Completed (100%) | 61% - 70% | 51% - 60% | 61% - 70% | Completed (100%) | 25% | N/A | 71% - 80% | 41% - 50% | Completed (100%) | 71% - 80%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 61% - 70% | 51% - 60% | 61% - 70% | 61% - 70% | 41% - 50% | 71% - 80% | 51% - 60% | N/A | N/A | Completed (100%) | 71% - 80% | 81% - 90% | 41% - 50% | 51% - 60% | N/A | Completed (100%) | N/A | N/A | 31% - 40% | 41% - 50% | N/A | Completed (100%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 21% - 30% | 21% - 30% | Not started (0%) | 11% - 20% | 21% - 30% | 41% - 50% | 51% - 60% | 25% | Not started (0%) | 61% - 70% | 71% - 80% | 51% - 60% | 31% - 40% | 1% - 10% | 11% - 20% | 41% - 50% | 0% | N/A | 61% - 70% | 11% - 20% | Not started (0%) | Completed (100%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | Completed (100%) | 91% - 99% | 71% - 80% | 71% - 80% | 81% - 99% | 51% - 60% | 25% | 81% - 90% | 61% - 70% | 61% - 70% | Completed (100%) | Completed (100%) | 81% - 90% | 51% - 60% | 61% - 70% | 75% | 81% - 99% | 81% - 99% | 61% - 70% | 61% - 70% | 41% - 50%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed (100%) | 61% - 70% | 51% - 60% | 41% - 50% | 71% - 80% | 71% - 80% | 51% - 60% | 25% | 81% - 90% | 41% - 50% | 61% - 70% | 71% - 80% | 71% - 80% | 51% - 60% | 41% - 50% | 41% - 50% | 25% | 81% - 99% | 81% - 99% | 1% - 10% | 31% - 40% | 51% - 60%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 51% - 60% | 51% - 60% | 21% - 30% | 1% - 10% | 21% - 30% | 11% - 20% | Not started (0%) | 25% | N/A | 31% - 40% | 61% - 70% | Not started (0%) | 21% - 30% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | 31% - 40% | 71% - 80% | 51% - 60% |  | Completed (100%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Completed (100%) | 91% - 99% | 71% - 80% | Completed (100%) | Completed (100%) | 51% - 60% | 75% | 81% - 90% | 41% - 50% | 81% - 90% | Completed (100%) | 81% - 99% | 81% - 90% | 71% - 80% | 71% - 80% | 75% | 81% - 99% | 81% - 99% | Completed (100%) | 71% - 80% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 99% | 81% - 90% | 91% - 99% | 71% - 80% | Completed (100%) | Completed (100%) | 51% - 60% | 75% | 61% - 70% | 41% - 50% | 71% - 80% | 71% - 80% | 61% - 70% | 51% - 60% | 71% - 80% | 71% - 80% | 50% | 81% - 99% | 81% - 99% | Completed (100%) | 61% - 70% | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 71% - 80% | 71% - 80% | 61% - 70% | 51% - 60% | 71% - 80% | 51% - 60% | 31% - 40% | 50% | 61% - 70% | 31% - 40% | 71% - 80% | 31% - 40% | 41% - 50% | 1% - 10% | 51% - 60% | 61% - 70% | 0% | 21% - 30% | 81% - 99% | 81% - 99% | 51% - 60% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Completed (100%) | 61% - 70% | 51% - 60% | 31% - 40% | 41% - 50% | 41% - 50% | 21% - 30% | 50% | Not started (0%) | 31% - 40% | 71% - 80% | 51% - 60% | 31% - 40% | Not started (0%) | 41% - 50% | 11% - 20% | 0% | 41% - 50% | 71% - 80% | 81% - 99% | 11% - 20% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 51% - 60% | 21% - 30% | 51% - 60% | 21% - 30% | 31% - 40% | 31% - 40% | Not started (0%) | 50% | Not started (0%) | 31% - 40% | 71% - 80% | 41% - 50% | 11% - 20% | Not started (0%) | Not started (0%) | 11% - 20% | 0% | 21% - 30% | 71% - 80% | 51% - 60% | 11% - 20% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 71% - 80% | 71% - 80% | 31% - 40% | 41% - 50% | 41% - 50% | 41% - 50% | 31% - 40% | 25% | 71% - 80% | Not started (0%) | 51% - 60% | 41% - 50% | 61% - 70% | 31% - 40% | 21% - 30% | 61% - 70% | 0% | 61% - 70% | 61% - 70% | 1% - 10% | 61% - 70% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 41% - 50% | 11% - 20% | Not started (0%) | 11% - 20% | Not started (0%) | 1% - 10% | 11% - 20% | 0% | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | 21% - 30% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo Power | WINconnect Pty LTD | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Completed | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed | Completed | Completed | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Completed | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | At risk | Not within schedule | At risk | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Not within schedule | At risk | Within schedule | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | Completed | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Completed | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Completed | Within schedule | Within schedule | At risk | Within schedule | Completed | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | N/A | N/A | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | At risk
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule | N/A | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Completed | At risk | At risk | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed | Within schedule | At risk | At risk | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Not within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | Within schedule | N/A | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule |  | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Completed | Within schedule | At risk | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Not within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Completed | Within schedule | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Not within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo Power | WINconnect Pty LTD | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | High level impact assessment has been conducted. |  |  | A high-level assessment of necessary business operational process and systems changes is near 100% completion noting the detailed assessment supporting the high-level view is still incomplete. | [7 empty] | n/a | [8 empty] | Less of an impact given geographic location being operated in is currently limited to Victoria
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Program established, Detailed plan in place and being tracked against. |  |  | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging. Additional changes to enable all other core operations post 1 December 2017 are being assessed. The aggressive timelines for systems build and testing, combined with contracting and establishment of an MC and the required implementation and testing combined systems is the basis of the 'at risk' status. | Planning progressing satisfactorily despite ongoing conversations around transition. | As a retailer, EEQ is heavily reliant on contracted parties being ready from go-live date. | [5 empty] | n/a | All necessary implementation plans are in place. Detailed cutover plan being finalised. | At risk due to process and system delays. | [6 empty] | Clarification received on handling in flight transactions across the cutover weekend.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [8 empty] | A detailed assessment of the revised legal and regulatory is significantly developed. In its current form the detailed assessment has provided the basis of Aurora Energy preparedness to date. The assessment continues to be informed by on-going AEMO market procedure consultation although remaining uncertainty over rule and procedure operations ensures this is still considered 'at risk'. Onboarding steps with Aurora Energy's prospective Metering Coordinator are further informing the detailed assessment. | Victorian Government embedded networks decision creates additional complexity. | Queensland jurisdictional safety requirements in relation to remote re-energisation are yet to be addressed. |  | scheduled and commenced. |  |  | Retailer timeframes to assess and agree to the T&Cs of the LNSPs are extremely tight and require the same pool of resources needed for establishing contractual agreements with Metering Coordinators and Embedded Network Owners. | n/a |  | Jurisdictional requirements for safety in relation to remote re-en/de-en in non-Vic jurisdictions unconfirmed. NSW decision to not allow remote re-en/de-en for 18 months; uncertainty of remaining jurisdictions. |  |  |  | Awaiting jurisdictional regulatory confirmation and update - due on 18 October | Semi-quantative Risk Assessments has been conducted by the AEC in conjunction with CMIG and final report will be discussed with safety regulators at Canberra on the 18th October.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [8 empty] | Aurora Energy has considered the wider and indirect regulatory implications of metering competition on business-as-usual activities (particularly given the existing regulatory framework was developed in the context of type 6 metering). | Progress has been made however late jurisdictional changes have created some schedule risks | Finalisation of jurisdictional changes to Metrology Part A to occur. |  | not yet scheduled. |  |  |  | n/a | Policy changes/decisions still being derived | Vic Government decision on PoC and timing of regulatory changes to reflect the decision not to proceed with PoC. Potential variance of process by QLD DNSP not accepting Service Orders from an MC. |  |  |  | Awaiting jurisdictional regulatory confirmation and update - due on 18 October |  |  |  | Still waiting on confirmation on VIC guidance on treatment of embedded network metering.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | All MC contracts received and in review/negotiation | Contract delivery is now behind revised schedule. | Engagement of MCs progressing but behind schedule. | Activity is well progressed customers and vendors as part of POC implementation. The major challenge is to finalise contractual arrangements with a Metering Coordinator, which will have to establish metering service capability in Tasmania where it currently does not exist. | Scheduled activities at risk due to complexities of numerous participants | Work is continuing on finalising commercial and performance arrangements. | The number of contracts and counter-parties put this item at risk. | in progress |  |  | Dependency on partnering with registered MC(s) | NBE is still waiting to receive and review contractual arrangements with MCs and MDPs. This places significant risk to the business with short timeframes to review and negotiate contracts before 1 December 2017. | Overall strategy has been developed and endorsed. Generic Meter provider contract drafted for new providers and contracts in play for current providers. | Requirements/services for various Service Providers yet to be finalised. Discussions with various Service Providers are in progress. MCs shortlisted and offerings currenlty under review. |  | Dependent on external providers delivery of commercial agreements | Negotiations have commenced | Internal management of this item | There is an external dependency where AEMO's MC registration might result in a rejection of some potential MC applications which poses a greater risk on Retailers.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Accreditation completed |  |  | Aurora Energy will be required to receive accreditation for using the B2B e-hub. The newly published B2B E-Hub Accreditation and Revocation process is currently being considered. The timeline and uncertainty for accreditation and registration activities of other participants (specifically, the Metering Coordinator role) also impacts on Aurora Energy's planning. Dialogue with the jurisdictional safety regulator has commenced. | [6 empty] | Currently liaising with AEMO to complete required activities | n/a | Request for registration/accreditation submitted as per AEMO deadlines | Despite 5.2, B2B accreditation is still required and for that purpose we still believe we will be in a position to complete in the required timeframe. |  |  |  | Internal management of this item
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Accreditation completed |  | Accreditation via testing | Fulfilment of the accreditation obligations is now being considered following AEMO publishing final version of the 'B2B Accreditation and Revocation Process'. | eHub application submitted, industry testing commenced | Email confirmation from AEMO |  |  |  |  | Currently liaising with AEMO to complete required activities | Scheduled for later in 2017. | Planning and preparation in progress | Per 5.2 and the limited timeframes for internal testing and commencement of Market Trial. |  |  |  | Internal management of this item
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Detailed assessment completed |  |  | This is underway and will be finalised following with the detailed assessment of operational and systems changes. | FTE validation is now complete and recruitment is under way | FTE impact analysis complete |  | No resource changes at this time |  |  |  | Procurement of additional resources underway. | Forecasted workload planning completed for key business areas and socialised to inform recruitment decisions. | Internal replanning drafted with resourcing requirements identified. |  |  |  | Internal management of this item |  |  | No additional staff operational required
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | The recruitment of specialist human resources to cater for the rule change is progressing as the need to fill key project roles arises. A key challenge is the availability of internal business subject matter experts to assist in change management. Further, total program resources represent a significant portion of Aurora Energy's total staff resource pool, which intensifies resourcing risk. | Recruitment of resources well under way. One area yet to start | Transition Support Team recruitment currently underway. | [5 empty] | Procurement of additional resources underway. | Recruitment for long lead time positions commenced. |  |  |  |  | Internal management of this item
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Training in development and training to schedule for execution |  |  | Training requirements are currently being assessed as part of the business process, change management and system planning. | Development of training tracking to key timelines | Initial modules of staff training commenced. Further training to occur October - November |  | Waiting on testing environment to be released, staff have been briefed and aware of industry change |  |  |  | Comprehensive training scheduled for November 2017. | Training requirements and resourcing determined and magnitude of change is understood, change planning started behind schedule. Learning curriculum being finalised and training material development commenced. Confirmation of some market transactions and treatments still pending which may impact training timelines given constraints in place. | At risk due to 5.2/4.1. |  |  |  | Internal management of this item
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Awaiting jurisdictional positions on Remote Re-Energisation/De-Energisation. Lack of clarification and certainty has delayed finalising processes and created uncertainty around increased cost of meter reads, by MC's, to customers. |  | Dependent on engagement of Metering partners | All impacted service order, B2B & B2M and business processes have been identified. Assessment of current and future processes is underway to enable gap analysis and identify process and system changes. Possible future changes puts the delivery scope and timeline at risk. | Transition and contingency planning have driven some late changes. | There remains a small number of outstanding business processes between market participants to be finalised. | The scope of change puts this item at risk. | commenced and in schedule | [5 empty] | Business process impact analysis almost complete. | [6 empty] | Back office service provider has assessed PoC impacts on BAU activity | In discussion with AEMO, we have concerns about the ENM discovery process in the MSATS market design.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Business Processes completed and Process Owners allocated. Validation continues to be done with MC's (depending on their maturity). Now under formal change control |  |  | Future business processes are currently being developed using the details from Work Package 1, 2 and 3, as well as the B2B procedures. The timeline for implementation and on-going procedural uncertainty is the basis for Aurora Energy reporting 'at risk'. | As above | Documentation of work instructions continuing. Majority of processes have been completed, but limited number of complex processes are being discussed. | The scope of change puts this item at risk. | commenced and in schedule |  |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing |  | Business process design mainly completed with 3-4 weeks of delays against baseline plan. Relevant number of outstanding clarifications to be addressed by Oct-end. | No longer within schedule due to system delay per 5.2 and 4.1. Development of PoC processes in progress.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Cycle 2 of Industry test completed |  |  | UAT and industry testing has started |  | EQL end to end processes walk throughs continuing. Testing continuing. |  |  |  |  | Delays from third parties are impacting our ability to participate in industry testing |  | Industry Testing underway with Cycle #2. An high number of end-to-end Test Scenarios is not complete, posing a risk to success of Cycle #3 and overall Industry Testing | At risk due to 5.2/4.1. |  | Scheduled for end of October. |  | AEMO dry run is likely to impact our bilateral testing.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [8 empty] | Detailed requirements have been gathered and vendors have deliver the changes to market messaging systems. |  |  |  | Vendor at 79% completion of overall project plan |  |  |  |  | Mass Market Design activities complete and Large Customers design in progress. Change requests being assessed and planned. | In addition to 4.1, identification of any interim system changes required to be compliant on 1 Dec drafted. | [7 empty] | Confirmation required on proposed process for ENM discovery in MSATS.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Drop 6 of 7 have been delivered |  |  | Aurora Energy has engaged its key market system vendors. System build has completed for essential market connectivity and system functionality for 1 December 2017 apart from future defect releases. |  | Build now complete. Several Change Request under analysis. |  |  |  |  | System development is reliant on external vendors, any delays in final market procedures will impact readiness activities. | Being managed by external vendors. | Build progressing on track, including the development of approved change requests. | Updated to 'Not within Schedule' given delays in system changes. Dependent on completed development and implementation of B2B Translation Tool, and any changes per 5.1. Uncertainty regarding B2B Errata process and timelines for potential schema updates.
5.3 |  | The internal testing of market systems for your business | [5 empty] | UAT and Regression Testing in progress |  |  | Aurora Energy is progressing through System Test and has started UAT and Industry test activities. |  | SIT Cycle 4 underway. UAT cycle 2 underway. Industry Testing Cycle 2 complete. Currently internal testing is behind schedule. | [5 empty] | Schedule to occur later in 2017. | Testing is progressing on track. Risks remain around the compressed schedule. | As per 5.2 |  |  |  |  | Continuing for B2M and B2B testing
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Completed accreditation scenario's with e-hub and participated in Cycle 1 of Industry Test |  |  | Aurora Energy is currently moving through AEMO's second round of testing. eHub connectivity has been tested and established and B2B accreditation testing has Completed and awaiting confirmation from AEMO. | Departure from previously agreed B2B processes by one participant & delays by other industry participants is increasing readiness risk. | Only partial completion of cycle 1 and 2 testing due to defects with testing partners and AEMO. In addition there are a limited number of misalignments between AEMO procedures, XSD and validation modules. | [5 empty] | Cycle two almost complete with some testing deferred to cycle 3. | Industry Testing progressing through Cycle #2 behind schedule. | As per 5.2 Agreement with test partners (particularly MCs) yet to be confirmed. No longer joining Market Trial Cycle 2. Plan to join in Cycle 3. |  |  |  |  | Testing with market participants in Cycle 2 of Phase 3, however as we're progressing with the testing, there are some issues identified with key participants and the overall status of Industry Testing report shows "Planned" vs "Actual" testing has a significant variance.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Cycle 2 of Industry test completed |  |  | Aurora Energy is planning to separately initiate performance testing, as distinct from market interface testing, scheduled for October 2017. Aurora Energy is reliant on key system vendors to perform performance testing and therefore continues to consider this to be 'at risk' |  | EEQ systems are functioning as designed and validation is complete for all outbound transactions, however completion of industry test scenarios relies on testing partners readiness. | [5 empty] | Schedule to occur later in 2017. | Batch performance and sizing in progress | As per 5.2 |  |  |  | Not able to validate performance in production environments.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Approach and highlevel plan approved - preparing for Dress Rehearsals. |  |  | A Transition Plan will be completed once commercial agreements with Metering Coordinator(s) are finalised. Aurora Energy is progressing discussions with TasNetworks regarding transition and cutover planning. We are now looking to include our Metering Co Ordinator in these meetings. | EA's planning is progressing however it is dependent on industry transition and cut-over planning. | Draft Deployment Approach prepared |  |  |  |  | Transition plans are dependent on timely delivery of earlier program stages | Schedule to occur later in 2017. | Deployment Strategy confirmed and Detailed Cutover Plan progressing on track. | Internal cutover planning commenced, based on output from ITCFG. |  |  |  | Transition and cut over working group has finalised document. Both brand run sheets are completed. Awaiting further information on the jurisdictional regulatory changes that may impact these outcomes. |  |  | Clarification regarding handling of inflight transactions across the cutover weekend becomomg clear at industry level.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Transition planning is progressing to schedule |  |  | Data Cleansing has begun and BCT activities have started. |  | Dress rehearsals scheduled for October. |  |  |  |  | Draft version of internal Momentum Transition and Cut Over Plan in progress | Schedule to occur later in 2017. | Business Transition planning started and on track. Data conversion for Meter Standing Data (MC/ENM role, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our Build / Test activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover;
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo Power | WINconnect Pty LTD | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms, within the context of the timeframe and procedural uncertainty. | [7 empty] | n/a
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Aurora Energy has implemented a program of work to effectively and efficiently work towards market compliance. | Accelerated transition planning. Hypercare planning ramped-up. | EEQ continues to work with delivery partners in go-live preparations | [5 empty] | n/a
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Meeting with ACT Government conducted- no expected barriers at this point. NSW Govt has proven to be more challenging to engage. |  |  | Aurora Energy has implemented a program of work to interpret and implement the POC reforms that factors in the challenging timeframe and procedural uncertainty. Aurora Energy continues to engage with AEMO and other market participants to inform its assessment. |  | Ongoing discussions with the Department of Energy and Water Supply and participation in development of a national framework for remote re-energisation. At this stage it is unlikely that remote re-energisation will be available to retailers on 1 December 2017. | [5 empty] | n/a |  | Monitor jurisdictional saftey discussion. |  |  |  |  | Pending decision from safety regulators on the use of remote services.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Internal documents related to Cth legislation are listed by branch and business unit. Dates for update and review have been set. Code of Practice drafted for Smart Metering and in review. |  |  | Aurora Energy continues to liaise with the Tasmania Government and WorkSafe Tasmanian to identify jurisdictional requirements that require amendment to facilitate metering competition. |  | AEMO and Department of Energy and Water Supply are currently addressing jurisdictional changes to Metrology Part A. Will need to be endorsed by COAG Energy Council by November. | [5 empty] | n/a |  | Closely review and monitor Vic Government's progress of the OIC. Discussions with DBs ongoing.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [6 empty] | MC contract submitted and now in review. Further contract development underway. |  | Aurora Energy's procurement process for securing a Metering Coordinator for small customers is at a progressed state with a preferred MC selected but not yet contracted. | [7 empty] | Adopting of staged approach for new connections and adds and alts - still awaiting confirmation that staged approach includes adds and alts. | Origin has onboarded additional Business and Technology resources | [5 empty] | AEMO to provide more information on pending MC applications and provide transparency on their registration statuses. AEMO to provide a list of registered MCs by early November so Retailers can take necessary actions in order to comply with the new set of Rules.
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy has submitted its accreditation application and is proceeding on the assumption that accreditation will be received. | [7 empty] | n/a |  | Dependent on AEMO delivery of B2B Translation Tool, and our implementation and testing. Draft B2B Accreditation Guide under review.
2.5 |  | The fulfilment of accreditation and registration obligations | [17 empty] | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [9 empty] | Tracking FTE uplift weekly | [6 empty] | n/a
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | Aurora Energy has established the core group of its Testing team and will continue to expand its testing resources over the coming months. | Tracking FTE uplift weekly | [6 empty] | n/a
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [9 empty] | Regular reporting in place to track completion of training development | Training approach being reviewed/revised. | [5 empty] | Access to additional, resources through external business consultants. |  | Reallocation of resources to cover this activity.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [8 empty] | Aurora Energy continues to invest considerable effort in participating in AEMO procedural consultation. Aurora Energy is proceeding on the basis of the currently available information and must continue to manage the risk of final procedures changing. | Added additional capacity to process development.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Additional resourcing on board |  | as above | Remaining (complex) work instructions are being discussed by senior project staff and SMEs for resolution. | [7 empty] | Reallocation of resources to cover this activity.
4.3 |  | The validation of business processes during industry testing | [6 empty] | Via cycle 1. Cycle 3 will concentrate on full e2e process testing | Moved some test cases to later cycles. Planned for additional bilateral testing |  |  | Daily EQL Industry Testing Working Group established
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [18 empty] | Assisting AEMO with testing of B2B Translation Tool. Reviewed draft Vic OIC.
5.2 |  | The development and build of appropriate market systems for your business | [10 empty] | If Change Requests are approved, additional system build elements will be required. | [7 empty] | Closely monitoring IEC/B2BWG/ASWG discussions and potential for additional B2B Errata/schema changes prior to 1 Dec.
5.3 |  | The internal testing of market systems for your business | [10 empty] | Additional testing resources have been allocated to assist in fast-tracking test executions for UAT cycle 2 and 3. | [7 empty] | As per 5.2
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | C&I instance testing to commence later. Using same PoC code line. |  |  | AEMO and B2B Working Group to align PoC technical solution with the market procedures as an entry criteria to cycle 3 of industry testing. | [7 empty] | As per 5.2 |  |  |  |  | AEMO has been requested in Exec Forum to facilitate Cycle 4, considering most of the Cycle 2 test cases will fall on to Cycle 3 and that might not be adequate for readiness.
5.5 |  | The validation of performance of market systems during industry testing | [18 empty] | As per 5.2
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [8 empty] | Aurora Energy transition and cutover preparations are being supported by its attendance at AEMO cutover and planning workshops.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Retailer Participation
References:
[9 empty] | AEMO | http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Participant-information/Current-participants/Current-registration-and-exemption-lists
[9 empty] | AER | https://www.aer.gov.au/retail-markets/authorisations/public-register-of-authorised-retailers-and-authorisation-applications
[9 empty] | ESC | http://www.esc.vic.gov.au/project/energy/2075-licensing/
Retailer | On Oct 2017 Report? | On Sep 2017 Report? | On Aug 2017 Report? | On Jul 2017 Report? | On Jun 2017 Report? | On May 2017 Report? | On April 2017 Report? | On March 2017 Report?
1st Energy Pty Ltd | No | No | No | No | No | No | No | No
ActewAGL Retail | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
AGL | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Alinta Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Aurora Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Blue NRG Pty Ltd | No | No | No | No | No | No | No | No
Click Energy Pty Ltd | No | No | No | No | No | No | No | No
Covau Pty Limited | No | No | No | No | No | No | No | No
COzero Energy Retail Pty Ltd | No | No | No | No | No | No | No | No
Diamond Energy Pty Ltd | No | No | No | No | No | No | No | No
Energy Locals Pty Ltd | No | Yes (using August report) | Yes | No | No | No | No | No
EnergyAustralia | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Enova Energy Pty Ltd | No | No | No | No | No | No | No | No
Ergon Energy Queensland (retail) | Yes | Yes | Yes | Yes | Yes | Yes | Yes (using March report) | Yes
ERM Power Retail Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | No | No
Globird Energy Pty Ltd | No | No | No | No | No | No | No | No
Lumo Energy (reporting with Red Energy) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
M2 Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes (using May report) | Yes | Yes | Yes
Macquarie Bank Limited | Yes | Yes | Yes | Yes | Yes | No | No | No
Mojo Power Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Momentum Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Next Business Energy Pty Ltd | Yes | Yes | Yes | Yes | No | No | No | No
Online Power and Gas Pty Ltd | No | No | No | No | No | No | No | No
Onsite Energy Solutions Pty Ltd | No | No | No | No | No | No | No | No
Origin Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Pacific Hydro / Tango | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
People Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Pooled Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No
Powerdirect Pty Ltd (reporting with AGL) | Yes | Yes | Yes | Yes | Yes | No | No | No
Powershop Australia Pty Limited | Yes (using Sep report) | Yes | Yes (using July report) | Yes | No | Yes (using April report) | Yes | No
Progressive Green Pty Ltd | No | No | No | No | No | No | No | No
Qenergy Limited | No | No | No | No | No | No | No | No
Red Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Sanctuary Energy Pty Ltd | No | No | No | No | No | No | No | No
Simply Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
SparQ Pty Ltd (Sumo Power) | Yes (using Sep report) | Yes | Yes | Yes (using June report) | Yes | No | No | No
Stanwell Corporation Limited (Stanwell Energy) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No
WINenergy Pty Ltd (WINenergy) | Yes | Yes | Yes | Yes | No | No | No | No

## Distributor Reports
| 2017-10-09 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule | Medium | AAD has completed internal testing with industry and bilateral testing continuing. Rollout plans and schedules are now being finalised. Business plans are being implemented with a focus on internal and external communication. Total progress is estimated at 76%. | [7 empty] | [Meter Provider and Meter Data Provider, Status = Within schedule, Risk = Medium]: AAD has recently received Type 3-4 accreditation and is continuing work on post PoC procedures and processes. [Metering Coordinator, Status = Within schedule, Risk = Low]: AAD has submitted the required information (for initial MC) to AEMO and has provided responses to clarification questions. | [5 empty] | AAD has submitted the required information for accreditation as the initial MC for type 5, 6 and 7 metering installations and has responded to AEMO queries. Type 3-4 metering accreditation has now been received and AAD is continuing work on systems development to maintain compliance with the PoC reforms. Registration as an MC for these latter meter types has been submitted. While industry testing has revealed no significant issues to date, AAD has reservations about the level of participation to date.
| Ausgrid | At risk | Medium | Awaiting resolution of NSW legislative changes in order to finalise staged transitional process requirements. Internal system testing continues, however, timeframes remain tight. | [7 empty] | As above
| AusNet Services | Within schedule | Medium | On track for 1st December cutover and go-live. Other participant readiness across the NEM remains a risk, the majority of contributing concerns are not relevant within Victoria given metering exclusivity. | [7 empty] | Refer to overall comment.
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | At risk | Medium | CitiPower/Powercor is continuing to progress its build/test phase. Program timing remains challenging with no tolerance for delays or further requirement changes. CitiPower/Powercor has participated in industry planning for market trials and 1 December 2017 industry transition and cutover. We have hosted an information forum for retailers. We are available to meet one-one with any industry participant at their request. | [7 empty] | The Victorian Government has decided that distributors will be required to continue to install remotely read interval metering after 1 December 2017 compliant with the Victorian AMI functionality and service levels specifications and that existing and new/replacement AMI metering will be continue to be classified as Type 5 metering. In line with this decision and the draft Orders in Council published by the Victorian Government, CitiPower and Powercor will not be making any changes to how we classify either existing or new/replacement AMI meters in MSATS, nor any changes to our forward estimates, meter data validation and/or substitution methodologies. The Government Orders are yet to be finalised and a discussion paper on embedded networks yet to be published.
| Endeavour Energy | Within schedule | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures, which requires significant system and process changes over a period of only 6-7 months to design, develop and test. This short timeframe increases the risk on quality vendor delivery, however to date our vendors have made good progress against our schedule having provided periodic system functionality drops enabling us to commence testing. A key dependency for our PoC project, which is technical currency of our core system, has been successfully implemented. Another project risk is that different interpretations from each market participant of the Rules, procedures and jurisdictional obligations may result in an ineffective or unworkable processes between businesses. To mitigate this we are actively engaging with retailers and metering service providers to foster an open dialog on managing key processes. These engagements are proving beneficial as they have in some cases highlighted differences in our assumptions and approaches to some of the processes at an early point of the project. To help industry and to provide us better confidence that our solution will work effectively with other market participants, we are participating in the industry testing and additional bi-lateral testing with other participants. We are also actively participating in various industry working groups to ensure an effective transition and cutover to the new Rules with minimal customer impacts. To assist the industry mitigate go-live risks that can impact on the customers, we are participating in the Staged Approach. | [7 empty] | [See project comment] | [5 empty] | This report is for Endeavour Energy as at 30 September 2017. Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5, 6 & 7 metering installations from 1 December 2017. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. The activities for the Market Systems testing and cutover are dependent on the development and build of the appropriate market system which is currently at risk.
| Energex Ltd. & Ergon Energy Corporation Ltd. | At risk | Medium | The Distribution project is tracking slightly behind its intended schedule however is confident that it will meet 1 December 17 compliance requirements. The project is undertaking its System Integration Testing and Industry Testing release in priority order. The changed transitional approach is adding additional work to a tight timeline at a critical point in the project. Similar to last month, the project's key focus is on testing its Market systems and new processes. Industry testing and ehub Accreditation testing is also a key focus. | [7 empty] | The Distribution project is tracking slightly behind its intended schedule however is confident that it will meet 1 December 17 compliance requirements. The project is undertaking its System Integration Testing and Industry Testing release in priority order. The changed transitional approach is adding additional work to a tight timeline at a critical point in the project. Similar to last month, the project's key focus is on testing its Market systems and new processes. Industry testing and ehub Accreditation testing is also a key focus.
| Essential Energy | At risk | High | Essential Energy's PoC program is progressing, with system changes on the critical path to deliver compliance by 1 December 2017. The program has delivered all systems changes required for industry testing, with positive results for cycle 1 & 2 of testing. A number of business efficiency system changes have been deferred for delivery post 1 December. A significant issue exists with Essential Energy's Initial MC registration, this is being worked through with AEMO. | [7 empty] | [Distributor, Status = Within schedule, Risk = High]: Risk rating remains at high Program schedule is tight and does not provide tolerance for any delays. Some business efficiency items deferred for delivery post 1 December. [Meter Provider, Status = Within schedule, Risk = Low] [Meter Data Provider, Status = Within schedule, Risk = Medium]: Risk rating is classified as moderate for systems changes to support amended B2B framework, including to receive and process meter exchange information to enable timely publishing of final readings for Type 5 & 6 meters. | [5 empty] | Essential Energy will be an Initial MC, MDP and MP for Type 5 and 6 meter installations connected as at 1 December 2017. Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Networks | Within schedule | Medium | With 9 weeks to go-live on 3 December 2017, JEN's build is complete, User Acceptance Testing, Industry Testing and Bilateral Testing is in progress as is end-user training. Transition, resumption and contingency planning is underway. Retail partner readiness risks to the JEN Program remain as AMBER given the severely limited industry testing planned prior to go-live. | [7 empty] | With 9 weeks to go-live on 3 December 2017, JEN's build is complete, User Acceptance Testing, Industry Testing and Bilateral Testing is in progress as is end-user training. Transition, resumption and contingency planning is underway. Retail partner readiness risks to the JEN Program remain as AMBER given the severely limited industry testing planned prior to go-live.
| SA Power Networks | At risk | Medium | SAPN continue to face significant project challenges, particularly with regards to the development of the market system. At this point we still believe that we will be in a positon to achieve minimum market compliance. Project team is working closely with the impacted Business Units, including CitiPower/PowerCor, to ensure manual work arounds are in place especially during the transition period. | [7 empty] | See overall project status comment
| TasNetworks | At risk | Medium | TasNetworks intends to be ready for the 1st December 2017. TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality which may have a flow on effect to market processes, training activities and potentially other market participants. Some program activities may need to be completed post 1st December. Whilst there are some challenges with the Market Systems other program activities have progressed and are now on schedule.
| United Energy | Within schedule | Medium | Preparations continue to progress well. UE participated in cycle 1 and 2 of market trials and bi-lateral testing , with generally positive results, although noting that only a subset of the industry is participating. The amber risk rating reflects general concerns about industry readiness, the possible operational impact of market disruption after go-live and the Vic Govt Orders not yet being gazetted. | [7 empty] | UE operates in Victoria only. Jurisdictional status reflects overall position. Vic deferral details are yet to be formalised via changed Govt orders. | [5 empty] | Key concerns regarding UE (and industry) readiness are as follows: 1) The Victorian Government draft orders confirm the assumptions that 1: UE's role as MC for new meters after 1 Dec will be on the basis of existing regulated services, 2: New meters after 1 Dec will need to meet only the Vic AMI specifications and 3: New meters after 1 Dec will be classified as Type 5 MRIM, per current practice, and existing meters will remain Type 5 MRIM. Until the amended Orders are finalised, the possibility of unexpected requirements or obligations remains. UE accepts that the likelihood of unexpected change at this late stage is very low, but will remain concerned until the Orders are finalised and gazetted (scheduled for 10 October 2017). 2) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. UE's compliance is also dependent on the draft Vic Govt amended Orders being gazetted (scheduled for 10 October 2017). Assuming the Vic Orders are gazetted and retailers appoint new MC's in a reasonable timeframe, UE will progressively exit its role as MC, MP and MDP for a small number of second-tier customers by 1 Dec 2018 in accordance with the Orders. 3) UE is concerned that the complexity and scale of changes may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections and supply processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers. It is important that higher participation in readiness reporting and in the remaining testing phases is achieved for a positive 1 Dec 17 start.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule | Medium
| Ausgrid |  |  | At risk | Medium
| AusNet Services | [10 empty] | Within schedule | Medium
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | At risk | Medium
| Endeavour Energy |  |  | Within schedule | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | At risk | Medium
| Essential Energy |  |  | At risk | High
| Jemena Electricity Networks | [10 empty] | Within schedule | Medium
| SA Power Networks | [6 empty] | At risk | Medium
| TasNetworks | [8 empty] | At risk | Medium
| United Energy | [10 empty] | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 61% - 70% | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | 91% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | 81% - 99% | Completed (100%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 61% - 70% | 81% - 99% | 81% - 99% | Completed (100%) | 81% - 90% | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | 91% - 99%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 61% - 70% | 61% - 70% | 81% - 99% | 81% - 99% | 41% - 50% | 61% - 70% | 71% - 80% | Completed (100%) | 71% - 80% | 71% - 80% | 91% - 99%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 51% - 60% | 71% - 80% | 81% - 99% | 81% - 99% | 81% - 90% | 61% - 70% | 61% - 70% | Completed (100%) | 61% - 70% | 81% - 99% | 91% - 99%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 61% - 70% | Completed (100%) | 71% - 80% | 81% - 99% | 61% - 70% | 81% - 90% | 41% - 50% | Completed (100%) | 61% - 70% | 61% - 70% | 91% - 99%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 71% - 80% | 81% - 99% | Completed (100%) | 71% - 80% | 71% - 80% | 81% - 99% | Completed (100%) | 71% - 80% | 51% - 60% | Completed (100%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 71% - 80% | 81% - 99% | Not started (0%) | 81% - 90% | 71% - 80% | 41% - 50% | N/A | N/A | 11% - 20% | 81% - 90%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 31% - 40% | 41% - 50% | 81% - 99% | 41% - 50% | 21% - 30% | 61% - 70% | 31% - 40% | 71% - 80% | 31% - 40% | 31% - 40% | 81% - 90%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 51% - 60% | 71% - 80% | Completed (100%) | Completed (100%) | 91% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%)
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 51% - 60% | 41% - 50% | Completed (100%) | Completed (100%) | 91% - 99% | 91% - 99% | 81% - 99% | Completed (100%) | 91% - 99% | 51% - 60% | Completed (100%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | 41% - 50% | Not started (0%) | 41% - 50% | 41% - 50% | 31% - 40% | 61% - 70% | 61% - 70% | Completed (100%) | 21% - 30% | 1% - 10% | 61% - 70%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 81% - 90% | Completed (100%) | Completed (100%) | 81% - 90% | Completed (100%) | Completed (100%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 61% - 70% | Completed (100%) | 81% - 99% | 81% - 99% | 41% - 50% | 81% - 90% | 81% - 99% | Completed (100%) | 81% - 90% | 61% - 70% | Completed (100%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | 31% - 40% | 51% - 60% | 71% - 80% | 71% - 80% | 61% - 70% | 61% - 70% | 61% - 70% | Completed (100%) | 61% - 70% | 31% - 40% | 91% - 99%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 21% - 30% | 51% - 60% | 51% - 60% | 51% - 60% | Completed (100%) | 71% - 80% | 51% - 60% | 31% - 40% | 51% - 60% | 1% - 10% | 61% - 70%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 1% - 10% | 51% - 60% | 51% - 60% | Not started (0%) | 21% - 30% | 41% - 50% | 51% - 60% | N/A | 61% - 70% | 1% - 10% | 61% - 70%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 21% - 30% | 41% - 50% | 71% - 80% | 81% - 99% | 31% - 40% | 51% - 60% | 31% - 40% | Completed (100%) | 71% - 80% | 31% - 40% | 91% - 99%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 41% - 50% | Not started (0%) | 51% - 60% | Not started (0%) | 41% - 50% | 41% - 50% | 31% - 40% | 61% - 70%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Completed | Within schedule | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | At risk | Completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule | Completed | Completed | Completed | Within schedule | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | At risk
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | At risk
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Completed | Completed | Within schedule | Completed | Completed | Completed | Within schedule | At risk
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | At risk | Completed
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk | Completed
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Completed | Completed | Completed | At risk | At risk | Completed | Completed | Within schedule | Within schedule | Completed
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Completed | Within schedule | At risk | At risk | Within schedule | At risk | Completed | At risk | Not within schedule | Completed
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | At risk | Within schedule | At risk | Within schedule | At risk | Within schedule | Completed | At risk | Not within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | Within schedule | At Risk | Within schedule | Within schedule | At risk | Within schedule | N/A | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | The high level impact assessment is complete. Some gaps may be identified as part of the more detailed program of works to be carried out in the period through to December 2017. | Impact assessment undertaken in line with staged transitional process |  |  |  | Business review of the Organisational Impact assessment is almost completed. |  |  | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD has completed all internal test cycles ahead of schedule. Industry and bilateral testing continue in accordance with the AEMO schedule and agreed plans between participants. AAD is currently working with retailers on retailer specific items. | Planning for final elements of staged transitional process underway |  |  |  | The Business Readiness Framework has been finalised and has received formal approval. |  |  | Completed ( July 2017) | TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | AAD has circulated its MC terms and conditions. | No jurisdictional safety requirements in place yet. Awaiting NSW legislative changes for staged transitional process. |  |  |  | Ongoing activity - currently in progress by organisational specialists. |  |  | Completed | Initial MC (Type 6) T&C's finalised and provided to Retailers. | This item will be marked as complete when the Victorian Orders in Council are gazetted, which is now expected on 10 October. No further action is required.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | AAD has commenced work on legal agreements relating to customer contracts, terms and conditions for provision of data/information to customers, etc. This work will continue until approximately September. The initial MC agreements with retailers has been circulated. | In progress. No jurisdictional safety requirements in place yet. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - the project is working with the internal regulatory team to ensure all regulatory requirements are met. |  |  | Within schedule; Work in progress with the business |  | This work is complete, but is based on the draft outcomes in the Vic Govt Order-in-Council. This item will be marked as complete when the Victorian Orders in Council are gazetted, which is now expected on 10 October. No further action is required.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | As above. | Initial MC T&Cs now issued. Ring-fenced service agreements in progress. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - amendments under consideration by each contract owner, updates will be made using existing procurement and contractual processes. Assessment of new agreements/contracts also ongoing. |  | Deemed T&C's have been issued to Retailers who have Customers on the JEN as draft until OIC is final. | Within schedule; Work in progress with the business | Initial MC (Type 6) T&C's finalised and provided to Retailers. | UE issued its Initial MC Contract in accordance with the relevant rules prior to 1 September, based on the draft Order-in-Council documentation issued by the Vic Govt on 20 July. Subsequent details issued by the Vic Govt require amendments to the Initial MC terms and conditions. These revisions are being developed and a revised version is expected to be issued by the 15 October deadline. However this is subject of the Victorian Orders being gazetted on 10 October. No other major commercial preparations are required.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | AAD has completed all requirements for the B2B accreditation for DNSP activities. We are awaiting clarification from AEMO on final requirements. MC registration (contestable and regulated) has been submitted to AEMO. AAD has responded to clarification questions relating to the MC registration application. Type 4 accreditation has been received and AAD is working towards systems compliance with PoC requirements. | Appropriate applications have been submitted |  |  |  | All of the required accreditation and registration documentation and associated activities have been completed. The project is currently progressing its self-accreditation with the E-Hub which is almost finalised. |  | Still waiting for AEMO written confirmation of accreditation. | Completed |  | Based on Vic Govt draft orders, UE continues to assume that accreditation as a Type 4 MDP is not required. Registration as MC and accreditation for use of e-Hub are required.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | As above. | Appropriate applications have been submitted |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The project is clear on the accreditation activities required for compliance and has almost finalised all of its associated obligations as planned. The project is in the process of collating Retailer feedback on the draft T&C's submitted to AEMO, which is one of the final steps required to fulfil all obligations. | Significant issue with Essential Energy's Initial MC registration |  | Within schedule; MC registration and accreditation logged with AEMO; acknowledgement received |  | Accreditation for use of e-Hub is progressing well, with testing and self-accreditation nearing completion. Registration as MC for Type 5, 6 and 7 meters is pending AEMO confirmation. Additional documentation was requested by AEMO on 5 October and was sent by UE on 9 October. The "at risk" flag reflects the remaining uncertainty about accreditation as a Type 4 MDP (which UE is assuming is not required).
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | A detailed assessment of ongoing operational resource requirements has commenced to ready the business for the transition and post PoC go-live activities. | Planning for final elements of staged transitional process underway |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - Impact assessment is approved and recruitment and training of new staff is underway. |  |  | Within schedule; Work in progress with the business | TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality | Change impact assessment and personnel budgets complete. Team-by-team impacts covered by 3.2 and 3.3 below.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Recruitment processes have now begun to fill these roles. | Planning for final elements of staged transitional process underway |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The engagement of additional resources has commenced. With the first tranche of new staff undergoing training. The proposed Transitional Approach will have a yet to be calculated impact on resources. Early estimates indicate that this can be absorbed with the return of project SMEs to BAU. |  |  | Not Applicable | TasNetworks is preparing to understand the role for operational functions but not yet confirmed FTEs as a result of the Market Systems readiness for 1 December. | Operational backfill resources in place to allow subject matter experts to carry out testing. Preparation is continuing for securing post-go-live operational resources, based on a Change Impact Assessment for all impacted teams. There is a limited requirement for additional resources after the stabilisation period following go-live.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | AAD has encountered delays in the revision of its S&I Rules due to additional consultation being required by the ACT Government. This may affect delivery of training but will not affect other deliverables or go-live. | Planning for final elements of staged transitional process underway. Operational staff to participate in Cycle 3 Industry Testing |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The training approach is progressing as planned, with training collateral in development. |  | End user training delivery is in progress. | Within schedule; All business units training delivery will commence soon | TasNetworks has commenced implementing the Training Plan for internal staff. Engagement with other market participants has allowed end-to-end processes to progress. | Work instructions are complete and are being verified as part of User Acceptance Testing. Training materials are nearing completion. Training delivery has commenced in certain business areas, but the majority of training will be delivered in November.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Detailed workshops with retailers to develop systems and processes have been completed. Further consultation continues in this area. Rollout of new processes is underway. | Planning for final elements of staged transitional process underway |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | High priority ‘to be’ business processes are complete. Lower priority ‘to be’ business processes are currently under review, with the intention of moving them to the Release 2 Schedule. |  |  | Completed (April 2017) | Business Process impacts well understood, challenges around final Market Systems solution may impact processes for 1 December.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | As above. | Planning for final elements of staged transitional process underway |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | High priority ‘to be’ business processes are completed and approved. Lower priority ‘to be’ business processes are currently under review, with the intention of moving them to the Release 2 Schedule. Still working through the detailed work instructions. |  |  | Within schedule; Finalisation of all business processes | To-be business processes well understood, intend to document the processes toward the backend of the project for approval.
4.3 |  | The validation of business processes during industry testing | [5 empty] | AAD all defects encountered during testing being addressed within schedule. Minor data and interpretation errors have been encountered and AAD has addressed these with the related parties. | Operational staff to participate in Cycle 3 Industry Testing |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The first cycle of industry testing has not revealed any significant assumption misalignment between participants. Cycle 2 has seen significant progress, and has uncovered some issues that have required engagement with other participants to resolve. Concerned by the level of industry testing that appears to be being undertaken through the MSATS browser rather than in participants' market systems. Creates the risk that data, assumption and validation issues are not found in cycle 1 of Industry testing. Intermittent AEMO Ehub issues are impacting industry testing. Bilateral testing has been limited due to competing priorities for our counterparties. A significant number of industry tests have been moved from cycle 2 to cycle 3 due to retailers failing to initiate tests. We are deeply concerned by the number of test cases involving MCs that have yet to be tested. |  |  | Within schedule; Industry testing still underway | TasNetworks is participating in industry testing during Cycle 2. | UE is has participated in cycles 1 and 2 of the AEMO-led Market Trials and has concurrently completed bi-lateral testing with multiple retailers in UE's distribution area. UE remains concerned that varying interpretations and inconsistencies between industry participants may emerge amongst those participants which have not commenced industry testing. However the results from industry testing completed to date have been positive.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | AAD has a change request process underway for several minor amendments to system design. Changes are at various stages ranging from conceptual design through to development. | All solution designs are complete. |  | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | Requirement specifications and high priority designs are complete. The project's phased implementation approach ensures the achievement of compliance in release 1 and further efficiencies in release 2 of which will occur post 1 December 2017. The Proposed Transitional Approach brings additional risk due to the significant re-work and potential of additional scope. The risk of misalignment of assumptions between participants continues, with assumptions being realised throughout participation in Industry Testing. |  |  | Within schedule; Work in progress with the business |  | Based on Vic Govt advice that existing and new meters are to remain Type 5 MRIM, all solution impacts have been assessed.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | All initial code has been received by AAD. System updates relating to change requests (see above) are resulting in ongoing development efforts. | The implementation phase is complete. All software builds are in testing. |  | Critical path has little remaining contingency | See above comment | The build and test phase is progressing well however is slightly behind schedule. There is very little contingency remaining in the build schedule. Key Risk: changes in retailer / MC assumptions of the interpretation of the B2B procedures may impact the build schedule. It is surprising how few issues of assumption misalignment have been raised in industry testing. Raises questions as to the quality of the testing or lack of testing progress in the more contentious transactions. | Agile delivery approach applied to system changes. Sprints required for market testing will be delivered just prior to commencement of market testing. |  | Working closely with VPN to ensure all Day 1 requirements are built and tested | TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality | Development of all solution components is complete.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Internal testing is approximately 90% complete. AAD has concerns around industry testing based on the participation rates to date. | Testing is well advanced. 15 testers are working across all solution components. Timeframes remain tight. This task remains "At Risk" given the volume of testing required. |  | Note: Refer above. |  | Testing is currently tracking to schedule. However, testing timelines are compressed and therefore are 'At risk'. |  |  | Refer to Section 5.2 comment | Testing progress has been impacted by the level of defects identified to-date. | End-to-end integration testing of the core "market" solution that will support the MC changes is complete. Cycle 1 of User acceptance testing is complete and cycle 2 is on track to commence 16 Oct.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | As above. | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete. Cycle 2 of Industry testing is nearing completion. |  | Note: Refer above. |  |  |  | The reporting of industry test results are unnecessarily complicated and in some instances not accurate. It is not possible to assess the level of regression risk from the industry testing reports. AEMO needs to improve the accuracy and relevance of reporting. | Testing of market system interfaces will depend on the built solution and appropriate participation. | TasNetworks is participating in industry testing during Cycle 2. | Cycles 1 and 2 of Market Trials and bi-lateral testing with retailers in UE's distribution area are complete. On track to commence cycle 3 on 16 Oct.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | As above. | Testing with market systems is underway. | Experiencing difficulties with retailers not being available / ready for industry and bi-lateral testing | Note: In line with CitiPower/Powercor program delivery schedule. |  | A significant number of industry tests have been moved from cycle 2 to cycle 3 due to retailers failing to initiate tests. We are deeply concerned by the number of test cases involving MC's that have yet to be tested. It is surprising how few issues of assumption misalignment have been raised in industry testing. Raises questions as to the quality of the testing or lack of testing progress in the more contentious transactions. |  | The industry test plan performance testing is out of scope. We are unsure as to why this line item is in the report as there is no scheduled structured industry performance testing in AEMO's Industry Program Plan. | Within schedule; SAPN participated in Phase 3, cycle 2 testing | TasNetworks is participating in industry testing during Cycle 2. | Cycles 1 and 2 of Market Trials and bi-lateral testing with retailers in UE's distribution area are complete. On track to commence cycle 3 on 16 Oct.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | AAD is currently preparing transition and cutover plans. This includes actively participating in the ITCFG with AEMO and engaging with market participants to plan for jurisdictional specific measures. AAD is working with retailers to ensure readiness to go live on 1 December 2017. | System transition planning being undertaken in ITCFG. Planning for final elements of staged transitional process underway. |  | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | New proposed transitional approach requires industry wide acceptance before planning can commence. The Distribution Project supports the New Connection transitional approach, which requires a considerable re-work to our solution. Interest in the Adds & Alts Transitional Approach is being canvassed with key retailers due to the significant risk it will add to meeting compliance requirements of 1 December 2017. The transitional approach is in development. |  |  | Within schedule; Business Transition Tasks Identified & Planning in Progress | This activity is under pressure due to the competing priorities and compressed timelines. This activity is also dependant on other market participants. | Detailed cutover plan is in place, and will be validated via a second Dress Rehearsal on track for 12/13 October. Transitional preparations and documentation are well progressed.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | As above. | Not due yet. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | A cutover plan and inflight management plan has been completed. A dry-run Dress Rehearsal was performed in early October to test the cutover and inflight management |  |  | Within schedule; Data Analysis and Data Cleaning underway. Second dress rehearsal planning commenced | Data migration strategy complete. Cutover Planning activities underway. | Preparation continues to progress well. The first of two full dress rehearsals was successfully completed in mid-August 2017 and learning points were addressed. A second dress rehearsal is on track for 12/13 October. No major data migrations or conversions are required.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | AAD has established risk, issue and decision registers to track and mitigate gaps that are identified as progress is made. |  |  |  |  | Further review is in progress to assess the impacts of the proposed transitional approach.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Weekend work and additional test resources have been approved to mitigate the risks associated with slower than expected progress. |  |  |  |  | Further review is in progress to assess the impacts of the proposed transitional approach.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [15 empty] | Given the deferral of competition in Victoria, United Energy has been proceeding on the basis of the following assumptions: 1: UE's role as MC for new meters after 1st of Dec will be on the basis of existing regulated services 2: New meters after 1 Dec will need to meet only the Vic AMI specifications. 3: New meters after 1 Dec will be classified as Type 5 MRIM, per current practice, and existing meters will remain Type 5 MRIM. No further mitigation is required unless the Orders in Council are not gazetted with their current content.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [15 empty] | As above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [15 empty] | As above.
2.4 |  | An assessment of the required accreditation and registration activities | [15 empty] | The updated MC contract is expected to be issued to retailers on 13 October. The Vic Gov have provided a transitional arrangement for existing EN child metering on 1 Dec 17 for a period of 1 year. The updated MC contract may reflect system limitations in the as built systems.
2.5 |  | The fulfilment of accreditation and registration obligations | [11 empty] | This is being worked through with AEMO |  |  |  | Assuming the Victorian Orders are gazetted on 10 October, and therefore no additional accreditation requirements arise, this item is expected to be complete by end of October.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Requirements for additional testers and a business analyst has begun to mitigate risks associated with testing and delivery.
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing | [14 empty] | Validation of business processes may be done outside of industry testing and during UAT | UE will participate fully in cycle 3 of AEMO-led Market Trials and will continue or commence bi-lateral testing will any retailer in a position to engage in testing.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | See above comment
5.2 |  | The development and build of appropriate market systems for your business | [9 empty] | See above comment | The Project has implemented a phased implementation approach. | Working closely with vendor and business to ensure sprints are delivered on time and of high quality. Some non-market facing items deferred for delivery after 1 December 207. |  |  |  | User Acceptance Testing and industry testing have prompted a number of minor revisions to the solution, which are being progressed as part of the testing framework.
5.3 |  | The internal testing of market systems for your business | [15 empty] | Refer note above.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [6 empty] | Certification of Ausgrid's' five participants against AEMO's eHub is underway. |  | Additional testing to be scheduled in Cycle 3 | [6 empty] | Refer note above.
5.5 |  | The validation of performance of market systems during industry testing | [15 empty] | Refer note above.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [10 empty] | Support of Transitional Approach through participation of industry working groups and other industry bodies.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2017-10-09 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | 1. DNSP Meter lock issues still to be resolved to allow contestable metering providers access to metering installations.
| Acumen Metering | At risk | Medium | Oct Status - Project remains at risk with significant work to be completed across development and testing. Cycle3 Industry Testing scope has grown as test scenarios across participants from previous testing carries overs. Release of development changes into test environments is tight, however clear plan exists for path to cutover. Ongoing work to finalise MP/MDP/MC submissions with AEMO progresses. Increasing time and effort invested to coordinate multiple parties across bilateral and commercial agreements in anticipation of next series of testing and aligning business for cutover activities. Ongoing identification and mitigation of risks and issues sustains confidence in readiness for go-live.
| Ausgrid Business Services | Within schedule | Medium | Test scripts continue to be executed internally and bilaterally to supplement Industry Testing. New interfaces for the customer to assist our customers in operating in the POC space with the first phase release continuing in UAT. Further enhancements are in development. Cycle 1 & 2 of industry testing has completed successfully, however, internal system testing is still underway. | [7 empty] | [Meter Data Provider, Status = Within schedule, Risk = Medium] [Meter Provider, Status = Within schedule, Risk = Low]
| intelliHUB Pty Ltd | Within schedule | Medium
| Metering Dynamics | Within schedule | Medium | Revised project delivery plan is progressing well. Jurisdictional differences continue to contribute to slow progress on key end to end process arrangements. The Optional staged approach to de-risk market commencement introduces uncertainty and additional workload. Accreditation and registration process requirements are taking longer than originally planned. | [7 empty] | Accreditation and registration activities taking longer than originally planned, and MD providing additional information to address AEMO requested clarifications.
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Powermetric Metering Pty Ltd | At risk | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the aggressive POC implementation, industry testing and MC Registration timeframes place Powermetric POC development at a Medium risk.
| Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Within schedule | Medium | The summary project status and risk rating relate to the activities as Metering Coordinator. Select Solutions overall PoC strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for MC Services. There are currently no substantial risks or issues impacting our existing Type 1-4 Large MP and MDP accreditations. Select Solutions system development, testing and business readiness activities are progressing to plan in readiness for 1 December 2017 Go Live. Project risks predominantly relate to the substantial volume of commercial updates to be undertaken (scoped, negotiated and executed) prior to 1 December 2017.
| Spotless Advanced Metering | Within schedule | Low | [8 empty] | Accreditation Audit completed early August. Minor actions still to be completed by SAM to finalise accreditation.
| VECTORAMS | Within schedule | Medium | Scope of change and tight timeframes to deliver IT changes and establish commercial arrangements result in a project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Ausgrid Business Services | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| intelliHUB Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metering Dynamics | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Spotless Advanced Metering | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 91% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | 81% - 99% | 51% - 60% | Completed (100%) | Completed (100%) | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 91% - 99% | 81% - 99% | 81% - 99% | Completed (100%) | 81% - 90% | 71% - 80% | 61% - 70% | Completed (100%) | Completed (100%) | 81% - 99%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 91% - 99% | 61% - 70% | Completed (100%) | Completed (100%) | 81% - 90% | Completed (100%) | 21% - 30% | Completed (100%) | 91% - 99% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 91% - 99% | 81% - 99% | 51% - 60% | Completed (100%) | 81% - 90% | 81% - 99% | 21% - 30% | Completed (100%) | Completed (100%) | 71% - 80%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 81% - 90% | 31% - 40% | 71% - 80% | Completed (100%) | 71% - 80% | 61% - 70% | 21% - 30% | 61% - 70% | 81% - 90% | 51% - 60%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | Completed (100%) | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 91% - 99% | 81% - 99% | 61% - 70% | 81% - 99% | 81% - 90% | 61% - 70% | 21% - 30% | 81% - 90% | 91% - 99% | 71% - 80%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 91% - 99% | 61% - 70% | 61% - 70% | Completed (100%) | 81% - 90% | Completed (100%) | 41% - 50% | Completed (100%) | 71% - 80% | 61% - 70%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 91% - 99% | 61% - 70% | 31% - 40% | Completed (100%) | 61% - 70% | 81% - 99% | 31% - 40% | 81% - 90% | 71% - 80% | 41% - 50%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 71% - 80% | 21% - 30% | 21% - 30% | Completed (100%) | 51% - 60% | 71% - 80% | Not started (0%) | 41% - 50% | 81% - 90% | 51% - 60%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Completed (100%) | 81% - 99% | 81% - 99% | Completed (100%) | 81% - 90% | 71% - 80% | 41% - 50% | Completed (100%) | Completed (100%) | 81% - 99%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed (100%) | 71% - 80% | 51% - 60% | Completed (100%) | 61% - 70% | 61% - 70% | 31% - 40% | 81% - 90% | Completed (100%) | 71% - 80%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 61% - 70% | 41% - 50% | 51% - 60% | Completed (100%) | 51% - 60% | 31% - 40% | Not started (0%) | 31% - 40% | 21% - 30% | 21% - 30%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 81% - 90% | 71% - 80% | Completed (100%) | 81% - 99% | 71% - 80% | 71% - 80% | 21% - 30% | Completed (100%) | Completed (100%) | 81% - 99%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 91% - 99% | 51% - 60% | Completed (100%) | 71% - 80% | 61% - 70% | 61% - 70% | 11% - 20% | 91% - 99% | Completed (100%) | 81% - 99%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 91% - 99% | 31% - 40% | 51% - 60% | 81% - 99% | 61% - 70% | 41% - 50% | Not started (0%) | 81% - 90% | 51% - 60% | 41% - 50%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 71% - 80% | 31% - 40% | 81% - 99% | 81% - 99% | 61% - 70% | 41% - 50% | Not started (0%) | 31% - 40% | 21% - 30% | 41% - 50%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 71% - 80% | 31% - 40% | 51% - 60% | 81% - 99% | 51% - 60% | 41% - 50% | Not started (0%) | 31% - 40% | 21% - 30% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 71% - 80% | 51% - 60% | 71% - 80% | 81% - 99% | 51% - 60% | 71% - 80% | Not started (0%) | 31% - 40% | Completed (100%) | 21% - 30%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 51% - 60% | Not started (0%) | Not started (0%) | 81% - 99% | Not started (0%) | 71% - 80% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Completed | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | Within schedule | Completed | Completed | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | At risk | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed | At risk | Within schedule | Completed | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | Completed | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | MC Application Checklist has been submitted
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Reviewing ITCFG plan document |  |  | Implementation plans to be revised in line with industry testing results.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Final reviews completed.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | In progress. Will not be finalised until design and early prototypes of user systems are available.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | Reviews in progress. This is a significant logistical effort to negotiate agreements with each prospective party. |  | Complexity of contractual and commercial arrangements is challenging. Transitional plan option introduces uncertainty and additional workload. | Metering Coordinator contractual arrangements being finalised with several major retailers. |  | Select Solutions is continuing to work through the review and update to a large volume of individual I&C customer contracts in readiness for 1 December commencement of MC services and PoC changes. Commercial activities include the addition of new services, transactions, fees and charges, each to be individually negotiated and agreed. There is a risk that protracted negotiation timeframes will impact arrangements for POC Go Live on 1 December 2017. This has been registered as part of our Risk Management framework and a risk treatment plan is currently being worked through to ensure readiness for 01/12.
2.4 |  | An assessment of the required accreditation and registration activities | [7 empty] | In hand. |  | Accreditation and registration activities taking longer than originally planned, and MD providing additional information to address AEMO requested clarifications.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | MC Accreditation obtained. MDP and MP re-accreditation obtained. |  | ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. Supporting documentation for registration of new role ENM is underway. MC Checklist has been submitted. Preparation for reaccreditation of MPB and MDP roles is in progress. |  | Accreditation and registration activities taking longer than originally planned, and MD providing additional information to address AEMO requested clarifications. | Metering Coordinator registration application submitted to AEMO. |  | MC Registration and all supporting documentation has been submitted to AEMO and AEMO has responded with requests for clarification that are currently being prepared.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [7 empty] | Awaiting final updates to policies and work instructions.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Relies on the above. |  | Impacted by recent merger and restructuring activity. |  |  | On Track to recruit additional MC resources as required to support Industry Transition and Go Live activities.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | Relies on the above. |  |  | Training to be developed inline with industry testing. |  | Change Management and Training Activities in progress.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | Policies, procedures and work instructions have been identified and are in update/generation.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Policies, procedures and work instructions have been identified and are in update/generation. |  | Evolving requirements based on MC contractual arrangements |  |  | We are on track to complete documentation updates as part of project activities.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Cycle 1 completed. Cycle 2 completed. |  | Cycle 1 & 2 Industry Testing successful. |  |  | Industry testing not completed. |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | All solution designs are complete. |  | Evolving requirements based on MC contractual arrangements
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | The implementation phase is complete with internal testing in progress. |  | Evolving requirements based on MC contractual arrangements |  |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Testing is well advanced. 15 testers are working across all solution components. Timeframes remain tight. This task remains "At risk" given the volume of testing required. |  | Evolving requirements based on MC contractual arrangements |  |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | eHub accreditation testing in progress. Dependency on AEMO defects to complete (due 12/10) |  | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete. | Web services still an issue between AEMO and IntelliHUB | Not all test cases could be executed as part of Industry Test Cycle 2 due to blocked test cases by other retailers. Integration testing delayed. |  |  | Select Solutions has successfully completed BPT Cycle 1 (internal test activity) and have participated in Industry Testing Cycle 2 activities as planned.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Testing with market systems is underway. |  |  |  |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Working with ITCFG. Cutover planning is in progress |  |  |  |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Not yet due. |  |  |  |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [9 empty] | Continuing analysis of commercial requirements between parties. Transition plan needs to be finalised quickly and clearly for all parties. |  |  | Contract amendments have been drafted, issued and a significant customer engagement activity is currently underway with a number of responses received. Commercial activities are progressing to plan and are also being closely monitored in our governance framework as a key project risk.
2.4 |  | An assessment of the required accreditation and registration activities | [9 empty] | Working in consultation with AEMO and providing information required in a timely manner.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | Working in consultation with AEMO and providing information required in a timely manner.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [9 empty] | Work progressing, additional staff being recruited.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [9 empty] | Revised plan now in place for addressing any potential differences
4.3 |  | The validation of business processes during industry testing | [12 empty] | We participated in Industry Testing Cycle 2 activities as planned and also engaged additional parties for Bilateral Testing with our industry customers and peers.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | Revised plan now in place for addressing any potential differences
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Revised plan now in place for addressing any potential differences
5.3 |  | The internal testing of market systems for your business | [9 empty] | Revised plan now in place for addressing any potential differences
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Certification of ABS's four participants against AEMO's eHub is underway. |  | Test plans updated to progress available systems and replanning for revised schedule. Actively working with other participants to finalise test cases.
5.5 |  | The validation of performance of market systems during industry testing | [12 empty] | We participated in Industry Testing Cycle 2 activities as planned and also engaged additional parties for Bilateral Testing with our industry customers and peers.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  |  |  |  | Select Solutions is on track to complete our project transition, deployment and business readiness detailed planning by end of September, enabling implementation throughout Oct-Dec.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [12 empty] | Select Solutions is on track to complete detailed cutover planning by end of September, in readiness for dress rehearsals and cutover in Nov-Dec.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| 2017-10-09 |  |  | Please note that the below organisations are voluntarily self-reporting readiness as intending MCs. This is not a reflection of their registration status or a complete list of all intending Metering Coordinators. The list of Registered Metering Coordinators can be found here:
http://www.aemo.com.au/-/media/Files/Electricity/NEM/Participant_Information/NEM-Registration-and-Exemption-List.xls
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | 1. DNSP Meter lock issues still to be resolved to allow contestable metering providers access to metering installations.
| Acumen Metering | At risk | Medium | Oct Status - Project remains at risk with significant work to be completed across development and testing. Cycle3 Industry Testing scope has grown as test scenarios across participants from previous testing carries overs. Release of development changes into test environments is tight, however clear plan exists for path to cutover. Ongoing work to finalise MP/MDP/MC submissions with AEMO progresses. Increasing time and effort invested to coordinate multiple parties across bilateral and commercial agreements in anticipation of next series of testing and aligning business for cutover activities. Ongoing identification and mitigation of risks and issues sustains confidence in readiness for go-live.
| Ausgrid Business Services | Within schedule | Medium | Test scripts continue to be executed internally and bilaterally to supplement Industry Testing. New interfaces for the customer to assist our customers in operating in the POC space with the first phase release continuing in UAT. Further enhancements are in development. Cycle 1 & 2 of industry testing has completed successfully, however, internal system testing is still underway.
| intelliHUB Pty Ltd | Within schedule | Medium
| Metering Dynamics | Within schedule | Medium | Revised project delivery plan is progressing well. Jurisdictional differences continue to contribute to slow progress on key end to end process arrangements. The Optional staged approach to de-risk market commencement introduces uncertainty and additional workload. Accreditation and registration process requirements are taking longer than originally planned. | [7 empty] | Registration activities taking longer than originally planned, and MD has provided additional information to address AEMO requested clarifications.
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Origin Energy | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Program is currently reporting Amber however remains highly dependant on the readiness of other participants to be successful and 9 out of 11 Distributors reporting at risk. A significant number of delivery risks continue to be monitored and mitigated for the duration of the project. Areas of concern include: Delivery • Origin believes that Phase 3 Market Testing is not mandatory, and has no quality hurdle for exit e.g. % of end to end scenarios completed. Cutover • There is no Go / No go option based on overall participant readiness e.g. successful completion of Market Testing. • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; | [7 empty] | Request for registration submitted to AEMO on 25/9. AEMO's initial feedback received and replied to.
| Powermetric Metering Pty Ltd | At risk | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the aggressive POC implementation, industry testing and MC Registration timeframes place Powermetric POC development at a Medium risk.
| Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Within schedule | Medium | The summary project status and risk rating relate to the activities as Metering Coordinator. Select Solutions overall PoC strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for MC Services. There are currently no substantial risks or issues impacting our existing Type 1-4 Large MP and MDP accreditations. Select Solutions system development, testing and business readiness activities are progressing to plan in readiness for 1 December 2017 Go Live. Project risks predominantly relate to the substantial volume of commercial updates to be undertaken (scoped, negotiated and executed) prior to 1 December 2017. | [7 empty] | Risk relates to the remaining timeframe to complete updated commercial arrangements by 1 Dec 2017.
| Spotless Advanced Metering | [10 empty] | Application for Registration as a MC submitted to AEMO. Minor actions still to be completed by SAM to finalise registration.
| VECTORAMS | Within schedule | Medium | Scope of change and tight timeframes to deliver IT changes and establish commercial arrangements result in a project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ausgrid Business Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| intelliHUB Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metering Dynamics | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Origin Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Spotless Advanced Metering | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Origin Energy | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 91% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | 81% - 99% | Completed (100%) | 51% - 60% | Completed (100%) | Completed (100%) | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 91% - 99% | 81% - 99% | 81% - 99% | Completed (100%) | 81% - 90% | 71% - 80% | 71% - 80% | 61% - 70% | Completed (100%) | Completed (100%) | 81% - 99%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 91% - 99% | 61% - 70% | Completed (100%) | Completed (100%) | 81% - 90% | Completed (100%) | 71% - 80% | 21% - 30% | Completed (100%) | 91% - 99% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 91% - 99% | 81% - 99% | 51% - 60% | Completed (100%) | 81% - 90% | 81% - 99% | 51% - 60% | 21% - 30% | Completed (100%) | Completed (100%) | 71% - 80%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 81% - 90% | 31% - 40% | 71% - 80% | Completed (100%) | 71% - 80% | 61% - 70% | 41% - 50% | 21% - 30% | 61% - 70% | 81% - 90% | 51% - 60%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | Completed (100%) | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 91% - 99% | 81% - 99% | 61% - 70% | 81% - 99% | 81% - 90% | 61% - 70% | Not started (0%) | 21% - 30% | 81% - 90% | 91% - 99% | 71% - 80%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 91% - 99% | 61% - 70% | 61% - 70% | Completed (100%) | 81% - 90% | Completed (100%) | 61% - 70% | 41% - 50% | Completed (100%) | 71% - 80% | 61% - 70%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 91% - 99% | 61% - 70% | 31% - 40% | Completed (100%) | 61% - 70% | 81% - 99% | 41% - 50% | 31% - 40% | 81% - 90% | 71% - 80% | 41% - 50%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 71% - 80% | 21% - 30% | 21% - 30% | Completed (100%) | 51% - 60% | 71% - 80% | 31% - 40% | Not started (0%) | 41% - 50% | 81% - 90% | 51% - 60%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Completed (100%) | 81% - 99% | 81% - 99% | Completed (100%) | 81% - 90% | 71% - 80% | Completed (100%) | 41% - 50% | Completed (100%) | Completed (100%) | 81% - 99%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed (100%) | 71% - 80% | 51% - 60% | Completed (100%) | 61% - 70% | 61% - 70% | 71% - 80% | 31% - 40% | 81% - 90% | Completed (100%) | 71% - 80%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 61% - 70% | 41% - 50% | 51% - 60% | Completed (100%) | 51% - 60% | 31% - 40% | 21% - 30% | Not started (0%) | 31% - 40% | 21% - 30% | 21% - 30%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 81% - 90% | 71% - 80% | Completed (100%) | 81% - 99% | 71% - 80% | 71% - 80% | 81% - 99% | 21% - 30% | Completed (100%) | Completed (100%) | 81% - 99%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 91% - 99% | 51% - 60% | Completed (100%) | 71% - 80% | 61% - 70% | 61% - 70% | 61% - 70% | 11% - 20% | 91% - 99% | Completed (100%) | 81% - 99%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 91% - 99% | 31% - 40% | 51% - 60% | 81% - 99% | 61% - 70% | 41% - 50% | 41% - 50% | Not started (0%) | 81% - 90% | 51% - 60% | 41% - 50%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 71% - 80% | 31% - 40% | 81% - 99% | 81% - 99% | 61% - 70% | 41% - 50% | 31% - 40% | Not started (0%) | 31% - 40% | 21% - 30% | 41% - 50%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 71% - 80% | 31% - 40% | 51% - 60% | 81% - 99% | 51% - 60% | 41% - 50% | 11% - 20% | Not started (0%) | 31% - 40% | 21% - 30% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 71% - 80% | 51% - 60% | 71% - 80% | 81% - 99% | 51% - 60% | 71% - 80% | 61% - 70% | Not started (0%) | 31% - 40% | Completed (100%) | 21% - 30%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 51% - 60% | Not started (0%) | Not started (0%) | 81% - 99% | Not started (0%) | 71% - 80% | 21% - 30% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Origin Energy | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Within schedule | Completed | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Completed | At risk | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | Within schedule | Completed | Completed | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | At risk | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Completed | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed | Within schedule | Completed | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed | At risk | Within schedule | Completed | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Origin Energy | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [7 empty] | MC Application Checklist has been submitted
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Reviewing ITCFG plan document |  |  | Implementation plans to be revised in line with industry testing results. | All necessary implementation plans are in place. Detailed cutover plan being finalised.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Final reviews completed.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | In progress. Will not be finalised until design and early prototypes of user systems are available. |  |  |  | Policy changes/decisions still being derived
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [7 empty] | Reviews in progress. This is a significant logistical effort to negotiate agreements with each prospective party. |  | Complexity of contractual and commercial arrangements is challenging. Transitional plan option introduces uncertainty and additional workload. | Metering Coordinator contractual arrangements being finalised with several major retailers. | Overall strategy has been developed and endorsed. Generic Meter provider contract drafted for new providers and contracts in play for current providers. |  | Select Solutions is continuing to work through the review and update to a large volume of individual I&C customer contracts in readiness for 1 December commencement of MC services and PoC changes. Commercial activities include the addition of new services, transactions, fees and charges, each to be individually negotiated and agreed. There is a risk that protracted negotiation timeframes will impact arrangements for POC Go Live on 1 December 2017. This has been registered as part of our Risk Management framework and a risk treatment plan is currently being worked through to ensure readiness for 01/12.
2.4 |  | An assessment of the required accreditation and registration activities | [7 empty] | In hand. |  | Accreditation and registration activities taking longer than originally planned, and MD providing additional information to address AEMO requested clarifications. |  | Request for registration/accreditation submitted as per AEMO deadlines
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | MC Accreditation obtained. MDP and MP re-accreditation obtained. |  | ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. Supporting documentation for registration of new role ENM is underway. MC Checklist has been submitted. Preparation for reaccreditation of MPB and MDP roles is in progress. |  | Accreditation and registration activities taking longer than originally planned, and MD providing additional information to address AEMO requested clarifications. | Metering Coordinator registration application submitted to AEMO. | Planning and preparation in progress |  | MC Registration and all supporting documentation has been submitted to AEMO and AEMO has responded with requests for clarification that are currently being prepared.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [7 empty] | Awaiting final updates to policies and work instructions. |  |  |  | Forecasted workload planning completed for key business areas and socialised to inform recruitment decisions.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Relies on the above. |  | Impacted by recent merger and restructuring activity. |  | Recruitment for long lead time positions commenced. |  | On Track to recruit additional MC resources as required to support Industry Transition and Go Live activities.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [7 empty] | Relies on the above. |  |  | Training to be developed inline with industry testing. | Training requirements and resourcing determined and magnitude of change is understood, change planning started behind schedule. Learning curriculum being finalised and training material development commenced. Confirmation of some market transactions and treatments still pending which may impact training timelines given constraints in place. |  | Change Management and Training Activities in progress.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | Policies, procedures and work instructions have been identified and are in update/generation.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Policies, procedures and work instructions have been identified and are in update/generation. |  | Evolving requirements based on MC contractual arrangements |  | Business process design mainly completed with 3-4 weeks of delays against baseline plan. Relevant number of outstanding clarifications to be addressed by Oct-end. |  | We are on track to complete documentation updates as part of project activities.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Cycle 1 completed. Cycle 2 completed. |  | Cycle 1 & 2 Industry Testing successful. |  |  | Industry testing not completed. | Industry Testing underway with Cycle #2. An high number of end-to-end Test Scenarios is not complete, posing a risk to success of Cycle #3 and overall Industry Testing |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | All solution designs are complete. |  | Evolving requirements based on MC contractual arrangements |  | Mass Market Design activities complete and Large Customers design in progress. Change requests being assessed and planned.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | The implementation phase is complete with internal testing in progress. |  | Evolving requirements based on MC contractual arrangements |  | Build progressing on track, including the development of approved change requests. |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Testing is well advanced. 15 testers are working across all solution components. Timeframes remain tight. This task remains "At risk" given the volume of testing required. |  | Evolving requirements based on MC contractual arrangements |  | Testing is progressing on track. Risks remain around the compressed schedule. |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | eHub accreditation testing in progress. Dependency on AEMO defects to complete (due 12/10) |  | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete. | Web services still an issue between AEMO and IntelliHUB | Not all test cases could be executed as part of Industry Test Cycle 2 due to blocked test cases by other retailers. Integration testing delayed. |  | Industry Testing progressing through Cycle #2 behind schedule. |  | Select Solutions has successfully completed BPT Cycle 1 (internal test activity) and have participated in Industry Testing Cycle 2 activities as planned.
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Testing with market systems is underway. |  |  |  | Batch performance and sizing in progress |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Working with ITCFG. Cutover planning is in progress |  |  |  | Deployment Strategy confirmed and Detailed Cutover Plan progressing on track. |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [7 empty] | Not yet due. |  |  |  | Business Transition planning started and on track. Data conversion for Meter Standing Data (MC/ENM role, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our Build / Test activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Origin Energy | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [9 empty] | Continuing analysis of commercial requirements between parties. Transition plan needs to be finalised quickly and clearly for all parties. |  | Origin has onboarded additional Business and Technology resources |  | Contract amendments have been drafted, issued and a significant customer engagement activity is currently underway with a number of responses received. Commercial activities are progressing to plan and are also being closely monitored in our governance framework as a key project risk.
2.4 |  | An assessment of the required accreditation and registration activities | [9 empty] | Working in consultation with AEMO and providing information required in a timely manner.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | Working in consultation with AEMO and providing information required in a timely manner. |  | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [9 empty] | Work progressing, additional staff being recruited.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [9 empty] | Revised plan now in place for addressing any potential differences
4.3 |  | The validation of business processes during industry testing | [13 empty] | We participated in Industry Testing Cycle 2 activities as planned and also engaged additional parties for Bilateral Testing with our industry customers and peers.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | Revised plan now in place for addressing any potential differences
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Revised plan now in place for addressing any potential differences
5.3 |  | The internal testing of market systems for your business | [9 empty] | Revised plan now in place for addressing any potential differences
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Certification of ABS's four participants against AEMO's eHub is underway. |  | Test plans updated to progress available systems and replanning for revised schedule. Actively working with other participants to finalise test cases.
5.5 |  | The validation of performance of market systems during industry testing | [13 empty] | We participated in Industry Testing Cycle 2 activities as planned and also engaged additional parties for Bilateral Testing with our industry customers and peers.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG | [5 empty] | Select Solutions is on track to complete our project transition, deployment and business readiness detailed planning by end of September, enabling implementation throughout Oct-Dec.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [13 empty] | Select Solutions is on track to complete detailed cutover planning by end of September, in readiness for dress rehearsals and cutover in Nov-Dec.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Embedded Networks
Embedded Network Manager (ENM) Readiness Assessment Reports
| 2017-10-09 |  |  | Please note that the below organisations are voluntarily self-reporting readiness as intending ENMs. This is not a reflection of their accreditation status or a complete list of all intending Embedded Network Managers. The list of Accredited Embedded Networks Managers can be found here:
http://www.aemo.com.au/-/media/Files/Electricity/NEM/Retail_and_Metering/Metering-Procedures/National-Electricity-Market-Accredited-Embedded-Network-Managers.pdf
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Utilities Pty Ltd | Within schedule | Medium | Completion of system access occurred 04/10/2017, process documentation completed and ready for testing. Migration plan for existing fleet developed and ready for submission to AEMO along with accreditation documentation. Resources trained and clients updated on pending industry changes. Final 3 weeks from 09/10/20178 is completing final testing and all documentation and having ready all required elements for submission to AEMO for ENM Accreditation review/feedback/approval. | [7 empty] | Currently Operating as an ENO Currently in final stages of draft documentation and readiness for process testing.
| Ausgrid Business Services | Within schedule | Medium | Test scripts continue to be executed internally and bilaterally to supplement Industry Testing. New interfaces for the customer to assist our customers in operating in the POC space with the first phase release continuing in UAT. Further enhancements are in development. Cycle 1 & 2 of industry testing has completed successfully, however, internal system testing is still underway.
| Choice Metering | Within schedule | Medium | Site management system 90% complete ENM Policies and Procedures are to be developed, commenced 6 Oct ISO9001 Accreditation process to commence early Oct17. Awaiting AEMO for MSATS and b2b hub access. | [13 empty] | This is first report from Choice Metering
| Energy & Plant Management Pty Limited | Within schedule | Low | Preparing for accreditation. Attended Pre-Application Meeting 4/8/17 ENM Accreditation Application Forms submitted 7/8/17 Received access credentials for MarketNet Connection 9/10/17
| Energy Intelligence | Within schedule | Low | Attended Pre-Application Meeting 24/8/17 ENM Accreditation Application Forms submitted 15/9/17 Received feedback; final stages of submission; preparing for audit, waiting on MarketNet
| Energy On | Within schedule | Medium
| ENM Solutions Pty Ltd | At risk | Medium
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Momentum Energy | At risk | Medium | Material risks are related to probable issues with development and implementation of system changes within given timeframes. There are dependencies on external vendors to develop required changes and merge codes for B2B and B2M market transactions. Also critical dependencies on external providers of MC role to meet their POC timeframes.
| Watts Energy | Within schedule | Low | Close to finalising application with supporting documentation. | [7 empty] | Assuming amendments to Qld Electricity Act will pass in coming weeks
| WINconnect Pty LTD | At risk | Medium | Working through clarification on market design and ENM discovery procedure in MSATS. | [7 empty] | Issues are arising in discussion with AEMO in regards to market design. | [5 empty] | Require guidance from AEMO as to process for ENM discover of MSATS to initiate the customer churn process. The ENM is not to be listed against a EN parent in MSATS. Require confirmation on validation in MSATS to ensure only appointed ENMs can perform CR against certain parent NMIS.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Utilities Pty Ltd | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Ausgrid Business Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Choice Metering | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Energy & Plant Management Pty Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Energy Intelligence | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Energy On |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| ENM Solutions Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Metropolis Metering Services Pty Ltd | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Momentum Energy |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Watts Energy |  |  |  |  | Within schedule | Low
| WINconnect Pty LTD | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium |  |  | Not within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Utilities Pty Ltd | Ausgrid Business Services | Choice Metering | Energy & Plant Management Pty Limited | Energy Intelligence | Energy On | ENM Solutions Pty Ltd | Metropolis Metering Services Pty Ltd | Momentum Energy | Watts Energy | WINconnect Pty LTD | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | Completed (100%) | 91% - 99% | 61% - 70% | 91% - 99% | Completed (100%) | 71% - 80% | 81% - 99% | 81% - 90% | Completed (100%) | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 71% - 80% | 81% - 99% | 41% - 50% | 21% - 30% | 91% - 99% | 51% - 60% | 91% - 99% | 71% - 80% | 71% - 80% | 81% - 90% | 71% - 80%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 71% - 80% | Completed (100%) | 1% - 10% | 21% - 30% | Completed (100%) | Completed (100%) | 91% - 99% | Completed (100%) | 71% - 80% | 91% - 99% | 41% - 50%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 71% - 80% | 51% - 60% | Not started (0%) | 21% - 30% | 91% - 99% | 81% - 90% | 81% - 90% | 81% - 99% | 61% - 70% | 91% - 99% | 11% - 20%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 31% - 40% | 71% - 80% | Not started (0%) | 41% - 50% | 91% - 99% | 51% - 60% | 91% - 99% | 61% - 70% | 61% - 70% | 71% - 80% | 41% - 50%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 61% - 70% | 91% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | 81% - 90% | 91% - 99% | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 71% - 80% | 61% - 70% | 41% - 50% | 1% - 10% | 91% - 99% | 71% - 80% | 81% - 90% | 61% - 70% | 81% - 90% | 71% - 80% | 71% - 80%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | 61% - 70% | 11% - 20% | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 90% | 71% - 80% | 71% - 80%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | 31% - 40% | 41% - 50% | 61% - 70% | Completed (100%) | N/A | Completed (100%) | 81% - 99% | 71% - 80% | 91% - 99% | Completed (100%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 81% - 90% | 21% - 30% | Not started (0%) | 41% - 50% | 91% - 99% | 51% - 60% | 71% - 80% | 71% - 80% | 71% - 80% | 61% - 70% | Completed (100%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 71% - 80% | 81% - 99% | 41% - 50% | 71% - 80% | Completed (100%) | Completed (100%) | 81% - 90% | 71% - 80% | 61% - 70% | 91% - 99% | 41% - 50%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 61% - 70% | 51% - 60% | Not started (0%) | 11% - 20% | Completed (100%) | 81% - 90% | 91% - 99% | 61% - 70% | 61% - 70% | 91% - 99% | 51% - 60%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 31% - 40% | 51% - 60% | Not started (0%) | 1% - 10% | 91% - 99% | Not started (0%) | 61% - 70% | 31% - 40% | 61% - 70% | 11% - 20% | Completed (100%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 81% - 90% | Completed (100%) | 41% - 50% | 51% - 60% | 81% - 90% | 91% - 99% | Completed (100%) | 71% - 80% | 81% - 90% | 61% - 70% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 90% | Completed (100%) | 61% - 70% | 41% - 50% | 81% - 90% | 71% - 80% | 81% - 90% | 61% - 70% | 71% - 80% | 51% - 60% | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Completed (100%) | 51% - 60% | 41% - 50% | 1% - 10% | Not started (0%) | 51% - 60% | 71% - 80% | 41% - 50% | 71% - 80% | 1% - 10% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 81% - 90% | 81% - 99% | 31% - 40% | Not started (0%) | Not started (0%) | Not started (0%) | 71% - 80% | 41% - 50% | 71% - 80% | 1% - 10% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 41% - 50% | 51% - 60% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | 71% - 80% | 41% - 50% | 71% - 80% | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 71% - 80% | 71% - 80% | 31% - 40% | 41% - 50% | 61% - 70% | N/A | 91% - 99% | 71% - 80% | 51% - 60% | 41% - 50% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 11% - 20% | Not started (0%) | N/A | 11% - 20% | 61% - 70% | N/A | N/A | 71% - 80% | 11% - 20% | 1% - 10% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Utilities Pty Ltd | Ausgrid Business Services | Choice Metering | Energy & Plant Management Pty Limited | Energy Intelligence | Energy On | ENM Solutions Pty Ltd | Metropolis Metering Services Pty Ltd | Momentum Energy | Watts Energy | WINconnect Pty LTD | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed |  | Within schedule | Within schedule | Within schedule | At risk
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | At risk | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Completed | Within schedule | Within schedule | Completed | Completed |  | Within schedule | At risk | Within schedule | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | At risk | Within schedule | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | Completed | Completed | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed |  | Within schedule | Within schedule | Within schedule | At risk
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Completed | Within schedule | Within schedule | Within schedule | Completed | N/A |  | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed |  | Within schedule | Within schedule | Within schedule | Not within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule |  | Within schedule | Within schedule | Within schedule | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | At risk | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule |  | Within schedule | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule |  | Within schedule | At risk | Within schedule | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | Completed | Within schedule | At risk | Within schedule | Not within schedule | Within schedule |  | Within schedule | At risk | At risk | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule |  | Within schedule | At risk | At risk | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule |  | Within schedule | At risk | At risk | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A |  | Within schedule | At risk | Within schedule | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | At risk | Within schedule | N/A | Within schedule | Within schedule | N/A |  | Within schedule | At risk | Within schedule | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Utilities Pty Ltd | Ausgrid Business Services | Choice Metering | Energy & Plant Management Pty Limited | Energy Intelligence | Energy On | ENM Solutions Pty Ltd | Metropolis Metering Services Pty Ltd | Momentum Energy | Watts Energy | WINconnect Pty LTD | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [6 empty] | MC Application Checklist has been submitted
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Process flows and systems are at final stage of completion. Testing to commence 09/10/17. | Reviewing ITCFG plan document | [5 empty] | Implementation plans to be revised in line with industry testing results.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Compliance monitoring against regulatory requirements now completed and in place. | Final reviews completed. | [6 empty] | Retailer timeframes to assess and agree to the T&Cs of the LNSPs are extremely tight and require the same pool of resources needed for establishing contractual agreements with Metering Coordinators and Embedded Network Owners.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Process flows and systems are at final stage of completion. Testing to commence 09/10/17. | In progress. Will not be finalised until design and early prototypes of user systems are available. | [8 empty] | Still waiting on confirmation on VIC guidance on treatment of embedded network metering.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Initial discussions had with all impacted customers. Final pricing and cost impact to be submitted for review and acceptance by clients. | Reviews in progress. This is a significant logistical effort to negotiate agreements with each prospective party. | [5 empty] | Metering Coordinator contractual arrangements being finalised with several major retailers. | Dependency on partnering with registered MC(s)
2.4 |  | An assessment of the required accreditation and registration activities | [6 empty] | In hand. | [6 empty] | Currently liaising with AEMO to complete required activities
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Final testing to commence 09/10/17 ready for AEMO submission end of October 17. | ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. Supporting documentation for registration of new role ENM is underway. MC Checklist has been submitted. Preparation for reaccreditation of MPB and MDP roles is in progress. | [5 empty] | Metering Coordinator registration application submitted to AEMO. | Currently liaising with AEMO to complete required activities
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [6 empty] | Awaiting final updates to policies and work instructions.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [6 empty] | Relies on the above.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Final stages of training to be completed post testing and final tweaks of new systems and processes initial training completed. | Relies on the above. | Need assistance with training for the use of MSATS browser, will request at next AEMO meeting 22Sep17 |  |  |  |  | Training to be developed inline with industry testing.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [6 empty] | Policies, procedures and work instructions have been identified and are in update/generation. | [8 empty] | In discussion with AEMO, we have concerns about the ENM discovery process in the MSATS market design.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [6 empty] | Policies, procedures and work instructions have been identified and are in update/generation. | [6 empty] | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing
4.3 |  | The validation of business processes during industry testing | [5 empty] | To commence week 09/10/2017. | Cycle 1 & 2 Industry Testing successful. | [5 empty] | Industry testing not completed. | Delays from third parties are impacting our ability to participate in industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [6 empty] | All solution designs are complete. |  |  | Waiting on access to MSAT preproduction to determine if there are additional changes. | [5 empty] | Confirmation required on proposed process for ENM discovery in MSATS.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Final connectivity established testing to commence 09/10/2017. | The implementation phase is complete with internal testing in progress. | It is thought MSATS browser can be used for ENM NMI market updates, as qty of transactions is expected to be low. Communication with participants will be via email |  | Waiting on access to MSAT preproduction to finalise process |  |  |  | System development is reliant on external vendors, any delays in final market procedures will impact readiness activities.
5.3 |  | The internal testing of market systems for your business | [6 empty] | Testing is well advanced. 15 testers are working across all solution components. Timeframes remain tight. This task remains "At risk" given the volume of testing required. |  |  | Waiting on access to MSAT preproduction
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Final connectivity established testing to commence 09/10/2017 | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete. |  |  | Waiting on access to MSAT preproduction
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Final connectivity established testing to commence 09/10/2017. | Testing with market systems is underway. |  |  | Waiting on access to MSAT preproduction
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Plan developed to be confirmed post final testing. | Working with ITCFG. Cutover planning is in progress | [6 empty] | Transition plans are dependent on timely delivery of earlier program stages
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | To commence post final Testing. | Not yet due. | [6 empty] | Draft version of internal Momentum Transition and Cut Over Plan in progress
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Utilities Pty Ltd | Ausgrid Business Services | Choice Metering | Energy & Plant Management Pty Limited | Energy Intelligence | Energy On | ENM Solutions Pty Ltd | Metropolis Metering Services Pty Ltd | Momentum Energy | Watts Energy | WINconnect Pty LTD | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [6 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [6 empty] | All available resources have been assigned to the design & development tasks.
5.3 |  | The internal testing of market systems for your business | [9 empty] | Once preproduction is available, we can test/amend/finalise/approve processes
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [6 empty] | Certification of ABS's four participants against AEMO's eHub is underway. |  |  | Once preproduction is available, we can test this
5.5 |  | The validation of performance of market systems during industry testing | [9 empty] | Once preproduction is available, we can action this
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [6 empty] | Member on ITCFG
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Third Party
| 2017-10-09 |  |  | Third Party Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2017-10-09 | [5 empty] | Within schedule | Medium | AEMO concluded and published planning documents for the Transition & Cutover which includes outputs from contingency planning and the staged approach. Industry and AEMO concluded cycle 2 of Market trial. Cycle 3 of market trial commences 16 October 2017. Registration and accreditation windows remain open. AEMO has notified parties which are currently undertaking the process to complete outstanding actions by end of October.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Medium | NSW: Currently consulting on maters that give effect metering competition, consultation closes 25 Oct VIC: Order-in-Council has been published Special Gazette S346
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | 81% - 90% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies consistent with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updated B2B retail electricity market procedures and associated documentation | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 81% - 90% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | 81% - 90% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS (EN/MC) | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B e-hub and MSATS | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | The internal testing of market systems for your business | [5 empty] | 81% - 90% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
[12 empty] | 41% - 50% | Retailer
[12 empty] | 51% - 60% | Distributor
[12 empty] | 61% - 70% | Meter Provider
[12 empty] | 71% - 80% | Meter Data Provider
[12 empty] | 81% - 90% | Metering Coordinator
[12 empty] | 91% - 99% | Embedded Network Manager
[12 empty] | Completed (100%) | Embedded Network Operator
[12 empty] | N/A | Third Party B2B Participant
81% - 99%
Within schedule
At risk
Not within schedule
N/A
[12 empty] | Completed | √
x
Low
Medium
High
N/A

## Harvey Balls 10% (hidden)
ü
Completed
| 100 | 90 | 80 | 70 |  | 60 | 50 | 40 | 30 | 20 | 10 | 0
| 0 | 10 | 20 | 30 |  | 40 | 50 | 60 | 70 | 80 | 90 | 100
WITHIN SCHEDULE | [12 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE
|  |  | ~0% |  | ~50%
|  |  | ~10% |  | ~60%
|  |  | ~20% |  | ~70%
|  |  | ~30% |  | ~80%
|  |  | ~40% |  | ~90%