## Slide 1: 5MS & GS Executive Forum #13
Wednesday, 7 July 2021
This meeting is recorded for the purpose of minute taking.
Please disconnect from your workplace VPN for the WebEx call​

## Slide 2: AEMO Competition Law Meeting Protocol
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require

## Slide 3: Agenda
# | Time | Topic | Presenter
1​ | 10:00 – 10:05 | Welcome, Introductions and Apologies | Violette Mouchaileh
2​ | 10:05 -10:10 | Actions from Previous Meetings​ | Violette Mouchaileh
3​ | 10:10 – 10:15 | Readiness Dashboard | Peter Carruthers
4 | 10:15 – 10:25 | Program Update | ​Rowena Leung
5 | 10:25 – 10:40 | Retail Go-Live Debrief | Graeme Windley
6​ | 10:40 – 10:55 | Readiness Reporting Round 8 | Greg Minney
7 | 10:55 – 11:10 | Market Trial Preparation | Greg Minney
8 | 11:10 - 11:35 | Contingency Planning | Peter Carruthers
9 | 11:35 – 11:45 | Key Industry Risks and Issues | Peter Carruthers
10 | 11:45 – 11:55 | General Questions | Violette Mouchaileh
11 | 11:55 – 12:00 | Meeting Close | Violette Mouchaileh

## Slide 4: Welcome
Violette Mouchaileh

## Slide 5: Actions from Previous Meetings
Violette Mouchaileh

## Slide 6: Actions Items
No. | Status | Action | Comment
12a.5.1 | Closed | AEMO to confirm whether the consideration of bundling B2B with the 5MS and Customer Switching go-live (should 1 October 2021 be delayed) includes the B2B for gas. | This will be addressed in the Regulatory Implementation Roadmap on 9 July.
12a.5.2 | Closed | AEMO to include compression timeline in the contingency planning conclusion at PCF on 17 June 2021 | Compression timeline no longer required as a result of 21 June Retail Go-Live confirmation.
12a.6.1 | Closed | AEMO to consider including additional Executive Forums in the 5MS stakeholder engagement schedule | Discussed during this session.
12.4.1 | Closed | AEMO to consider seeking information on whether Retailers are deploying the code for Customer Switching at the same time as 5MS Retail through readiness reporting survey or direct poll. | Information gathered through discussions with participants.
12.6.1 | Closed | AEMO to include an agenda item on contingency planning at the next Executive Forum | Included in agenda.
12.7.1 | Closed | AEMO to consider the positioning of the Regulatory Implementation Roadmap webpage within the AEMO website. | This feedback has been provided to the Corporate Affairs team. ​
12.8.1 | Closed | AEMO to issue invitation for an Executive Forum in May or June. | AEMO issued an invitation to a Special Executive Forum for 01-June. ​

## Slide 7: Readiness Dashboard
Peter Carruthers

## Slide 8: Overall Market Readiness
 | On track | On track for commencement date
 | Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
Activity | Status | Trend | Comments
AEMO Business Readiness for 5MS and GS (Part A) | On-track | Up | Status: On-track All AEMO platforms are now in Production operating at 30 minute Settlement. Retail Platform deployed 21 June Market Trial scheduled for 19th July commencement Trend: Up AEMO’s last platform (Retail) went live on the 21st June
Essential Industry Capabilities for 5MS commencement (Part A) | At-risk |  | Status: At-risk Multiple MSPs plans reflect 10% tranche 1 meters made 5-minute capable post MTP completion date of 31 July, providing little schedule contingency for Metering Data delivery. Current plans satisfy compliance obligations but are late against MTP dates AEMO to engage the RWG to conduct detailed contingency planning for metering scenarios Generators “on-track” with individual program risks reported Trend: Down Multiple MSPs with limited contingency for meter capability upgrade and metering data delivery
Summary: Part A 5MS Rule Commencement Essential Industry Capability | On-track |  | Status: On-track AEMO’s Retail platform went live on the 21st June. All key 5ms platforms now in production Tranche 1 metering plans meet compliance obligations but have reduced schedule contingency in event of delayed delivery Trend: Down AEMO’s Retail platform is now live, however, MSP time contingency has reduced with heightened risk profile
Other industry capabilities for 5MS and GS (Part B) | On-track |  | Status: On-track Majority of Participants reporting their overall programs as on-track, but some Participants are now reporting some non-essential capabilities as at-risk or late Metering transition activities have heightened risk profile Trend: Down Increase in Participants reporting items at-risk or late compared to the previous readiness reporting round

## Slide 9: Program Update
Rowena Leung

## Slide 10: 5MS Program Timeline Readiness and Go-Live
Current as at 01-07-2021
5MS Retail IT Platform – successful go-live on 21 June
Retail and Settlements Industry Test periods complete.
Market Trial preparation ongoing. Over 30 participants have registered to date. Registration closed 25 June.
5MS Settlements IT Platform – successful go-live on 17 May
5MS Bidding Service – successful go-live on 1 April

## Slide 11: 5MS Program – IT Systems Status
Stream | Status | Commentary
Retail |  | The Retail solution is now in Production (further details on later slides)
Dispatch |  | 5MS Bidding Service went live on 01-Apr-21. Participants may choose to submit 5-min bids (must be equal for a 30-min period). Pre-dispatch P5 – Fast Start Inflexibility Profile (FSIP) & 5MPD Price Sensitivity – on track for 07-Jul-21 release
Settlements |  | Settlements systems was successfully deployed in the production environment on 16-May-21 Remains in 30-min mode until 01-Oct-21
Overall AEMO Status |  | Overall, the AEMO 5MS program reverts to Green status with the completion of the Retail Metering Go-Live Milestone 5MS Market Trial preparation activities are underway and currently on track If issues arise that compromise Market Trial start dates, status will be reviewed
 | Go-live date impacted
 | At risk
 | On schedule

## Slide 12: Retail Go-Live Debrief
Graeme Windley

## Slide 13: Retail IT Platform Go-Live - Cutover weekend debrief
The new Retail MDM IT solution was successfully migrated to production on 21 June 2021.
  A number of minor internal facing issues were encountered on Sunday 20 June that caused delays to the cutover process. These were successfully remediated by the team and the time was recovered.
One major issue was identified – Profile Area Update. A workaround was established for this issue which allowed the team to progress with the cutover. The impacted participants have been contacted.
Verification testing was successfully completed. B2M restart was completed on schedule at 4am Monday 21 June.

## Slide 14: Retail IT Platform – Operation since Go-Live
Overall health of market functions is sound.
  Metering data being accepted and ingested.
  Metering data processing for Settlement purposes is producing timely and accurate Settlement runs and Prudentials operations.
  B2B processing operating normally.
  RM reports are being produced, but issues exist with performance that are creating constraints for participants.
Attention turns to incident and defect management
  3 participant sessions each week, includes a daily circulation of Issues / Incidents Log
  Heightened level of support by AEMO, will continue until there is tangible evidence that the Retail solution is in a stable state e.g. number of issues being raised is within normal BAU volumes
Key issues are operational impacts to participants of performance or defect issues
  See overleaf

## Slide 15: Key issues impacting multiple participants
Defect | AEMO Systems/Services impacted | Comments | Status
5002 | RM Report requests | Observed Issue: Delivery failures/delays of RM reports. Root Cause: There is a current performance issue processing an RM request with a lot of transactions. Work Around: AEMO has requested participants do not submit RM Report requests with greater than x10 transactions in an individual file. This limitation does not affect RM Report requests via MSATS Browser. | Fix under design. Tactical fixes being reviewed.
5251 | RM Report response | Observed Issue: Delay with report responses while AEMO is running Settlement Case reports. Delays of 5 hours were seen. Root Cause: Constraints on generating reports Work Around: AEMO is running these reports out of business hours. After 5pm on weekdays or on the weekends. | Fix in design. Tactical fixes being reviewed.
Current Challenges:
Open incidents that participants are waiting on AEMO to respond with a diagnosis, and
Incidents with identified defects that participants are waiting for AEMO to provide a defect fix release schedule

## Slide 16
AEMO is working to provide participant certainty on defect fix releases in the week beginning 5 July.
  Release information will be communicated through the Retail Q&A sessions
The defect release schedule will be decided on a prioritising approach. Defects that impact on multiple participants and defects with a high impact will be prioritised
  Issues relating to IT Architecture i.e. performance issues require more time to resolve
AEMO plans to complete a release drop every two weeks.
  This frequency minimises industry impact by reducing the outage time.
  In addition, defects need to be scheduled with other known defects e.g. Profile Area Update and sufficient time needs to be allowed for comprehensive testing
Path forward

## Slide 17: Readiness Reporting Round 8
Greg Minney

## Slide 18: Part A 5MS Essential Capability (as at 22 June)
Responsible Participant | Essential Criteria | Status | Trend | Comments
Generator | Generators and MNSPs are able to submit 5-min offers | On-track |  | Status: On-track 18 Generators and MNSPs representing 93% of NEM volume reporting on-track Important participant previously not reporting status has commenced reporting against industry timelines Participants to consider contingency options in event of delays in systems deployment Trend: Neutral All respondents intend to participate in 5MS Market Trials 2 participants have now implemented their 5-minute bidding service, with 13 out of 16 generators intending to commence their implementations within the bidding transition period.
MP, MC, MDP | All essential meters* are able to produce and store and deliver 5-min data | At-risk |  | Status: At-risk 4 MSPs are reporting late against MTP transition end dates regarding the installation and delivery of metering data for essential meters, however on track for meeting compliance requirements Trend: Down Reduced time contingency associated to the installation and metering data delivery of essential meters
AEMO | The 5-minute bidding and dispatch solution, including the web bidding interface is deployed | On-track |  | Status: On-track Platform deployed in ‘Bidding Transition’ configuration Additional capability on track for implementation prior to 1 October Trend: Neutral
 | The Metering Data Management (MDM) solution is deployed | On-track |  | Status: Retail Platform deployed into Production on 21st June 5-minute metering processes to be verified during 5MS Market trial Trend: Up Retail platform deployed successfully
 | The 5-minute settlements solution is deployed | On-track |  | Status: On-track AEMO’s Settlement Platform successfully deployed 17th May, to support 30-minute settlement 5-minute settlement processes to be verified during the 5MS Market trial Trend: Neutral
Summary - Essential Criteria |  | On-track |  | Overall, essential criteria to support the 5MS rule commencement is considered to be on track. Trends reflect the reduced time contingencies for the installation and delivery of Tranche 1 5-minute metering data
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date

## Slide 19: Part B – Other Industry Capabilities (as at 22 June)
Responsible Participant | Criteria | Status | Trend | Comments
Retailer | Receive and process 5-minute metering data. Receive and process 5-minute settlement data. | On-track |  | Status: On-track 18 out of 20 retailers reporting their overall programs as on-track 17 out of 20 retailers planning on participating in the 5MS Market Trial, with 2 reporting participation at risk Trend: Down 2 retailers reporting late for the processing of 5-minute metering data and 2 for the processing of 5-minute settlement data
DNSP | Receive and process 5-minute metering data. | At-risk |  | Status: At-risk Multiple DNSPs are reporting at risk or late for numerous GS related items, including: Cross boundary supplies, 2 reporting at-risk or late NCONUML, 3 reporting at-risk or late There will be an impact on the UFE values initially published for those profile areas, overall impacts to be established and remediation/management options developed Trend: Down Increased occurrence of at-risk or late items being reported, impact is to initial UFE accuracy
 | Provide GS metering and standing data updates (incl. NCONUML). |  |  | 
TNSP | Receive and process 5-minute metering data | On-track |  | All TNSPs reporting their overall programs as on track 2 out of 6 have the intention to receive 5-minute metering data prior to the Rule commencement date
 | Provide GS metering and standing data updates |  |  | 5 out of 6 reporting as on-track, 1 response not received (noting that their Round 7 response showed them as on-track)
MDP | Provide 5-minute metering data T1-3 distribution connected meters, type 7 meters. | On-track |  | Status: On-track 13 out of 16 MDPs reporting as on-track, representing approx. 95% coverage of Tranche 1 meters 16 out of 16 MDPs reporting on-track for the delivery of 5-minute metering data by 1 October Trend: Neutral
 | Provide type 4, 4A, Vic Ami metering data at 5-minute granularity by 1 December 2022 |  |  | 
 | Provide basic metering data for tier 1 NMIs to AEMO. |  |  | 
MP, MC | All T1-3,4* meters are able to produce and store 5-minute data. | On-track |  | 19 MPs servicing tranche 1 meters reporting as on-track against compliance requirements with up to 10% of installations planned for August, September Approx. 40% of tranche 1 meters currently 5-minute capable, expecting a large increase in this percentage once rollout plan updates, due 1 July, are provided by Participants
Summary – Other Industry Capabilities |  | On-track |  | Overall, on-track for 5MS rule commencement. Trending down due to the increased number of at-risk and late activities being reported
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date

## Slide 20: Response Requested
Emerging pressures on some sections of participant readiness require industry-wide and individual participant response.
  Key area of concern for 1 October market readiness is pressures in Metering Service Provider timelines
Industry-wide Response:
  Review and engagement via RWG of Industry Contingency Plans to confirm appropriateness of planned response
Individual Participant:
  Responsible executives are requested to confirm with their own project :
    Progress against Metering Transition Plan and compliance obligations
    Opportunities for remediation where possible/practical
    Adequate contingency plans to meeting rule commencement and compliance obligations
  Where practical, suggest that commercial partners confirm timeframes and contingency approaches with their service providers

## Slide 21: Market Trial Preparation
Greg Minney

## Slide 22: Market Trial Preparations
Objectives:
  Provide participants opportunity to prove their updated systems against AEMO's market systems
  Test end-to–end scenarios in a co-ordinated trial of updated processes and procedures
  Contribute to assessment of overall industry readiness for rule commencement
5MS Market Trial to be conducted 19 July – 10 September
  Scheduled scenarios commence 26 July
  5 minute settlement scenarios commence 30 July
Approach:
  Overall schedule to reflect settlement operation during “transition week” and subsequent 5 minute operation
  Settlement runs to mimic production operation
  Key Market scenarios for industry transition to 5MS will be executed from 26 July
    Address high impact market scenarios as early as possible in Market Trial execution period
    5-minute Bidding scenarios follow bidding transition approach
    Prelim Settlement statements for week of transition
  Retail scenarios to support key participant process testing and verification
  Retail and metering processes incorporated subject to participant capacity
    Meter Reads estimated where no actual reads provided

## Slide 23: Market Trial Preparations
Participant Engagement
  Twice weekly planning sessions
  30 Organisations have registered and are planning involvement
    Satisfies condition for substantial level of participant involvement
    Registration is now closed - Program will aim to accommodate those who still wish to participate
  Scenario selection and pairing in progress
Management:
  Participant execution of selected scenarios
  AEMO reporting and defect management
  Market Trial outcomes contribute to Market Start decision
    Supporting Participant readiness reporting

## Slide 24: Contingency Planning
Peter Carruthers

## Slide 25: Risk Scenario and approach to contingency
Confirmation of 21 June Retail Go-Live has changed the nature of the “delay” risk, but prudent planning means a contingency plan is still required
The potential scenarios that may lead to compression of the critical path and potential for a delay to 5MS market start on 1 Oct:
  Cutover or significant post go-live issue with the Retail IT Platform
  Unexpected significant issue during Market Trial
  Essential capability issue for participant readiness (without a contingency response)
Purpose of this section:
  Set out the contingency plan for a change to the market start date
  Set out the timeline and triggers
Risk ID | Description | Current Residual Rating | Comments
R33 | Further delays to AEMO Retail Systems impact 5MS rule commencement critical path There is a risk that cutover issues or post go-live issues cause delays that impact on Market Trial start date thereby impacting the critical path to 5MS rule commencement (01-Oct-21) | Significant | Residual Likelihood –unlikely Residual Consequence – extreme Residual rating – significant Trend: redefined, therefore neutral Risk description has been updated to reflect the 21 June go-live of Retail Platform and redefined to address the ongoing risks to the critical path.

## Slide 26: Contingency Plan Move the Market Start Date
Option 1 – Full Rule Deferral will be the basis for any change to the market start date
  Option 1 had the widest support
  Option 2 (partial rule deferral) had limited support and Option 3 (resettling in 5-min through the revised settlement statements) gave rise to concerns for a number of participants
A rule change process will be adopted
  AER has advised that a Letter of No Action is not well suited to Option 1
Key planning objectives
  Do not want to move the market start date unless it is necessary
  If the market start date needs to be moved, then earliest practical notification is to be provided
Key challenge is managing uncertainty, with rule change lead times
  An urgent rule change process requires 8 weeks – from commencement of consultation to final determination
The following approach is proposed
  If the 5MS market start date moves to RED status at any time, then a rule change will be submitted immediately and a revised date determined asap
  A checkpoint at 8 weeks prior to go-live is proposed. At this time:
    Path A, 5MS market start date is RED: a rule change with a revised date will be submitted
    Path B, 5MS market start date status is AMBER or GREEN with heightened risk: a provisional rule change, which will be subject to a Market Start Notice on 1 Sept from AEMO, will be submitted. (In view of the 5MS challenges to date and overall risk profile, AEMO confirms that the provisional rule change will be submitted).
    The Market Start Notice mechanism is intended to replicate the regime that is generally established for implementing a major reform – i.e. market start is confirmed 1 month prior to go-live.
The timeline overleaf sets out how this proposal integrates with the project timeline

## Slide 27
Contingency Plan Timeline
Notes
Participants should assume that the Path B provisional rule change process will NOT result in a change to the market start date. This is a contingency measure only and under this path it is expected 5MS will start on 1 Oct as scheduled.
The Path B provisional rule change process raises risks in relation to “down tools” or distraction. Communication on readiness status will need to be strong and participant support for managing this risk is sought.
Additional Executive Forums will be scheduled around the key dates. September EF will be moved forward.
AEMO is seeking Executive support to ensure participant focus and delivery against the 1 October 2021 5MS Rule Commencement date, and managing the communication process in relation to the provisional rule change.

## Slide 28: Level 2 Contingency Triggers Table
Trigger | Timing | Criteria | Action
1. Rule Change Decision | No later than 2 August | Status of Retail Go-Live Status of Market Trial readiness and conduct Assessment against 1 October readiness - utilising Market Readiness Essential Capability Informed by industry engagement through the PCF and EF | If Market Start Readiness is Red, then submit a “Revised Date Rule Change” If Market Start is Amber or Green with heightened risk, then submit a “Provisional Rule Change based on Market Start Notice” In view of the 5MS challenges to date and overall risk profile, AEMO confirms that the provisional rule change will be submitted
2. Market Start Notice | No later than 1 September | Only applies if a “Provisional rule change based on Market Start Notice” has been submitted Assessment against 1 October readiness – utilising Market Readiness Essential Capability Informed by industry engagement through the PCF and EF | AEMO submits a Market Start Notice to the AEMC (and to industry) advising the proposed date for rule commencement AEMC takes the Market Start Notice into account when preparing its Final Determination (informs the Commission’s decision, but without pre-empting the Commission’s decision making powers)

## Slide 29: Key Industry Risks and Issues
Peter Carruthers

## Slide 30: Summary
The Executive Forum has been tracking three key risks.
The purpose of this slide is to summarise key changes to these risks:
  No remaining contingency for Retail Solution deployment
    This issue has been closed with the successful 5MS Retail IT Platform go-live.
    AEMO and the PCF has acknowledged that there is a risk cutover issues or post go-live issues cause delays that impact Market Trial and the critical path to 1 October 2021. R33 has been updated to reflect this. A contingency plan has been developed that is discussed in this pack.
  Volume of regulatory change
    This risk has improved since reviewed in March. Significant work has been undertaken to plan the regulatory implementation roadmap with input from industry. Further clarity on release dates has also been provided.
    However, this remains a “significant” risk.
  Participant and AEMO readiness
    Changes to status outlined in section on Readiness Dashboard. Risk remains “medium” for industry readiness and has been updated to “medium” for AEMO readiness
    Contingency plans have been discussed with PCF and RWG to address remaining risks
    Readiness Survey Round 9 is due in early August and will provide the main source of information on industry essential capability which will be the input for the Market Start Notice.
Risks are attached in Appendix. Industry Risks and Issues Register is being reviewed regularly through the PCF and RWG in the lead up to 1 October 5MS Rule Commencement.

## Slide 31: General Questions
Violette Mouchaileh

## Slide 32: Upcoming Executive Forums
Date | Topics
Thursday 29-Jul-21 | Market Trial Update Risk review Rule Change Decision
Monday 30-Aug-21 | Market Trial – assessment of progress Market Start Notice
Late September – date TBD | Market Trial Conclusions 5MS Rule Commencement preparation Post rule commencement support Global Settlements program

## Slide 33: Upcoming Meetings AEMO | Program Calendar and Timelines
Current as at 01/07/2021
5MS Market Trial Prep Calls – Tuesdays and Thursdays until 16 July
5MS Market Trial calls daily from 19 July to 10 September
5MS Retail Q&A – Monday, Wednesdays, Fridays – finish date to be agreed with working groups

## Slide 34: Meeting Close
Peter Carruthers

## Slide 35: Appendix: Risks and Issues as presented at PCF 17 June 2021

## Slide 36: Retail Risk
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​
ID | Description | Rating | Mitigations
I12 | No Remaining Contingency for Retail Deployment Issues identified during Dress Rehearsal 2 and Azure migration coupled with existing Retail timeline challenges mean that delays have occurred within the 5MS Retail workstream. There is no schedule contingency within this workstream to compensate for the time needed to remediate these issues therefore the scheduled go-live of 31-May-21 will not be met. | High | Remains High but trend is improving due to confirmation of the Retail go-live on 21 June Issue will be closed post successful go-live on 21 June
I13 NEW | Delay to NCONUML Functionality in Production The delay to the release on the NCONUML functionality in production has resulted in some participants reporting activity “Population and activation of NCONUML NMIs and Associated Metering Data Delivery from 1 Oct” as at risk/ late. This may cause a compliance risk for those participants. | High | See next section for mitigation
R33 | Further delays to AEMO Retail Systems impact 5MS rule commencement critical path There is a risk that cutover issues or post go-live issues cause delays that impact on Market Trial start date thereby impacting the critical path to further delays beyond those identified put the critical path through market trial to 5MS rule commencement (01-Oct-21) at risk | Significant | Residual Likelihood – unlikely Residual Consequence – extreme Residual rating – significant Trend: redefined, therefore neutral Risk description has been updated to reflect the 21 June go-live of Retail Platform Refer to Contingency Plan.
As presented at PCF on 17 June 2021

## Slide 37: AEMO & Industry Readiness
Risk ID | Description | Residual Rating | Comments
R34 | Delay to AEMO 5MS Retail impacts participants readiness There is a risk that the delayed availability of the 5MS Retail solution impacts participants readiness programs resulting in delays in some participants programs. | Significant | Residual Likelihood – remains as possible. The functionality required for participants to continue their readiness programs will be available. The exception to this will be NCONUML. Issue I13 has been raised to address this. Participants have highlighted reduce remediation period available post Market Trial. Residual Consequence – remains major Residual rating – remains significant Trend: worsened – reflecting the reduced time post Market Trial
R11 | The AEMO business and operations are not ready for 5MS Rule Commencement on 1 Oct 21 The AEMO business may not be ready to deliver the full extent of the 5MS deliverables by 5MS and GS rule commencement including business processes and resource training, results in failure of Go Live for 5MS and GS Program | Medium | Residual Likelihood – remains as unlikely Residual Consequence – remains as major Residual rating – remains as medium Trend: improving as AEMO progresses with Retail releases and preparation for Market Trial is underway
R19 | Risk of a critical mass of participants not being ready at identified critical path milestones Critical capability of participants fail to meet expected industry Readiness critical path milestones, resulting in failure to be ready for go-live and impacting the proper functioning of the market. | Medium | Residual Likelihood – remains as unlikely, key Residual Consequence – remains as major Residual rating – remains as medium Trend: worsened -reflecting the reduced time post Market Trial
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​
As presented at PCF on 17 June 2021

## Slide 38: Volume of Regulatory Change
Risk ID | Description | Residual Rating | Comments
R37 | New 5MS Retail Solution Go-Live Dates impact other regulatory change programs There is a risk that the changes to the 5MS retail timeline may have impacts on other AEMO change programs (e.g. Customer Switching or WDR) which may result in a need for those programs to replan having knock-on effects to the industry. | Medium | Retail go-live has been confirmed and dates for 5MS Market Trial are firm. Risk to be closed with successful go-live
R06 | Interaction with other industry changes that have already been adopted through rule changes Significant regulatory changes across the energy sector will stretch resources allocated to market change programs, resulting in potential impacts to participants resourcing and program delivery. | Significant | No change to risk since last review. Residual Likelihood – remains as possible Residual Consequence – remains as major Residual rating – remains as significant Trend: neutral
R09 | Impact to 5MS from other rule changes that are being considered Future rule changes could affect the implementation of 5MS, resulting in impacts to industry program implementation timelines | Medium | Residual Likelihood – reduce from possible to unlikely as 4 months remaining until 1 October. Standard AEMC rule change process is 6 months. Expedited process would need to be used which is an exceptional process. Residual Consequence – remains as major Residual rating – reduces from significant to medium as a result of the change to likelihood Trend: improving as no further rule changes are being considered close to 1 October that would impact 5MS.
R30 | Risk that new 5MS and GS Go-Live dates could impact other industry change programs The new commencement dates are closer to some other industry change programs. There is a risk that industry and AEMO resources and systems may be constrained during a period of multiple major go-lives which may lead to difficulties with timelines and system stability. | Significant | Residual Likelihood – reduce from likely to unlikely. Retail Go-Live dates have been included in the Regulatory Implementation Roadmap and any necessary changes to other programs have been made. Residual Consequence – remains as major Residual rating – reduces from significant to medium as a result in change to likelihood Trend: neutral
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​
As presented at PCF on 17 June 2021