## Slide 1: 5MS & GS Executive Forum Update – Special Session
Tuesday, 1 June 2021
This meeting is recorded for the purpose of minute taking.
Please disconnect from your workplace VPN for the WebEx call​

## Slide 2: AEMO Competition Law Meeting Protocol
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require

## Slide 3: Agenda
# | Time | Topic | Presenter
1​ | 10:30 – 10:35 | Welcome, Introductions and Apologies | Violette Mouchaileh
2​ | 10:35 -10:40 | Actions from Previous Meetings​ | Violette Mouchaileh
3​ | 10:40 – 10:50 | Program Update | ​Rowena Leung
4 | 10:50 – 11:10 | Retail Status Update | Graeme Windley & Greg Minney
5 | 11:10 – 11:20 | Contingency Planning | Peter Carruthers
6​ | 11:20 – 11:25 | General Questions | Violette Mouchaileh
7 | 11:30 | Meeting Close | Violette Mouchaileh

## Slide 4: Welcome
Violette Mouchaileh

## Slide 5: Purpose of this Special Executive Forum
On 14 May AEMO notified the PCF that the Retail Go-Live milestone of 31 May 2021 would be missed and that AEMO was deferring the Go-Live until the back-up date of 21 June 2021
AEMO discussed the reasons for this change and implications on key milestones and activities with PCF on 19 May and RWG on 28 May
The purpose of this Executive Forum is to:
  Present the reasons for the change and the issues impacting the Retail workstream
  Provide an update on the status of 21 June Go-Live
  Provide an overview of the contingency planning status

## Slide 6: Actions from Previous Meetings
Violette Mouchaileh

## Slide 7: Actions Items
No. | Status | Action | Comment
12.4.1 | Open | AEMO to consider seeking information on whether Retailers are deploying the code for Customer Switching at the same time as 5MS Retail through readiness reporting survey or direct poll. | AEMO is gathering feedback on this topic through discussions with Retailers.
12.6.1 | Closed | AEMO to include an agenda item on contingency planning at the next Executive Forum. | Included in today’s agenda.
12.7.1 | Closed | AEMO to consider the positioning of the Regulatory Implementation Roadmap webpage within the AEMO website. | Feedback has been provided to AEMO External Affairs.
12.8.1 | Closed | AEMO to issue invitation for an Executive Forum in May or June. | Booked for 1 June 2021.

## Slide 8: Program Update
Rowena Leung

## Slide 9: 5MS Program – IT Systems Status
Stream | Status | Commentary
Retail |  | Retail go-live milestone of 31-May-21 will not be met. Go-Live has been deferred until back-up date of 21-June-21 Further detail provided in next section.
Dispatch |  | 5MS Bidding Service went live on 1 April 2021. Participants may choose to submit 5-min bids (must be equal for a 30-min period). Pre-dispatch P5 – Fast Start Inflexibility Profile (FSIP) and 5MPD Price Sensitivity – targeting 7th July for both items to be in Production.
Settlements |  | Settlements' systems was successfully deployed in the production environment on 16-May-21. Remains in 30-min mode until 01-Oct-21. Release included web changes, new APIs, dashboard for settlements direct and prudentials, and new look for invoices and statements.
Overall AEMO Status |  | Overall, the AEMO 5MS program remains Amber due to Retail platform delay.
 | Go-live date impacted
 | At risk
 | On schedule

## Slide 10: Updated 5MS Program Timeline
Retail Go-Live moved from 31-May to 21-June
Rule Commencement remains green but with heightened risk profile and subject to achievement of Retail go-live backup date
Retail Industry Test period extended from 21-May to 14-June
Market Trial period moved from 05-Jul – 28-Aug to 19-Jul – 10-Sep (TBC with RWG)
Market Trial prep milestone moved from 05-Jul to 12-Jul
Retail Industry Go-Live Plan will be reissued by 28-May. Cutover walk-through session will be rescheduled with RWG.

## Slide 11: 5MS Rule Commencement – Round 7 as at 25/5 – updated for Retail platform
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
Activity | Status | Comments
AEMO Business Readiness for 5MS and GS (Part A) |  | Bidding Platform deployed to Production 1 April Settlements platform deployed for 30 minute settlement on 17th May Retail Platform go-live rescheduled to 21 June AEMO Program rated Amber for Retail Go-Live rescheduling Market trial commencement rescheduled, with trial period maintained prior to 1 October.
Essential Industry Capabilities for 5MS commencement (Part A) |  | On track for 1 Oct 21 commencement Metering Service Providers (MCs, MPs, MDPs) generally reporting on track, metering installation and configuration well progressed One MSP highlighting their program as on track for compliance requirements but Amber against MTP criteria Generators reporting on-track
Summary: 5MS Rule Commencement |  | Overall, Industry and AEMO components of essential capability is rated as on track for 5MS Rule commencement, noting the rescheduling of the AEMO Retail Platform, and Market trial commencement. The heightened risk profile is noted, with the risk that further slippage may impact critical path transitional activities, along with individual participant impacts.
Other industry capabilities for 5MS and GS (Part B) |  | Other Participant readiness activities proceeding in line with 5MS and GS rule commencements Individual participant readiness risks noted in regards Global Settlement activities, with no systemic risks
On track
On track
On track
Risk 1
Risk 2
Risk 1
On track

## Slide 12: Retail Status Update
Graeme Windley

## Slide 13: Reasons for Retail Go-Live Delay
5MS was delayed in completing the final UAT cases, largely impacted by issues with current MSATS data.
The same MSATS data issues blocked the production data migration process, and meant the critical path to 31 May could not be met
5MS has been impacted by COVID, which has slowed down the defect fix rate.
During industry testing, two defects were found that would have significantly impacted multiple participants at Platform go-live:
  CH35 limit on filename – Remediation: change going into Pre-Production week commencing Monday 24 May.
  Settlement run output RM Reports not containing from and to dates – Remediation: change going into Pre-Production week commencing Monday 31 May (successful testing permitting)

## Slide 14: Retail Checkpoint Criteria
Criteria​ | Description | Status | Commentary
Testing | All UAT test cases executed with no critical defects that cannot be remedied for 31 May go-live. | Delayed | 5MS has had delays completing its final UAT cases, largely impacted by data issues from current MSATS data. Initial fixes supplied were not successful. A change in approach has had positive results, but considerable time has been lost. The Pre-Production environment will receive these fixes week commencing Monday 31 May, then 5MS is to complete profiling runs.
Solution Stability | End-to-end solution operating stably in Test with no process blockers or unexplainable pauses/interruptions to processing. |  | Stability has improved, and enabled testing execution to progress. Improvements (i.e. defensive programming) introduced have been successful. Some initial stability issues were experienced in Pre-Production however AEMO is confident this has been tuned and therefore rectified.
Remediation | Known remediation work (internal reports performance, business activity monitoring) completed and remediation for any new defects scheduled. | In Progress | Internal work on Business Activity Monitoring has progressed well. Challenges continue to be experienced with Operational Reporting delivery that may impact business efficiency, but not presently expected to block go-live.
Performance | “Day in the Life Testing” completed with no performance issues identified that cannot be remedied for 31 May go-live. |  | All Day In The Life testing now completed, with the volumes ingested / outputted matched live industry requirements.
Production Cutover | Data migration on track and no blockers to meeting criteria/schedule for pre-production deployment. | Delayed | Data Migration to Production was delayed by the MSATS data issues, and would not have met 31 May deployment timelines. These issues have been rectified for the Production migration, which is now on track for 21 June.
Industry Test | On track to commence Retail Industry Test on 19 April. | In Progress | From industry testing two defects have been found that would significantly impact multiple participants, and therefore risk market function at the Platform go live. Both of these need development then testing by industry personnel: CH35 limit on filename – change into Pre-Production week commencing Monday 24 May. Settlement run output RM Reports not containing from and to dates – change into Pre-Production week commencing Monday 31 May (successful testing permitting)
Overall |  |  | 21 June is amber. Retail platform test status shown overleaf. The 5MS program has been impacted by COVID, with multiple team members either in India or with family members in India impacted by the virus and needing time off work. This has slowed down issue resolution.

## Slide 15: Retail Test Status
Comprehensive test regime undertaken – over 5000 test cases executed and passed
  Market outcomes from test cases are solid, parallel testing completed
  Remaining number of test cases is very small and workarounds available for most
Regression test to be completed by 14 June
Testing that must be completed before Go-Live
  Remediation of MSATS data issues
  2 remaining Profiling test cases
  Regression testing
Testing that is underway, but will not stop Go-Live if not complete as workarounds are available
  Non Contestable Unmetered Load (7 test cases). If testing is incomplete, participants will be asked to hold-off submission of NCONUML meter info for a short period. Being addressed through the RWG.
  Enterprise data platform (5 test cases). Internal AEMO impact only and workarounds available.
  AEMO Operational reports. Not all reports will be delivered by go-live, internal impact only, workarounds being developed
  Severity 3 defects. Not all Sev 3 defects will be remediated and re-tested. Workarounds are being developed. Any impacts to participants will be published through the known defects list.

## Slide 16: Approach to Retail Status Updates
14-May
Retail No-Go Communicated to PCF via email
19-May PCF
Timeline replanning
Impacts of replan
Retail Checkpoint update
21-June
5MS Retail/ Metering Solution Go-Live
Key milestones
Communication timeline
07-May
PCF Update Session
01-June Exec Forum
Retail Checkpoint Update
Impacts of replan
14-June
Retail Go/No-Go Communicated to PCF via email
17-June PCF
Confirming Go/No-Go
Issue management
Contingency discussion if necessary
04-June PCF Update
Retail Checkpoint Update

## Slide 17: What happens if AEMO reports a No-Go on 14 June 2021?
Brief PCF at 17 June to provide an update on the reasons and next steps
Review timeline for opportunities to compress schedule and maintain 1 October start date (noting opportunities may be limited)
Commence process to assess against Contingency Plan
Prepare for Executive Forum for first week of July

## Slide 18: Contingency Planning
Peter Carruthers

## Slide 19: Risk Scenario and approach to contingency
The first level of contingency is to maintain 1 October 2021 through compressing the transition period (as discussed in previous section)
The second level of contingency, if no other options are available, is to move the market start date using one of the contingency options discussed with PCF and RWG
Purpose of this section is to provide an overview of the options that were presented to PCF/RWG, a summary of the feedback received and provide an update on AEMO’s current position
Risk ID | Description | Residual Rating
R33 | Further delays to AEMO Retail Systems impact 5MS rule commencement critical path There is a risk that further delays beyond those identified put the critical path through market trial to 5MS rule commencement (01-Oct-21) at risk | Significant

## Slide 20: Overview of Contingency Options and Scenarios
At the last PCF three contingency options were discussed:
Option 1: Move the commencement date for all aspects of 5MS rule
Option 2: Move the start date for a subset of the 5MS rule (i.e. for AEMO settlement only)
Option 3: Resettle the market at 5-min
At the RWG on 04-May two timeline scenarios were discussed:
Scenario 1: Short Slippage – 4 weeks max
Scenario 2: Slippage longer than 4 weeks

## Slide 21: Conclusions from feedback provided by PCF
19 responses were received
A wide variety of responses were received from participants on each of the topics, without consensus emerging
A number of participants emphasised the importance of meeting 1 October
Other conclusions/themes emerging from the feedback include the following:
  Option 1 was the most supported option. Option 3 flagged as having negative impacts by multiple participants.
  No clear distinction emerged for preferred options in the event of a short delay vs a longer delay.
  GS soft start transition period is currently 7 months. Support exists for a shorter transition period, in the range of 4 - 5 months – but not unanimous.
  Advanced notice period emerged as a theme, with support for notification in the June timeframe – although not unanimous.
  Certainty of go-live date emerged as important for a number of participants (planning and resource deployment) – consistent with feedback on the advanced notice period. But counter-balanced by participants seeking to minimise delays (cost implications).
Tension exists between the objective of meeting 1 October vs providing certainty of date
  Do not want to move the market start date if it is not necessary
  But if the market start date cannot be met, the earliest possible notification is required

## Slide 22: Consequences to other regulatory initiatives
2021 initiatives impacted by any change to 5MS date:
  Wholesale Demand Response, Customer Switching and B2B v3.5/3.6
2022 initiatives potentially impacted by 5MS date change, depending on duration of deferral:
  Global settlements, MSDR, MCPI
AEMO’s Regulatory Implementation Roadmap process will be utilised to identify and consult on consequential changes. This process has been running since early 2020 and is now well understood. It will be triggered as part of the contingency plan.
General points to be considered in reviewing impacts to dates:
  Industry preference for bundling noted
  15 Dec to 31 Jan no-go period for scheduling of go-lives
Specific points:
  Wholesale Demand Response date will need to move as it can not go live before 5MS
  Strong advocacy from industry participants on bundling of Customer Switching and 5MS is noted
  Advocacy to bundle B2B changes with 5MS is noted and will be investigated for practicality within AEMO
  Maintaining the bundled approach for Global Settlements, MSDR and MCPI is seen as desirable
  Some compression of transition period between GS soft-start and GS financial start appears workable, will be considered depending on extent of 5MS delay

## Slide 23: Next Steps
Given the feedback, AEMO considers that Option 1 (full rule deferral) is the emerging option
AEMO is discussing the feedback on the options and the regulatory tool that would be most appropriate for each option with AEMC and AER
Contingency plan finalisation expected mid-June (subject to governance processes at the market bodies)
  Option, regulatory tool, trigger, timing
AEMO will update the PCF (17 June) and present to Executive Forum at start of July

## Slide 24: General Questions
Violette Mouchaileh

## Slide 25: Upcoming Executive Forums
Date | Topics
07-Jul-21 | Debrief on Retail Platform deployment Market Trial Update Readiness Reporting incl update against Rule commencement criteria
02-Sep-21 (changing to last week of August likely) | Rule Commencement review Market Trial results summary Preparing for 1 October 2021 – Industry Go-Live Plan

## Slide 26: Upcoming Meetings AEMO | Program Calendar and Timelines
Current as at 28/05/2021

## Slide 27: Meeting Close
Peter Carruthers