## Slide 1: 5MS & GS Readiness Working Group #17 (incl. Systems Working Group)
Monday 16 November 2020
WebEx only: **Please disconnect from your workplace VPN for the WebEx call**
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol.
Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol.
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require.
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
Greg Minney

## Slide 4: Agenda **Please disconnect from your workplace VPN for the WebEx call**
#` | Time | AGENDA ITEM | Responsible
1 | 10:00 – 10:05 | Welcome, introduction and apologies | Greg Minney
2 | 10:05 – 10:10 | Agenda | Greg Minney
3 | 10:10-10:15 | Minutes/Actions | Anne-Marie McCague
General Update |  |  | 
4 | 10:15 – 10:25 | 5MS Program Update | Greg Minney
5 | 10:25 – 10:30 | Procedure update | Simon Tu
6 | 10:30 – 10:40 | Testing Update | Tui Grant
7 | 10:40 – 10:55 | Readiness Reporting Round 4 | Austin Tan
8 | 10:55 – 11:05 | Industry Readiness Report – Review | Austin Tan
Dispatch / Bidding Readiness |  |  | 
9 | 11:05 – 11:15 | Dispatch / Bidding Update | Ian Devaney
Settlements Readiness |  |  | 
10 | 11:15 – 11:20 | Settlements Update | Mark Hillaby
Retail / Metering Readiness |  |  | 
11 | 11:20 – 11:35 | Retail / Metering Update | Jim Agelopoulos
12 | 11:35 – 11:45 | Retail Go-Live Plan | Greg Minney
Meeting Closing Items |  |  | 
13 | 11:45 – 11:50 | Forward Plan and Other Business | Greg Minney
14 | 11:50 – 11:55 | Upcoming meetings/ focus groups | Anne-Marie McCague
15 | 11:55 | Meeting Close | Greg Minney

## Slide 5: List of Appendices
A1: L2 Readiness Milestones

## Slide 6: Minutes & Actions
Anne-Marie McCague

## Slide 7: RWG Actions
No. | Status | Action | Comment
15.3.2 ​ | Closed​ | RWG to provide feedback on the proposed settlements platform go-live date of 19 April 2021, including any impacts to participants’ programs, testing requirements, and any suggested mitigations ​ | Updated to be provided in Program Update section of this session. RWG 17
16.9.1 | Open | AEMO to provide RWG with implementation approach, timeframes and testing approach of Global Settlement changes (e.g. LR to GLOOPOOL transition). | Update to be provided in RWG meeting
16.9.2 |  | AEMO will confirm considerations for the provision of Tier 2 accumulation meter data to LRs post GS go live | To be covered during this RWG 17
16.11.1 | Closed | AEMO to organise a separate focus group session to discuss the potential system impacts associated to the anticipated volume of MTP related CATS CR transactions and notifications. | Complete – joint SWG / TFG organised for 26-Nov. Proposed agenda at the end of this session.
16.12.1 | Closed | RWG to provide feedback on the Retail platform industry go-live plan | To be covered during this RWG 17
16.13.1 | Closed | AEMO to make a recommendation to the PCF regarding if 5MS readiness reporting should incorporate considerations involving customer switching and WDR. | Under discussion. Added to the PCF agenda for December.

## Slide 8: Program Update
Greg Minney

## Slide 9: 5MS Program Timeline Level 1 and External Level 2 Milestones 1/2
Current as at 16-10-2020

## Slide 10: 5MS Program Timeline Level 1 and External Level 2 Milestones 2/2
Current as at 16-10-2020

## Slide 11: Program update and current activities
AEMO program
Overall Program remains Green trending down. Delivery pressures remain.
The program continues to be in an intense period of delivery focusing on:
  Non-critical build items
  Testing
  Dress Rehearsal
  Certification
The Testing program remains in full flight, we have progressed further into the test program, with concurrent testing phases across all 3 releases.
AEMO internal readiness preparation activities for go-live also continue.
Systems
Testing and deployment work continues across all streams - no change to any upcoming Staging deployment, Pre-Production or Production deliveries.
Issues with performance testing of running >3 high-frequency RM reports (as reported at the PCF in October) not resolved, resolution work is continuing in November. Update to be provided to the December PCF.
Dispatch Pre-Prod deployment moved one day to complete by 30-Nov-2020 (was on a Sunday).
Upcoming SWG scheduled for 26-Nov-2020 focusing on system implications of volume of GLOPOOL. Combined with ITWG.
Readiness
Readiness Survey #4 conducted. Strong response from 44 participants. Essential Capability indicators stable.
Retail Platform go-live preparation in progress with invitation industry test planning and draft go-live plan
Consolidation of industry plans for metering activation indicate likely peak transactions 3rd quarter 2022. TFG to consider volume implications

## Slide 12: AEMO Systems Deployment Cutover Risk – Update
Risk Description | Risk Assessment |  | 
The current Cutover approach has the 3 AEMO systems deployments in close succession. Retail Metering the largest, most technically complex and riskiest cutover going first on 9 March, then followed by both the Dispatch and Settlements systems deployments together 3 weeks later on 1 April. A go-live criteria for Settlements is a stable metering platform. The current timetable only allows one week for the Retail solution to be stabilised prior to commencing cutover activity for Settlements which is high-risk. | Inherent Likelihood | Inherent Consequence | Inherent Risk Rating
 | Possible | Major | Significant
 | Residual Likelihood | Residual Consequence | Residual Risk Rating
 | Unlikely | Moderate | Medium
AEMO has presented the proposal to change the deployment date for the Settlements solution to 19 April 2021 to the PCF (03-Sep and 01-Oct) and RWG (14-Sep and 13-Oct)
MSUG was held on 16-Oct-20 to discuss the 5MS and non-5MS impacts to the data model v5.0
Feedback was requested from RWG and PCF by 23-Oct-20. Feedback indicated that there was no impact to participants.
AEMO considers this approach to be confirmed and timelines will be updated with Settlements Go-live on 19-Apr-21
Milestones will be updated to reflect

## Slide 13: Procedure update
Simon Tu

## Slide 14: 5MS/GS-related procedure change log
Procedure issue | Status | Final Determination Date
Proposed procedural change to MDFF quality flag (N flag)* | Consultation commenced 6 August, anticipated to be concluded early December. | December 2020
Removal of end user details from inventory table | Consultation commenced 6 August, anticipated to be concluded early December. | December 2020
Removal of register ID = suffix requirement | Consultation commenced 6 August, anticipated to be concluded early December. | December 2020
Clarification on existing requirements for the 5 minute load profile and RM reports | Consultation commenced 12 October. Part of the Retail Procedures (Wholesale Demand Response) consultation. | March 2021
New NCONUML NMI Class codes available in list for SORD #​ | Part of broader requirements for the changes to the SORDs (v3.5 of the procedures) scheduled for an effective date of 10 Nov 2021.​ Final Determination has been published. | Published – 22 July 2020
Proposal for RWD | Part of MSATS Standing Data Review. Final Determination has been published. | Published – 7 September 2020
TNI 2 for cross-boundary meters *# | Part of MSATS Standing Data Review. Final Determination has been published. | Published – 7 September 2020
*raised by the 5MS Program
# aseXML schema impact

## Slide 15: 5MS/GS-related procedure change log
Procedure issue | AEMO Retail Systems Impact | Available in Staging | Readiness Considerations
Proposed procedural change to MDFF quality flag (N flag)* | Rejection of B2M MTRD MDFF meter reads where quality flag is ‘N’. Results in B2M MTRD Transactions with the status of ‘Partial’ or ‘Rejected’. | R1 - 1-Dec-19 - Support for new B2M MTRD validations. | Participant Mkt Systems must not send ‘N’ for B2B or B2M MTRDs.
Removal of end user details from inventory table | No impact to 5MS Retail systems. | N/A | N/A
Removal of register ID = suffix requirement | No impact to 5MS Retail systems. | N/A | Material participant readiness activity impact if existing requirement retained.
Clarification on existing requirements for the 5 minute load profile and RM reports | 5MLP included in RM20 and RM25 reports | R27 - 31-Oct-20 - Existing Settlements Reports @5-min: RM16, RM17, RM20, RM21, RM22, RM26 | 
New NCONUML NMI Class codes available in list for SORD #​ | System impacts are yet to be identified. Likely B2B schema change. | TBD: Dependant on evaluation of system impacts and finalisations of v3.5 of the B2B Procedures: Service Order Process. | TBD
Proposal for RWD | No impact to 5MS Retail systems. | N/A | ReadTypeCode amended from ‘Optional’ to ‘Required’. Fourth character added to identify whether a meter is capable of reading at five-minute granularity.
TNI 2 for cross-boundary meters* | CATS CR support for TNI2 field. MSATS Browser to support display TNI2 for NMI Discovery Transactions. aseXML schema support extension to support TNI2 inclusion (r39). | R18 and R19 - 31-Aug-20 - Support for TNI2 for CATS CRs. | TNI Code assigned, by AEMO, however Participants to undertake the generation of associated CR2xxx transactions, to register a cross boundary meter using TNI 2. Migration to r39 aseXML necessitated.
*raised by the 5MS Program
# aseXML schema impact
Notes: Enumeated field, added to a number of schema changes to make contestable metering more efficient for service orders (to avoid special instructions and common comments – created new fields and lists to assist SORD processing v 3.4 / split dates for v3.5 items different effective dates, v3.6
Removed:
10MB file size

## Slide 16: Testing Update
Tui Grant

## Slide 17: General Update
31 Oct Staging – 5 minute settlements run in MSATS has encountered performance issues which have been addressed this week and we are planning to complete by the end of this week (13-Nov)
13 Nov – cut off for responses for participants to respond with test cases to be executed for invitation testing. The next steps after this date will see AEMO start to pair up participants and identify specific data.
Testing of MDMT files by MDPs against eMDM prior to Retail platform implementation to ensure compliance with validation routines

## Slide 18: 5MS Staging Environment Defects Identified
Issue ID​ | Description​ | Status​ | Action​
2805 | Screen display issue only - An extra TNI2 field is getting displayed under Address Information section in NMI Master, Point in Time NMI Master Summary and NMI Discovery Type 1 and Type 2 search page.​ | In Progress | It is a display issue only no functionality affected​
2185​ | Unable to login to MSATS with newly created or updated user id and password​ | In Progress​ | Once created/updated in MSATS users can reset password by logging onto the market portal​
2655 | In flight CRs during schema upgrade do not get published with correct aseXML | Fixed – being deployed | REQ/PEND/COM etc still produced as expected but will have an incorrect asexml response
2856 | Staging: Cleanackhandler sometimes sends incorrect X-initiatingParticipantID request header | In Progress | No impact to participants
2880 | Event Only Nack from Participant Results in a badack | In Progress | Acknowledge the file from MSATS browser to remove the badack
2882 | CATS Report Requests not getting processed in Staging for ENERGYAP, TCAUSTM, TCAMP | In Progress | Issue only affects some participants
2890 | Updated Data Stream type for K1 and Q1 not reporting correctly in C1 | Under Investigation | 
Current as at 06-Nov-20

## Slide 19: Retail – Functionality in Staging Release 3

## Slide 20: Industry readiness reporting – Round 4
Austin Tan

## Slide 21: Summary of coverage, status and progress
Strong survey coverage, with 44 respondents representing 95-100% of the industry. Response rate across all participant types provides representative industry coverage.
Two-thirds of respondents now focused on development and testing. The remaining participants are in the scoping and design phase of their programs. All except one respondent noted that they are on track.
AEMO is on track to deliver the market systems in line with committed milestones. AEMO's progress towards 'Switching Local Retailer and FRMP to GLOPOOL' has advanced to the next quartile (25 - 49% Complete).
Chart: 
No change | 39
Minor change | 5
Major change | 0
Compared to the previous round of reporting, 88% of participants are not experiencing any change in their ability to implement 5MS and GS due to COVID-19. A minority (12%) are experiencing minor changes. No impact was noted against overall program progression.

## Slide 22: Critical Capability leading Indicators
Generation - Two generators noted that they were at risk or late, however number of on-track generators was sufficient to meet essential criteria. The generator that reporting a late status in the previous reporting round is now on track.
Essential meters – MDPs are reporting on track, however three MPs and one MC with responsibility of essential meters did not respond to this survey, responded with inconsistencies, or did not respond to the essential metering criteria. AEMO will be following up to clarify.
AEMO market systems criteria is on track.

## Slide 23: Participant Readiness Risks for Review
ID | Title | Residual Rating | Trend | Comments
01 | Some MPs and MCs are not providing readiness updates on essential metering criteria Three MPs and one MCs with responsibility of essential meters did not respond to the survey, or did not respond to the essential metering criteria. | TBC |  | AEMO to follow up with relevant MPs and MCs with essential meters to confirm program status and if remediation is required. Any required remedial action will be highlighted in the next readiness report
02 | Industry vendors not having access to the 5MS staging environment One participant noted that a major vendor is constrained in testing their 5-minute product because the 5MS staging environment accessible only to industry participants. | TBC |  | RWG to discuss impact across industry and approaches to address
 | Improving No Change / Stable Worsened

## Slide 24: Participant Readiness Risks for Review
ID | Title | Residual Rating | Trend | Comments
03 | Risk of inaccurate UFE information if cross boundary meters are not appropriately configured by the transition end dates. A number of LNSPs have flagged a potential inability to meet the transition end dates / rule commencement dates for the installation of new cross boundary meters. One retailer noted the potential impact on the accuracy of UFE Global Settlements soft start, hampering retailers readiness for Global Settlements. | TBC |  | RWG to consider industry impact if all cross boundary meters are not appropriately configured by GS Soft Start. DNSPs to confirm delivery timeframes as per MTP.
04 | Customer switching going live on the same day as 5MS could created dependency and risks. One retailer noted that going live on the same day creates dependency and risks. | TBC |  | AEMO provided an update to the PCF regarding Customer Switching considerations on the 5MS program on 5 November, including the testing and stakeholder engagement approach. RWG to identify any additional risks and dependencies to 5MS and GS delivery.
 | Improving No Change / Stable Worsened

## Slide 25: Participant Readiness Risks for Review
 | Improving No Change / Stable Worsened
ID | Title | Residual Rating | Trend | Comments
05 | A number of MPs have not performed a data cleanse of the meter installation type code in MSATS by the MTP transition end date As outlined in sub-category S39 of the MTP, MPs are required to perform a data cleanse of the meter installation type code in MSATS by November 2019. However one MPs reported a 'late' status, noting that only a small amount of meters will require updates. Nine other MPs noted that they were 'On track (started)', these statuses have been adjusted to a 'late' status given that the transition end date has now passed. | TBC |  | Performing a data cleanse of the meter installation type code in MSATS by November 2019 was to provide a firm basis for the evaluation of required metering upgrades. All MPs are now reporting progress against the update of the required T1-3 meters RWG to consider impact of late delivery and flow on impact to overall programs (MPs). Relevant MPs to report on remediation approach and progress in next round of reporting.

## Slide 26: Readiness reporting – Round 5
Round 5 of industry readiness reporting will commence on Tuesday 17 November 2020. Survey responses are due by COB Thursday 26 November 2020.
Survey results will be distributed on Thursday 10 December 2020, and discussed at the next RWG on Monday 14 December 2020.

## Slide 27: Industry readiness reporting – Review
Austin Tan

## Slide 28: Considerations for future readiness reports
AEMO proposes to introduce summary reporting in future readiness reports, to focus on emerging trends, risks and issues. Summary reports will include reporting on:
  - essential criteria
  - emerging key risks and issues
  - actions and follow ups from previous report
  items for consideration (e.g. milestones, MTP transition end dates, testing considerations)
  Comparisons to MTP rollout plans
Detailed information will continue to be available in appendices.

## Slide 29: Updates to the readiness reporting approach
Considering the stage of industry 5MS and GS programs, with 66% of participants now focused on delivery, and over 95% of participants with ‘established’ programs - should AEMO still track and report on program establishment criteria?
General Criteria
Project team onboarded
Project governance established
Project plan established
Project funding secured
Are there any other readiness criteria that should be monitored through readiness reporting?​
Any other changes to the readiness reporting plan?

## Slide 30: Dispatch / Bidding Update
Ian Devaney

## Slide 31: Bidding / Dispatch Staging, Pre-production & Production timelines
STAGING
PRE-PRODUCTION
PRODUCTION
01 Oct 2021
05 Jul 2021
29 Nov 2020
01 Apr 2021
01 Oct 2021
LEGACY | BIDDING TRANSITION | 5MS RULE
30-minute bidding only via: FTP (txt) Web Bidding (Legacy) | 30-minute bidding via: FTP (txt) Web Bidding (Legacy) 5-minute bidding* via: FTP (JSON) Web Bidding (5MS) API *Each 5-minute bid within each half hour must be identical, giving the same effect as the submission of a 30-minute bid. | 5-minute bidding* only via: FTP (JSON) Web Bidding API *30-minute bid emulation restriction lifted
LEGEND
For business continuity reasons, 30-mins offers and bids will be accepted until
01 Oct 21

## Slide 32: Systems Workstream – Dispatch & Operations
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
DISPATCH and OPERATIONS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Bidding FTP and API |  |  |  |  |  |  |  |  |  | 
Transition | Aug-18 | Oct-18 | Aug-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Bidding Data Model | Aug-18 | - | Sep-18 | Mar-19 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Bidding Format | Aug-18 | - | Sep-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 2 - Bidding Web UI |  |  |  |  |  |  |  |  |  | 
Bidding Web UI and APIs | Aug-18 | Nov-18 | Dec-18 | Jan-19 | Mar-19 | 31-Jul-19 | 16-Dec-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 3 - Dispatch, Pre-dispatch and PASA |  |  |  |  |  |  |  |  |  | 
Dispatch | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Predispatch P30/7DAY | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Predispatch P5 | Nov-18 | Oct-18 | Nov-18 | TBC | TBC | TBC | - | TBC | 30-Nov-20 | 01-Apr-21
ST and PD PASA | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 4 - Pricing and Miscellaneous |  |  |  |  |  |  |  |  |  | 
Trading Price / Price Revision | Aug-18 | - | Feb-19 | Nov-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 30-Nov-20 | 01-Apr-21
Administered Pricing and CPT | Aug-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 30-Nov-20 | 01-Apr-21
Suspension Pricing | Sep-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 30-Nov-20 | 01-Apr-21
Negative Residue Management | Sep-18 | - | Feb-19 | Dec-18 | Jun-19 | 31-Jul-19 | - | 15-May-20 | 30-Nov-20 | 01-Apr-21
PACKAGE 5 - Full Data Model |  |  |  |  |  |  |  |  |  | 
Full Data Model | Sep-18 | Ongoing | Ongoing | Apr-19 | Ongoing | 31-Jan-20 | 16-Mar-20 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Current as at 02-11-2020
Pre-Production Go-Live date has changed from Sunday the 29th of November to Monday the 30th of November.

## Slide 33: Dispatch Pre-Production Deployment
Industry test for Dispatch in the AEMO pre-production available to commence from 13:00 (AEST) 30-Nov-20
  NB provides for Industry test support during business hours from Monday 30-Nov
Support:
  Participant testing webpage – background information and FAQs
  Functionality Deployment Matrix – includes a list of the functionality that will be available in pre-prod
  The 5MS team will be available for a daily call for one week from 01-Dec. This can be extended/repeated in Jan. Invites will be sent to ITWG and RWG.
  Support is also available through AEMO Support Hub

## Slide 34: Tech Spec Updates
There is a new version of the EMMS 5MS Technical Specification - Dispatch and Operations with details of the P5MIN tables included in v5.00 of the Data Model, reflecting the 5-min Pre-dispatch price sensitivity.

## Slide 35: Settlements Update
Mark Hillaby

## Slide 36: Settlements Staging, Pre-production & Production timelines
Staging
Pre-production
Production
1 Oct 2021
19 Apr 2021
1 Oct 2021
Legacy | New Settlement Platform | 5MS Rule | GS Rule
30-minute Settlements | 30-minutes settlement to 1 October 2021 | Five-minute settlement and Global Settlement soft-start - UFE Reporting | All Retailers become liable for UFE
1 May 2022
Incl. UFE Reporting from 05/07/21
Supports 30MS, 5MS and GS modes
Legend
17 Feb 2021
1 Feb 2022
5 Jul 2021

## Slide 37: Systems Workstream - Settlements
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
SETTLEMENTS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Reallocations |  |  |  |  |  |  |  |  |  | 
Reallocations | Dec-18 | Nov-18 | Dec-18 | Mar-19 | 31-Jul-19 | 15-Oct-19 | 1-Nov-19 | 1-Nov-19 | 1-Mar-20 | 1-Apr-20
PACKAGE 2 - Settlements and Billing |  |  |  |  |  |  |  |  |  | 
Settlements | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 30-Aug-19 | 15-Dec-19 | - | 16-Mar-20 | Feb-21 | Apr-21
Billing | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 30-Aug-19 | 15-Dec-19 | - | 16-Mar-20 | Feb-21 | Apr-21
PACKAGE 3 - Prudentials and Estimation |  |  |  |  |  |  |  |  |  | 
Prudentials | Sep-18 | Nov-18 | Dec-18 | Mar-19 | 31-Oct-19 | 31-Jan-20 | 15-May-20 | 15-May-20 | Feb-21 | Apr-21
Estimation | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 31-Oct-19 | 31-Jan-20 | - | 15–May-20 | Feb-21 | Apr-21
Full Data Model | Refer DISPATCH |  |  |  |  |  |  |  |  | 
Current as at 16-10-2020

## Slide 38: Settlements Workstream Update
Build of our new SQL Pre Production environments is in progress ahead of Feb Pre Prod migration
Certification activities continue to plan
Migration activities underway
UAT in progress

## Slide 39: Retail/Metering Update
Jim Agelopoulos

## Slide 40: Retail Metering Staging, Pre-production & Production timelines
Staging
Pre-production
Production
Legacy | 30MS with new platform | 5MS Rule | GS Rule
30-minute meter reads | 30-min settlement 5-min reads supported Standing data updates for GS | UFE calculation and 5-min settlement | LR updated to GLOPOOL
5 Jul 2021
1 Feb 2021
1 Feb 2022
31 Oct 2020
1 Oct 21
1 May 2022
9 Mar 2021
Legend
GS from 1st quarter 2021 - TBC
1 Oct 2021
Date to be confirmed.

## Slide 41: Systems Workstream - Metering
Current as at 16-10-2020
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
METERING |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Metering Data & Metrology |  |  |  |  |  |  |  |  |  | 
MDFF • MDFF Specification NEM12 NEM13 v20 | Aug-18 | Oct-18 | Oct-18 | Nov-18 | Jan-19 | Apr-19 | - | 1-Dec-19 | 01-Feb-21 | 09-Mar-21
PACKAGE 2 - MSATS & SLPs |  |  |  |  |  |  |  |  |  | 
Transition • MSATS Technical Specification | Aug-18 | Sep-18 | Aug-18 | Nov-18 | 31-May-19 | 30-Sep-19 | - | - | - | -
Meter Data - MDFF and MDMF • MDM File Format and Load Process (User Guide) • MSATS Technical Specification | Aug-18 | Oct-18 | Sep-18 | Nov-18 | 31-May-19 | 30-Sep-19 | - | 1-Dec-19 | 01-Feb-21 | 09-Mar-21
PACKAGE 3 - Miscellaneous |  |  |  |  |  |  |  |  |  | 
B2M via API • MSATS Technical Specification | Oct-18 | - | Apr-19 | 9-May-19 | 31-May-19 | 30-Sep-19 | 01-Jun-20 (Draft) | N/A | 01-Feb-21 | 09-Mar-21
 |  |  |  |  |  |  | 14-Sep-20 (Final) |  |  | 
MSATS Browser (LVI) changes • MSATS Technical Specification | Aug-18 | - | May-19 | 9-May-19 | 28-Jun-19 | 30-Sep-19 | 10-Oct-20 | 15-Jun-20 | 01-Feb-21 | 09-Mar-21
MSATS Report changes • MSATS Procedures MDM Procedure • MDM File Format and Load Process (User Guide) • MSATS Technical Specification General Process & Document Clean-up | Oct-18 | - | Apr-19 | Apr-19 | 28-Jun-19 | 30-Sep-19 | - | 31-Aug-20 | 01-Feb-21 | 09-Mar-21

## Slide 42: aseXML schema update
During AEMO system integration testing a defect was identified in the r39 aseXML schema.
What was the defect?
  The issue related to the LocalArea field size
  The current size is 10 characters field which does not support the value length
  This field will be updated to allow 50 characters
  This change has been presented to the ASWG for consultation.
  The ASWG has authorised the change to be tested prior to Final approval.
Why wasn't this picked up previously?
  Schemas go through desktop and regression testing as part of the approval process.
  The r39 schema has a valid structure and supports existing functionality
  This issue was only identified during end-to-end testing of the new UFE reports.
  Full end to end testing will be performed prior to requesting Final consultation approval
What does this mean to participants?
  The proposed r39 schema will be replaced by r39_p1
  Once r39_p1 goes live the superseded version will remain as r35
  If your business has downloaded the r39 version, it will need to be replaced with the r39_p1 version once final approval has been received.
ASWG – aseXML Standards Working Group

## Slide 43: Tier 2 Manually Read Metering Data
Participant question relating to the delivery of Tier 2 manually read metering data to Local Retailer after Global Settlements Rule Commencement 01-May-22, where those actual reads include periods prior to GS Rule Commencement (e.g. actual read for basic meter delivered for the period 01-Mar – 30-May)
AEMO's review of the GS rule is as follows:
The GS Rule does not consider this issue relating to Tier 2 manually read metering data being sent to LR after GS go live.
  There were no LR comments in the consultation submissions about this issue.
The GS Rule is focussed on identifying all forms of energy consumption in order that UFE energy volumes will be most meaningful, rather than delving into the mechanics of settling LRs up to GS go-live.
Conclusion:
If LRs consider this to be a material issue, they may want to initiate a Rule change or identify processes to overcome the meter data delivery issue.
Actions
LR's to consider materiality of the issue in the period of transition to GS
  Forward estimates should be available for all Tier 2 manually read meters

## Slide 44: Changes to MSATS Technical Specification
AEMO shall update the MSATS 46.98 Technical Specification to remove functions now in the MSATS 49.99 and MSATS 49.nn releases and move these into new Technical Specification documents
  46.98
    Covers 09-Mar-21, go-live of MDM platform ahead of 5MS market start where AEMO accepts 5-, 15- and 30-minute reads and settles the market at 30 minutes.
    Details the aseXML schema r39_p1 changes required to support 5MS as well as the schema elements required for the NEM Customer Switching changes to become effective in 46.99.
  46.99
    Covers 1-Oct-21, 5MS market start where AEMO settles the market at 5-minute intervals and begins reporting on UFE.
    Includes NEM Customer Switching functionality.
    Provides a view of the Change Request changes under both NEM initiatives.

## Slide 45: Changes to MSATS Technical Specification
  46.nn
    Covers 01-May-22, go-live of GS specific capability to enable GS market settlement where the GLOPOOL Participant ID becomes effective and UFE reporting is formalised.
    Provides a view of the Change Request rejection logic for GLOPOOL Participant ID.

## Slide 46: Retail platform go-live plan
Austin Tan & Greg Minney

## Slide 47: Feedback Received and next steps
  Draft Retail Go-Live Plan – Areas to be Addressed
Confirmation of timings and approach for placing B2M and B2B transactions on hold while cutover occurs​
  AEMO cutover processes will be confirmed during DR2, to confirm timing and approach to holding of B2B and B2M transactions
  Industry Go-live plan to be updated with further detail on approach and timing to support participant planning
Detail confirmation re Vic TUOS migration​
  FAQ and participant process options to be included in next draft
  Briefing / options assessment with impacted MDPs
Communication of Backlog processing timeframes​
  To be confirmed post DR2 based on updated timing
Approach and involvement for Production Verification Monitoring​
  AEMO to confirm participants and indicative transactions
  AEMO to establish comms approach for PVM participants
Next Steps:
Updated draft of Industry Go-live Plan issues for feedback 20th November
AEMO to establish working group for PVM approach (once confirmed)
Review at December RWG

## Slide 48: Forward Plan and Other Business
Greg Minney

## Slide 49: Next RWG Meeting
Next RWG scheduled 14 December
Proposed agenda:
  Dispatch platform go-live plan
  Settlements platform go-live plan engagement
  Retail Pre-Prod and Go-Live
  2021 Stakeholder Engagement Plan – 2021 calendar to be circulated by the end of the month

## Slide 50: Proposed TFG/SWG Agenda
Further consideration of CATS transaction volumes
MTP activity update

## Slide 51: Upcoming meetings/focus groups
Anne-Marie McCague

## Slide 52: Upcoming meetings
Current as 6 Nov 2020
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement

## Slide 53: Questions

## Slide 55: Appendices

## Slide 56: Appendix Contents
A1: L2 Readiness Milestones

## Slide 57: A1: L2 Readiness Milestones

## Slide 58: Level 2 Milestones – Readiness
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-RE11 | Metering Service Provider Accreditation Plan Finalised | 13-Mar-2020 | 18-Feb-2020 | AEMO | Complete
L2-S12 | Reallocations Go-Live | 01-Apr-2020 | 01-Apr-2020 | AEMO | Complete
L2-RE32 | Industry Test for Reallocations Concludes | 31-Mar-2020 | 31-Mar-2020 | AEMO | Complete
L2-RE22 | Industry Transition Plan – Dispatch​ final complete | 28-Aug-2020 | 28-Aug-2020 | AEMO | Complete
L2-M11 | Industry Test preparation completed by participants for MDM and B2M Go-Live | 01-Feb-2021 | 01-Feb-2021 | Participants | 
L2-M12 | Industry Test preparation completed by AEMO for MDM and B2M Go-Live | 01-Feb-2021 | 01-Feb-2021 | AEMO | 
L2-RE29 | Retail MDM (incl. B2M) Industry Test Commences | 01-Feb-2021 | 01-Feb-2021 | AEMO | 
L2-RE30 | Retail MDM (incl. B2M) Industry Test Concludes | 03-Mar-2021 | 03-Mar-2021 | AEMO | 
L2-RE18 | Industry Go-Live Plan Retail MDM finalised | 20-Nov-2020 | 20-Nov-2020 | AEMO | 
L2-M24 | B2M Go-Live | 09-Mar-2021 | 09-Mar-2021 | AEMO | 
L2-M10 | 5 minute files in MDFF accepted by AEMO | 01-Apr-2021 | 01-Apr-2021 | AEMO | 
L2-D7 | Dispatch Industry Test preparation completed by participants | 29-Nov-2020 | 29-Nov-2020 | Participants | 
L2-D8 | Dispatch Industry Test preparation completed by AEMO | 29-Nov-2020 | 29-Nov-2020 | AEMO | 
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-RE11
L2-RE32
L2-S12
L2-RE22
L2-M11
L2-M12
L2-RE18
L2-M24
L2-M10
L2-D7
L2-D8
L2-RE29
L2-RE30
Current as at 16-10-2020

## Slide 59: Level 2 Milestones – Readiness
Key Milestones (Program) |  |  |  |  | 
ID | Milestone | Target Date | Expected Date | Owner | Status
L2-S10 | Settlements Industry Test preparation completed by participants | 17-Feb-2021 | 17-Feb-2021 | Participants | 
L2-S11 | Settlements Industry Test preparation completed by AEMO | 17-Feb-2021 | 17-Feb-2021 | AEMO | 
L2-RE28 | Dispatch Industry Test concludes | 15-Mar-2021 | 15-Mar-2021 | AEMO | 
L2-RE32 | Settlements Industry Test concludes | 15-Mar-2021 | 14-Apr-2021 | AEMO | 
L2-RE19 | Industry Go-Live Plan Settlements, Dispatch & Bidding finalised | 19-Mar-2021 | 19-Mar-2021 | AEMO | 
L2-RE23 | 5MS Capability Market Trial preparation completed by participants | 05-Jul-2021 | 05-Jul-2021 | Participants | 
L2-RE24 | 5MS Capability Market Trial preparation completed by AEMO | 05-Jul-2021 | 05-Jul-2021 | AEMO | 
L2-RE31 | 5MS Capability Market Trial commences | 05-Jul-2021 | 05-Jul-2021 | AEMO | 
L2-RE20 | Industry Go-Live Plan – 5MS Capability final complete | 01-Aug-2021 | 01-Aug-2021 | AEMO | 
L2-D10 | 5MS Capability Market Trial concludes | 27-Aug-2021 | 27-Aug-2021 | AEMO | 
L2-D11 | 30-min Bidding no longer accepted by AEMO | 01-Oct-2021 | 01-Oct-2021 | AEMO | 
L2-RE25 | MDMT format no longer accepted by AEMO for interval meters | 01-Oct-2021 | 01-Oct-2021 | AEMO | 
L2-RE26 | GS Market Trial preparation completed by participants | 01-Feb-2022 | 01-Feb-2022 | Participants | 
L2-RE27 | GS Market Trial preparation completed by AEMO | 01-Feb-2022 | 01-Feb-2022 | AEMO | 
L2-RE21 | Industry Go-Live Plan – GS Capability final complete | 21-Dec-2021 | 21-Dec-2021 | AEMO | 
Domain | Initiative | 2019 |  |  |  |  |  |  |  |  |  |  |  | 2020 |  |  |  |  |  |  |  |  |  |  |  | 2021 |  |  |  |  |  |  |  |  |  |  | 
 |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Readiness |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec
L2-S10
L2-S11
L2-RE32
L2-RE23
L2-RE24
L2-RE20
L2-D10
L2-D11
L2-RE25
L2-RE21
L2-RE31
L2-RE328
Current as at 16-10-2020
Milestone complete
Milestone on track
Milestone not achieved
Milestone at risk
Milestone deferred
L2-RE19