## Slide 1: 5MS & GS Readiness Working Group #20 (incl. Systems Working Group)
Tuesday 9 February 2021
WebEx only: **Please disconnect from your workplace VPN for the WebEx call**
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol.
Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol.
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require.
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
Greg Minney

## Slide 4: Agenda **Please disconnect from your workplace VPN for the WebEx call**
# | Time | AGENDA ITEM | Responsible
1 | 10:00 – 10:05 | Welcome, introduction and apologies | Greg Minney
2 | 10:05 – 10:10 | Agenda | Greg Minney
3 | 10:10-10:15 | Minutes/Actions | Anne-Marie McCague
General Update |  |  | 
4 | 10:15 – 10:30 | 5MS Program Update | Greg Minney
5 | 10:30 – 10:40 | Industry Testing Update | Tui Grant
6 | 10:40 – 11:00 | TFG/ MTP Update | Blaine Miner
7 | 11:00 – 11:10 | Industry Risks and Issues Register | Anne-Marie McCague
8 | 11:10 – 11:15 | Procedure update | Simon Tu
Dispatch / Bidding Readiness |  |  | 
9 | 11:15 – 11:25 | Dispatch / Bidding Update | Ian Devaney
Settlements Readiness |  |  | 
10 | 11:25 – 11:35 | Settlements Update | Mark Hillaby
Meeting Closing Items |  |  | 
11 | 11:35 – 11:45 | Readiness Survey | Austin Tan
12 | 11:45 – 11:50 | Forward Plan and Other Business | Greg Minney
13 | 11:50 | Meeting Close | Greg Minney

## Slide 5: Minutes & Actions
Anne-Marie McCague

## Slide 6: RWG Actions
No. | Status | Action | Comment
19.2.1 | Closed | AEMO to confirm that NCONUML NMI class codes related changes in the B2B schema relates to the NCONUML CustomerType field and not the ability for all NCONUML to use B2B (even if the field does not apply to them) | Use existing process for requesting NCONUML NMIs until B2B changes come into effect.
19.7.1 | Closed | MCs and MDPs who did not provide a rollout plan update to AEMO in Dec 2020 to forward one to the 5MS inbox as soon as possible | Complete
19.9.1 | Closed | AEMO to provide a list of the UAT Bidding Service defect fixes that will be put into pre-production in February 2021 before they are applied | Update provided in this RWG.
19.13.1 | Closed | MDPs to advise if they are able to continue delivering metering data in MDMT in the event of a rollback during the retail cutover | 2 responses received. Both confirmed they would be in a position to use MDMT for a period of time after the scheduled go-live if rollback was necessary. AEMO will close action on understanding that all impacted MDPs have addressed this action.

## Slide 7: Program Update
Greg Minney

## Slide 8
Revised Retail Go-Live Timeline
Critical path timeline indicates completion of Retail stream activities for a 31-May-21 go-live
  Based on detailed planning and reasonable estimates, predicated on timely resolution of issues
Additional contingency could be added to improve certainty
  Would result in a 21-Jun-21 go-live
  Offers greater certainty in achieving Retail Go-Live date
  Better meets participant objectives of date certainty
Consequences of late June go-live
  Compresses the schedule through the remainder of the program to 5MS market go-live
  Close to Market Trial start (05-Jul-21), creates resourcing conflict if stabilisation issues occur
  Later to switch-on 5-min meter data collection capability – for AEMO, MDPs and Participants alike
  Compresses participant time for UFE soft start transition activities
Options for Consideration
  31-May-21 go-live date with 21-Jun-21 as a fallback. To be determined by a checkpoint in early March.
  21-Jun-21
AEMO preference is for Option 1
  Allows maximum time for transition activities after Retail Go-Live through to market go-live
Seeking participant views
  Input is requested by Friday 05-Feb-21
  Exec forum to be scheduled for 11-Feb-21 at 13:00

## Slide 9: Initial Impact Assessment Key dates
Area | Original Date | New Date | Implication
5MS Rule Commencement | 1 Oct 21 | No change | No change to 5MS market start date Risk assessment requires review and re-rating to reflect revised schedule
UFE soft start | 1 Oct 21 | No change | Compresses available DNSP population time for some UFE Standing data activities and may result in re-scheduling of activities Leads to potentially less accurate UFE on 1 Oct 21 soft start
GS Rule Commencement | 1 May 22 | No change | No impact expected
5MS Market Trial | 5 July 21 | No change | No change to start date for 5MS market trial Acknowledge heightened risks around timely commencement
Dispatch IT Go-Live | 1 Apr 21 | No change | No impact expected
Settlements IT Go-Live | 15 Apr 21 | Mid-May | Will now go-live before Retail MDM Further testing required to allow for this Date currently being finalised, mid-May expected
Regulatory roadmap | Various | No change | No change currently anticipated to any dates: Customer Switching, WDR Regulatory roadmap session currently being arranged at which the overall view can be reviewed

## Slide 10: 5MS Program Timeline – Option 1 Level 1 and External Level 2 Milestones 1/2
Current as at 15-01-2021
R3 Go-live : 31/05/21
Note: Pre-prod and Settlement dates under review

## Slide 11: 5MS Program Timeline – Option 2 Level 1 and External Level 2 Milestones 1/2
Current as at 15-01-2021
R3 Go-live : 21/06/21
Note: Pre-prod and Settlement dates under review

## Slide 12: External Milestones Impacted by Change – to be confirmed at Executive Forum 11-Feb
[Settlements dates under review]
ID | Milestone | Previous Date | Option 1 | Option 2 | Owner
L1-19 | AEMO Metering Solution - Go-Live | 9-Mar-21 | 31-May-21 | 21-Jun-21 | AEMO
L2-RE35 | Industry Go-Live Plan final - Release 3 - Retail MDM | 25-Jan-21 | 16-Apr-21 | 14-May-21 | AEMO
L2-M11 | Industry Test Preparation completed by Participants for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | 10-May-21 | Participants
L2-M12 | Industry Test Preparation completed by AEMO for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | 10-May-21 | AEMO
L2-RE29 | Retail MDM (incl. B2M) Invitation Industry Test Commences | 1-Feb-21 | 19-Apr-21 | 10-May-21 | AEMO
L2-RE30 | Retail MDM (incl. B2M) Invitation Industry Test Concludes | 3-Mar-21 | 21-May-21 | 12-Jun-21 | AEMO
L2-M24 | Retail MDM (incl. B2M) Go-Live | 9-Mar-21 | 31-May-21 | 21-Jun-21 | AEMO
L2-M10 | 5 minute files in MDFF format accepted by AEMO | 1-Apr-21 | 22-Jun-21 | 22-Jun-21 | AEMO
L1-22 | Settlements Platform Go-Live | 19-Apr-21 | [17-May-21] | [17-May-21] | AEMO
L2-S10 | Settlements Industry Test preparation completed by participants | 17-Feb-21 | [22-Mar-21] | [19-Apr-21] | Participants
L2-S11 | Settlements Industry Test preparation completed by AEMO | 17-Feb-21 | [22-Mar-21] | [19-Apr-21] | AEMO
L2-RE19 | Industry Go-Live Plan - Settlements finalised | 19-Mar-21 | [16-Apr-21] | [16-Apr-21] | AEMO
L2-RE32 | Settlements Industry Test Concludes | 14-Apr-21 | [13-May-21] | [13-May-21] | AEMO
Dates subject to change

## Slide 13: Actions to mitigate participant program impacts
Area | Mitigation | Participant Category | Implementation Status | Impact support
Bilateral Testing | Staging environment to support more extensive B2B and B2M bilateral testing | Retailer, DNSP, MDP | Under consideration, Updates being planned | Increased support of participant bilateral testing programs in advance of Retail pre-prod availability
5-minute Meter Data | Reduce period between retail platform go-live and acceptance of 5 minute granularity metering data | MDP | Under Consideration, Subject to participant input | Maximises transition window for the delivery of 5 minute metering data to AEMO prior to rule commencement
UFE | AEMO Support for bulk population of NCONUML | DNSP | Not currently Planned No TFG request as yet | Reduce impact of smaller transition window for the population of NCONUML NMIs, once approved
Industry Testing | Extend Industry Test period in advance of Retail Platform go-live | Retailer, DNSP, MDP | Only option 2 | Increase opportunity for participant process testing in upgraded environment prior to go-live

## Slide 14: Impacts to Participants
AEMO will endeavour to minimise impacts to participant programmes in meeting overall 5MS and GS rule commencements. We anticipate many of the impacts will entail replanning of activity in-line with available market capability. Key areas impacted may include:
At the TFG scheduled for 29-Jan, impact on the Metering Transition Plan Activities (1-3) undertaken – Feedback in Progress
ITWG will realign activity and participant availability for Invitation Industry Test – In Progress
AEMO will reissue Retail Industry Go-Live plan to support rescheduling of new cutover dates – 16 April under Option 1
Readiness Survey #6 includes specific questions to consolidate view of industry impacts
Participants are asked to identify other areas requiring industry consideration at upcoming RWG
  Timing of metering data delivery migration for interval meters to MDFF Format
  Adjusting the plans for the commencement of 5-minute metering data delivery to AEMO, and potentially retailers/ DNSPs
  Adjusting the timing for the population of NMI Standing data and NCONUML - for those activities with direct capability dependency on Retail Platform deployment
  Timing of participant implementation of capability delivered with Retail Platform, including B2M via API capability
  Rescheduling Industry Test involvement and resourcing
  Rescheduling planned cutover activity

## Slide 15: Summary of feedback received to date
NB this will be updated for presentation at the RWG.
General industry support for the AEMO to progress toward May 31 go-live with March checkpoint (as at 04-Feb)
No participant has identified a blocker with either date, but a number of participants have flagged the earlier date as preferred to provide additional time for participant testing and other readiness activities
Some Participants have requested that in the case where 31-May-21 become unfeasible, AEMO will consider going live as soon after the 31-May-21 as possible rather than reverting directly to Option 2 – 21-Jun-21
MTP impacts understood, participants assessing changes to their programs and transition timings
Clarity on checkpoint approach, criteria and timings to be provided to industry
Participant concerns on impact to delivery and timing to other regulatory reforms
Participant changes may be required to transition plans (timing and approach) to mitigate capacity concerns
Approaches and environment support for the conduct of bi-lateral testing being evaluated by participants to support their planned timelines
Note: Drafted prior to final feedback received.

## Slide 16: Next Steps
Executive Forum – 11-Feb-21
  AEMO to confirm Retail timeline including pre-prod and Settlements dates
  Summarise options feedback
  AEMO to confirm criteria that will be reported against at PCF in March
  PCF – 18-Mar-21
  AEMO will discuss the status of the checkpoint criteria
  Status will be provided in advance of the meeting

## Slide 17: Industry Testing Update
Tui Grant

## Slide 18: ITWG Update - Topics for Discussion with RWG
5MS Staging Environment
Outage on the 02 Feb – 03 Feb to allow for security protocols to be updated.
Outage scheduled 08 Feb -12 Feb to move MDM to the ‘end state’ platform
5 minute settlement run being completed for participants who want to test with a fresh example.
Participant use of Staging environment for Bi-Lateral testing
Invitation Industry Test
Rescheduling participation to address participant timing and resourcing.
Settlements Industry Test Approach
Aligning settlement runs with current and new MDM platforms

## Slide 19: 5MS Staging Environment – 29 January 2021
Forecasting, SD/CD
Issue ID​ | Description​ | Status​ | Action​
2805 | Screen display issue only - An extra TNI2 field is getting displayed under Address Information section in NMI Master, Point in Time NMI Master Summary and NMI Discovery Type 1 and Type 2 search page.​ | In Progress | It is a display issue only no functionality affected​ Release in staging planned for 2 Feb
2856 | Staging: Cleanackhandler sometimes sends incorrect X-initiatingParticipantID request header | In Progress | No impact to participants Release in staging planned for 20 Feb
2880 | Event Only Nack from Participant Results in a badack | In Progress | Acknoledge the firel from MSATS browser to remove the badack Release in staging planned for 2 Feb
3683 | Align systems and documentation on Market field within the B2M aseXML header | In progress | Does not affect all participants. This is an issue for participants who have considered <Market>NEM</Market? field as optional for .ack
New | Issue with generation of new settlement run in wholesale due to NEM reports being out of sync with SIT | Closed | Need to realign the data interchange NEM reports for settlements to reflect the most up to date reports.
3715 | B2B outbox batch handler is down in Staging | In Progress | Under investigation no B2B transactions are moving between participants
3716 | RM37 report request processing Failure | In Progress | This is the only report that we aware of that will not complete

## Slide 20: AEMO Pre-Prod 5MS Bidding Service Defects only – 29 -Jan-21
Issue ID​ | Description​ | Status​ | Action​
001 | Web bidding screens issue. If a user enters a band availability that is too high (higher than the maximum capacity of the unit), or a ramp down rate that is too high (higher than the registered maximum ramp rate), then the web screens will highlight an adjacent cell as the source of the error. | In Progress | AEMO to confirm timeline for fix, currently estimated for mid Feb-21
This table only refers to defects in the AEMO pre-production environment related to the 5MS Bidding Service.

## Slide 21: TFG/MTP Update
Blaine Miner

## Slide 22: TFG/MTP Update
TFG meeting held on Friday 29th Jan
  Agenda:
    Previous actions
    Delay to AEMO’s MDM & Settlement Solutions
    Proposed changes to the MTP
    Risk Review
    Rollout Plan Summary
    Upcoming MTP Activities
    Cross boundary metering arrangements
    GLOPOOL TFG requirements
    MTP CATS transaction volume management update
Next meeting Thursday 11th Feb
  Focus areas
    Industry feedback to AEMO delay options
      Potential transition implications
    CATS transaction volume estimate assumptions
      Inclusion into the MSDR Data Transition WG
    Requests from the RWG?

## Slide 23: Proposed Changes to the MTP
Category | Activity ID | Activity Description | Change Type | Change Detail
Meter Installation & Reconfiguration | A19a | Provide progress and amendments to ‘Known’ Cross Boundary forward plans to AEMO every 2mths | New activity | MC Rollout plans required for Cross Boundary meters (Known) meters
 | A31 | For any registered ‘Special Site’ (as defined in the ‘Special Sites and Technology Related conditions within the National Electricity Market Version 1.2) or any Logical NMI, update and distribute algorithms adjusted for introduction of 5 minute interval length to AEMO, FRMP and LNSP for approval. | Change to description | Addition of “…or any Logical NMI…”
Meter Data Delivery | A32a, A37a, A42a, A52b, A58b, A64b, A70b, A82a | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths | New activities | MDPs to provide conversion plans from 1 Mar 2021 every 2mths
 | A35, A41, A46, A50, A56, A62, A68, A74, A86, A92 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) | Change Transition Start Date | Transition Start Date changed from 1 Apr 2021 to 22 June 2021
 | A52a, A58a, A64a, A70a | Provide progress and amendments to forward plans to AEMO and industry every 2mths | Change in frequency | Proposing to change frequency to every 2mths, to align to other rollout plan requirements
 | A36, A40, A45, A51, A57, A63, A69, A75 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021
 | A94 | Meter data delivery of 30min interval reads only in MDFF to AEMO | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021
MSATS Standing Data Creation & Maintenance | A95, A96, A97 | Create Cross Boundary NMIs, including associated datastreams and registers | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021
 | A95a, A99a | Provide NMI Create plans for Cross Boundary and NCONUML to AEMO every 2mths | New activities | NMI Create plans to be provided from 1 Mar 2021

## Slide 24: Proposed Changes to the MTP
Category | Activity ID | Activity Description | Change Type | Change Detail
MSATS Standing Data Creation & Maintenance | A99, A100, A101 | Create NCONUML NMIs, including associated datastreams and registers | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021
 | A102, A104, A106, A108, A110, A112, A114 | Ensure capability to receive and process new NMI classification codes | Change Transition End Date | Transition End Date changed from 30 Apr 2021 to 31 May 2021
 | A103, A105, A107, A109, A111, A113, A115 | Update NMI Class Codes for existing NMIs as required | Change Transition Start Date | Transition Start Date changed from 1 May 2021 to 1 June 2021
 | A119 | Ensure all Sample meters have a Datastream type code of 'P' and are attached to a Profile | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021
 | A120 | Update Datastream type codes from 1-4 to 'I' or 'N' as required | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021

## Slide 25: Upcoming MTP Activities (Assumes Option 1 MDM Go-Live Dates)
Description | Date | Activity ID
MPs to provide progress and amendments to forward plans for Type 1-3, subset of 4 and ‘known’ cross boundary meters to AEMO | By 1 March 2021 | A3a, A8a, A13a, A19a
MDPs to provide progress and amendments to forward plans for Type 4, 4A, VICAMI and Sample meters to AEMO | By 1 March 2021 | A52a, A58a, A64a, A70a
MDPs to provide datastream conversion plans to convert Net datastreams to register level | By 1 March 2021 | A32a, A37a, A42a
LNSPs to provide NMI Create plans for Cross Boundary and NCONUMLs to AEMO | By 1 March 2021 | A95a, A99a
MPs to update the Meter Read Type code with RWDA or RWDD, as applicable | From 9 March 2021 | A36b, A40b, A45b, A51a, A57b, A63b, A69b, A75b
MCs to ensure that details of the Inventory Table, calculation methodologies and Agreed Loads are agreed prior to implementation by relevant Registered Participants | By 31 March 2021 | A87
MCs to provide visibility of the approach / timeframe for required meter replacement or reconfiguration for ‘Unknown’ Cross Boundary meters | By 31 March 2021 | A23
Participants to establish agreements to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO, as applicable | By 31 May 2021 | A32, A37, A42, A47, A53, A59, A65, A71, A84, A88
AEMO to establish agreements with MDPs to allow the delivery of 5min metering data pre 1 Oct 2021 for B2M purposes | By 31 May 2021 | A34, A39, A44, A49, A55, A61, A67, A73, A85, A91
MDPs to create/convert export and import Active (kWh) and Reactive (kVarh) energy datastreams, where applicable, in the CNDS table | From 31 May 2021 | A36, A40, AA45, A51, A57, AA63, A69, A75
MDPs to deliver tier 1 basic meter metering data (Actuals, Subs and Forward Estimates) to AEMO | By 30 June 2021 | A93

## Slide 26: Metering rollout plans – Industry response rate (Tranche 1 meters)
Organisation | Rollout plan provided at some stage? | Rollout plan update provided in latest round?
Mondo | Y | Y
Origin | Y | Y
PLUS ES | Y | Y
TransGrid | Y | N
Yurika | Y | N
Ausgrid | Y* | N
AusNet Services | Y* | N
ElectraNet | Y* | N
Intellihub | Y* | N
Powerlink | Y* | N
Metropolis | N | N
Powermetric | N | N
TasNetworks | N | N
Out of the 13 top MCs with Tranche 1 meters, 10 MCs representing approximately 90% of Tranche 1 meters have provided their metering rollout plans, five of which are in the template format. Only three MCs have provided updates on their rollout plan in the latest update.

## Slide 27: Metering rollout plans – Industry response rate (Tranche 2 meters)
Out of the 14 MDPs with Tranche 2 meters, 10 have provided their Tranche 2 metering rollout plan, nine of which are in the template format. Only seven MDPs have provided updates on their rollout plan in the latest update.
Organisation | Rollout plan provided at some stage? | Rollout plan update provided in latest round?
CitiPower Powercor | Y | Y
Jemena | Y | Y
Mondo | Y | Y
PLUS ES | Y | Y
Secure Meters | Y | Y
United Energy | Y | Y
Vector | Y | Y
Intellihub | Y | N
Yurika | Y | N
Ausnet Services | Y* | N
ActewAGL Distribution | N | N
Essential Energy | N | N
Metropolis Metering Services | N | N
Powermetric | N | N

## Slide 28: Metering rollout plan provision schedule
Update # | Provide rollout plans by
3 | 01-Mar-21
4 | 01-May-21
5 | 01-Jul-21
6 | 01-Sep-21
7 | 01-Nov-21
8 | 01-Jan-22
9 | 01-Mar-22
10 | 01-May-22
11 | 01-Jul-22
12 | 01-Sep-22
13 | 01-Nov-22
Please provide metering rollout plan updates according to the below schedule. Please include relevant participant IDs when submitting rollout plans.
This schedule applies for all metering rollout plans:
  MCs to provide MP installation and reconfiguration plans for Type 1-3, subset of type 4 meters, type 7 and known cross boundary
  MDP 5-min data delivery for new and repl. 4/4A, VIC AMI, SAMPLE meters
  MDP conversion plans for Type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level
  LNSP NCONUML and cross boundary NMI creation plans

## Slide 29: Industry Risks and Issues Register
Anne-Marie McCague

## Slide 30: Purpose of the session
A full Readiness and Systems risk review was undertaken at RWG in January 2021
This session focuses on:
  news risks that are related to Readiness or Systems that have been raised as a result of the Retail go-live delay
  those existing Readiness / Systems that are impacted by the Retail go-live delay

## Slide 31: New Risks (1/2)
Risk ID | Description | Inherent Rating | Residual Rating | Comments
R34 (NEW) | Delay to AEMO 5MS Retail impacts participants readiness There is a risk that the delayed availability of the 5MS Retail solution impacts participants readiness programs resulting in delays in some participants programs. | Critical | TBD | Inherent Likelihood: Possible Inherent Consequence: Major Residual Likelihood: to be determined after feedback received Residual Consequence: to be determined after feedback received Actions: Mitigation measures to be identified should there be an impact Risk rating to be reviewed post Readiness Round 6 results and timeline decision Enhanced bilateral testing in 5MS Staging Environment being investigated
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 32: New Risks (2/2)
Risk ID | Description | Inherent Rating | Residual Rating | Comments
R35 (NEW) | Compression of window for transition 5-min metering data delivery There is a risk that the compression of the Metering Transition Plan results in the transition of NMIs to 5-min granularity at an unsustainable rate | Significant | Medium | Inherent Likelihood: Possible Inherent Consequence: Major Actions: Update Metering Transition Plan to reflect capability availability dates Support delivery of 5-minute metering data from Retail platform deployment maximise transition window – under consideration Align Participant readiness reporting to updated MTP dates Industry to prioritise activation of 5MS essential meters when planning rollouts Monitor participant impacts and programs via readiness reporting and RWG interaction Residual Likelihood: Unlikely Residual Consequence: Major
R36 (NEW) | Compressed MTP transition windows for the population of NCONUML NMIs impacts the accuracy of UFE Reporting Risk that a subset of the MTP standing data and NCONUML population activities are dependent on capability made available by the deployment of the Retail Platform, will not be completed prior to the UFE soft start on 1/10/21 resulting in less available data to calculate UFE accurately | Medium | Medium | Inherent Likelihood: Possible Inherent Consequence: Moderate Actions: Update Metering Transition Plan to reflect impacted activity transition windows for participants Assessment of accuracy impacts for UFE based on participant readiness reporting against revised timeframes Residual Likelihood: Unlikely Residual Consequence: Moderate
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 33: Impact to Existing Risks
Risk ID | Description | Residual Rating (Proposed) | Comments
R11 | The AEMO business and operations are not ready for 5MS Rule Commencement on 1 Oct 21 The AEMO business may not be ready to deliver the full extent of the 5MS deliverables by 5MS and GS rule commencement including business processes and resource training, results in failure of Go Live for 5MS and GS Program | Medium | While the changes in Retail and Settlements date do impact AEMO’s 5MS Program, the focus of this risk is on the AEMO business readiness. The impact of the changes in dates for retail and settlements to AEMO’s business and operational readiness to support 5-min expected to be minor. Actions: Proposing that trend should be changed to Worsened until results of Readiness Round 6 have been reviewed
R28 | AEMO Systems Deployment Cutover Risk The current approach to the AEMO systems deployments elements of the cutover has the Retail stream (the most complex and riskiest) going first on 9 March, then both the Dispatch and Settlements systems deployments together 3 weeks later on 1 April. There is a risk that the Retail deployment could lead to push back on the following deliveries from the 5MS program, the AEMO business and/or market participants. | Medium | This specific risk was mitigated through moving the Settlements date to 19-Apr-21 The change to the Retail Go-Live requires reconsideration of the Settlements Go-Live date Trend is improving since the Settlement dependencies on Retail have been removed. Actions: Remove the dependencies between the go-live of Retail and Settlements solutions, enabling Settlements solution to go-live before retail solution. Conduct additional Settlements testing to facilitate this Bidding system deployment is still separate from both Settlements and Retail system.
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 34
Any other risks or issues to be raised?

## Slide 35: Procedure update
Simon Tu

## Slide 36: 5MS/GS-related procedure change log
Procedure issue | Status | Final Determination Date
Consolidation of Retail Electricity Procedures | Consultation to commence Feb-2021 The consolidation of Procedures will not be a full consultation as the Procedures (BAU and 5MS/GS) have already gone through their respective formal consultations. | Jun-2021
Update to published settlement formulas* | 5MS/GS & Customer Switching B2M Consultation commenced 12-Jan-2021 | 17-May-2021
Cross Boundary (CB) connections, inclusion of cross boundary energy formulas and a Change Request type for CB updates update * | 5MS/GS & Customer Switching B2M Consultation commenced 12-Jan-2021 | 17-May-2021
MDFF Specification NEM12 & NEM13 update to clarify MDP obligation where a NULL exists in their systems | 5MS/GS & Customer Switching B2M Consultation commenced 12-Jan-2021 Related to Endeavour Energy’s feedback of the Aug-2020 Metering ICF Package update of the MDFF Specification to remove the ‘N’ quality flag. | 17-May-2021
Clarification on existing requirements for the 5-minute load profile and RM reports | Consultation commenced 12-Oct-2021. Part of the Retail Procedures (Wholesale Demand Response) consultation. | Mar-2021
Updated from last RWG
*raised by the 5MS Program
# aseXML schema impact

## Slide 37: 5MS/GS-related procedure change log – no change
Updated from last RWG
*raised by the 5MS Program
# aseXML schema impact
Procedure issue | AEMO Retail Systems Impact | Available in Staging | Readiness Considerations
Consolidation of Retail Electricity Procedures | No impact to 5MS Retail systems. | N/A | N/A
Update to published settlement formulas* | No impact to 5MS Retail systems. | N/A | N/A
Cross Boundary (CB) connections, inclusion of cross boundary energy formulas* | No impact to 5MS Retail systems. | N/A | N/A
MDFF Specification NEM12 & NEM13 update to clarify MDP obligation where a NULL exists in their systems | No impact to 5MS Retail systems. | N/A | N/A
Clarification on existing requirements for the 5 minute load profile and RM reports | 5MLP included in RM20 and RM25 reports | R27 - 31-Oct-20 - Existing Settlements Reports @5-min: RM16, RM17, RM20, RM21, RM22, RM26 | N/A
Proposed procedural change to MDFF quality flag (N flag)* | Rejection of B2M MTRD MDFF meter reads where quality flag is ‘N’. Results in B2M MTRD Transactions with the status of ‘Partial’ or ‘Rejected’. | R1 - 1-Dec-19 - Support for new B2M MTRD validations. | Participant Mkt Systems must not send ‘N’ for B2B or B2M MTRDs.
Removal of end user details from inventory table | No impact to 5MS Retail systems. | N/A | N/A
Removal of register ID = suffix requirement | No impact to 5MS Retail systems. | N/A | Material participant readiness activity impact as the existing requirement is to be retained.
Notes: Removed:
10MB file size

## Slide 38: 5MS/GS-related procedure change log – no change
*raised by the 5MS Program
# aseXML schema impact
Procedure issue | AEMO Retail Systems Impact | Available in Staging | Readiness Considerations
Proposal for RWD | No impact to 5MS Retail systems. | N/A | ReadTypeCode amended from ‘Optional’ to ‘Required’. Fourth character added to identify whether a meter is capable of reading at five-minute granularity. 4th char field is already avail for data updates in PROD
TNI 2 for cross-boundary meters *# | CATS CR support for TNI2 field. MSATS Browser to support display TNI2 for NMI Discovery Transactions. aseXML schema support extension to support TNI2 inclusion (r39). | R18 and R19 - 31-Aug-20 - Support for TNI2 for CATS CRs. | TNI Code assigned, by AEMO, however Participants to undertake the generation of associated CR2xxx transactions, to register a cross boundary meter using TNI 2. Migration to r39 aseXML necessitated.
New NCONUML NMI Class codes available in list for SORD #​ | Likely B2B schema change. AEMO confirms that the Electricity B2B changes for v3.5 will be made available in pre-production in September or early October 2021. The changes will be in pre-production for a minimum of 4 weeks. 5MS will have to merge the changes from Electricity B2B for the GS May 2022 release. | TBD | 10-Nov-2021 effective date decided as part of the regulator implementation roadmap.
Notes: Removed:
10MB file size

## Slide 39: Dispatch / Bidding Update
Ian Devaney

## Slide 40: Bidding / Dispatch Staging, Pre-production & Production timelines
STAGING
PRE-PRODUCTION
PRODUCTION
01 Oct 2021
05 Jul 2021
29 Nov 2020
01 Apr 2021
01 Oct 2021
LEGACY | BIDDING TRANSITION | 5MS RULE
30-minute bidding only via: FTP (txt) Web Bidding (Legacy) | 30-minute bidding via: FTP (txt) Web Bidding (Legacy) 5-minute bidding* via: FTP (JSON) Web Bidding (5MS) API *Each 5-minute bid within each half hour must be identical, giving the same effect as the submission of a 30-minute bid. | 5-minute bidding* only via: FTP (JSON) Web Bidding API *30-minute bid emulation restriction lifted
LEGEND
For business continuity reasons, 30-mins offers and bids will be accepted until 01 Oct 21

## Slide 41: Systems Workstream – Dispatch & Operations
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
DISPATCH and OPERATIONS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Bidding FTP and API |  |  |  |  |  |  |  |  |  | 
Transition | Aug-18 | Oct-18 | Aug-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Bidding Data Model | Aug-18 | - | Sep-18 | Mar-19 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Bidding Format | Aug-18 | - | Sep-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 2 - Bidding Web UI |  |  |  |  |  |  |  |  |  | 
Bidding Web UI and APIs | Aug-18 | Nov-18 | Dec-18 | Jan-19 | Mar-19 | 31-Jul-19 | 16-Dec-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 3 - Dispatch, Pre-dispatch and PASA |  |  |  |  |  |  |  |  |  | 
Dispatch | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Predispatch P30/7DAY | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Pre-dispatch P5 (FSIP and 5MPD Price Sens.) | Nov-18 | Oct-18 | Nov-18 | Jan-20 | May-20 | 10-Nov-20 | - | - | TBC | 01-Apr-21
ST and PD PASA | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 4 - Pricing and Miscellaneous |  |  |  |  |  |  |  |  |  | 
Trading Price / Price Revision | Aug-18 | - | Feb-19 | Nov-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 05-Jul-21 | 01-Oct-21
Administered Pricing and CPT | Aug-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 05-Jul-21 | 01-Oct-21
Suspension Pricing | Sep-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 05-Jul-21 | 01-Oct-21
Negative Residue Management | Sep-18 | - | Feb-19 | Dec-18 | Jun-19 | 31-Jul-19 | - | 15-May-20 | - | -
RERT | Oct-18 | - | - | - | - | - | - | - | - | -
PACKAGE 5 - Full Data Model |  |  |  |  |  |  |  |  |  | 
Full Data Model | Sep-18 | Ongoing | Ongoing | Apr-19 | Ongoing | 31-Jan-20 | 16-Mar-20 | 29-Nov-19 | 30-Nov-20 | Apr-21
Current as at 20-11-2020

## Slide 42: Pre-Production Status Updates Performance Testing
Performance testing of the new 5-Minute bidding service commenced this month. Industry has been sent an advisory relating to these activities.
No impact to industry testing is expect or has been observed during our first round of testing.

## Slide 43: Remediation work on the Bidding Service
Error message change when an Energy bid is submitted with exceeding MFP.
  Currently states – “Band prices must be greater than or equal to market floor price"
  This has now been changed to – “Band prices must be greater than or equal to market floor price XXX“
Error message change when a bid is submitted with rampdown rate exceeding registered values
  Was titled: "Invalid Rampuprate", this has now changed to “Invalid Rampdownrate”
Get Bid API
  When Fast start profile and rebid explanation did not have a value it used to give the response for get bid with a null tag.”{}”
  This tag has been removed and fast start profile and rebid explanation is only populated in the response for a “get bid” when there is a value for Fast start profile.
Get Bids API
  The trading date in the “get bids” response has changed from YYYY-MM-DD 00:00:00 to YYYY-MM-DD.
  The null tag for rebid explanation {} has now been removed from the response.

## Slide 44: Remediation work on the Web Bidding Screens
Enabled for MNSP to up-load a JSON file.
“Upload bid File” functionality is used in web bidding there were no information about where errors located in the submitted JSON files. These errors will be visible to the user in the web screen upon the new release.
In the current version the error indicators do not point to the right place regarding the specific error, this has been remediated.
  Example if Rampdown indicator has an invalid value when submitted, there will correct highlight against that field, currently this was not the case.
User are able to enter negative and real numbers for “Daily Energy Constraint”, “Fast Start Min Load”, T1, T2, T3 and T4 fields. This has been remediated by restricting the user by implementing checking processes on for the screens ensuring users are unable to enter negative and real numbers for these fields.
Improvements have been made on the tab functionality, it was observed that on occasions the tab key would to not function.
Participant can pre-fill DUID and Service Type on the first screen. This pre-fill information is then preserved when “Enter Bid” is clicked. However, on the “Enter Bid” screen, if the participant changes the “Trading Date”, then, the pre-filled DUID would not be retained, this will be remediated, upon next release.

## Slide 45: 5MS Bidding Service Go-live Plan
Milestone | Date
Initial engagement with the RWG | 12 January 2021
Publish draft for industry feedback | 8 February 2021
Deadline for industry feedback | 22 February 2021
Publish final plan | 8 March 2021
The draft 5MS Bidding service go-live plan was published on Monday 8 February 2021. Please respond by COB Friday 22 February 2021 with any comments.
The final document will be issued on Monday 8 March 2021

## Slide 46: Settlements Update
Mark Hillaby

## Slide 47: Settlements Workstream Update
Settlements timeline under review as a result in the delay of the Retail Go-Live
Update to be provided during RWG

## Slide 48: Readiness Survey
Austin Tan

## Slide 49: Readiness survey – new questions
At the last RWG, AEMO was asked to consider if there was any new questions that should be added to the readiness survey.
New questions were added relating to:
  Bilateral testing for retail and wholesale processes
  Generators participation in the bidding transition period, and use of the pre-production environment for industry testing

## Slide 50: Readiness reporting – 2021 schedule
The sixth readiness survey was released on Tuesday 2 February. Please respond by this Thursday 11 February. Survey results will be presented at the next RWG on 2 March.
Readiness reporting | Survey released | Survey responses due | Distribute results | Discuss at RWG meeting | Discuss at PCF | Discuss at EF
Round #6 | 02-Feb-21 | 11-Feb-21 | 25-Feb-21 | 02-Mar-21 | 18-Feb-21 | 25-Mar-21
Round #7 | 06-Apr-21 | 15-Apr-21 | 29-Apr-21 | 04-May-21 | 20-May-21 | 24-Jun-21
Round #8 | 02-Jun-21 | 11-Jun-21 | 25-Jun-21 | 06-Jul-21 | 17-Jun-21 | 24-Jun-21
Round #9 | 04-Aug-21 | 13-Aug-21 | 27-Aug-21 | 07-Sep-21 | 19-Aug-21 | 02-Sep-21

## Slide 51: Forward Plan and Other Business
Greg Minney

## Slide 52: RWG 2021 Proposed Topics
Month | Topics | Month | Topics
January | Preparing for Retail Invitation Industry Test Platform Go Lives criteria Market Commencement criteria Risk Review | June | Preparing for Market Trial Metering rollout progress Risk review – any Market Trial risks? Approach to Global Settlements engagement
February | Update on Retail systems go-live changes Metering Transition Preparation | July | Market Trial progress, Readiness Reporting #8 Market Commencement Criteria
March | Preparing for 5MS Bidding Cutover Settlements Industry Test (Subject to replanning) Readiness Reporting #6 | August | Market Trial progress Go-Live risks
April | Debrief on Bidding go-live Debrief on Settlements go-live Preparing for Settlements Cutover – new date TBC Metering provider implementation planning Risk review | September | Results of Market Trial, Preparing for 1 Oct – Ind Go-Live Plan review Readiness Reporting #9
May | Readiness Reporting #7 Approach to Global Settlements engagement 5MS Market Trial approach Industry Go-Live plan approach | October | Debrief and reconfirmation of approach for Global Settlements
To be revised once date changes are confirmed

## Slide 53: ITWG 2021 Proposed Topics
Month | Topics | Month | Topics
January | Retail invitation test plan Status of Dispatch and Bidding in Pre Prod | June | Final review of tests for market trials Review of production across all 5MS systems
February | Retail invitation test plan and participant involvement | July | Results of Market Trials
March | Settlement Platform industry testing Scope for the market trials Status of Retail in Production | August | Results of Market Trials
April | Test scenario review in preparation for market trials Status of Dispatch and Bidding in Production | September | General update on upcoming market start
May | Review pairing and finalise market trials Status of Settlements in Production |  | 
To be revised once date changes are confirmed

## Slide 54: Upcoming meetings
Current as at 02/02/2021
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement

## Slide 55: Questions