## Slide 1: 5MS & GS Readiness Working Group #21 (incl. Systems Working Group)
Tuesday 2 March 2021
WebEx only: **Please disconnect from your workplace VPN for the WebEx call**
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol.
Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol.
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require.
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
Greg Minney

## Slide 4: Agenda **Please disconnect from your workplace VPN for the WebEx call**
# | Time | AGENDA ITEM | Responsible
1 | 10:00 – 10:05 | Welcome, introduction and apologies | Greg Minney
2 | 10:05 – 10:10 | Agenda | Greg Minney
3 | 10:10-10:15 | Minutes/Actions | Anne-Marie McCague
General Update |  |  | 
4 | 10:15 – 10:30 | 5MS Program Update | Greg Minney
5 | 10:30 – 10:50 | Readiness Report Round #6 | Austin Tan
6 | 10:50 – 11:00 | Industry Testing Update – settlements industry testing, invitation testing, Staging | Tui Grant
7 | 11:00 – 11:10 | TFG/ MTP Update | Blaine Miner
8 | 11:10 – 11:15 | Procedure update | Simon Tu
Retail/ Metering Readiness |  |  | 
9 | 11:15 – 11:20 | Retail / Metering Update | Jim Agelopoulos
Dispatch / Bidding Readiness |  |  | 
8 | 11:20 – 11:35 | Dispatch / Bidding Update | Ian Devaney
Settlements Readiness |  |  | 
9 | 11:35 – 11:45 | Settlements Update | Mark Hillaby
Meeting Closing Items |  |  | 
10 | 11:45 – 11:50 | Forward Plan and Other Business | Greg Minney
11 | 11:50 | Meeting Close | Greg Minney

## Slide 5: Minutes & Actions
Anne-Marie McCague

## Slide 6: RWG Actions
No. | Status | Action | Comment
20.3.1 | Closed | AEMO to provide update to RWG on Regulatory roadmap changes | Regulatory Implementation Roadmap Forum took place on 24-Feb. 5MS will circulate slides to working groups for information.

## Slide 7: RWG Actions – Schema change schedule
aseXML schema | Release Date | Market (ASWG CR#) | Content
r39 | Replaced | 5MS & GS and Customer Switching projects B2M Enhancements (CR64 & CR65) | 5MS - Additional of new RM Reports 5MS - Update of existing ‘Last Sequence Number’ elements to optional 5MS - Addition of new x of y message block 5MS - Addition of new Second TNI number for Cross boundary NMIs CS - Addition of Previous Read Dates to NMI Standing Data Response
r39_p1 | 1 May 2021 | 5MS & GS and Customer Switching projects (CR69) | Correction of defect identified in r39 during testing
r40 | 29 Nov 2021 | Gas FRC (CR67 & CR68) | Job Enquiry Code enumerations Meter status enumerations
r41 | 10 Nov 2021 | B2B Enhancements (CR70) (B2B 3.5 Consultation) | Removal of Meter Exchange Notification Updates to Planned Interruption Notification New fields (7) added to Service Orders New Customer Type Value
rXX | 1 May 2022 | MSDR - MSATS Standing Data Review | Updates to Standing Data 23 new Fields 27 updated fields
rXX | 1 Nov 2022 | MSDR - MSATS Standing Data Review | Update to Standing Data 28 removed fields

## Slide 8: Program Update
Greg Minney

## Slide 9: 5MS Program Timeline A Level 1 and External Level 2 Milestones 1/2
Current as at 12-02-2021
On track
Dispatch SIT and UAT – Complete
Performance testing is in progress
Settlements SIT & UAT in progress. Performance testing to commence late Feb
Retail SIT & UAT in progress. Performance testing to recommence early March
Milestones in blue changed due to Retail replan

## Slide 10: 5MS Program Timeline Level 1 and External Level 2 Milestones 2/2
Current as at 12-02-2021
No changes

## Slide 11: List of L1 and L2 Milestones impacted by change
ID | Milestone | Previous Date | Baselined Dates | Owner
L1-19 | AEMO (Retail) Metering Solution - Go-Live | 9-Mar-21 | 31-May-21* | AEMO
L2-RE35 | Industry Go-Live Plan final - Release 3 - Retail MDM | 25-Jan-21 | 16-Apr-21 | AEMO
L2-M11 | Industry Test Preparation completed by Participants for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | Participants
L2-M12 | Industry Test Preparation completed by AEMO for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | AEMO
L2-RE29 | Retail MDM (incl. B2M) Invitation Industry Test Commences | 1-Feb-21 | 19-Apr-21 | AEMO
L2-RE30 | Retail MDM (incl. B2M) Invitation Industry Test Concludes | 3-Mar-21 | 21-May-21 | AEMO
L2-M24 | Retail MDM (incl. B2M) Go-Live | 9-Mar-21 | 31-May-21 | AEMO
L2-M10 | 5 minute files in MDFF format accepted by AEMO | 1-Apr-21 | 22-Jun-21 | AEMO
L1-22 | Settlements Platform Go-Live | 19-Apr-21 | 17-May-21 | AEMO
L2-S10 | Settlements Industry Test preparation completed by participants | 17-Feb-21 | 22-Mar-21 | Participants
L2-S11 | Settlements Industry Test preparation completed by AEMO | 17-Feb-21 | 22-Mar-21 | AEMO
L2-RE19 | Industry Go-Live Plan - Settlements finalised | 19-Mar-21 | 16-Apr-21 | AEMO
L2-RE32 | Settlements Industry Test Concludes | 14-Apr-21 | 13-May-21 | AEMO
* Confirmation of date is dependent upon status at the March Checkpoint

## Slide 12: Approach to Retail Status Updates
18-Feb PCF
Forward Planning for Retail
Update on Interim Checkpoint Criteria Status
Week beginning 5-Apr
18-Mar PCF
March Checkpoint Criteria – assessment and outcomes
Pre-prod – status and go/no-go date
Production go-live – checkpoint date and criteria, go/no-go date
Pre-Prod Go/No-Go email
19-Apr
Retail Industry Testing Commences
12-May [TBC]
Retail Go/No-Go Communicated to PCF via email
23-Apr PCF
April Checkpoint Criteria - assessment and outcomes
Go/No-Go – confirm date
19-May PCF
Confirming Go/No-Go
Issue management
Replanning (if necessary)
31-May
5MS Retail / Metering Solution Go-Live
Key milestones
Communication timeline

## Slide 13: Approach to Checkpoint Criteria
Assessment Approach
Criteria represent activities that are due for completion by the end of February
Objective is for criteria to be fully met
  Reflects on-time completion of scheduled activities
If one (or more) criteria not fully achieved, then implications and remedies are assessed before broader conclusions are made
5MS Program objective is to maintain 31-May go-live and will work to find remedies if not all criteria are met
31-May target go-live will be deferred if criteria are not met and remedies are judged as insufficient
Criteria for April checkpoint will adopt a similar approach

## Slide 14: Checkpoint Criteria – Interim Status
Criteria | Interim Status
Enterprise Azure migration successfully completed | Migration completed in all five environments. Testing and defect fixing has recommenced. Staging is now available for participants. Some teething issues but B2B is working for participant testing. Verbal update to be provided in meeting.
Build for critical defects completed | In progress and currently on track.
Target execution of test cases achieved, with no critical defects that cannot be remedied for 31 May go-live | In progress but behind schedule, slowed by 2 x technical issues (one now resolved and one with a workaround being built). Will be a key item for assessment at the March checkpoint. Test metrics (dashboard) to be made available to PCF
Successful completion of Dress Rehearsal (DR2B) | Scheduled for the end of February. No current issues impeding on-time commencement before March.
Pre-Production environment established | In progress and on track for completion by end of February.
Performance remediation for RM11 & RM16 completed, no new performance blockers | Remediation of RM11 & RM16 satisfactory for go-live completed, planning underway for “day in the life” performance test mid-March.

## Slide 15: Readiness Report Round #6
Austin Tan

## Slide 16: Summary of coverage, status and progress
Minor drop in response, with 45 respondents representing 87-100% of the industry. Response rate across all participant types provides representative industry coverage.
Half of participants have now commenced the testing phase of their program, increasing from 30% to 56% between rounds. All except three respondents noted that they are on track, 1 reporting "late" and 2 "at risk".
The AEMO Bidding Platform was deployed for industry test on schedule. The AEMO Retail Platform deployment was rescheduled to May 2021, and the AEMO Settlement platform go-live was rescheduled to May 2021. A heightened risk profile is reflected as a result of these changes.
Compared to the previous round of reporting, one participant was experiencing major changes in their ability to implement 5MS and GS due to COVID-19. Two other participants reported minor changes. The remaining participants reported no change. No impact was noted against overall program progression.
Chart: 
No change | 42
Minor change | 2
Major change | 1

## Slide 17: Critical Capability leading Indicators
Generation - One generator reported a 'late' status for their readiness to submit 5-min offers, noting that they expect to be on track by March 2021.
Essential meters – One MP/MC reported a late status for MTP activities relating to essential meters, however it was noted that there is a plan to deliver by the target dates. All other MPs, MDPs and MCs are reporting on track. 1 MDP has reported completion of meter installation activities for Tranche 1 meters
The AEMO retail platform and settlements platform go-live dates were rescheduled. These changes are not expected to impact 5MS commencement or 5MS Market Trial, but a heightened risk profile is noted.
5MS GS Essential Industry Capabilities |  |  |  |  |  |  |  |  | 
Essential capability |  | Relevant participants | Reporting criteria met | Number of participants |  |  |  |  | 
 |  |  |  | On Track | At Risk | Late | Not responded | Remediation Plan? | Escalation Required?
Generators and MNSPs are able to submit 5-min offers |  | Generators / MNSPs | Yes | 16 | 0 | 1 | 3 | No | No
All essential meters* are able to produce and store 5-min data |  | MPs | No | 8 | 0 | 1 | 1 | No | Yes
All essential meters* are able to produce and store 5-min data |  | MCs | No | 11 | 0 | 1 | 1 | No | Yes
All essential meters* are able to deliver 5-min metering data |  | MDPs | Yes | 3 | 0 | 0 | 0 | No | No
The 5-minute bidding and dispatch solution is deployed, including the web bidding interface |  | AEMO | Yes | 1 | 0 | 0 | 0 | No | No
The Metering Data Management (MDM) solution is deployed |  | AEMO | No | 0 | 1 | 0 | 0 | No | No
The 5-minute settlements solution is deployed |  | AEMO | Yes | 1 | 0 | 0 | 0 | No | No

## Slide 18: 5MS Rule Commencement – Round 6- Draft
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
Activity | Status | Comments
AEMO Business Readiness for 5MS and GS (Part A) |  | Bidding platform operating successfully in Industry test, on schedule for 1 April Go-live. Retail Platform go-live rescheduled to 31 May, Settlements platform rescheduled to 17 May. Rescheduling of platform deliveries is not expected to impact 5MS Rule commencement or 5MS market trials.
Essential Industry Capabilities for 5MS commencement (Part A) |  | On track for 1 Oct 21 commencement Metering Data Providers and MPs reporting on track with minor exceptions. Generators reporting on-track delivery.
Summary: 5MS Rule Commencement |  | Overall Industry and AEMO components of essential capability currently on track for 5MS Rule commencement.
Other industry capabilities for 5MS and GS (Part B) |  | Other Participant readiness activities proceeding in line with 5MS rule commencement. Individual participant readiness risks noted in regards Global Settlement population activities. No systemic issues noted
On track
On track
On track
On track
Risk 1
Risk 2
Risk 1
*** As At 22 Feb 2021

## Slide 19: Part A 5MS Essential Capability - Draft
Responsible Participant | Essential Criteria | Status | Comments
Generator | Generators and MNSPs are able to submit 5-min offers |  | 16/17 Generators representing 95% of NEM volume reporting on-track. 15/17 intend to participate in Market Trials. Average program completion in range 50-74%. 12/17 intend to commence 5 minute bidding within transition period.
MP, MC | All essential meters* are able to produce and store 5-min data |  | 9/10 MPs reporting on track, 1 MP reporting “late” with identified remediation Rollout plans for all critical meters due 1 March 1 MP has reported completion of meter installation activities
MDP | All essential meters* are able to deliver 5-min metering data |  | 3/3 MDPs for Essential meters are reporting programs on track. Rollout plans to be used to validate responses
AEMO | The 5-minute bidding and dispatch solution, including the web bidding interface is deployed |  | AEMO platform deployed for Industry test, on track for 1 April production deployment.
 | The Metering Data Management (MDM) solution is deployed |  | Mitigation Action: Retail Platform Deployment rescheduled to 31 May, criteria rated Amber to reflect the increase in delivery risk
 | The 5-minute settlements solution is deployed |  | Mitigation Action: AEMO Settlement Platform deployment rescheduled to 17th May. Industry test period extended to reflect changed order of platform deployment. Certification testing of platform completed
Summary - Essential Criteria | - | - | All components on track for delivery at 5MS rule commencement, AEMO Metering and Settlement rating reflects shift in planned go-lives and subsequent compression of transitional activity
On track
On track
On track
On track
Risk 1
Risk 1
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
On track
Risk 1
Risk 2
*** As At 22 Feb 2021
On track

## Slide 20: Part B – Other Industry Capabilities - Draft
Responsible Participant | Criteria | Status | Comments
Retailer | Receive and process 5-minute metering data. Receive and process 5-minute settlement data. |  | All responding retailers (18, representing 95% of retail load) reporting ‘On track’. 17/18 retailers plan to participate in Market trials. 6/18 intend to perform in Bi-Lateral Testing. 18/18 ‘On-track’ for 5 min settlement data, with 2 late for UFE Allocation
DNSP | Receive and process 5-minute metering data. |  | 10/10 DNSPs reporting ‘On track’ to receive 5-minute data and planning on participating in market trials.
 | Provide GS metering and standing data updates (incl. NCONUML). |  | 10/10 DNSPs reporting ‘On track’ with average program completion of 50-74% GS Standing Data updates reported as ‘On track’ (including NCONUML). Type 7 Metering Data “On Track” 1 Participant reporting ‘At-risk’ for the delivery of NCONUML,
TNSP | Receive and process 5-minute metering data |  | 6/6 TNSPs reporting ‘On track' to receive 5-minute data 2/6 have the intention to receive 5-minute data prior to the Rule commencement date
 | Provide GS metering and standing data updates |  | 6/6 reporting ‘On track’.
MDP | Provide 5-minute metering data T1-3 distribution connected meters, type 7 meters. |  | 16/17 MDPs reporting ‘On track’, representing 100% coverage of Tranche 1 NMIS 1 participant ‘At risk’, recovery plan is in place 17/17 MDPs report ‘On track’ for the delivery of interval metering data by 1 October, including 1 MDP flagging “A risk” for delivery of T1-3 customer meters
 | Provide type 4, 4A, Vic Ami metering data at 5-minute granularity by 1 December 2022 |  | Majority of Roll-out scheduled to commence 3rd quarter of 2021. Rollout plans requested from impacted participants by 1 March 2021 100% of MDPs reporting ‘On track’ for interval meter delivery by Rule commencement.
 | Provide basic metering data for tier 1 NMIs to AEMO. |  | 3 MDPs reporting ‘Completed’, 6 MDPs reporting “On Track” 1 MDP reporting ‘Late’, with plan to commence delivery prior to 1 Oct
MP, MC | All T1-3,4* meters are able to produce and store 5-minute data. |  | 18 /19 MPs representing tranche 1 meters reporting ‘On track’, 1 reporting ‘Late’ with a stated remediation plan Meter Installation confirmation of roll-out plans will be sought.
Summary | - | - | Overall summary “on track” , no systemic issues identified, individual exceptions noted
*** As At
22 Feb 2021
On track
On track
On track
On track
On track
On track

## Slide 21: Participant Readiness Risks for Review
 | Improving No Change / Stable Worsened
ID | Title | Residual Rating | Trend | Comments
01 | Retail platform go-live deferral Two participants noted that their program will be at risk if Option 1 of AEMO's retail platform deferral is not realised, and also highlighted that the reduced timeline between platform go-live and 5MS Market Trials allows for less time to resolve any issues. | TBC |  | AEMO is working towards Option 1 of the retail platform go-live, and will provide an update to the PCF in March regarding progress and status. RWG to consider impacts to programs and mitigation approaches in event option 1 is not achieved.
02 | Quantum of UFE One participant noted that there is an increased risk that the of quantum of UFE is not being fully understood due to the retail platform go-live delay. | TBC |  | RWG has previously noted impacts where population of GS data will result in initial inconsistencies in UFE reported Currently, with minor exceptions, GS soft Start activities are reported as being “on-track”. RWG to consider level of impact analysis where readiness reporting highlights significant lags in data population

## Slide 22: Participant Readiness Risks for Review
ID | Title | Residual Rating | Trend | Comments
03 | Congestion in market / participant systems One participant noted that there is a risk that many participants will leave the initiation of many transition activities to the last possible moment leading to congestion in market / participant system. | TBC |  | AEMO metering rollout plans indicate that majority of participants will be conducting transition activities up to rule commencement. RWG to assess likelihood and impact of risk
04 | Sharing of Metering Rollout Plans One participant raised a risk of not having a single source of truth for Metering Rollout Plans, and requested that AEMO share rollout plans from consenting participants. | TBC |  | Participants were asked to provide latest rollout plans by 1 March, and inform AEMO if plans can be distributed to other participants. Discussion at TFG 13 on 11 March
 | Improving No Change / Stable Worsened

## Slide 23: Participant Readiness Risks for Review
ID | Title | Residual Rating | Trend | Comments
05 | Meter Read Type Code Update One participant noted that there is confusion among the industry regarding the methodology and timeline of updating Meter Read Type Codes | TBC |  | RTC Draft Transition Approach to be discussed at this RWG and at TFG 13
 | Improving No Change / Stable Worsened

## Slide 24: Readiness Reporting Actions and Follow ups – Summary
A total of 18 actions were captured, with AEMO to follow up with 14 organisations
The full list of actions is captured in the readiness report, and is included in the appendices of this meeting pack.
At a high level, AEMO will be following up to understand:
  The activity status and adequacy of remediation plans for any items that were not on track, including Metering Transition Plan activities
  Why some generators are not planning to utilise the 5-minute bidding service and/or pre-production environment before 1 October 2021
Are they any actions / insights not reflected in the latest readiness report?

## Slide 25: Readiness reporting – 2021 schedule
The next readiness survey will be released on Tuesday 6 April, with the final report released on Thursday 29 April.
Readiness reporting | Survey released | Survey responses due | Distribute results | Discuss at RWG meeting | Discuss at PCF | Discuss at EF
Round #6 | 02-Feb-21 | 11-Feb-21 | 25-Feb-21 | 02-Mar-21 | 18-Feb-21 | 25-Mar-21
Round #7 | 06-Apr-21 | 15-Apr-21 | 29-Apr-21 | 04-May-21 | 20-May-21 | 24-Jun-21
Round #8 | 02-Jun-21 | 11-Jun-21 | 25-Jun-21 | 06-Jul-21 | 17-Jun-21 | 24-Jun-21
Round #9 | 04-Aug-21 | 13-Aug-21 | 27-Aug-21 | 07-Sep-21 | 19-Aug-21 | 02-Sep-21

## Slide 26: Industry Testing Update
Tui Grant

## Slide 27: ITWG Update- 23-Feb
Settlements Industry Testing:
  Commences 22-Mar-21
  No coordinated testing
  Support through AEMO Support Hub
  Defects published through weekly email from 5MS mailbox
Retail Invitation Testing:
  Commences 19-Apr-21
  Participants have been nominated – all participants can listen in on daily meetings during invitation testing
  Support through AEMO Support Hub
  Defects published through weekly email from 5MS mailbox
Market Trial Preparation
  Nominations for Market Trial Focus Group (MTFG) due by 12-Mar-21
  Terms of Reference have been circulated
  MTFG will develop test plans – will be circulated to ITWG for input and consideration
Training has been scheduled for MSATS and Practitest.
Further training will be available in the lead up to Market Trails for Practitest.

## Slide 28: Settlements Industry Testing
3 settlement runs will be generated and made available on:
  23 March for Settlement week TBA
  26 March for Settlement week TBA
  30 March for Settlement week TBA
Post deployment of the new Retail solution 3 more settlement runs will be generated
The invoices will be thirty-minute invoices in line with what participants can expect at go-live of the new solution.
Five-minute testing will be conducted as part of Market Trials in July.
Support through AEMO Support Hub

## Slide 29: 5MS Staging Environment – 19 February 2021
Forecasting, SD/CD
Issue ID​ | Description​ | Status​ | Action​
2805 | Screen display issue only - An extra TNI2 field is getting displayed under Address Information section in NMI Master, Point in Time NMI Master Summary and NMI Discovery Type 1 and Type 2 search page.​ | Closed | It is a display issue only no functionality affected​ Release in staging planned for 2 Feb
2856 | Staging: Cleanackhandler sometimes sends incorrect X-initiatingParticipantID request header | Closed | No impact to participants Released into staging on 11-Feb and is being retested.
2880 | Event Only Nack from Participant Results in a badack | In Retest | Acknowledge the file from MSATS browser to remove the badack Released into staging on 11-Feb and is being retested.
3683 | Align systems and documentation on Market field within the B2M aseXML header | Closed | Does not affect all participants. This is an issue for participants who have considered <Market>NEM</Market? field as optional for .ack
New | Issue with generation of new settlement run in wholesale due to NEM reports being out of sync with SIT | Closed | Settlement run completed for Week 20 2020
3716 | RM37 report request processing Failure | Closed | This is the only report that we aware of that will not complete, will be retested once when MDM is on the new platform. Released into staging on 11-Feb and is being retested.
3832 | Set participant functionality is broken and throwing error | In Progress | System returns and error message but does allow you to use the functionality. Estimated fix due 15th March
3834 | Metering Data Search screen is throwing error when searching for Interval Reads | Closed | No searching of interval meter reads possible at this stage.

## Slide 30: AEMO Pre-Prod 5MS Bidding Service Defects only – 19-Feb-21
Issue ID​ | Description​ | Status​ | Action​
001 | Web bidding screens issue. If a user enters a band availability that is too high (higher than the maximum capacity of the unit), or a ramp down rate that is too high (higher than the registered maximum ramp rate), then the web screens will highlight an adjacent cell as the source of the error. | In Progress | AEMO to confirm timeline for fix, currently estimated for mid Feb-21
This table only refers to defects in the AEMO pre-production environment related to the 5MS Bidding Service.

## Slide 31: TFG/MTP Update
Blaine Miner

## Slide 32: TFG/MTP Update
Last TFG meeting was held on Thursday 11th Feb
  Agenda:
    Previous actions
    Delay to AEMO’s MDM & Settlement Solutions
    Proposed changes to the MTP
    Upcoming MTP Activities
      Rollout plans
      Read Type Code approach and timings (conflicting views)
    MTP CATS transaction volume management update
Next meeting Thursday 11th March
  Draft Agenda
    Readiness report summary
    Roll-out plans overview (due by 1 March)
      Consolidated consenting Participant data
    RTC transition approach
    Changes to MTP
      Publishing of v1.7
    Upcoming MTP activities
    MSDR Data Transition WG engagement
    GLOPOOL planning
  RWG requests?

## Slide 33: RTC Draft Transition Approach
By 1 Oct 2021
  All Tranche 1 meters (type 1-3, subset of 4 and cross boundary) to have their RTC updated with a fourth character of ‘A’ or ‘D’
    Note, ‘D’ is only to be applied to metering installations that must be producing 5-minute data but cannot be converted because the connection point is de-energised
From 1 Oct 2021 to 30 Nov 2022
  All Tranche 2 meters (new and replacement type 4, 4A, VICAMI, etc.) to have their RTC updated with a fourth character of ‘A’ or ‘D’
    Note, ‘D’ is only to be applied to metering installations that must be producing 5-minute data but cannot be converted because the connection point is de-energised
From 1 Dec 2022 onwards
  All other meters (e.g. basic meters) to have their RTC updated with a fourth character
    Triggers to be discussed at the MSDR Data Transition WG
Caveats:
  From 1 May 2021, MPs can update RTCs, with the appropriate 4 character code, resulting from BAU activities only
    This is to help avoid MPs having to develop additional exception logic into their systems to suppress these updates
  ‘Mass’ updating of this field is not to occur without prior engagement with the effected Participants

## Slide 34: Proposed Changes to the MTP – For RWG endorsement
Category | Activity ID | Activity Description | Change Type | Change Detail
Meter Installation & Reconfiguration | A4a, A9a, A14a, A20a, A25a, A26a, A27a, A28a | Update Meter Read Type code with RWDA | Change in activity ID and Transition Start Dates | Activities moved to ‘Meter Installation & Reconfiguration’ from the ‘Meter Data Delivery’ section of the MTP Transition Start dates amended to reflect draft transition approach (Tranche 1 - 1 May 2021 & Tranche 2 - 1 Oct 2021)
 | A19a | Provide progress and amendments to ‘Known’ Cross Boundary forward plans to AEMO every 2mths | New activity | MC Rollout plans required for Cross Boundary (Known) meters
 | A31 | For any registered ‘Special Site’ (as defined in the ‘Special Sites and Technology Related conditions within the National Electricity Market Version 1.2) or any Logical NMI, update and distribute algorithms adjusted for introduction of 5 minute interval length to AEMO, FRMP and LNSP for approval. | Change to description | Addition of “…or any Logical NMI…”
Meter Data Delivery | A32a, A37a, A42a, A52b, A58b, A64b, A70b, A82a | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths | New activities | MDPs to provide datastream conversion plans from 1 Mar 2021 every 2mths
 | A34, A39, A44, A49, A55, A61, A67, A73, A85, A91 | Agreement to allow the delivery of 5min metering data pre 1 Oct 2021 for B2M purposes | Activities removed | Activity removed as AEMO will not require a formal agreement with MDPs for the early delivery of 5min metering data
 | A35, A41, A46, A50, A56, A62, A68, A74, A86, A92 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) | Change Transition Start Date | Transition Start Date changed from 1 Apr 2021 to 21 June 2021
 | A36, A40, A45, A51, A57, A63, A69, A75 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 31 May 2021
 | A52a, A58a, A64a, A70a | Provide progress and amendments to forward plans to AEMO and industry every 2mths | Change in frequency | Change in frequency to every 2mths, to align to other rollout plan requirements
 | A94 | Meter data delivery of 15 and 30min interval reads only in MDFF to AEMO | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 31 May 2021

## Slide 35: Proposed Changes to the MTP – For RWG endorsement
Category | Activity ID | Activity Description | Change Type | Change Detail
MSATS Standing Data Creation & Maintenance | A95, A96, A97 | Create Cross Boundary NMIs, including associated datastreams and registers | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 31 May 2021
 | A95a, A99a | Provide NMI Creation plans for Cross Boundary and NCONUML to AEMO every 2mths | New activities | NMI Creation plans to be provided from 1 Mar 2021
 | A99, A100, A101 | Create NCONUML NMIs, including associated datastreams and registers | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 31 May 2021
 | A102, A104, A106, A108, A110, A112, A114 | Ensure capability to receive and process new NMI classification codes | Change Transition End Date | Transition End Date changed from 30 Apr 2021 to 30 May 2021
 | A103, A105, A107, A109, A111, A113, A115 | Update NMI Class Codes for existing NMIs as required | Change Transition Start Date | Transition Start Date changed from 1 May 2021 to 31 May 2021
 | A119 | Ensure all Sample meters have a Datastream type code of 'P' and are attached to a Profile | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to ‘At the discretion of the Participant’
 | A120 | Update Datastream type codes from 1-4 to 'I' or 'N' as required | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 31 May 2021

## Slide 36: Upcoming MTP Activities (Assumes Option 1 MDM Go-Live Dates)
Description | Date | Activity ID
MPs to provide progress and amendments to forward plans for Type 1-3, subset of 4 and ‘known’ cross boundary meters to AEMO | By 1 March 2021 | A3a, A8a, A13a, A19a
MDPs to provide progress and amendments to forward plans for Type 4, 4A, VICAMI and Sample meters to AEMO | By 1 March 2021 | A52a, A58a, A64a, A70a
MDPs to provide datastream conversion plans to convert Net datastreams to register level | By 1 March 2021 | A32a, A37a, A42a
LNSPs to provide NMI Create plans for Cross Boundary and NCONUMLs to AEMO | By 1 March 2021 | A95a, A99a
MCs to ensure that details of the Inventory Table, calculation methodologies and Agreed Loads are agreed prior to implementation by relevant Registered Participants | By 31 March 2021 | A87
MCs to provide visibility of the approach / timeframe for required meter replacement or reconfiguration for ‘Unknown’ Cross Boundary meters | By 31 March 2021 | A23
Creation of 5-minute metering data based on SCADA data | By 1 April 2021 | A30
MPs to update the Meter Read Type code with RWDA or RWDD, as applicable | From 1 May 2021 for Tranche 1 meters and BAU updates | A36b, A40b, A45b, A51a, A57b, A63b, A69b, A75b
Participants to establish agreements to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO, as applicable | By 31 May 2021 | A32, A37, A42, A47, A53, A59, A65, A71, A84, A88
MDPs to create/convert export and import Active (kWh) and Reactive (kVarh) energy datastreams, where applicable, in the CNDS table | From 31 May 2021 | A36, A40, AA45, A51, A57, AA63, A69, A75
Meter data delivery of 15 and 30min interval reads only in MDFF to AEMO | From 31 May 2021 | A94
5min metering data delivered to AEMO (MDFF) | From 21 June 2021 | A35, A41, A46, A50, A56, A62, A68, A74, A86, A92
MDPs to deliver tier 1 basic meter metering data (Actuals, Subs and Forward Estimates) to AEMO | By 30 June 2021 | A93

## Slide 37: Metering rollout plan provision schedule
Update # | Provide rollout plans by
3 | 01-Mar-21
4 | 01-May-21
5 | 01-Jul-21
6 | 01-Sep-21
7 | 01-Nov-21
8 | 01-Jan-22
9 | 01-Mar-22
10 | 01-May-22
11 | 01-Jul-22
12 | 01-Sep-22
13 | 01-Nov-22
Please provide metering rollout plan updates according to the below schedule. Please include relevant participant IDs when submitting rollout plans.
This schedule applies for all metering rollout plans:
  MCs to provide MP installation and reconfiguration plans for Type 1-3, subset of type 4 meters, type 7 and known cross boundary
  MDP 5-min data delivery for new and repl. 4/4A, VIC AMI, SAMPLE meters
  MDP conversion plans for Type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level
  LNSP NCONUML and cross boundary NMI creation plans

## Slide 38: Metering rollout plan update – Industry response rate
Notes:
Please let us know if your organisation's position is not correctly reflected in the table above
Only aggregated monthly volumes are planned to be distributed to the RWG/TFG from consenting Participants only
Organisation | 1 Mar Update Provided?
Ausgrid | Yes
Ausnet Services | No
CitiPower Powercor | Yes
ElectraNet | Yes
Endeavour Energy | Yes - Confidential
Energex | Yes
Ergon Energy | Yes
Essential Energy | Yes - Confidential
Evoenergy | Yes - Confidential
Intellihub | Yes
Jemena | Yes
Metropolis | No
Organisation | 1 Mar Update Provided?
Mondo | Yes - Confidential
Origin | Yes - Confidential
PLUS ES | Yes
Powerlink | No
Powermetric | Yes - Confidential
SA Power Networks | Yes
Secure Meters | No
TasNetworks | Yes
Transgrid | Yes
United Energy | Yes
Vector | No
Yurika (MD) | Yes - Confidential

## Slide 39: Procedure update
Simon Tu

## Slide 40: 5MS/GS-related procedure change log
Procedure issue | Status | Final Determination Date
Consolidation of Retail Electricity Procedures | Consultation to commence Feb May-2021 The consolidation of Procedures will not be a full consultation as the Procedures (BAU and 5MS/GS) have already gone through their respective formal consultations. | 30-Jun-2021
Update to published settlement formulas* | 5MS/GS & Customer Switching B2M Consultation commenced 12-Jan-2021, first submissions closed 18-Feb-2021 | 17-May-2021
Cross Boundary (CB) connections, inclusion of cross boundary energy formulas and a Change Request type for CB updates update * | 5MS/GS & Customer Switching B2M Consultation commenced 12-Jan-2021, first submissions closed 18-Feb-2021 | 17-May-2021
MDFF Specification NEM12 & NEM13 update to clarify MDP obligation where a NULL exists in their systems | 5MS/GS & Customer Switching B2M Consultation commenced 12-Jan-2021, first submissions closed 18-Feb-2021 Related to Endeavour Energy’s feedback of the Aug-2020 Metering ICF Package update of the MDFF Specification to remove the ‘N’ quality flag. | 17-May-2021
Clarification on existing requirements for the 5-minute load profile and RM reports | Consultation commenced 12-Oct-2021. Part of the Retail Procedures (Wholesale Demand Response) consultation. | Mar-2021
Updated from last RWG
*raised by the 5MS Program
# aseXML schema impact

## Slide 41: 5MS/GS-related procedure change log – no change
Updated from last RWG
*raised by the 5MS Program
# aseXML schema impact
Procedure issue | AEMO Retail Systems Impact | Available in Staging | Readiness Considerations
Consolidation of Retail Electricity Procedures | No impact to 5MS Retail systems. | N/A | N/A
Update to published settlement formulas* | No impact to 5MS Retail systems. | N/A | N/A
Cross Boundary (CB) connections, inclusion of cross boundary energy formulas* | No impact to 5MS Retail systems. | N/A | N/A
MDFF Specification NEM12 & NEM13 update to clarify MDP obligation where a NULL exists in their systems | No impact to 5MS Retail systems. | N/A | N/A
Clarification on existing requirements for the 5 minute load profile and RM reports | 5MLP included in RM20 and RM25 reports | R27 - 31-Oct-20 - Existing Settlements Reports @5-min: RM16, RM17, RM20, RM21, RM22, RM26 | N/A
Proposed procedural change to MDFF quality flag (N flag)* | Rejection of B2M MTRD MDFF meter reads where quality flag is ‘N’. Results in B2M MTRD Transactions with the status of ‘Partial’ or ‘Rejected’. | R1 - 1-Dec-19 - Support for new B2M MTRD validations. | Participant Mkt Systems must not send ‘N’ for B2B or B2M MTRDs.
Removal of end user details from inventory table | No impact to 5MS Retail systems. | N/A | N/A
Removal of register ID = suffix requirement | No impact to 5MS Retail systems. | N/A | Material participant readiness activity impact as the existing requirement is to be retained.
Notes: Removed:
10MB file size

## Slide 42: 5MS/GS-related procedure change log – no change
*raised by the 5MS Program
# aseXML schema impact
Procedure issue | AEMO Retail Systems Impact | Available in Staging | Readiness Considerations
Proposal for RWD | No impact to 5MS Retail systems. | N/A | ReadTypeCode amended from ‘Optional’ to ‘Required’. Fourth character added to identify whether a meter is capable of reading at five-minute granularity. 4th char field is already avail for data updates in PROD
TNI 2 for cross-boundary meters *# | CATS CR support for TNI2 field. MSATS Browser to support display TNI2 for NMI Discovery Transactions. aseXML schema support extension to support TNI2 inclusion (r39). | R18 and R19 - 31-Aug-20 - Support for TNI2 for CATS CRs. | TNI Code assigned, by AEMO, however Participants to undertake the generation of associated CR2xxx transactions, to register a cross boundary meter using TNI 2. Migration to r39 aseXML necessitated.
New NCONUML NMI Class codes available in list for SORD #​ | Likely B2B schema change. AEMO confirms that the Electricity B2B changes for v3.5 will be made available in pre-production in September or early October 2021. The changes will be in pre-production for a minimum of 4 weeks. 5MS will have to merge the changes from Electricity B2B for the GS May 2022 release. | TBD | 10-Nov-2021 effective date decided as part of the regulator implementation roadmap.
Notes: Removed:
10MB file size

## Slide 43: Retail/ Metering Readiness
TBC

## Slide 44: Retail Metering Staging, Pre-production & Production timelines
Staging
Pre-production
Production
Legacy | 30MS with new platform | 5MS Rule | GS Rule
30-minute meter reads | 30-min settlement 5-min reads supported Standing data updates for GS | UFE calculation and 5-min settlement | LR updated to GLOPOOL
5 Jul 2021
19 Apr 2021
1 Feb 2022
31 Oct 2020
01 Oct 2021
31 May 2021
Legend
GS from 1st quarter 2021 - TBC
1 Oct 2021
Date to be confirmed.
1 May 2022
Updated to reflect replanned pre-prod and prod dates

## Slide 45: Systems Workstream – Metering
Current as at 12-02-2021
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
METERING |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Metering Data & Metrology |  |  |  |  |  |  |  |  |  | 
MDFF • MDFF Specification NEM12 NEM13 v20 | Aug-18 | Oct-18 | Oct-18 | Nov-18 | Jan-19 | Apr-19 | - | 1-Dec-19 | 19-Apr-21 | 31-May-21
PACKAGE 2 - MSATS & SLPs |  |  |  |  |  |  |  |  |  | 
Transition • MSATS Technical Specification | Aug-18 | Sep-18 | Aug-18 | Nov-18 | 31-May-19 | 30-Sep-19 | - | - | - | -
Meter Data - MDFF and MDMF • MDM File Format and Load Process (User Guide) • MSATS Technical Specification | Aug-18 | Oct-18 | Sep-18 | Nov-18 | 31-May-19 | 30-Sep-19 | - | 1-Dec-19 | 19-Apr-21 | 31-May-21
PACKAGE 3 - Miscellaneous |  |  |  |  |  |  |  |  |  | 
B2M via API • MSATS Technical Specification | Oct-18 | - | Apr-19 | 9-May-19 | 31-May-19 | 30-Sep-19 | 01-Jun-20 (Draft) | 15-Jun-20 | 19-Apr-21 | 31-May-21
 |  |  |  |  |  |  | 14-Sep-20 (Final) |  |  | 
MSATS Browser (LVI) changes • MSATS Technical Specification | Aug-18 | - | May-19 | 9-May-19 | 28-Jun-19 | 30-Sep-19 | 10-Oct-20 | 15-Jun-20 | 19-Apr-21 | 31-May-21
MSATS Report changes • MSATS Procedures MDM Procedure • MDM File Format and Load Process (User Guide) • MSATS Technical Specification General Process & Document Clean-up | Oct-18 | - | Apr-19 | Apr-19 | 28-Jun-19 | 30-Sep-19 | - | 31-Aug-20 | 19-Apr-21 | 31-May-21
R3 Go-live : 31/05/21
Updated to reflect replanned pre-prod and prod dates

## Slide 46: Dispatch / Bidding Update
Ian Devaney

## Slide 47: Bidding / Dispatch Staging, Pre-production & Production timelines
STAGING
PRE-PRODUCTION
PRODUCTION
01 Oct 2021
05 Jul 2021
29 Nov 2020
01 Apr 2021
01 Oct 2021
LEGACY | BIDDING TRANSITION | 5MS RULE
30-minute bidding only via: FTP (txt) Web Bidding (Legacy) | 30-minute bidding via: FTP (txt) Web Bidding (Legacy) 5-minute bidding* via: FTP (JSON) Web Bidding (5MS) API *Each 5-minute bid within each half hour must be identical, giving the same effect as the submission of a 30-minute bid. | 5-minute bidding* only via: FTP (JSON) Web Bidding API *30-minute bid emulation restriction lifted
LEGEND
For business continuity reasons, 30-mins offers and bids will be accepted until 01 Oct 21
No change

## Slide 48: Systems Workstream – Dispatch & Operations
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
DISPATCH and OPERATIONS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Bidding FTP and API |  |  |  |  |  |  |  |  |  | 
Transition | Aug-18 | Oct-18 | Aug-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Bidding Data Model | Aug-18 | - | Sep-18 | Mar-19 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Bidding Format | Aug-18 | - | Sep-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 2 - Bidding Web UI |  |  |  |  |  |  |  |  |  | 
Bidding Web UI and APIs | Aug-18 | Nov-18 | Dec-18 | Jan-19 | Mar-19 | 31-Jul-19 | 16-Dec-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 3 - Dispatch, Pre-dispatch and PASA |  |  |  |  |  |  |  |  |  | 
Dispatch | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Predispatch P30/7DAY | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Pre-dispatch P5 (FSIP and 5MPD Price Sens.) | Nov-18 | Oct-18 | Nov-18 | Jan-20 | May-20 | 10-Nov-20 | - | - | TBC | 01-Apr-21
ST and PD PASA | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 4 - Pricing and Miscellaneous |  |  |  |  |  |  |  |  |  | 
Trading Price / Price Revision | Aug-18 | - | Feb-19 | Nov-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 05-Jul-21 | 01-Oct-21
Administered Pricing and CPT | Aug-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 05-Jul-21 | 01-Oct-21
Suspension Pricing | Sep-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 05-Jul-21 | 01-Oct-21
Negative Residue Management | Sep-18 | - | Feb-19 | Dec-18 | Jun-19 | 31-Jul-19 | - | 15-May-20 | - | -
RERT | Oct-18 | - | - | - | - | - | - | - | - | -
PACKAGE 5 - Full Data Model |  |  |  |  |  |  |  |  |  | 
Full Data Model | Sep-18 | Ongoing | Ongoing | Apr-19 | Ongoing | 31-Jan-20 | 16-Mar-20 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
No change

## Slide 49: 5MS Bidding Transition Plan – Quick Reminder
The 5MS Bidding Service will go-live on 01-Apr-21 at 12:00 (mid-day)
Up until midnight on 30-Sep-21 bids must either be submitted in:
  30-minute
  Or 5-min – with 6 identical 5-min bis in every 30-min period to simulate a 30-min bid
  Unique 5-min bids will be rejected
From 00:01 01-Oct-21 participants must submit 5-min bids, they may be unique. 30-Min bids will be rejected
During the transition period the following interfaces are available:
Interfaces - Legacy
  Web: manually in the interface, copy/paste into the web Bid Sheet, upload a plain text or zip file.
  FTP: a txt or zip file to the Participant File Server.
Interfaces – 5MS
  API (JSON): 5-minute files only
  Web: manually in the interface, import (or export) a csv file, upload a JSON file.
  FTP a JSON schema file to the Participant File Server.
Only the 5MS Interfaces will be available from 00:01 01-Oct-21

## Slide 50: 5MS Bidding Service Go-Live Plan
The 5MS Bidding Plan will be published on 08-Mar-21 taking into consideration participant feedback received over the consultation period (see next slide)
Participants do not need to take any action during the cutover process.
Cutover does not interrupt the AEMO Bidding Service, and no action is required to continue to submit 30-min bids
Participants must update to EMMS Data Model v5.00 prior to commencing submitting 5-min bids
Communication:
  Participants will be kept informed of the cutover process through the AEMO Support Hub Bulletin which will be forwarded to all 5MS working groups from 5MS mailbox.
  Support Hub Bulletins are sent to a nominated point of contact in each organisation (generally only one per organisation)
Support:
  Post go-live support will be through AEMO Support Hub
  As participants will commence using 5MS bidding at different times, AEMO will not establish a dedicated Q&A session at this time. However, these can be scheduled if the need arises.
  The monthly Q&A sessions will continue to be available
  Support will be provided to participants during their cutover through Support Hub. AEMO business and IT SMEs will be available through this medium.
Participant transition plans as reported through Readiness Reporting Round 6:
  12 out of 17 will use pre-01-Oct-21
  2 Participants in April, 1 early April and 1 late April,
  1 Participant indication of June

## Slide 51: 5MS Bidding Service Go-Live Plan – Industry feedback
# | Feedback | Response
a) | Query on level of support provided during the transition period and post go-live. | To be discussed at the RWG
b) | Clarification on the bidding service go-live time of 12pm | To be discussed at the RWG
c) | Request for diagrammatic table of the 30MS/5MS tables and environments after go-live | To be discussed at the RWG
d) | Request for further details on AEMO go-live criteria, and rollback scenario | To be discussed at the RWG
    Four participants provided feedback on the draft 5MS Bidding service go-live plan.

## Slide 52: Bidding transition – Industry participation
Chart: 
Yes | 12
No | 5
Does your organisation plan to utilise the 5MS Bidding Service pre-production environment for industry testing?
Chart: 
Yes | 14
No | 3
Does your organisation plan to commence 5-minute bidding during the bidding transition period (1 Apr 2021 to 30 Sep 2021) ?
12 out of 17 generators that responded to the latest readiness survey plan to commence bidding during the bidding transition period. 14 out of 17 generators plan to utilise the pre-production environment for industry testing.

## Slide 53: 5MS Bidding Service Go-live Plan
Milestone | Date
Initial engagement with the RWG | 12 January 2021
Publish draft for industry feedback | 8 February 2021
Deadline for industry feedback | 22 February 2021
Publish final plan | 8 March 2021
The draft 5MS Bidding service go-live plan was published on Monday 8 February 2021. Please respond by COB Friday 22 February 2021 with any comments.
The final document will be issued on Monday 8 March 2021

## Slide 54: Related Documents
Readiness Documents | Systems Technical Documents
Final Bidding Transition Plan v1.0 - 28 August 2020 (Document) | EMMS Technical Specification - 5MS - Data Model v5.00
5MS Bidding Transition Plan v1.0 (Spreadsheet) | EMMS Release FAQ - October 2020 - Data Model v5.00
5MS Bidding Transition Plan FAQ’s | EMMS 5MS Technical Specification - Dispatch and Operations - v6.0
5MS Bidding Service Go-Live Plan | Format and Validation for Energy, FCAS, and MNSP Bids and Offers
 | Draft Guide to Energy and FCAS Web Bids - v2.02
 | Guide to API Energy, FCAS, and MNSP Bids and Offers
Readiness Document webpage: https://www.aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement/readiness-workstream/key-readiness-documents
Systems Technical Documents webpage: https://www.aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement/systems-workstream/systems-technical-documents

## Slide 55: Settlements Update
Mark Hillaby

## Slide 56: Settlements Staging, Pre-production & Production timelines
Staging
Pre-production
Production
1 Oct 2021
17 May 2021
1 Oct 2021
Legacy | 30MS with New Settlement Platform | 5MS Rule | GS Rule
30-minute Settlements | The 5MS capable solution is available in the relevant environment, however 30-minute settlement will remain until the environment reflects the 5MS Rule solution | Five-minute settlement and Global Settlement soft-start - UFE Reporting | All Retailers become liable for UFE
1 May 2022
Incl. UFE Reporting from 05/07/21
Supports 30MS, 5MS and GS modes
Legend
22 Mar 2021
1 Feb 2022
5 Jul 2021
APIs for Settlements Direct and Prudential dashboard added
Updated to reflect replanned pre-prod and prod dates

## Slide 57: Systems Workstream – Settlements
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
SETTLEMENTS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Reallocations |  |  |  |  |  |  |  |  |  | 
Reallocations | Dec-18 | Nov-18 | Dec-18 | Mar-19 | 31-Jul-19 | 15-Oct-19 | 1-Nov-19 | 1-Nov-19 | 1-Mar-20 | 1-Apr-20
PACKAGE 2 - Settlements and Billing |  |  |  |  |  |  |  |  |  | 
Settlements | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 30-Aug-19 | 15-Dec-19 | - | 16-Mar-20 | 22-Mar-21 | 17-May-21
Billing | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 30-Aug-19 | 15-Dec-19 | - | 16-Mar-20 | 22-Mar-21 | 17-May-21
PACKAGE 3 - Prudentials and Estimation |  |  |  |  |  |  |  |  |  | 
Prudentials | Sep-18 | Nov-18 | Dec-18 | Mar-19 | 31-Oct-19 | 31-Jan-20 | 15-May-20 | 15-May-20 | 22-Mar-21 | 17-May-21
Estimation | Oct-18 | Nov-18 | Dec-18 | Mar-19 | 31-Oct-19 | 31-Jan-20 | - | 15–May-20 | 22-Mar-21 | 17-May-21
Full Data Model | Refer DISPATCH |  |  |  |  |  |  |  |  | 
Current as at 12-02-2021
Pre-prod and Production dates updated as a consequence of Retail re-plan.

## Slide 58: Settlements Implementation Plan
Full description of implementation principles is set out in the Industry transition and go-live strategy at: https://aemo.com.au/Electricity/National-Electricity-Market-NEM/Five-Minute-Settlement/Readiness-Workstream/Key-Readiness-Documents.
  Rules start dates must be met
  Operation of the NEM must be uninterrupted
  Flexibility in implementation must be maximised for Participants.
  Participants and AEMO are each responsible for their own transition and go-live planning.
In addition, the following principles are specific to this plan:
  AEMO must keep Participants informed with status updates during implementation.
  Participants must comply with directions from AEMO during implementation.

## Slide 59: Settlements Implementation Plan
'Go/No go' decision will be provided to Participants one week before release.
Plan to start cutover on Friday 14 May. Access to Settlements Web pages will be shut down. AEMO will communicate ‘Proceed’ decision to Participants.
Plan to complete release on Saturday then perform verification.
  AEMO may invite selected Participants to perform implementation verification over the cutover weekend.
  Need to roll back may delay the return to operational state until Sunday afternoon at the latest. Participants will be advised in this eventuality.
Notification of successful release expected on Sunday 16 May.

## Slide 60: Settlements Changes at Platform Go-live
Web pages including Prudential and Prudential Forecast dashboards, and Settlements Direct change the look-and-feel; ‘Credit Support’ pages are re-activated.
New APIs matching the web pages become available for use by Participants.
Settlement reconciliation report (SR report) has new UFE columns. However, these are not populated until 1 Oct 2021.
Participant Data Model changes (v5.00 - still reporting in 30-minute intervals) are implemented with the Dispatch release so no further changes for this release.
  New tables:
  BILLRESERVETRADERPAYMENT, BILLRESERVETRADERRECOVERY, SETLOCALAREAENERGY, SETLOCALAREATNI
  BILLINGCPDATA
  UFE fields added to SetCPData and BILLINGCPDATA tables
  New field: SETTLEMENT_DATA:DAYTRACK.SETTLEMENTINTERVALLENGTH
  PeriodID changed to Number(3,0) for SetCPData, SetMarketFees and SetIR[Auc|NSP|Part]Surplus tables.
  Adding FeeRate & FeeUnits to SetMarketFees tables
New look for invoices & statements. Two items are removed: ‘Smelter reductions’ and ‘Mandatory Restrictions’.

## Slide 61: Forward Plan and Other Business
Greg Minney

## Slide 62: RWG 2021 Proposed Topics
Month | Topics | Month | Topics
January | Preparing for Retail Invitation Industry Test Platform Go Lives criteria Market Commencement criteria Risk Review | 02-June | Preparing for Market Trial Metering rollout progress Risk review – any Market Trial risks? Approach to Global Settlements engagement
09-February | Update on Retail systems go-live changes Metering Transition Preparation | 06-July | Market Trial progress, Readiness Reporting #8 Market Commencement Criteria
02-March | Retail Go-Live Update Preparing for 5MS Bidding Cutover Settlements Industry Test Readiness Reporting #6 5MS Market Trial – planning approach | 03-August | Market Trial progress Go-Live risks
06-April | Retail Go-Live Update – checkpoint outcomes Debrief on Bidding go-live Debrief on Settlements Industry Test commencement 5MS Market Trial – planning update Metering provider implementation planning Risk review | 07-September | Results of Market Trial, Preparing for 1 Oct – Ind Go-Live Plan review Readiness Reporting #9
04-May | Retail Go-Live Update and preparing for cutover* Readiness Reporting #7 Preparing for Settlements Cutover Approach to Global Settlements engagement 5MS Market Trial approach Industry Go-Live plan approach | TBC-October | Debrief and reconfirmation of approach for Global Settlements
*Dates depend on Checkpoint outcomes

## Slide 63: ITWG 2021 Proposed Topics
Month | Topics | Month | Topics
January | Retail invitation test plan Status of Dispatch and Bidding in Pre Prod | June | Final review of tests for market trials Review of production across all 5MS systems
February | Retail invitation test plan and participant involvement Settlements Industry Test Market Trail approach to preparation | July | Results of Market Trials
23-March | Settlement Platform industry testing Nomination for MTFG to define test approach for Market Trials | August | Results of Market Trials
27-April | Test scenario review in preparation for market trials Status of Dispatch and Bidding in Production | September | General update on upcoming market start
May | Review pairing and finalise market trials Status of Settlements in Production |  | 

## Slide 64: Upcoming meetings
Current as at 24/02/2021
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement

## Slide 65: Questions

## Slide 66: Appendix

## Slide 67: Readiness Reporting Actions and Follow ups – Round 4
No. | Status | Action | Comment
4.1 | Closed | AEMO to follow up with relevant MPS and MCs with essential meters to confirm program status and if remediation is required. | Met with all MPs and MCs, all except one are responding appropriately in the latest round of reporting
4.2 | Closed | AEMO to follow up to understand generators responding with a 'late’ or ‘at risk’ status and establish level of remediation expected | Generator that responded with a ‘late’ status noted that they expect to be on track in Q1 2021. Generator that responded with a ‘at risk’ status reported as ‘on track’ in the latest round of reporting.
4.3 | Closed | RWG to consider impact of potential industry risks | Risks discussed at RWG 17
4.4 | Closed | AEMO to follow up with relevant MC and confirm expected completion date of activity | Meeting held with relevant MC. Now responding as ‘on track’ in latest round of reporting.
4.5 | Open | RWG to consider risk of cross boundary meters not appropriately configured by transition end date | Discussion continued at RWG 18
4.6 | Open | Participants to consider impact of late delivery of MTP S39, and flow on impact to overall programs | Four participants are still responding that they are ‘late’ to complete this activity, however no major impact to programs have been flagged.
4.7 | Closed | Participants to schedule address accreditation requirements and suitable remediation approach. | All participants are reporting as ‘on track’ for accreditation requirements in the latest round of reporting

## Slide 68: Readiness Reporting Actions and Follow ups – Round 5
No. | Status | Action | Comment
5.1 | Closed | AEMO to follow up with non-responding MP/MC with essential meters to confirm program status and if remediation is required. | AEMO followed up and relevant MP/MC is now responding to the latest readiness survey
5.2 | Closed | AEMO to establish with generator reporting 'late' if a remediation plan or escalation is required | Generator continues to report a ‘late’ status and has noted they expect to be on track in March 2021. AEMO will continue to monitor the readiness responses of this participant
5.3 | Closed | RWG to consider risk of cross boundary meters not appropriately configured by transition end date | Risk discussed at RWG 18
5.4 | Closed | AEMO to follow up with relevant DNSP on potential risk to delivery timelines on MTP subcategories ‘S26 - Cross boundary supplies' and 'S29 - NCONUML'. | Initial meeting held, with follow up meeting pending
5.5 | Closed | Participants to consider impact of late delivery of MTP subcategory ‘S39 – Meter installation type code’, and flow on impact to overall programs | As presented at the TFG, considering that S39 is a preliminary activity in the MTP, with its transition end date now past due, AEMO considers this activity to be complete.

## Slide 69: Readiness Reporting Actions and Follow ups – Round 6
No. | Status | Action | Comment
6.1 | Open | AEMO to confirm progress and status of non-responding TNSP's readiness activities | One TNSP did not respond as a TNSP in this round of reporting, however provided readiness responses for the other participant types they represent.
6.2 | Open | AEMO to seek clarification from generator reporting 'late' and if remediation action is successful | Participant is reporting that they expect to be on track by March 2021, and intend to commence 5-minute bidding as soon as possible during the transition period after April 2021.
6.3 | Open | AEMO to monitor status of MDP reporting that their overall program is 'at risk' in round 7 of readiness reporting | AEMO to provide update in the next readiness report
6.4 | Open | AEMO to follow up with TNSP reporting 'at risk' to understand timing of remediation | AEMO to provide update in the next readiness report
6.5 | Open | RWG to consider if risks raised by respondents in readiness reporting should be captured as industry risks | AEMO to facilitate discussion at RWG 18 on 2 March 2021
6.6 | Open | AEMO to follow up with MP/MC with essential meters reporting a 'late' status to confirm timing of remediation | AEMO to follow up with participant and provide update in the next readiness report
6.7 | Open | AEMO to clarify 5-minute bidding go-live approach with generators that are not planning to utilise the bidding transition period, and establish level of industry risk | AEMO to follow up with participants and provide update in the next readiness report

## Slide 70: Readiness Reporting Actions and Follow ups – Round 6
No. | Status | Action | Comment
6.8 | Open | AEMO to follow up with MP responding that 'S09 - New and replacement SAMPLE meters' is 'at risk' to confirm status and if remediation is required. | AEMO to follow up with participant and provide update in the next readiness report
6.9 | Open | AEMO to follow up with MP responding that 'S01 - BULK/ Wholesale Meters', 'S02 - Type 1 - 3 Meters', and 'S03 - Subset of type 4 meters - TNI, Market Generator or SGA' is late to confirm timing on remediation and if escalation is required | Participant has noted remediation activities are underway. AEMO to follow up and provide update in the next readiness report
6.10 | Open | AEMO to follow up with MP responding that 'S15 - Cross Boundary meters (KNOWN)' and 'S20 - New and replacement SAMPLE Meters' is 'at risk' to confirm status and if remediation is required. | AEMO to follow up with participant and provide update in the next readiness report
6.11 | Open | AEMO to follow up with MP responding that 'S41 - MP accreditation update (for 1 Oct 2021)' is 'late' to confirm remediation and consider if escalation is required | AEMO to follow up with participant and provide update in the next readiness report
6.12 | Open | AEMO to follow up with MDP responding that 'S24 - Tier 1 basic metering data' is 'late' to confirm delivery timing | AEMO met with participant, and confirmed that activities are planned to be completed before 1 October 2021
6.13 | Open | AEMO to follow up with MDP responding that 'S14 - Type 1-3, subset of Type 4' is 'at risk' to confirm status and if remediation is required. | Participant advised that program has been delayed by two weeks. AEMO to follow up with participant and provide update in the next readiness report

## Slide 71: Readiness Reporting Actions and Follow ups – Round 6
No. | Status | Action | Comment
6.14 | Open | AEMO to follow up with MDP responding that 'S37 - Interval meter datastreams' is 'at risk' to confirm status and if remediation is required | AEMO to follow up with participant and provide update in the next readiness report
6.15 | Open | AEMO to follow up with MDP responding that 'S36 - Tier 1 basic meter datastreams' is 'late' to confirm status and if remediation is required | AEMO met with participant, and confirmed late status. RWG to consider impact on UFE accuracy for distribution area.
6.16 | Open | AEMO to follow up with MDP responding that 'S27 - Non-contestable metered loads' is 'late' to confirm status and if remediation is required | AEMO met with participant, and confirmed that activities will be completed before 1 October 2021
6.17 | Open | AEMO to follow up with MC responding that 'S01 - BULK/Wholesale Meters', 'S02 - Type 1-3 Meters', 'S03 - Subset of type 4 meters, TNI, Market Generator or SGA' is 'late' to confirm remediation plans and if escalation is required | Participant has noted remediation activities are underway. AEMO to follow up and provide update in the next readiness report
6.18 | Open | AEMO to follow up with MC responding that 'S02 - Type 1-3 Meters' is 'at risk' to confirm remediation plans and if escalation is required | AEMO to follow up with participant and provide update in the next readiness report