## Slide 1: 5MS & GS Readiness Working Group #24 (incl. Systems Working Group)
Friday, 28 May 2021
This meeting is recorded for the purpose of minute taking.
Please disconnect from your workplace VPN for the WebEx call

## Slide 2: AEMO Competition Law Meeting Protocol
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require

## Slide 3: Agenda
Greg Minney

## Slide 4: Agenda
#​ | Time​ | Topic​ | Presenter​
1​ | 10:30 – 10:35​ | Welcome and Agenda​ | Greg Minney​
2​ | 10:35-10:40​ | Minutes/Actions | Anne-Marie McCague​
3​ | 10:40 – 10:50​ | 5MS Program Update | Greg Minney & Graeme Windley​
4 | 10:50 – 11:05 | Market trial and industry testing update | Tui Grant​
5 | 11:05 – 11:25​ | MTP Update​ | Blaine Miner​
6 | 11:25 – 11:35 | Procedure Update​ | Simon Tu​
7 | 11:35 – 11:50 | 5MS Staging Environment Availability​ | Greg Minney​
8 | 12:05 – 12:20 | Dispatch & Bidding Update | Ian Devaney
9 | 12:20 – 12:35 | Retail Functionality Update | Simon Tu, Jim Agelopoulos & Paul Lyttle
10 | 12:35 – 12:50 | Retail Industry Go-Live Plan Update​ | Greg Minney
11 | 12:50 – 13:05 | Upcoming Readiness Survey | Blaine Miner​
12 | 13:05 – 13:20​ | Forward Plan and Other Business​ | Greg Minney​
13 | 13:20 – 13:30 | Meeting Close​​ | Greg Minney​

## Slide 5: Minutes & Actions
Anne-Marie McCague

## Slide 6: RWG Actions (1/2)
No. | Status | Action | Comment
23.2.1 | Open | AEMO to reword Risk R02 in advance of next risk review. | To be addressed in next RWG risk review session (next RWG).
23.4.1 | Closed | AEMO to provide further clarity on the functionality that will be available under each contingency option. | Completed, and included in RWG meeting pack #23 published on RWG webpage
23.4.2 | Closed | AEMO to provide two timeline scenarios to aid RWG in their review of the impacts of each contingency option. | Completed, and included in RWG meeting pack #23 published on RWG webpage
23.4.3 | Closed | AEMO to provide a summary of the impacts of the contingency options on other regulatory implementation programs. | Completed, and included in RWG meeting pack #23 published on RWG webpage
23.9.1 | Closed | RWG to provide feedback on the impact of withdrawing the 5MS Staging Environment on their programs from 31 May 2021. | Completed. Discussed in section 7 of this pack.

## Slide 7: RWG Actions (2/2)
No. | Status | Action | Comment
23.11.1 | Closed | RWG to provide feedback on the following points on slide 64: • Participants to advise length of extension to B2B outage post 8:00am Monday morning that could be managed to extend the cutover window to allow resolution of AEMO cutover issues. • Participants to advise compliance or operational impacts (B2B and B2M) once the cutover window is exceeded • Participants to advise capability for restarting the delivery of B2M metering data delivery in a staggered manner versus or releasing all backlog at once | Outcomes discussed in section 10.
23.11.2 | Closed | RWG to provide feedback on the impacts (if any) of the non-population of optional fields in the report response parameters for automatically generated reports RM16, RM27, RM20 | Feedback indicated that issue impacted multiple participants. Fix to be deployed. See section 9.
23.11.3 | Closed | RWG to provide feedback on the proposal that NCONUML NMI creation would be delayed until mid-June if it were to impact Retail go-live on 31 May 2021. | Feedback was requested prior to the change in Retail Go-Live date. NCONUML is discussed in section 9.

## Slide 8: 5MS Program Update
Greg Minney & Graeme Windley

## Slide 9: Proposed Updated 5MS Program Timeline
Retail Go-Live moved from 31-May to 21-June
Rule Commencement remains green but with heightened risk profile and subject to achievement of Retail go-live backup date
Retail Industry Test period extended from 21-May to 14-June
Market Trial period moved from 05-Jul – 28-Aug to 19-Jul – 10-Sep (TBC with RWG)
Market Trial prep milestone moved from 05-Jul to 12-Jul
Retail Industry Go-Live Plan will be reissued by 28-May. Cutover walk-through session will be rescheduled with RWG.

## Slide 10: Proposed Date Change to Milestones Impacted by Retail Go-Live to be discussed with RWG
ID | Description | Previous Date | New Date | Owner
L1-19 | AEMO Metering Solution – Go-Live | 31-May-21 | 21-Jun-21 | AEMO
L1-17 | 5MS Market Trial Commences | 05-July-2021 | [19-July-21] | AEMO
L1-9 | 5MS Market Trial Successfully completed | 27-Aug-2021 | [10-Sept-21] | AEMO
L2-RE30 | Retail MDM (incl. B2M) Industry Test Concludes | 21-May-2021 | 14-Jun-21 | AEMO
L2-RE35 | Industry Go-Live Plan Retail MDM final (reissue) | 10-May-21 | 28-May-21 | AEMO
L2-M24 | Retail MDM (incl. B2M) Go-Live | 31-May-2021 | 21-Jun-21 | AEMO
L2-M10 | 5 minute files in MDFF accepted by AEMO | 22-Jun-2021 | 22-Jun-21 | AEMO
L2-RE23 | 5MS Capability Market Trial preparation completed by participants | 05-Jul-2021 | 12-Jul-21 | Participants
L2-RE24 | 5MS Capability Market Trial preparation completed by AEMO | 05-Jul-2021 | 12-Jul-21 | AEMO
L2-RE31 | 5MS Capability Market Trial commences | 05-Jul-2021 | [19-Jul-21] | AEMO
L2-D10 | 5MS Capability Market Trial concludes | 27-Aug-2021 | [10-Sept-21] | AEMO

## Slide 11: Retail Checkpoint Criteria / Reasons for Delay
Criteria​ | Description | Status | Commentary
Testing | All UAT test cases executed with no critical defects that cannot be remedied for 31 May go-live. | Delayed | 5MS has had delays completing its final UAT cases, largely impacted by data issues from current MSATS data. Initial fixes supplied were not successful. We now have a different approach for these issues, and will proceed with the remainder of the test cases when these are fixed. These fixes will be delivered into the Pre-Production environment week commencing Monday 24 May, after which 5MS will complete profiling runs there.
Solution Stability | End-to-end solution operating stably in Test with no process blockers or unexplainable pauses/interruptions to processing. |  | Stability has improved, and enabled testing execution to progress. Improvements (i.e. defensive programming) introduced have been successful. Some initial stability issues were experienced in Pre-Production however AEMO is confident this has been tuned and therefore rectified.
Remediation | Known remediation work (internal reports performance, business activity monitoring) completed and remediation for any new defects scheduled. | In Progress | Internal work on Business Activity Monitoring has progressed well. Challenges continue to be experienced with Operational Reporting delivery that may impact business efficiency, but not presently expected to block go-live.
Performance | “Day in the Life Testing” completed with no performance issues identified that cannot be remedied for 31 May go-live. |  | All Day In The Life testing now completed, with the volumes ingested / outputted matched live industry requirements.
Production Cutover | Data migration on track and no blockers to meeting criteria/schedule for pre-production deployment. | Delayed | Data Migration to Production was delayed by the MSATS data issues, and would not have met 31 May deployment timelines.
Industry Test | On track to commence Retail Industry Test on 19 April. | In Progress | From industry testing two defects have been found that would significantly impact multiple participants, and therefore risk market function at the Platform go live. Both of these need development then testing by industry personnel: CH35 limit on filename – change into Pre-Production week commencing Monday 24 May. Settlement run output RM Reports not containing from and to dates – change into Pre-Production week commencing Monday 31 May (successful testing permitting)
Overall | 5MS has been impacted by COVID, which has slowed down defect fix rate. However over the last week three key personnel have returned to work |  | The Retail workstream is now red as it is not in a position to meet the 31 May 2021 eMDM Platform go-live date. There are currently no unresolvable items, but more time is required to resolve the data issues and deliver the functional changes for the industry.

## Slide 12: Market Trial & Industry Testing Update
Tui Grant

## Slide 13: Market Trial & Industry Testing
5MS Market Trial:
Market trials plan distributed for comment
Proposed Test Schedule and workbook distributed to ITWG for input
Next Steps:
  Participant registration and nomination of test scenarios
  Participant / scenario paring
  NMI identification for agreed scenarios (if applicable)
Market trial schedule reflects transition from 30 to 5 minute settlement
Requires alignment of bidding capability with Market trial schedule
  Full 5 minute capability to take effect in pre-prod on 30 Jul
30-Jul will reflect operating conditions for 1 Oct
  5 minute bidding profiles
  Rejection of MDMT for interval meters
  Customer switching capability

## Slide 14: Industry Testing Settlements / Retail
Retail Industry Test as at 25/5
Industry Test Defects:
11 - in state of Test Ready
3 - with AEMO for Investigation
17 - closed / rejected
Settlement Runs to be generated from the new Retail Platform:
2020Wk40 Prelim (27 Sep to 4 oct 2020)
2020Wk38 Final (13 Sep to 19 Sep 2020)
2020Wk24 RREV1 (7 Jun to 13 Jun 2020)
Industry Testing Support:
Environment will continue to be available for Industry to test
Status / issue meetings reduced in frequency as majority of test scenarios have been addressed
Confirmation of file length issue available for participant verification in current release

## Slide 15: MTP Update
Blaine Miner

## Slide 16: MTP Considerations and Engagement
AEMO notified industry on 14 May that the Retail go-live would be re-scheduled for the back-up date of 21 June 2021
AEMO drafted suggested changes to the MTP and circulated v1.8 of the MTP to the TFG for its consideration and feedback
TFG agreed with the proposed changes and did not raise any specific concerns re the delay
The TFG did however suggest other unrelated changes to the MTP, to ensure an ongoing smooth transition to the Rule commencements
The following slides illustrate the TFG recommended changes for RWG endorsement
Once endorsed, v1.8 of the MTP will be published to AEMO’s website

## Slide 17: MTP Update
Proposed Changes
Notes:
The delivery of 5min metering data to AEMO is proposed to remain as 21 June 2021, once cutover backlog has been addressed
Participants capability to receive and process new NMI classification codes is proposed to remain as 30 May 2021, no dependency on AEMO’s Retail solution, noting participant update dates have been aligned to 21 June
Description | Date | Activity ID
AEMO Metering Business approve MDP NCONUML profiles/algorithms | By 1 May 2021 | A89
MDPs to provide AEMO estimated number of NMIs and associated energy volumes for each Unmetered Device category within calculation methodology | By 1 May 2021 | A89a
Activities Now Deemed Completed
Type | Activity Description | Proposed Date
Amendment to Transition Start Date | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table Meter data delivery of 15 and 30min interval reads only in MDFF to AEMO Create cross-boundary NMIs (relies on new NMI Classification Code being available) Create NCONUML NMIs in MSATS (relies on new NMI Classification Code being available) Update existing NMIs to new NMI Classification Codes Update VIC TUoS Datastream type codes from 1-4 to 'I' or 'N' as required | From 21 June 2021
New Activities | Information provided when seeking approval from AEMO, in accordance with section 3.1(c) of the Cross Boundary Supply Guideline, must include evidence of the agreement of the LNSP and NSP2 roles (A95b) Provisioning of cross boundary information to AEMO to enable the determination of TNI2 values (A97c) AEMO to provide TNI2 values to LNSPs to support the updating of applicable TNI fields i.e. TNI fields associated to NMIs downstream of a cross boundary NMI (A97a) LNSPs to update the TNI field, for NMIs downstream of a cross boundary NMI, with the AEMO provided TNI2 value (A97b) | By 31 August 2021

## Slide 18: Upcoming Transition Start Date Activities
Description | Transition Start Date | Activity ID
MDPs able to create/convert export and import Active (kWh) and Reactive (kVarh) energy datastreams, where applicable, in the CNDS table | From 21 June 2021 | A36, A40, A45, A51, A57, A63, A69, A75
Participants able to create cross-boundary NMIs, datastreams and registers | From 21 June 2021 | A95, A96, A97
Participants able to create NCONUML NMIs, datastreams and registers | From 21 June 2021 | A99, A100, A101
MDPs able to send 15 and 30min metering data via MDFF to AEMO | From 21 June 2021 | A94
LNSPs able to apply new NMI classification codes | From 21 June 2021 | A103, A105, A107, A109, A111, A113, A115
MDPs able to update VIC TUoS Datastream type codes from 1-4 to 'I' or 'N' as required | From 21 June 2021 | A120
MDPs able to provide 5min metering data to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) | From 21 June 2021 | A35, A41, A46, A50, A56, A62, A68, A74, A86, A92

## Slide 19: Upcoming Transition End Date Activities
Description | Transition End Date | Activity IDMDPs
Participants to ensure capability to receive and process new NMI classification codes | By 30 May 2021 | A102, A104, A106, A108, A110, A112, A114
Participants to establish agreements to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO, as applicable | By 31 May 2021 | A32, A37, A42, A47, A53, A59, A65, A71, A84, A88
SAPN - Convert 'SASCALE NMI’ Make existing 'Bulk' NMI extinct in MSATS Create individual controlled load Datastreams in MSATS Create individual controlled load Registers in MSATS | By 30 June 2021 | A101a, A101b, A101c
MDPs - Create/activate tier 1 basic meter datastreams as required | By 30 June 2021 | A117, A118
MDPs - Delivery of tier 1 basic meter metering data (Actuals, Subs and Forward Estimates) to AEMO | By 30 June 2021 | A93
MPs - Install or reconfigure meters as required | By 31 July 2021 | A4, A9, A14, A20
MPs - Update Meter Read Type code with RWDA | By 31 July 2021 | A4a, A9a, A14a, A20a
MPs - Apply for data storage exemptions as required | By 31 July 2021 | A5, A10, A15, A21

## Slide 20: Procedure Update
Simon Tu

## Slide 21: 5MS/GS-related procedure change log
Procedure issue | Status | Final Determination Date
Consolidation of Retail Electricity Procedures Phase 1 | Submissions for feedback on the consolidation exercise finished 25-May-2021 Focusing on Oct-2021 requirements The consolidation of Procedures will not be a full consultation as the Procedures (BAU and 5MS/GS) have already gone through their respective formal consultations. | 29-Jun-2021
Consolidation of Retail Electricity Procedures Phase 2 | Expected to be published late 2021 Focusing on May-2022 requirements | 31-Jan-2022
Changes since April RWG
*raised by the 5MS Program
# aseXML schema impact

## Slide 22: 5MS/GS-related procedure change log
Procedure issue | AEMO Retail Systems Impact | Available in Staging | Readiness Considerations
Consolidation of Retail Electricity Procedures. | No impact to 5MS Retail systems. | N/A | N/A
Update to published settlement formulas* | No impact to 5MS Retail systems. | N/A | N/A
Cross Boundary (CB) connections, inclusion of cross boundary energy formulas* | No impact to 5MS Retail systems. | N/A | N/A
MDFF Specification NEM12 & NEM13 update to clarify MDP obligation where a NULL exists in their systems. | No impact to 5MS Retail systems. | N/A | N/A
Clarification on existing requirements for the 5 minute load profile and RM reports | 5MLP included in RM20 and RM25 reports | R27 - 31-Oct-20 - Existing Settlements Reports @5-min: RM16, RM17, RM20, RM21, RM22, RM26 | N/A
Proposed procedural change to MDFF quality flag (N flag)* | Rejection of B2M MTRD MDFF meter reads where quality flag is ‘N’. Results in B2M MTRD Transactions with the status of ‘Partial’ or ‘Rejected’. | R1 - 1-Dec-19 - Support for new B2M MTRD validations. | Participant Mkt Systems must not send ‘N’ for B2B or B2M MTRDs.
Removal of end user details from inventory table | No impact to 5MS Retail systems. | N/A | N/A
Removal of register ID = suffix requirement | No impact to 5MS Retail systems. | N/A | Material participant readiness activity impact as the existing requirement is to be retained.
22
Changes since April RWG
*raised by the 5MS Program
# aseXML schema impact
Notes: Removed:
10MB file size

## Slide 23: 5MS/GS-related procedure change log – no change
*raised by the 5MS Program
# aseXML schema impact
Procedure issue | AEMO Retail Systems Impact | Available in Staging | Readiness Considerations
Proposal for RWD | No impact to 5MS Retail systems. | N/A | ReadTypeCode amended from ‘Optional’ to ‘Required’. Fourth character added to identify whether a meter is capable of reading at five-minute granularity. 4th char field is already avail for data updates in PROD
TNI 2 for cross-boundary meters *# | CATS CR support for TNI2 field. MSATS Browser to support display TNI2 for NMI Discovery Transactions. aseXML schema support extension to support TNI2 inclusion (r39). | R18 and R19 - 31-Aug-20 - Support for TNI2 for CATS CRs. | TNI Code assigned, by AEMO, however Participants to undertake the generation of associated CR2xxx transactions, to register a cross boundary meter using TNI 2. Migration to r39 aseXML necessitated.
New NCONUML NMI Class codes available in list for SORD #​ | Likely B2B schema change. AEMO confirms that the Electricity B2B changes for v3.5 will be made available in pre-production in September or early October 2021. The changes will be in pre-production for a minimum of 4 weeks. 5MS will have to merge the changes from Electricity B2B for the GS May 2022 release. | TBD | 10-Nov-2021 effective date decided as part of the regulator implementation roadmap.
Notes: Removed:
10MB file size

## Slide 24: 5MS Staging Environment Availability
Greg Minney

## Slide 25: 5MS Staging Environment Availability
AEMO has reviewed its position on the support of Staging environment as at 31 May
In light of participant feedback regarding the utilisation of the staging environment, in particular for the testing of full 5 minute capability in the period up to the commencement of 5MS Market Trial – Staging environment support will be maintained until the commencement of Market Trial, currently scheduled for 19th July.
  At this time the pre-production environment will be reflective of the1 Oct capability.
  Multiple have indicated the bi-lateral testing would be more effectively carried out in the pre-prod environment
Support for participant issues raised will be on a best endeavours basis and prioritised behind production and pre-production environment support
  Noting that Staging environment has been support ed only for 5MS capability and will not be supported for CS, WDR or future initiatives at this stage

## Slide 26: Dispatch & Bidding Update
Ian Devaney

## Slide 27: Bidding / Dispatch Staging, Pre-production & Production timelines
STAGING
PRE-PRODUCTION
PRODUCTION
01 Oct 2021
30 Jul 2021
29 Nov 2020
01 Apr 2021
01 Oct 2021
LEGACY | BIDDING TRANSITION | 5MS RULE
30-minute bidding only via: FTP (txt) Web Bidding (Legacy) | 30-minute bidding via: FTP (txt) Web Bidding (Legacy) 5-minute bidding* via: FTP (JSON) Web Bidding (5MS) API *Each 5-minute bid within each half hour must be identical, giving the same effect as the submission of a 30-minute bid. | 5-minute bidding* only via: FTP (JSON) Web Bidding API *30-minute bid emulation restriction lifted
LEGEND
For business continuity reasons, 30-mins offers and bids will be accepted until 01 Oct 21
Bidding Transition update in Pre-prod updated

## Slide 28: Systems Workstream – Dispatch & Operations
Current as at 09-04-2021
5 MINUTE SETTLEMENT SYSTEMS TRACKING | TIMING |  |  |  |  |  |  |  |  | 
 | Internal HLIA | Focus/Group | SWG Engagement | External HLIA | Draft Tech Spec | Final Tech Spec | User Guides | 5MS Staging | Preprod | Production
DISPATCH and OPERATIONS |  |  |  |  |  |  |  |  |  | 
PACKAGE 1 - Bidding FTP and API |  |  |  |  |  |  |  |  |  | 
Transition | Aug-18 | Oct-18 | Aug-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Bidding Data Model | Aug-18 | - | Sep-18 | Mar-19 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Bidding Format | Aug-18 | - | Sep-18 | Nov-18 | Dec-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 2 - Bidding Web UI |  |  |  |  |  |  |  |  |  | 
Bidding Web UI and APIs | Aug-18 | Nov-18 | Dec-18 | Jan-19 | Mar-19 | 31-Jul-19 | 16-Dec-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 3 - Dispatch, Pre-dispatch and PASA |  |  |  |  |  |  |  |  |  | 
Dispatch | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Predispatch P30/7DAY | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | - | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Pre-dispatch P5 - Fast Start Inflexibility Profile | Nov-18 | Jan-20 | Nov-18 | Jan-20 | May-20 | 10-Nov-20 | - | - | 01-Apr-21 | 07-Jul-21
5MPD - Price Sensitivities | - | Jan-20 | Nov-18 | Jan-20 | May-20 | 10-Nov-20 | - | - | 16-Jun-21 | 07-Jul-21
ST and PD PASA | Aug-18 | - | Oct-18 | Nov-18 | Oct-18 | 2-Apr-19 | 31-Oct-19 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
PACKAGE 4 - Pricing and Miscellaneous |  |  |  |  |  |  |  |  |  | 
Trading Price / Price Revision | Aug-18 | - | Feb-19 | Nov-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 05-Jul-21 | 01-Oct-21
Administered Pricing and CPT | Aug-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 05-Jul-21 | 01-Oct-21
Suspension Pricing | Sep-18 | - | Feb-19 | Dec-18 | Mar-19 | 31-Jul-19 | - | 15-May-20 | 05-Jul-21 | 01-Oct-21
Negative Residue Management | Sep-18 | - | Feb-19 | Dec-18 | Jun-19 | 31-Jul-19 | - | 15-May-20 | - | -
RERT | Oct-18 | - | - | - | - | - | - | - | - | -
PACKAGE 5 - Full Data Model |  |  |  |  |  |  |  |  |  | 
Full Data Model | Sep-18 | Ongoing | Ongoing | Apr-19 | Ongoing | 31-Jan-20 | 16-Mar-20 | 29-Nov-19 | 30-Nov-20 | 01-Apr-21
Changes Highlighted

## Slide 29: Special Note: Pre-Dispatch Daily Energy Constraints
EMMS Release FAQ - October 2020 - Data Model v5.00
The dailyEnergyConstraint is an optional element of the JSON schema.
Therefore it can be left out if you do not want to use it.
However, if you do submit a dailyEnergyConstraint as part of your bid, then you must provide a number between 0 and 999 999 MWh, the number will be used literally i.e. a zero will be treated as zero.
dailyEnergyConstraint is used only in (30-minute) Pre-Dispatch. It is not used in Dispatch or 5-Minute Pre-Dispatch.

## Slide 30: Retail Functionality Update
Simon Tu, Jim Agelopoulos & Paul Lyttle

## Slide 31: Retail Functionality Update
Status of highlighted Industry issues:
Inbound meter Data messages with > 35 Characters in File Name rejected
  Fix delivered to Pre-prod for industry verification
  File name length updated to 45 characters
RM Reports (RM16, 20, 27) to populate Optional fields in XML header
  Fix has been developed
  Internal testing required prior to release into pre-prod
  Expected to be included in June 21 prod Release
NCONUML inclusion in June 21
  NCONUML capability release on June 21 subject to finalisation of AEMO UAT
  MTP updates (1.8) have aligned transition start date with June 21 release

## Slide 32: Retail Industry Go-Live Plan Update
Greg Minney & Libby Leonard

## Slide 33: Production cutover updates
Go-live plan for re-issue 28/ 29th May
  Incorporate updated approach and dates to account for 21st June deployment
  Industry Walkthrough scheduled 2nd June
B2M outage – Including MSATS browser, commencing 6.00am Saturday
  Participants to clear outboxes boxes by 6.00am Saturday / AEMO moves unacknowledged messages to archive folder
  MSATS browser access stopped for duration of cutover, includes NMI inquiry
B2B outage – Outage timeframe
  Review of outage requirements for B2B to allow B2B processing to resume in advance of B2M go decision
    Timing TBC, anticipated prior to 5.00pm Sunday
    In event of rollback B2B will require Outage for duration of Rollback
  Principle to minimise extent of B2B outage
B2M Metering Data restart and Backlog processing
  MDP feedback on Restart capability requested
    Responses requested if not yet provided
    Initial responses indicate scheduling by read day with minimal basic meter reading
  Friday and Saturday metering data delivered for settlement run performed Tuesday to meet data compliance timeframes
  Staggered delivery of daily files by MDPs on basis of capability.

## Slide 34: Production cutover update
Rollback Processing
  Approach refined to target reduced industry outage
  Timings updated in revised Industry Go-live Plan
  In event of rollback B2B processing will be halted during rollback process
  Reminder: Retail Industry Go-Live Plan Walk-Through session has been scheduled for 10:00am 2 June

## Slide 35: Upcoming Readiness Survey
Blaine Miner

## Slide 36: Readiness reporting – 2021 schedule
The next readiness survey will be released next Wednesday 2nd June, with the final report being distributed on Friday 25th June.
A new Participant Type has been added to this survey “Market Network Service Provider”, with applicable specific questions included
Responses are to assume a 21st June AEMO Retail go-live date
Readiness reporting | Survey released | Survey responses due | Distribute results | Discuss at RWG meeting | Discuss at PCF | Discuss at EF
Round #8 | 02-Jun-21 | 11-Jun-21 | 25-Jun-21 | 06-Jul-21 | 17-Jun-21 | 24-Jun-21
Round #9 | 04-Aug-21 | 13-Aug-21 | 27-Aug-21 | 07-Sep-21 | 19-Aug-21 | 02-Sep-21

## Slide 37: Forward Plan and Other Business
Greg Minney

## Slide 38: Upcoming Meetings AEMO | Program Calendar and Timelines
Current as at 25/05/2021

## Slide 39
Document tracker updates – in May 2021
39
The document tracker is located in the Participant toolbox under the Program Logs & Register menu option.
Where is the document tracker located?
Document/ Item | Version | Status | Type
Retail Platform Industry Go-live Plan | 1.0 | Final | Readiness
EMMS Release FAQ - October 2020 - Data Model v5.00 | 0.2 | Draft | Systems
This page will appear in all RWG packs moving forward to represent the updates that were made to 5MS and GS documents for the month.
This information is also captured within the document tracker, with recently updated documents highlighted in yellow.
Note: The Pre-dispatch sensitivities document has also been updated on the AEMO website, but as it is a BAU document it will not appear in the 5MS document log.

## Slide 40: Questions