## Slide 1: 5MS/GS Transition Focus Group #11:
Friday 29th Jan, 2021
WebEx only [details in calendar invitation]
**Please disconnect from your workplace VPN for the WebEx call**
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda **Please disconnect from your workplace VPN for the WebEx call**
NO | Indicative Time | AGENDA ITEM | Responsible
1 | 10:30 - 10:40 | Welcome and introduction | Greg Minney
2 | 10:40 - 10:50 | Previous Actions | Blaine Miner
3 | 10:50 - 11:05 | Delay to AEMO’s MDM & Settlement Solutions | Greg Minney
4 | 11:05 - 11:30 | Proposed changes to the MTP | Blaine Miner
5 | 11:30 – 11:40 | Risk Review | Greg Minney
6 | 11:40 - 11:50 | Rollout Plan Summary | Austin Tan
7 | 11:50 - 12:00 | Upcoming MTP Activities | Blaine Miner
8 | 12:00 - 12:10 | Cross boundary metering arrangements | David Ripper
9 | 12:10 - 12:15 | GLOPOOL TFG requirements | Paul Lyttle
10 | 12:15 - 12:25 | MTP CATS transaction volume management update | Blaine Miner/Paul Lyttle
11 | 12:25 - 12:30 | Next steps and general business | Greg Minney

## Slide 4: Attendees (1/2)
Organisation | Attendee | Organisation | Attendee
AEMO (Chair) | Greg Minney | Jemena | Chantal Wright
AEMO | Anne-Marie McCague | Red and Lumo Energy | Christophe Bechia
AEMO | Austin Tan | AusNet Services | Con Michailides
AEMO | Blaine Miner | Energex | Dannii Upham
AEMO | Carol Bosnjak | CitiPower and Powercor | David Hanger
AEMO | David Ripper | CitiPower and Powercor | Greg Szot
AEMO | Jim Agelopoulos | Essential Energy | Helen Rickards
AEMO | Naomi Byrnes | Origin Energy | Mario Iogha
AEMO | Paul Lyttle | Mondo | Jay Summers
AEMO | Peta Hatzikides | Evo Energy | Jeff Roberts
AEMO | Rowena Leung | Evoenergy | Joe Milazzo
Transgrid | Adam Hoare | Energy Australia | Jon Ham
Stanwell | Adam Neilson | Aurora Energy | Kevin Boutchard
TasNetworks | Adrian Honey | Jemena | Leon Vilfand
Origin Energy | Amanda Pollard | PLUS ES | Linda Blackenbury

## Slide 5: Attendees (2/2)
Organisation | Attendee | Organisation | Attendee
Jemena | Marina Bakh | CitiPower and Powercor | Ron Dittman
Red and Lumo Energy | Mark Reid | Energy Queensland | Steve Blair
Jemena | Michael Flynn | Essential Energy | Tim Lloyd
AGL | Pieter Wijtzes | CitiPower and Powercor | Trent Smith
Jemena | Rajiv Balasubramanian | IntelliHUB | Warren Van Wyk
Electranet | Ramesh Khadka | Endeavour Energy | Yi Zheng
Mondo | Richard Metherell |  | 

## Slide 6: Previous Actions
Blaine Miner

## Slide 7: Previous Actions
# | Topic | Action | Comments
10.1 | Meter Read Type Codes | AEMO to confirm the requirements re ReadTypeCodes for Type 7 and Non-contestable Unmetered Loads | Meter Read Type Code is not applicable to calculated meter types as evidenced by the first character representing either R (remote) or M (manual), hence, Type 7 and non-contestable unmetered loads are not included in this field. Refer to MSATS Standing Data Review Draft Determination and Report page 44.
10.2 | Meter Read Type Codes | AEMO to confirm the requirements re the updating of ReadTypeCodes to ‘A’ as the fourth character e.g. the successful reconfiguration of a meter to be able to support the measurement of 5min metering data or something else | 4th character identifies what interval length the meter is capable of reading. To illustrate this definition, the Metering RTC should be set to ‘RWDA’ once the metering installation has been configured to measure and store 5-minute energy data.
10.3 | Meter Read Type Codes | MPs to confirm if they plan on updating the fourth character of the meter read type code pre-9 March 2021 | Based on the responses received, none of the MPs now plan on updating the RTC to 4 characters prior to the 9th March 2021.
10.4 | Meter Read Type Codes | MPs to engage with effected Participants prior to commencing the process of updating the fourth character of the ReadTypeCode | While some MPs have initiated Participant engagement, other MPs have placed the onus on Participants to engage with them should they not be ready to receive 4 character RTCs from 9th March 2021.
10.5 | Meter Read Type Codes | TFG to confirm the indicative scale and type of impact associated with the fourth character of the meter read type code being updated pre-9 March 2021 | Two Participant did callout that their billing systems would error these standing data updates, requiring manual handling and leading to a misalignment between the market standing data and their standing data. One Participant also called out potential impacts to their Customer quoting systems.
10.6 | CATS CR volume analysis | TFG members to advise AEMO of any concerns with the provisioning of additional information, as required, to support key inputs into the industry level CATS CR volume analysis e.g. MDP type 1-3 datastream conversion to register level plans and NCONUML and cross boundary NMI creation plans | No concerns raised by responding Participants.
10.7 | CATS CR volume analysis | TFG to provide their views around the inclusion or exclusion of NCONUML CRs in the AEMO CATS CR volume analysis, noting that if these CRs are excluded then Participants would need to compile their own aggregated view of potential 5MS/GS volumes | Multiple respondents preferred the inclusion of NCONUML transaction volumes into AEMO’s analysis. Two Participants did however suggest that NCONUML volumes should be shown as separate types on the volumes graphs, to differentiate for Participants who are not impacted.
10.8 | CATS CR volume analysis | AEMO to communicate how Participant requests for increases in MSATS daily transaction limits may be best managed and shared with other Industry Participants | 
10.9 | MP and MDP Participant rollout plans | MPs and MDPs to confirm if rollout plans provided to AEMO can be shared with the TFG going forward, noting that some Participants have previously labelled as confidential | Two respondents did not wish for their rollout plans to be shared with the TFG, either presently or going forward, citing that this data is confidential and may expose commercially sensitive data to its competitors.
10.10 | Metering transition plan | AEMO to publish a new version of the MTP to communicate any recent changes | Version 1.6 attached.
10.11 | Standing Data bulk updates | TFG to advise if any assistance from AEMO is required to support bulk standing data updates re the completion of MTP activities, noting that any requests would need to go through applicable AEMO approval processes and, if approved, subsequent development activities (likely lead-time required - 6mths+) | All respondents stated that no support was required at this stage to complete 5MS/GS activities. Two respondents did however mention that support may be required to complete MSDR activities e.g. updating of the read type code for all BASIC meters and VICAMI 30min meters before October 2021. They intend on requesting this support from AEMO via the ERCF.
10.12 | GLOPOOL cutover | AEMO to include various NMI create/LR update scenarios e.g. to specify how retrospective NMI create transactions should be populated post 1 May 2022 with an effective date pre-1 May 2022, as well as any pre and post cutover activities, in its more detailed GLOPOOL ‘cutover plan’. This plan is anticipated to be developed late next year (2021). | One respondent requested for the cutover plan to be completed by April 2021

## Slide 8: Consolidated meeting actions
# | Action | Owner | Due Date
11.1 | AEMO to consider how to share rollout plans from consenting participants | AEMO | 11 February
11.2 | AEMO to investigate the possibility of circulating 5MS working group invitations to Customer Switching representative mailing list. | AEMO | 11 February
11.3 | AEMO to provide templates for net to register level datastream conversion plans, and LNSP NCONUML and cross boundary NMI creation plans | AEMO | 11 February
11.4 | AEMO to update and issue the “AEMO 5MS Functional Deployment Matrix”, in line with the new retail platform go-live date for Option 1 | AEMO | 11 February
11.5 | AEMO to issue a version of the MTP that considers Option 2 of the retail platform go-live | AEMO | 11 February
11.6 | TFG to provide feedback on how the retail platform deferral impacts their ability to support the retention of the transition start date of 9 March 2021 for the application of a four character read type code | TFG | 5 February
11.7 | TFG to provide feedback on the GLOPOOL update plan outline on slide 39, including comments on timeframes and if additional information is required | TFG | 5 February

## Slide 9: Notes (1/9)
AEMO presented the responses to the actions from TFG 10
A number of TFG members noted that they are waiting on the establishment of the MSDR data transition working group to progress preferred approaches and timings for MSATS standing data updates
In response to a TFG member query on how AEMO intended to manage the performance impact of Participant requests for increases in MSATS daily transaction limits, AEMO noted that it is ensuring that market systems are able to handle peak expected volumes, and would be monitoring the performance of the AEMO platform, noting that the B2B Hub has separately been performance tested
AEMO clarified that version 1.7a of the Metering Transition Plan assumes that the retail platform will go-live on 31 May 2021
A number of TFG members expressed a preference for AEMO to share the metering rollout plans from consenting participants. AEMO noted that the few participants that objected to the sharing of their plans represent a significant portion of tranche 2 meters, however AEMO will consider how available plans can be shared with the industry.
Action 11.1: AEMO to consider how to share metering rollout plans of consenting participants.

## Slide 10: Delay to AEMO’s MDM & Settlement Solutions
Greg Minney

## Slide 11: Retail Go-Live Delay - Introduction
On 05-Jan-21, AEMO’s 5MS Program notified participants of a delay to the Retail deployment into both pre-Prod (01-Feb) and Prod (09-Mar)
This delay was driven by 2 new issues, coupled with existing Retail timeline pressures and lack of schedule contingency
2 options for a new Retail go-live date are identified – late May and late June. Participant views are sought.
5MS commencement on 01-Oct-21 is unchanged
The AEMO 5MS team acknowledges there are implications for industry participants and the 5MS Program
PCF Discussion:
  Explain the nature of the issues encountered in the Retail stream
  Identify two Retail go-live date options and discuss pros and cons
  Review implications of delay
  Open discussion with PCF
  Review next steps

## Slide 12
Revised Retail Go-Live Timeline
Critical path timeline indicates completion of Retail stream activities for a 31-May-21 go-live
  Based on detailed planning and reasonable estimates, predicated on timely resolution of issues
Additional contingency could be added to improve certainty
  Would result in a 21-Jun-21 go-live
  Offers greater certainty in achieving Retail Go-Live date
  Better meets participant objectives of date certainty
Consequences of late June go-live
  Compresses the schedule through the remainder of the program to 5MS market go-live
  Close to Market Trial start (05-Jul-21), creates resourcing conflict if stabilisation issues occur
  Later to switch-on 5-min meter data collection capability – for AEMO, MDPs and Participants alike
  Compresses participant time for UFE soft start transition activities
Options for Consideration
  29-May-21 go-live date with 21-Jun-21 as a fallback. To be determined by a checkpoint in early March.
  21-Jun-21
AEMO preference is for Option 1
  Allows maximum time for transition activities after Retail Go-Live through to market go-live
Seeking participant views
  Input is requested by Friday 05-Feb-21
  Exec forum to be scheduled for 11-Feb-21 at 13:00

## Slide 13: 5MS Program Timeline – Option 1 Level 1 and External Level 2 Milestones 1/2
Current as at 15-01-2021
R3 Go-live : 31/05/21
Note: Pre-prod and Settlement dates under review

## Slide 14: Initial Impact Assessment Key dates
Area | Original Date | New Date | Implication
5MS Rule Commencement | 1 Oct 21 | No change | No change to 5MS market start date Risk assessment requires review and re-rating to reflect revised schedule
UFE soft start | 1 Oct 21 | No change | Compresses available DNSP population time for some UFE Standing data activities and may result in re-scheduling of activities Leads to potentially less accurate UFE on 1 Oct 21 soft start
GS Rule Commencement | 1 May 22 | No change | No impact expected
5MS Market Trial | 5 July 21 | No change | No change to start date for 5MS market trial Acknowledge heightened risks around timely commencement
Dispatch IT Go-Live | 1 Apr 21 | No change | No impact expected
Settlements IT Go-Live | 15 Apr 21 | Mid-May | Will now go-live before Retail MDM Further testing required to allow for this Date currently being finalised, mid-May expected
Regulatory roadmap | Various | No change | No change currently anticipated to any dates: Customer Switching, WDR Regulatory roadmap session currently being arranged at which the overall view can be reviewed

## Slide 15: Impacts to Participants
AEMO will endeavour to minimise impacts to participant programmes in meeting overall 5MS and GS rule commencements. We anticipate many of the impacts will entail replanning of activity in-line with available market capability. Key areas impacted may include:
At the TFG scheduled for 29-Jan, impact on the Metering Transition Plan Activities (1-3) will be undertaken
ITWG will realign activity and participant availability for Invitation Industry Test
AEMO will reissue Retail Industry Go-Live plan to support rescheduling of new cutover dates
Readiness Survey #6 will include specific questions to consolidate view of industry impacts
Participants are asked to identify other areas requiring industry consideration at upcoming RWG
  Timing of metering data delivery migration for interval meters to MDFF Format
  Adjusting the plans for the commencement of 5-minute metering data delivery to AEMO, and potentially retailers/ DNSPs
  Adjusting the timing for the population of NMI Standing data and NCONUML - for those activities with direct capability dependency on Retail Platform deployment
  Timing of participant implementation of capability delivered with Retail Platform, including B2M via API capability
  Rescheduling Industry Test involvement and resourcing
  Rescheduling planned cutover activity

## Slide 16: Industry Next Steps
Feedback sought from participants (via PCF) by Friday 05 Feb 2021
  Preferred option, why, strength of views
  Via email 5MS@aemo.com.au
  AEMO 5MS Team is available for discussion on implications
TFG
  Provide input through discussion at todays session
  AEMO to consolidate feedback / impacts as input to Executive Forum
    Notes circulated to TFG 2/2 to ensure consistency of findings
  Updated MTP to be used as basis for next round of readiness reporting – issued 2/2
RWG
  Respond to Readiness Survey on basis of agreed options- noting new risks/ dependencies
Executive Forum
  Enable Execs to comment/question
  Summarise options feedback
  Advise of decision
  Date/time: 11 Feb 2021 at 13:00 ADST

## Slide 17: Notes (2/9)
AEMO provided an overview of the delay to AEMO’s MDM & Settlement Solutions
TFG members suggested that industry members implementing Customer Switching should be included in 5MS discussions, so that they could be aware of any 5MS program changes that may impact Customer Switching. AEMO noted that it will investigate the possibility of circulating 5MS working group invitations to the Customer Switching representative mailing list.
Action 11.2: AEMO to investigate the possibility of circulating 5MS working group invitations to the Customer Switching representative mailing list

## Slide 18: Proposed Changes to the MTP
Blaine Miner

## Slide 19: Proposed Changes to the MTP
Category | Activity ID | Activity Description | Change Type | Change Detail
Meter Installation & Reconfiguration | A19a | Provide progress and amendments to ‘Known’ Cross Boundary forward plans to AEMO every 2mths | New activity | MC Rollout plans required for Cross Boundary meters (Known) meters
 | A31 | For any registered ‘Special Site’ (as defined in the ‘Special Sites and Technology Related conditions within the National Electricity Market Version 1.2) or any Logical NMI, update and distribute algorithms adjusted for introduction of 5 minute interval length to AEMO, FRMP and LNSP for approval. | Change to description | Addition of “…or any Logical NMI…”
Meter Data Delivery | A32a, A37a, A42a, A52b, A58b, A64b, A70b, A82a | Provide datastream conversion plans to convert Net datastreams to register level to AEMO every 2mths | New activities | MDPs to provide conversion plans from 1 Mar 2021 every 2mths
 | A35, A41, A46, A50, A56, A62, A68, A74, A86, A92 | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVarh)) energy metering data as applicable) | Change Transition Start Date | Transition Start Date changed from 1 Apr 2021 to 22 June 2021
 | A52a, A58a, A64a, A70a | Provide progress and amendments to forward plans to AEMO and industry every 2mths | Change in frequency | Proposing to change frequency to every 2mths, to align to other rollout plan requirements
 | A36, A40, A45, A51, A57, A63, A69, A75 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021
 | A94 | Meter data delivery of 30min interval reads only in MDFF to AEMO | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021
MSATS Standing Data Creation & Maintenance | A95, A96, A97 | Create Cross Boundary NMIs, including associated datastreams and registers | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021
 | A95a, A99a | Provide NMI Create plans for Cross Boundary and NCONUML to AEMO every 2mths | New activities | NMI Create plans to be provided from 1 Mar 2021

## Slide 20: Proposed Changes to the MTP
Category | Activity ID | Activity Description | Change Type | Change Detail
MSATS Standing Data Creation & Maintenance | A99, A100, A101 | Create NCONUML NMIs, including associated datastreams and registers | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021
 | A102, A104, A106, A108, A110, A112, A114 | Ensure capability to receive and process new NMI classification codes | Change Transition End Date | Transition End Date changed from 30 Apr 2021 to 31 May 2021
 | A103, A105, A107, A109, A111, A113, A115 | Update NMI Class Codes for existing NMIs as required | Change Transition Start Date | Transition Start Date changed from 1 May 2021 to 1 June 2021
 | A119 | Ensure all Sample meters have a Datastream type code of 'P' and are attached to a Profile | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021
 | A120 | Update Datastream type codes from 1-4 to 'I' or 'N' as required | Change Transition Start Date | Transition Start Date changed from 9 Mar 2021 to 1 June 2021

## Slide 21: Notes (3/9)
AEMO presented changes to the MTP based on a new retail platform go-live of 31 May 2021 (Option 1)
AEMO clarified that the request for MDPs to provide net to register level datastream conversion plans, and for LNSPs to provide NCONUML and cross boundary NMI creation plans were to understand potential upcoming CATS transaction volumes, and to assess if the industry is on track with the metering transition and market commencement requirements. AEMO will be providing a template to facilitate the provision of this information.
AEMO clarified that some MDPs have informed AEMO that they are not converting net to register level datastreams in alignment with their 5 minute metering data rollout plans. Therefore AEMO is requesting net to register level datastream conversion plans. AEMO will be providing a template to facilitate the provision of this information.
In response to TFG member asking about DNSPs progress in having NCONUML profile calculations approved in line with MTP timeframes, a number of participants indicated that their processes were in progress and proceeding in line with expected timeframes.
Action 11.3: AEMO to provide templates for net to register level datastream conversion plans, and LNSP NCONUML and cross boundary NMI creation plans
Action 11.4: AEMO to update and issue the “AEMO 5MS Functional Deployment Matrix”, in line with the new retail platform go-live date for Option 1

## Slide 22: Notes (4/9)
AEMO noted that Option 1 of the retail platform delay currently appears to be Industry’s preferred option and that industry should respond to the sixth readiness survey on that basis e.g. based on the content in MTP v1.7a.
In response to a participant suggestion, AEMO agreed that a MTP version (v1.7b) considering Option 2 of the retail platform go-live will be released to assist industry planning.
In response to a participant query, AEMO noted that the transition start date for the population of the fourth character of the read type code has been proposed to be retained as 9 March 2021. The rationale for this retention is that the updating of this code has no dependency on the implementation of AEMO’s new MDM solution. It was acknowledged that the associated procedures currently accommodate this approach and that there was no technical dependency on the new retail platform for this activity to be undertaken.
A TFG member noted that the retail platform go-live deferral will also impact the timing of their systems ability to process updates to the read type code (RTC). Another TFG member noted that their systems will be able to receive updates to the RTC for Tranche 1 meters from 9 March 2021, however a later start date is preferred.
Action 11.5: AEMO to issue a version of the MTP (v1.7b) that considers Option 2 of the retail platform go-live (v1.7b)
Action 11.6: TFG to provide feedback on how the retail platform deferral impacts their ability to support the retention of the transition start date of 9 March 2021 for the application of a four character read type code

## Slide 23: Risk Review
Greg Minney

## Slide 24: MTP related risks that are impacted by change to Retail Go-Live
Risk ID | Description | Residual Rating (Current) | Comments
R14 | Metering implementation activities affecting participant business functions during transitional period Potential for disconnect between Procedure effective dates and required transitional activities. Need to consider interdependencies between Participants (e.g. MDPs and Retailers) | Medium | This risk was flagged for review by the RWG AEMO does not consider that the changes to the Retail go-live dates impact this risk Therefore, AEMO proposes that the trend should return to stable. Controls: - Metering Transition Plan - Industry Readiness Reporting - Industry engagement/visibility of requirements – RWG and TFG
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 25: New Risks Raised at PCF Relating to MTP
Risk ID | Description | Inherent Rating | Residual Rating | Comments
R35 (NEW) | Compression of window for transition 5-min metering data delivery There is a risk that the compression of the Metering Transition Plan results in the transition of NMIs to 5-min granularity at an unsustainable rate | Significant | Medium | Inherent Likelihood: Possible Inherent Consequence: Major Actions: Update Metering Transition Plan to reflect capability availability dates Support delivery of 5-minute metering data from Retail platform deployment maximise transition window – under consideration Align Participant readiness reporting to updated MTP dates Industry to prioritise activation of 5MS essential meters when planning rollouts Monitor participant impacts and programs via readiness reporting and RWG interaction Residual Likelihood: Unlikely Residual Consequence: Major
R36 (NEW) | Compressed MTP transition windows for the population of NCONUML NMIs impacts the accuracy of UFE Reporting Risk that a subset of the MTP standing data and NCONUML population activities are dependent on capability made available by the deployment of the Retail Platform, will not be completed prior to the UFE soft start on 1/10/21 resulting in less available data to calculate UFE accurately | Medium | Medium | Inherent Likelihood: Possible Inherent Consequence: Moderate Actions: Update Metering Transition Plan to reflect impacted activity transition windows for participants Assessment of accuracy impacts for UFE based on participant readiness reporting against revised timeframes Residual Likelihood: Unlikely Residual Consequence: Moderate
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​
Subject to review by PCF on 28/02

## Slide 26: Notes (5/9)
AEMO presented MTP related risks that are impacted by the deferral of the Retail Go-Live, noting the actions AEMO will be taking to manage these risks. It was noted that R35 and R36 will be reviewed at the PCF on 28 February 2021.
AEMO requested participants to review the proposed updates to the readiness risks but unless otherwise advised would consider the updates as confirmed

## Slide 27: Rollout Plan Summary
Austin Tan

## Slide 28: Metering rollout plans – Industry response rate (Tranche 1 meters)
Organisation | Rollout plan provided at some stage? | Rollout plan update provided in latest round?
Mondo | Y | Y
Origin | Y | Y
PLUS ES | Y | Y
TransGrid | Y | N
Yurika | Y | N
Ausgrid | Y* | Y*
AusNet Services | Y* | Y*
ElectraNet | Y* | N
Intellihub | Y* | N
Powerlink | Y* | N
Metropolis | N | N
Powermetric | N | N
TasNetworks | N | N
Out of the 13 top MCs with Tranche 1 meters, 10 MCs representing approximately 90% of Tranche 1 meters have provided their metering rollout plans, five of which are in the template format. Only three MCs have provided updates on their rollout plan in the latest update.
Update 10/2/2021 - Slide updated to reflect latest information

## Slide 29: Metering rollout plans – Industry response rate (Tranche 2 meters)
Out of the 14 MDPs with Tranche 2 meters, 10 have provided their Tranche 2 metering rollout plan, nine of which are in the template format. Only seven MDPs have provided updates on their rollout plan in the latest update.
Organisation | Rollout plan provided at some stage? | Rollout plan update provided in latest round?
CitiPower Powercor | Y | Y
Jemena | Y | Y
Mondo | Y | Y
PLUS ES | Y | Y
Secure Meters | Y | Y
United Energy | Y | Y
Vector | Y | Y
Ausnet Services | Y* | Y*
Intellihub | Y | N
Yurika | Y | N
ActewAGL Distribution | N | N
Metropolis Metering Services | N | N
Powermetric | N | N
Update 10/2/2021 - Slide updated to reflect latest information

## Slide 30: Metering rollout plan provision schedule
Update # | Provide rollout plans by
3 | 01-Mar-21
4 | 01-May-21
5 | 01-Jul-21
6 | 01-Sep-21
7 | 01-Nov-21
8 | 01-Jan-22
9 | 01-Mar-22
10 | 01-May-22
11 | 01-Jul-22
12 | 01-Sep-22
13 | 01-Nov-22
Please provide metering rollout plan updates according to the below schedule. Please include relevant participant IDs when submitting rollout plans.
This schedule applies for all metering rollout plans:
  MCs to provide MP installation and reconfiguration plans for Type 1-3, subset of type 4 meters, type 7 and known cross boundary
  MDP 5-min data delivery for new and repl. 4/4A, VIC AMI, SAMPLE meters
  MDP conversion plans for Type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level
  LNSP NCONUML and cross boundary NMI creation plans

## Slide 31: Notes (6/9)
AEMO presented a summary of Tranche 1 and Tranche 2 metering rollout plans, noting that participants are expected to provide updates on their rollout plans according to the presented schedule
A number of participants indicated that the slides did not represent their responses correctly as they had provided the required updates
AEMO indicated that if there was “no change” to a Participant’s prior schedule that an email to that effect would be deemed sufficient

## Slide 32: Upcoming MTP Activities
Blaine Miner

## Slide 33: Upcoming MTP Activities
Description | Date | Activity ID
MPs to provide progress and amendments to forward plans for Type 1-3, subset of 4 and ‘known’ cross boundary meters to AEMO | Due by 1 Mar 2021 | A3a, A8a, A13a, A19a
MDPs to provide progress and amendments to forward plans for Type 4, 4A, VICAMI and Sample meters to AEMO | Due by 1 Mar 2021 | A52a, A58a, A64a, A70a
MDPs to provide datastream conversion plans to convert Net datastreams to register level | Due by 1 Mar 2021 | A32a, A37a, A42a
LNSPs to provide NMI Create plans for Cross Boundary and NCONUMLs to AEMO | Due by 1 Mar 2021 | A95a, A99a
MCs to provide visibility of approach & timeframe for required new cross boundary metering installation | Due by 31 Mar 2021 | A23
MCs to ensure that details of the Inventory Table, calculation methodologies and Agreed Loads are agreed prior to implementation by relevant Registered Participants | Due by 31 Mar 2021 | A87
Participants to establish agreements to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO, as applicable | Due by 31 May 2021 | A32, A37, A42, A47, A53, A59, A65, A71, A84, A88
AEMO to establish agreements with MDPs to allow the delivery of 5min metering data pre 1 Oct 2021 for B2M purposes | Due by 31 May 2021 | A34, A39, A44, A49, A55, A61, A67, A73, A85, A91
MDPs to create/convert export and import Active (kWh) and Reactive (kVarh) energy datastreams, where applicable, in the CNDS table | Start from 1 June 2021 | A36, A40, AA45, A51, A57, AA63, A69, A75
MPs to update the Meter Read Type code with RWDA, where applicable | Start from 1 June 2021 | A36b, A40b, A45b, A51a, A57b, A63b, A69b, A75b
MDPs to deliver tier 1 basic meter metering data (Actuals, Subs and Forward Estimates) to AEMO | Due by 30 June 2021 | A93

## Slide 34: Notes (7/9)
AEMO presented the upcoming MTP activities, noting that the start date for the updating of the RTC should read 9 March 2021 and not 1 June 2021
In response to a query from AEMO, the TFG did not raise any concerns with the progress of defining the agreed profiles for NCONUML by 1 May 2021.

## Slide 35: Cross boundary metering arrangements
David Ripper

## Slide 36: Cross Boundary Categories
Cross Boundary Supply Categories
Cross Boundary connection points in regular use
  Circuit connecting supply DB’s distribution network to receiving DB’s distribution network (Guideline 3.3.1, 3.3.2 and 3.3.3)
  Service connecting end user connection point in receiving DB’s Local Area to supply DB’s distribution network (Guideline 3.3.4)
Cross Boundary circuit connecting supply and receiving distribution networks, used infrequently under emergency conditions (Guideline 3.4)

## Slide 37: Cross Boundary Conditions and Requirements
Cross Boundary circuit connecting supply and receiving distribution networks
Cross Boundary connection point NMI
DNSPs, in consultation with AEMO, will create Cross Boundary NMI
LNSP = Supply DB Participant ID
TNI = Supply DB TNI
NMI Classification = XBOUNDRY
NSP2 = Receiving DB Participant ID – populated by AEMO
TNI2 populated by AEMO
NMIs connected downstream od Cross Boundary connection point
LNSP = receiving DB Participant ID
TNI = TNI2 code value from Cross Boundary NMI
No NSP2
Normal NMI Classification codes – SMALL, LARGE, etc.

## Slide 38: Cross Boundary Conditions and Requirements
Cross Boundary service connecting end user connection point in receiving DB’s Local Area to supply DB’s distribution network
DNSPs must provide AEMO with End User NMIs identifying LNSP and NSP2
LNSP = Receiving DB Participant ID
TNI = Supply DB TNI
NSP2 = Supply DB Participant ID – populated by AEMO
No TNI2
Normal NMI Classification codes – SMALL, LARGE, etc.
Receiving DB must notify AEMO when the service is no longer connected to supply DB’s distribution network – AEMO to re-assign NSP2 value

## Slide 39: Cross Boundary Conditions and Requirements
Cross Boundary – emergency conditions
Further analysis to develop appropriate methods of measuring these energy flows. Information required includes:
Identification of each emergency connection
Frequency of operation
Description and start and end dates of each energy transfer incident
Energy transfer direction (LNSP A to LNSP B and TNI XXXX to TNI YYYY)
Identification of metering installation requirements
Available forms of energy measurement
Measured or estimated energy volume transferred and assessment methodology
NMIs impacted by energy transfer
Identify MDPs with capability to collate energy transfer volumes into 5-minute trading intervals

## Slide 40: Cross Boundary Supply Cost Recovery and Ring-Fencing
AEMC (GS Rule Final Determination) expects cost incurred by DNSPs performing Cross Boundary MC role or engaging MC recovered as standard control service.
AER confirmed this to be a standard control service.
AER also noted that the role of Metering Coordinator (MC) for the Cross Boundary service is different to the distributor’s role as MC for types 5&6 meters which is classified as an alternative control service.
The AER considers there are no ring-fencing issues because there are no substitutes and no prospect for the development of competition.

## Slide 41: Cross Boundary Supply MC Registration
As the DNSP’s role as MC for cross boundary connections differs from their role as MC type 5 and 6 metering installations, a new form of MC Registration will be needed.
AEMO is reviewing the following documents to identify changes to be made for DNSP Cross Boundary MC Registration. Considering requirement to identify all Cross Boundary NMIs for which the DNSP MC would be responsible (similar to TNSP MC Registration requirement).
Guide to the Role of the Metering Coordinator
Application for Registration as a Metering Coordinator in the NEM
General Application Guide – Guide to Application Registration Forms in the NEM
AEMO also reviewing whether TNSP MC Registration can be used for Cross Boundary NMIs.
Aiming for review completion by end Feb 2021.

## Slide 42: Notes (8/9)
AEMO presented the Cross Boundary metering arrangements, including the Cross Boundary Categories, Cross Boundary Conditions and Requirements, Cross Boundary Supply Cost Recovery and Ring-Fencing, and Cross Boundary Supply MC Registration
In response to a participant query, AEMO noted that the final version of the Cross-boundary supply guidelines is expected late February 2021 or early March 2021.

## Slide 43: GLOPOOL Update
Paul Lyttle

## Slide 44: GLOPOOL Update
AEMO’s suggested time frames
  What additional information are participants looking to be included in plan?
  Timeframes are for discussion.

## Slide 45: Notes (9/9)
AEMO presented an update on the implementation of the GLOPOOL update, including an outline of the GLOPOOL update plan.
Action 11.7: TFG to provide feedback on the GLOPOOL update plan outline on slide 39, including comments on timeframes and if additional information is required

## Slide 46: MTP CATS Transaction Volume Management Update
Blaine Miner

## Slide 47: Objective
The objective of the analysis is to create a consolidated Industry view of indicative transaction volumes relating to the MTP activities
  Detailed at a monthly level
  Spanning from today to Dec 2022
The analysis is being performed to:
  Support Participant and AEMO system and general business impact assessments
  Facilitate Participant to Participant engagements
  Create appropriate inputs into the MSDR Data Transition working group
Questions:
  What level should this analysis be performed at for industry overview: CR transaction, notification, acknowledgement?
  Do MDPs intend to convert datastreams to register level as they convert metering data delivery to 5min for type 4, 4A and VicAMI meters?

## Slide 48: Scope
In-scope considerations:
  By 31 Aug 2021
    Convert type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level
    Update type 1-3, subset type 4, type 7 and existing cross boundary ReadTypeCodes to ‘A’, where required
    Create NCONUML and ‘new’ Cross boundary NMIs, Registers and Datastreams
    Update NMI Classification codes, where required
    Create/activate Basic meter 1st tier datastreams
    Update VIC TUoS datastreams from 1-4 to ‘N’
  By 30 Nov 2022
    Update new and replacement type 4, 4A and VIC AMI meter ReadTypeCodes to ‘A’, where applicable
Out-of-scope items:
  MSDR standing data updates
  Other standing data updates associated to:
    Market reform initiatives
    Non-market based initiatives
      E.g. Participant based activities/initiatives

## Slide 49: Required Participant Inputs
In-scope Item | Inputs Currently Being Received | Additional Inputs Required
Convert type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level |  | MDP conversion plans for Type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level
Update type 1-3, subset type 4, type 7 and existing cross boundary ReadTypeCodes to ‘A’, where required | MP Type 1-3 reconfiguration plans | MP Reconfiguration plans to also include subset type 4, type 7 and existing cross boundary
Create NCONUML and ‘new’ Cross boundary NMIs, Registers and Datastreams |  | LNSP NCONUML and cross boundary NMI creation plans
Update NMI Classification codes, where required |  | TBD
Create/activate basic meter 1st tier datastreams | Participant information as requested | 
Update VIC TUoS datastreams from 1-4 to ‘N’ | MDP Type 4, 4A and VIC AMI rollout plans | 
Update new and replacement type 4, 4A and VIC AMI meter ReadTypeCodes to ‘A’, where applicable | MDP Type 4, 4A and VIC AMI rollout plans | 

## Slide 50: Next steps and general business
Greg Minney

## Slide 51: Next steps & general business
Next TFG 11th of Feb
  Agenda items
    CATS transaction volume assumption validation
    MSDR Data Transition WG engagement

## Slide 52: Thank you for your attendance and participation!