## Slide 1: 5MS/GS Transition Focus Group #12:
Thursday 11th Feb 2021
WebEx only [details in calendar invitation]
**Please disconnect from your workplace VPN for the WebEx call**
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda **Please disconnect from your workplace VPN for the WebEx call**
NO | Indicative Time | AGENDA ITEM | Responsible
1 | 10:30 - 10:40 | Welcome and introduction | Greg Minney
2 | 10:40 - 10:50 | Previous Actions | Blaine Miner
3 | 10:50 - 11:10 | Feedback from Industry re AEMO’s proposed Go-live delays | Greg Minney
4 | 11:10 - 11:20 | Upcoming MTP Activities | Blaine Miner
5 | 11:20 - 11:50 | MTP CATS transaction volume management assumptions | Blaine Miner/Paul Lyttle
6 | 11:50 - 12:00 | Next steps and general business | Greg Minney

## Slide 4: Previous Actions
Blaine Miner

## Slide 5: Previous Actions
# | Topic | Action | Owner | Comments
11.1 | Metering rollout plans | AEMO to consider how to share rollout plans from consenting participants | AEMO | 
11.2 | Customer Switching | AEMO to investigate the possibility of circulating 5MS working group invitations to Customer Switching representative mailing list. | AEMO | AEMO does not hold a Customer Switching mailing list. Engagement for CS takes place through ERCF. Participants are welcome to forward 5MS materials to their CS reps or to email us at 5MS@aemo.com.au and sign reps up to the relevant working groups.
11.3 | Metering rollout plans | AEMO to provide templates for net to register level datastream conversion plans, and LNSP NCONUML and cross boundary NMI creation plans | AEMO | Update to be provided at this meeting
11.4 | Retail platform go-live | AEMO to update and issue the “AEMO 5MS Functional Deployment Matrix”, in line with the new retail platform Option 1 go-live date | AEMO | Update to be provided at this meeting
11.5 | Metering Transition Plan | AEMO to issue a version of the MTP that considers Option 2 of the retail platform go-live | AEMO | Completed – circulated 29 Jan
11.6 | Read type code update | TFG to provide feedback on how the retail platform deferral impacts their ability to support the retention of the transition start date of 9 March 2021 for the application of a four character read type code | TFG | Summary of received feedback to be provided at this meeting
11.7 | GLOPOOL update | TFG to provide feedback on the GLOPOOL update plan outline on slide 39, including comments on timeframes and if additional information is required | TFG | Summary of received feedback to be provided at this meeting

## Slide 6: Feedback from Industry re AEMO’s proposed Go-live delays
Greg Minney

## Slide 7: Summary of feedback received to date
Feedback received from 15 participants all in favour of May 31 go-live with March checkpoint
No participant has identified a blocker with either date, but a number of participants have flagged the earlier date as preferred to provide additional time for participant testing and other readiness activities
Earliest possible deployment to pre-prod would be well received
Some Participants have requested that in the case where 31-May-21 becomes unfeasible, AEMO will consider going live as soon after the 31-May-21 as possible rather than reverting directly to Option 2 (21-Jun-21)
MTP impacts understood, participants assessing changes to their programs and transition timings
Clarity on checkpoint approach, criteria and timings to be provided to industry
Participant concerns on impact to delivery and timing to other regulatory reforms
Participant changes may be required to transition plans (timing and approach) to mitigate capacity concerns
Approaches and environment support to conduct bi-lateral testing being evaluated by participants to support their planned timelines
Updated

## Slide 8: Retail Go-Live Dates
Confirmation of the Retail Go-Live dates and the Settlements Go-Live dates will be given at the 5MS Executive Forum on 11-Feb-21, with the pack being circulated on 08-Feb-21
TFG will be provided with an update.

## Slide 9: Upcoming MTP Activities
Blaine Miner

## Slide 10: Upcoming MTP Activities (Assumes Option 1 MDM Go-Live Dates)
Description | Date | Activity ID
MPs to provide progress and amendments to forward plans for Type 1-3, subset of 4 and ‘known’ cross boundary meters to AEMO | By 1 March 2021 | A3a, A8a, A13a, A19a
MDPs to provide progress and amendments to forward plans for Type 4, 4A, VICAMI and Sample meters to AEMO | By 1 March 2021 | A52a, A58a, A64a, A70a
MDPs to provide datastream conversion plans to convert Net datastreams to register level | By 1 March 2021 | A32a, A37a, A42a
LNSPs to provide NMI Create plans for Cross Boundary and NCONUMLs to AEMO | By 1 March 2021 | A95a, A99a
MPs to update the Meter Read Type code with RWDA or RWDD, as applicable | From 9 March 2021 | A36b, A40b, A45b, A51a, A57b, A63b, A69b, A75b
MCs to ensure that details of the Inventory Table, calculation methodologies and Agreed Loads are agreed prior to implementation by relevant Registered Participants | By 31 March 2021 | A87
MCs to provide visibility of the approach / timeframe for required meter replacement or reconfiguration for ‘Unknown’ Cross Boundary meters | By 31 March 2021 | A23
Participants to establish agreements to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO, as applicable | By 31 May 2021 | A32, A37, A42, A47, A53, A59, A65, A71, A84, A88
AEMO to establish agreements with MDPs to allow the delivery of 5min metering data pre 1 Oct 2021 for B2M purposes | By 31 May 2021 | A34, A39, A44, A49, A55, A61, A67, A73, A85, A91
MDPs to create/convert export and import Active (kWh) and Reactive (kVarh) energy datastreams, where applicable, in the CNDS table | From 31 May 2021 | A36, A40, AA45, A51, A57, AA63, A69, A75
MDPs to deliver tier 1 basic meter metering data (Actuals, Subs and Forward Estimates) to AEMO | By 30 June 2021 | A93

## Slide 11: Consent to Distribute Roll-out Plans
Participant | Plans Previously Rec’d | Yes/No/ No Response
ActewAGL Dist. | No | No Response
Ausgrid | Yes | No Response
AusNet Services | Yes | No Response
CitiPower Powercor | Yes | Yes
ElectraNet | Yes | No Response
Intellihub | Yes | No
Jemena | Yes | No Response
Metropolis | No | No Response
Mondo | Yes | No
Participant | Plans Previously Rec’d | Yes/No/ No Response
Origin | Yes | No Response
Powerlink | Yes | No Response
Powermetric | No | No Response
PLUS ES | Yes | Yes
Secure Meters | Yes | No Response
TransGrid | Yes | No Response
United Energy | Yes | Yes
Vector | Yes | No
Yurika (MD) | Yes | Yes
Notes:
Please let us know if your organisation's position is not correctly reflected in the table above
Only aggregated monthly volumes are planned to be distributed to the RWG/TFG from consenting Participants only

## Slide 12: MTP CATS Transaction Volume Management Assumptions
Blaine Miner & Paul Lyttle

## Slide 13: Objective
The objective of the analysis is to create a consolidated Industry view of indicative transaction volumes relating to the MTP activities
  Detailed at a monthly level
  Spanning from today to Dec 2022
The analysis is being performed to:
  Support Participant and AEMO system and general business impact assessments
  Facilitate Participant to Participant engagements
  Create appropriate inputs into the MSDR Data Transition working group

## Slide 14: Scope
In-scope considerations:
  By 31 Aug 2021
    Convert type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level
    Update type 1-3, subset type 4 and existing cross boundary connection point ReadTypeCodes to ‘A’ (or ‘D’ where applicable)
    Create NCONUML and ‘new’ Cross boundary NMIs, Registers and Datastreams
    Update NMI Classification codes, where required
    Create/activate Basic meter 1st tier datastreams
    Update VIC TUoS datastreams from 1-4 to ‘N’
  By 30 Nov 2022
    Update new and replacement type 4, 4A and VIC AMI meter ReadTypeCodes to ‘A’, where applicable
Out-of-scope items:
  MSDR standing data updates
  Other standing data updates associated to:
    Market reform initiatives
    Non-market based initiatives
      E.g. Participant based activities/initiatives

## Slide 15: Required Participant Inputs
In-scope Item | Inputs Currently Being Received | Additional Inputs Required
Convert type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level |  | MDP conversion plans for Type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level
Update type 1-3, subset type 4, type 7 and existing cross boundary ReadTypeCodes to ‘A’ (or D where applicable) | MP Type 1-3 reconfiguration plans | MP Reconfiguration plans to also include subset type 4 and existing cross boundary connection points
Create NCONUML and ‘new’ Cross boundary NMIs, Registers and Datastreams |  | LNSP NCONUML and cross boundary NMI creation plans
Update NMI Classification codes, where required |  | TBD
Create/activate basic meter 1st tier datastreams | Participant information as requested | 
Update VIC TUoS datastreams from 1-4 to ‘N’ | MDP Type 4, 4A and VIC AMI rollout plans | 
Update new and replacement type 4, 4A and VIC AMI meter ReadTypeCodes to ‘A’, where applicable | MDP Type 4, 4A and VIC AMI rollout plans | 

## Slide 16: Tranche 1 and Tranche 2 Definitions
Tranche 1
  Meter types whose MTP activities are to be completed by 1 Oct 2021
    Type 1-3
    Subset of type 4 meters - TNI, Market Generator or SGA
    Cross Boundary meters
    Non-contestable unmetered loads
    Type 7
Tranche 2
  Meter types whose MTP activities are to be completed by 1 Dec 2022
    New and Replacement Type 4 from 1 Dec 2018
    New and Replacement Type 4A from 1 Dec 2019
    New and Replacement VICAMI from 1 Dec 2018
    New and Replacement Sample from 1 Dec 2018
Note, as discussed previously:
  Only MTP related transaction volume estimates have been included in this analysis i.e. assumptions regarding BAU and other initiative-based transaction volumes have not been included
  TFG estimates will be provided to the MSDR Data Transition WG for their consideration

## Slide 17: Transaction Volume Analysis - Current Assumptions and Inputs
Tranche | Category | Assumption(s) | Input(s)
1 | Reconfiguration/ replacement of meters | Read Type Code updates to occur from 9 Mar 2021 RTCs to be updated as meters are reconfigured Noting that Meters reconfigured pre-9 March assumed to be updated in March One CR30xx CATS transaction per RTC update | MC/MP rollout plans
1 | Transition of meters to 5min metering data delivery | No CATS transactions required | N/A
1 | Conversion of Net to Register Level datastreams | Two CR40xx CATS transactions expected One to deactivate the Net datastream and one to active the register level datastreams | MDP datastream conversion plans
1 | Creation of NCONUML and Cross Boundary NMIs | One-step NMI create process i.e. NMIs are created post new NMI Class Codes being deployed to Production Corresponding datastreams and registers are created within the same month as the NMI is planned to be created Three CATS transactions per NMI CR20xx to create the NMI CR40xx to create the datastream(s) CR30xx to create the Register(s) Assumes single CR25xx will not be used by Participants Is this a valid assumption? | LNSP NCONUML and Cross Boundary NMI creation plans

## Slide 18: Transaction Volume Analysis - Current Assumptions and Inputs
Tranche | Category | Assumption(s) | Input(s)
1 | Activation of Basic meter datastreams | Smooth transition between Jan and June 2021 with simple ramp up and ramp down assumptions One CATS transaction per activation (CR40xx) | MSATS extracts
1 | New NMI Classification code updates for existing NMIs | Smooth transition between June and Aug 2021 One CATS transaction per NMI update (CR50xx) | MSATS extracts

## Slide 19: Transaction Volume Analysis - Current Assumptions and Inputs
Tranche | Category | Assumption(s) | Input(s)
2 | Reconfiguration/ replacement of meters | Read Type Code updates to occur from 9 Mar 2021 RTCs to be updated as meters are reconfigured Noting that Meters reconfigured pre-9 March assumed to be updated in March One CR30xx CATS transaction per RTC update | MDP rollout plans
2 | Transition of meters to 5min metering data delivery | No CATS transactions required | MDP rollout plans
2 | Conversion of Net to Register Level datastreams | Two CR40xx CATS transactions expected One to deactivate the Net datastream and one to active the register level datastream | MDP datastream conversion plans
2 | Creation of residual NCONUML and Cross Boundary NMIs | One-step NMI create process i.e. NMIs are created post new NMI Class Codes being deployed to Production Corresponding datastreams and registers are created within the same month as the NMI is planned to be created Three CATS transactions per NMI CR20xx to create the NMI CR40xx to create the datastream(s) CR30xx to create the Register(s) Assumes single CR25xx will not be used by Participants Is this a valid assumption? | LNSP NCONUML and Cross Boundary NMI creation plans

## Slide 20: Transaction Volume Analysis - Current Assumptions and Inputs
Tranche | Category | Assumption(s) | Input(s)
2 | Activation of Basic meter datastreams | N/A Updates have occurred pre-Oct 2021 | N/A
2 | New NMI Classification codes for existing NMIs | N/A Updates have occurred pre-Oct 2021 | N/A

## Slide 21: Next steps and general business
Greg Minney

## Slide 22: Next steps & general business
Readiness Survey responses due Friday 12 Feb 2021
Initial MSDR WG meetings expected to be called for late March and late April
Next TFG scheduled for 11 March
  Agenda items for next meeting?
    GLOPOOL Introduction planning e.g. scenarios

## Slide 23: Thank you for your attendance and participation!