## Slide 1: 5MS/GS Transition Focus Group #8:
Wednesday 29th July, 2020
WebEx only [details in calendar invitation]
**Please disconnect from your workplace VPN for the WebEx call**
This slide pack was developed for the Transition Focus Group meeting. This version of the slides has been annotated with notes from the meeting. These additional notes are either in blue text or are on new slides that have a yellow background.

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Attendees
Organisation | Name
ActEWAGL | Matt Porter
AEMO | Anne-Marie McCague
AEMO | Austin Tan
AEMO | Blaine Miner
AEMO | Carol B
AEMO | Craig Shelley
AEMO | Emily Brodie
AEMO | Greg Minney
AEMO | Liz Bernhardt
AEMO | Meghan Bibby
AEMO | Paul Lyttle
AGL | Pieter
Alinta | Natasha Rajdev
Organisation | Name
Alinta | Soham Roy Chaudhuri
Aurora | Kevin Boutchard
AusNet | Con Michailides
Citipower/Powercor | Greg Szot
Citipower/Powercor | Mark Pilkington
Endeavour | Dino Ou
Energy Queensland | Nicole Bright
EnergyAustralia | Jon Ham
Engie | Andrew Lenga
ERM Power | Rob Oshlack
ERM Power | Sharleen Flanagan
Essential Energy | Tim Lloyd
EvoEnergy | Jeff Roberts
Organisation | Name
Intellihub | Warren Van Wyk
Jemena | Leon Vilfand
Jemena | Marina Bakh
Jemena | Matthew Mullen
Jemena | Rajiv Balasubramanian
Metering Dynamics | Cindy Matthews
Metering Dynamics | Steven Smith
Mondo | Justin Stute
Neoen | Jeremy Lloyd
Origin Energy | Marian Vasjuta
Origin Energy | Mario Iogha
Plus ES | Helen Rickards
Plus ES | Linda Brackenbury
Organisation | Name
Red/Lumo | Christophe Bechia
Red/Lumo | Nick Gustafsson
Red/Lumo | Stephen Kluck
SAPN | David Woods
Simply Energy | Aakash Sembey
Snowy | Sandra Ho
Snowy hydro | Audrey Follet
Stanwell | Carmel Williamson
TasNetworks | Adrian Honey
Telstra | Piera Lorenz
Vector | Paul Greenwood
? TBC | Stephen Blair

## Slide 4: Consolidated meeting actions(1/2)
# | Topic | Action | Responsibility | Due date
1 | Metering procedure update | AEMO to confirm its MDM build assumptions against the list of potential procedural changes | AEMO | 17 Aug 20
2 | Metering procedure update | AEMO to consider if any standing data updates will be required by participants where a particular procedure change is approved | AEMO | TBD
 | Metering procedure update | AEMO to advise how to register for the regulatory roadmap workshop on Monday, 10 Aug 2020. RESPONSE: Those who wish to register, please contact StakeholderRelations@aemo.com.au | AEMO (Complete) | 4 Aug 20
 | Metering Transition Plan | AEMO to consolidate and circulate an updated MTP, to allow for outcomes of this workshop | AEMO (Complete) | 3 Aug 20
3 | Metering Transition Plan | TFG to provide feedback on any concerns with the updated transition start/end dates associated to Meter Installation & Reconfiguration MTP activities. | TFG | 7 Aug 20
4 | Metering Transition Plan | TFG to provide feedback on any concerns with the updated transition start/end dates associated to Meter Data Delivery MTP activities. | TFG | 7 Aug 20
5 | Metering Transition Plan | TFG to provide feedback on any concerns with the updated transition start/end dates associated to Standing Data Management MTP activities. | TFG | 7 Aug 20

## Slide 5: Consolidated meeting actions (2/2)
# | Topic | Action | Responsibility | Due date
6 | Metering Transition Plan | Do Participants expect to not be able to apply/consume the ‘N’ datastream type code from 9 Mar 2021? Should a Participant not be able to apply/consume this code from 9 Mar 2021, what are the likely implications on Participant downstream processes? | TFG | 17 Aug 2020
7 | Metering Transition Plan | AEMO and TFG to start considering what approach the TFG should take in planning for and managing potential aggregate CATS Transaction volumes associated to numerous MTP activities e.g. development of a CATS notification plan and associated template to gather information from Participants | AEMO & TFG | Next TFG

## Slide 6: Agenda **Please disconnect from your workplace VPN for the WebEx call**
NO | Time | AGENDA ITEM | Responsible
1 | 10:00 - 10:10 | Welcome and introduction | Greg Minney
2 | 10:10 – 10:20 | Notes/actions from previous meeting | Greg Minney
3 | 10:20 – 10:30 | 5MS/GS delayed implementation | Emily Brodie
4 | 10:20 – 10:25 | Update on metering procedure changes | Meghan Bibby
5 | 10:25 – 10:30 | Update on Bidding Transition Plan | Emily Brodie
6 | 10:30 – 10:35 | Readiness reporting | Austin Tan
7 | 10:35 – 11:50 | MTP update workshop | Greg Minney Blaine Miner
BREAK 11:00- 11:10 |  |  | 
 |  | MTP update workshop continued | Greg Minney Blaine Miner
8 | 11:50 – 12:00 | Next steps and general questions | Greg Minney
 | APPENDIX | Refresher on 5MS and GS metering and metering data obligations | 

## Slide 7: Introduction
Greg Minney

## Slide 8: Session objective
Update the MTP to accommodate the 3-month delay to the 5MS and GS Rule commencement dates. The updated MTP will:
Become the latest version for industry and AEMO reflecting revised rule commencement dates.
Provide a basis for participants to evaluate impact to their project plans.
Provide the baseline against which participants will report progress on their metering transition activities

## Slide 9: Notes and actions from previous meeting
Greg Minney

## Slide 10: Actions from TFG #7: 6 May 2020 (1/3)
Section | Action | Responsibility | Response
Actions from TFG #6 | TFG to provide feedback on whether there were MP activities associated with the conversion of new/replacement type 4/4A/VIC AMI meters. | TFG | Four responses received. It was noted that: These meters are not essential to 5MS MDPs will engage with MPs as required and also set the rollout timeframes. MDPs would also engage MPs to manually reconfigure if remote upgrades fail. Therefore it is unnecessary to monitor MP rollouts separately in the MTP. Avoids creating further administrative burden.
 | AEMO to add any identified MP activities for new/replacement type 4/4A/VIC AMI meters to the MTP. | AEMO | n/a (See action #1 above)
 | AEMO to provide template for MP new/replacement type 4/4A/VIC AMI meters rollout plans | AEMO | n/a (See action #1 above)
 | TFG to provide feedback on MP template for new/replacement type 4/4A/VIC AMI meters rollout plans | TFG | n/a (See action #1 above)
 | AEMO to finalise template for MP new/replacement type 4/4A/VIC AMI meters rollout plans | AEMO | n/a (See action #1 above)
 | TFG to provide feedback on existing NCONUML template | TFG | 4 responses received. AEMO distributed updated template on 28 May.
 | AEMO to send out updated template once feedback received. Expected to include indicative NMI volumes vs specific NMI lists | AEMO | Updated template attached for TFG feedback.
 | AEMO to update MTP to include specific activities relating to participants providing AEMO with detailed NMIs lists at a future date i.e. algorithm approval process activities to be treated separately to provision of NMI lists. | AEMO | Complete. AEMO distributed updated MTP (v1.4) on 28 May

## Slide 11: Actions from TFG #7: 6 May 2020 (2/3)
Section | Action | Responsibility | Response
CNDS clarification document | AEMO to issue an updated version of the document to reflect the changes in the MDM go-live dates | AEMO | Document has been updated but will only be published once the once new milestones have been agreed with PCF.
MDM reschedule impact on MTP | TFG to provide feedback on MTP activity date changes resulting from the MDM implementation date change | TFG | Four responses received. Key theme was 5-min metering data delivery, both B2M and B2B, and transition start/end dates for associated MTP actions. AEMO notes that: B2M 5-min data delivery should be considered separately to B2B 5-min data delivery. As discussed and agreed through the TFG and RWG, the MTP has a focus on wholesale meters being ready prior to go-live to ensure a smooth commencement. For these reasons, AEMO doesn’t consider that the suggested MTP changes relating to the MDM go-live change are necessary.
 | AEMO to ensure “RegisterID to Suffix alignment” activity is added for Type 7 and NCONUML installations | AEMO | Complete – see updated MTP (v1.4)

## Slide 12: Actions from TFG #7: 6 May 2020 (3/3)
Section | Action | Responsibility | Response
MTP “12-month delay” scenario | TFG to provide feedback on MTP proposed 12-month 5MS/GS delay scenario, including the minor edits proposed by TFG members during the meeting: A52, A58, A64 and A70 for the Forward Plan to AEMO be moved back until after the date of FINAL determination from AEMC (say Sept-Oct 2020) should A98a "Provide AEMO with NCONUML NMI list" - be pushed back to closer to the MDM Go-live date given that previously it was to be provided only 1 week before the MDM Go Live date? | TFG | Five responses received. Key issues: Similarly to MDM change scenario, concerns raised about transition end dates for B2B 5-min data delivery. AEMO note that as discussed and agreed through the TFG and RWG, the MTP has a focus on wholesale meters being ready and their data being sent to AEMO prior to go-live to ensure a smooth commencement. Propose to monitor rule change process and discuss with TFG when outcome known. Suggestion to change transition end date relating to matching suffix and register ID. AEMO notes that the end date relates to a procedure, not the proposed rule, and a procedure change is under consideration by the ERCF. Propose to monitor both proposed rule and procedure change processes and discuss with TFG when outcomes known. Suggestion to maintain start dates for activities relating to rollout plans. AEMO agrees and also proposes that regular rollout plan updates are incorporated into the MTP.

## Slide 13: 5MS/GS delayed implementation
Emily Brodie and Greg Minney

## Slide 14: AEMC Deferral Decision
Activity | Original date | New date
Commencement of 5MS | 1 July 2021 | 1 October 2021
Commencement of “soft start” GS | 1 July 2021 | 1 October 2021
Commencement of financial settlement of GS | 6 February 2022 | 1 May 2022
Compliance date for all new and replacement metering installations (other than excluded metering installations) to be configured to record and provide 5-minute data | 1 December 2022 | 1 December 2022
AEMO required to publish UFE data report | 1 July 2021 | 1 October 2021
AEMO required to publish UFE report on unaccounted for energy trends | 1 March 2022 | 1 June 2022

## Slide 15: Summary of Impact
AEMO 5MS Program: will continue to progress with system development and deployments to meet the current milestones
  Platform release of MDM, Settlements and 5-min Bidding into 5MS Staging Environment, AEMO pre-production environment and production will remain as scheduled
Procedures: New effective dates are likely the only impact to those procedures already updated for 5MS/GS
  Final determination indicates that AEMO can change the effective date of already-determined procedures (updated for 5MS and GS) without further consultation. Timeframes for updates to be discussed with the RWG.
Industry readiness activities will change to accommodate the new rule commencement dates
  PCF/RWG are discussing appropriate timing and duration of market trials
Extension of the 5MS Staging Environment is under consideration
Reallocations update will be needed with new 5MS commencement date – plan will be communicated through RWG/SWG
Stakeholder engagement:
  RWG and SWG have been combined as system design and development largely complete
  ITWG will be convened as needed – now more like a focus group
  Working Groups will remain on a monthly basis until 5MS go-live with focus groups being used as needed
  Working Groups/ Focus Groups used as needed up until GS go-live
  5MS mailbox will remain active until GS go-live

## Slide 16: Summary: Impact on approach to transition
Phased implementation approach is maintained:
Platform go-lives to deliver require capabilities
5MS and GS implementations aligned to Rule Commencement
Limited impact to Transition timeframes and windows:
Shorter deferral has reduced the need for a “2 speed” transition
Bidding transition period extends from 1 Apr to 1 Oct 2021
Transition approach will continue to support commencement of transition activities as early as possible (subject to appropriate counter party agreements)
Metering Transition:
Plan to be revised to take into consideration new Rule Commencement requirements
Participants plans may need to be revised, with progress reported against new timings
Participant accreditation timings to be reviewed

## Slide 17: Summary: Impact on market trials and readiness reporting
Industry Testing and Market Trials:
Market Trials realigned with revised Rule Commencement dates
Staging environment to be utilized for participant testing of all releases, in mode agreed with Industry
Industry tests for platform deployments as per current strategy
Readiness reporting:
Participant special survey issued to provide the Executive Forum a consolidated view of participant impacts associated to the Rule Change request process and outcome
Cadence of planned Readiness Reporting to be maintained
Participants expected to report against their updated plans i.e. reflective of the revised Rule Commencements

## Slide 18: Metering procedures update
Meghan Bibby

## Slide 19: 5MS/GS-related procedure change log
Procedure issue | Status
MDFF file size and transaction limit in file | Procedure has been finalised: MDFF file size 10MB MDFF 1,000 transaction limit in file non-contestable unmetered loads – use of existing B2B transactions for this family of NMIs
Proposed procedural change to MDFF quality flag (N flag) | AEMO submitted an ICF for ERCF consideration at March meeting. AEMO to compiled a ‘change information pack’, presented at the 15 May ERCF. ERCF and AEMO decided to take to consultation. Consultation commences early August, anticipated to be concluded early December.
Proposal for RWD[?] | Part of MSATS Standing Data Review. Second draft determination was published 3 Jul 20. Submissions period closes Mon 27 Jul. Final report is due to be published Mon 7 Sep.
Removal of end user details from inventory table | Consultation commences early August, anticipated to be concluded early December.
TNI 2 for cross-boundary meters | Part of MSATS Standing Data Review. Second draft determination was published 3 Jul 20. Submissions period closes Mon 27 Jul. Final report is due to be published Mon 7 Sep.
Obligation for MC to provide updated or substitution data in the cases of theft or fraud | Original ICF lodged by AGL. Relates to UFE calculation. Discussed at ERCF May meeting. On hold pending compliance discussions. New ICF would need to be lodged to reinitiate procedure change process.
Removal of register ID = suffix requirement | ICF lodged by AusNet discussed at ERCF May meeting. Consultation commences early August and is anticipated to conclude early December.

## Slide 20: NOTES: 5MS/GS-related procedure change log
Discussions were held about the need for participants to understand AEMO’s functional assumptions that relate to “Open” procedural consultations.
ACTION: AEMO to confirm its MDM build assumptions against the list of potential procedural changes
In response to a query from AEMO as to which assumptions are most important to participants, Endeavour Energy stated that the RWD outcome was the most important one from their perspective. AEMO suggested that each participant may need to make its own assumptions regarding the likely outcome of the Open consultations and that AEMO will be endeavouring to support all of the proposed changes, where applicable.
ACTION: AEMO to consider if any standing data updates will be required by participants where a particular procedure change is approved e.g. updates to the values in the Meter Read Type field for the population of RWDx. Should any updates be required, new activities should be added to the MTP for reporting and monitoring purposes.
Evoenergy asked if AEMO has/is planning to have a central location to capture, manage and communicate broader changes associated to the regulatory roadmap, to minimise the likelihood of overlooking any material items. AEMO responded that it is revising its “regulatory roadmap” with industry to manage the issues around overlapping reform implementations. A workshop is set for Mon 10 August.
ACTION: AEMO to advise how to register for the regulatory roadmap workshop on Monday, 10 Aug 2020. RESPONSE: Those who wish to register, please contact StakeholderRelations@aemo.com.au

## Slide 21: Metering procedures update
Electricity Retail Consultative Forum - next meeting Tue 11 Aug 20
https://aemo.com.au/Stakeholder-Consultation/Industry-forums-and-working-groups/Retail-meetings/Electricity-Retail-Consultative-Forum
B2B Working Group – recent meeting Thu 6 Aug 20
https://aemo.com.au/Stakeholder-Consultation/Industry-forums-and-working-groups/Retail-meetings/B2B-Working-Group

## Slide 22: Update on Bidding Transition Plan
Emily Brodie

## Slide 23: Context: Bidding transition plan
MARKET READINESS STRATEGY
INDUSTRY READINESS REPORTING PLAN
MSP ACCREDITATION UPDATE PLAN
INDUSTRY TRANSITION & GO-LIVE STRATEGY
INDUSTRY TESTING & MARKET TRIALS STRATEGY
TEST PLANS
TRANSITION PLANS
- Metering
- Bidding
GO-LIVE PLANS
CONTINGENCY PLAN
Market readiness reports
Readiness assessment questionnaires
TRANSITION REFERENCE MATERIAL
- CNDS and Meter Data Delivery Clarifications

## Slide 24: BTP consultation approach
Early engagement
23 Jun 20 DFG reviews detailed plan
Draft paper
13 Jul 20 AEMO publishes draft paper
Feedback
28 Aug 20 AEMO publishes final paper after considering suggestions
Final paper
31 Jul 20 Participants provide suggestions on draft paper to AEMO
14 May 20 RWG refresher on approach to bidding transition
AEMO seeks early feedback from RWG and DFG:
Revisions
TBC Revisions as required in consultation with the RWG & DFG
DRAFT BTP is currently out for consultation
BTP approach was discussed with RWG & Dispatch Focus Group

## Slide 25: Impact of 3-month delay to BTP
The 3-month 5MS delay:
  Has no impact on the deployment timeframes of AEMO’s 5MS bidding system changes:
    Some bidding capability is already in the staging environment
    Deployment into pre-production is on track for 29-Nov-20
    Deployment into production on track for 01-Apr-21.
    From 01-Apr-21, 5-min capability will be available alongside 30-min capability until 5MS commencement.
  Provides the option of extending the 5-min bidding transition period
DFG agreed that a longer 5-minute bidding transition period is acceptable and it could be extended by 3-months (the duration of the 5MS commencement deferral).

## Slide 26: Bidding transition
STAGING ENVIRONMENT
PRE-PRODUCTION
PRODUCTION GO-LIVE
5MS START
From 1 Oct 2021
P1: Bidding FTP & API
P2: Bidding Web UI
P3: Dispatch, Pre-dispatch and PASA
15 May 2020
P4: Pricing & Miscellaneous
29 Nov 2019
29 Nov 2020
5-min Bidding (all packages)
1 Apr 2021
5-min Bidding (all packages)
Only 5-min bids in JSON format
PREPARATION for 5-minute bidding
    AEMO to ensure valid 5-min bids before the start of the transition period
TRANSITION: 1 Apr 2021 to 30 Sep 2021
Submit 5-min or 30-min bids
5-min bids must be in JSON format
Each 5-min bid within each half hour must be identical, giving the same effect as the submission of a 30-min bid

## Slide 27: Readiness reporting
Austin Tan

## Slide 28: Readiness Reporting
Readiness reporting will resume on Tuesday 11 August, with participants now considering their progress against the new Rule Commencement dates.
The frequency of reporting will be every two months.
An updated reporting timeline for 2020 is provided below:
Reporting timeline for 2021 will be discussed at the RWG on 16 November 2020
Readiness reporting | Survey released | Survey responses due | Distribute results | Discuss at RWG | Discuss at PCF | Discuss at EF
Round #1 | 05-Feb-20 | 14-Feb-20 | 2-Mar-20 | 11-Mar-20 | 05-Mar-20 | 12-Mar-20
Round #2 | 14-Apr-20 | 23-Apr-20 | 07-May-20 | 14-May-20 | 02-Jun-20 | TBC
Special survey | 10-Jul-20 | 17-Jul-20 | 24-Jul-20 | 24-Jul-20 | 24-Jul-20 | 30-Jul-20
Round #3 | 11-Aug-20 | 20-Aug-20 | 03-Sep-20 | 14-Sep-20 | 01-Oct-20 | TBC
Round #4 | 06-Oct-20 | 15-Oct-20 | 29-Oct-20 | 16-Nov-20 | 01-Dec-20 | TBC
Round #5 | 17-Nov-20 | 26-Nov-20 | 10-Dec-20 | 14-Dec-20 | TBC | TBC

## Slide 29: Essential capabilities for 5MS and GS commencements
Essential capability | Relevant participants | Critical Path Criteria
Generators and MNSPs are able to submit 5-min offers (i.e. over FTP, API or web bidding interface) | Generators, MNSPs | Generators representing >80% of regional load are responding to Industry Readiness Surveys, and; Generators representing >80% of regional load are reporting ‘On-track’ to be able to submit 5-minute granularity offers
All essential meters* are able to produce and store 5-min data | MPs | 100% of MPs associated to essential metering are responding to Industry Readiness Surveys, and; 100% of MPs associated to essential metering are reporting ‘On-track’ for all applicable MTP activities (S01)
All essential meters* are able to produce and store 5-min data | MCs | 100% of MCs associated to essential metering are responding to Industry Readiness Surveys, and; 100% of MCs associated to essential metering are reporting ‘On-track’ for all applicable MTP activities (S01)
All essential meters* are able to deliver 5-min metering data | MDPs | 100% of MCs associated to essential metering are responding to Industry Readiness Surveys, and; 100% of MCs associated to essential metering are reporting ‘On-track’ for all applicable MTP activities (S01)
The 5-minute bidding and dispatch solution, including the web bidding interface is deployed | AEMO | AEMO reporting ‘On-track’ for all Bidding/Dispatch reporting criteria and milestones
The Metering Data Management (MDM) solution is deployed | AEMO | AEMO reporting ‘On-track’ for all MDM Milestones
The 5-minute settlements solution is deployed | AEMO | AEMO reporting ‘On-track’ for all Settlement Milestones
In future readiness reports, AEMO will be providing additional analysis on essential industry capabilities that are on the critical path for minimum viable 5MS and GS operations. This analysis is intended to highlight if the industry is ‘on track’ against rule commencement and ties directly to the Industry Contingency Plan.
Participant responses to the readiness surveys are key as inputs, including reporting on the status of relevant MTP activities. Outputs from this reporting will also help to identify whether contingency responses need to be triggered.
*Essential meters are defined in the Industry Contingency Plan as ‘Transmission connected types 1-4 meters’, and ‘Distribution to distribution cross-boundary types 1-4 meters’

## Slide 30: MTP update workshop
Greg Minney and Blaine Miner

## Slide 31: MTP Update: Key considerations
AEMC Rule Deferral dates:
  5MS/UFE Publication – 1 Oct 2021
  Transition of New and replacement meters – 1 Dec 2022
  GS Financial start – 1 May 2022
AEMO functional releases to Production:
  Retail/MDM – 9 Mar 2021
  5 and 15min metering data delivery via B2M – 1 Apr 2021
  Settlements and Dispatch/Bidding – 1 Apr 2021
Changes to Transition window options:
  Defer by 3mths
  Extend transition windows e.g. no deferral
  Other
Dependencies
  Impacted Participant readiness to process transactions
  Technical e.g. reliance on new schema/configuration/fields
  Effective dates for procedures as end state assumed in MTP
More broadly, implications on:
  CR notification volume management
  Participant compliance
  Transition risk

## Slide 32: NOTES: Meter installation and reconfiguration
Discussion was held around the appropriate transition end date for meter installation and reconfiguration across the range of metering types that need to be delivering 5min data by 5MS start. On the whole, the TFG agreed that it would be useful to extend the transition end date for these meters by 3 month (in line with the 5MS deferral) to provide additional capacity and flexibility.
The TFG agreed with AEMO’s proposal for participants to provide progress and amendments, re their meter installation and reconfiguration “forward plan”, to AEMO every 2mths.
Jemena and CitiPower enquired about the transition end date for “Cross-boundary – Unknown” meters being 30 Sept 2021, instead of a date closer to the GS ‘financial start’ date (1 May 2022). AEMO confirmed that all cross boundary meters (known and unknown) are required for the accurate publication of UFE values from 1 Oct 2021, therefore the proposed transition end date of 30 Sept 2021 is appropriate.
ACTION: TFG to provide feedback on any concerns with the updated transition start/end dates associated to Meter Installation & Reconfiguration MTP activities.

## Slide 33: NOTES: Meter data delivery
AEMO proposed that most meter data delivery activity transition dates should shift by 3 months in alignment with the new 5MS/GS start dates
AEMO confirmed that activity A36 (and others ) did not require participants to migrate to the R39 schema in order to process this activity.
Endeavour Energy questioned the intent of the comment for MTP activity A36 (Create/activate export and import (active (kWh) and reactive (kVArh)) energy datastreams in CNDS table) i.e. whether participants need to be ready by 9 March or if participant wants to use then need agreement. AEMO responded that the new datastream type code of ‘N’ will be available in MSATS from 9 March 2021, to support required MDP CNDS updates. It is up to participants to consider how they accommodate the introduction of this new code into their programs, and whether they are impacted by the population of those values in MSATS
ACTION: Do Participants expect to not be able to apply/consume the ‘N’ datastream type code from 9 Mar 2021? Should a Participant not be able to apply/consume this code from 9 Mar 2021, what are the likely implications on Participant downstream processes?
AEMO summarised the meter data delivery conversation, highlighting:
  The importance of CATS notification volume management and that the TFG should consider how to best manage/plan for this issue at the next TFG
  The need to add MTP activities to allow for the likely endorsement of the RWDx consultation
In relation to A52 (forward plans for new and replacement type 4 meters) AEMO queried whether the transition start date should be 1 Sep 2020. No comments were received so it was assumed that this was a suitable start date.
In relation to new activity A52a (providing progress on and amendments to forward plans to AEMO and industry every 3mths), AEMO queried whether this was an appropriate approach. No comments were received so it was assumed that a quarterly basis was appropriate. Therefore this activity will have a transition start date of 1 Dec 2020 and updates will occur every 3 months thereafter to AEMO and industry.
ACTION: AEMO and TFG to start considering what approach the TFG should take in planning for and managing potential aggregate CATS Transaction volumes associated to numerous MTP activities e.g. development of a CATS notification plan and associated template to gather information from Participants

## Slide 34: NOTES: Standing data management
AEMO mostly proposed a three month shift to transition start/end dates to align with the 5MS/GS deferral. The TFG broadly agreed with this approach.
With respect to updating NMI classification codes, the TFG considered it appropriate to maintain (i.e. not shift) the 1 May transition start date.
ACTION: TFG to provide feedback on any concerns with the updated transition start/end dates associated to Standing Data Management MTP activities.

## Slide 35: NOTES: Other
Endeavour Energy enquired if when AEMO populates TNI2 for cross-boundary meters, whether the network will also populate that value for existing TNIs. AEMO noted it would work in conjunction with relevant LSNP.
ACTION: AEMO to consolidate and circulate an updated MTP, to allow for outcomes of this workshop
  Complete – Updated MTP circulated on the 3 Aug 2020

## Slide 36: Key findings
Chart: 
| If your organisation's delivery of 5MS and GS has been impacted by the AEMC decision, is there any additional support that AEMO can provide to help mitigate this impact? | Considering your organisation's 5MS project current status, is your organisation on track to deliver against the new commencement dates? | Has your organisation previously decided to defer its project resources or activities in anticipation of the rule change determination?
Yes | 0.18919 | 1 | 0.35135
No | 0.81081 | 0 | 0.64865
Figure 1: Participant impacts from delayed implementation of five minute and global settlement
Chart: 
| To what extent has your organisation's delivery of 5MS and GS changed as a result of the AEMC's decision to defer the rule commencement dates by 3 months?
No change | 0.40541
Minor change | 0.54054
Major change | 0.054054
Observations:
One in three respondents (35%) decided to defer their project resources or activities in anticipation of the determination.
All respondents, including those who deferred projects noted that they are on track to deliver against the new commencement dates.
Participants are focused on re-mobilisation and re-planning activities, with a majority (81%) not requiring any additional support from AEMO. Suggestions of additional support include providing more flexibility around participant engagement and transition activities.
Only 5% of respondents were making major changes to their program in response to the rule change determination. Approximately half (54%) had minor changes to their program, with 41% not making any changes to their program.
n = 37

## Slide 37: Participant transition activities
Chart: 
| For type 4 and 4A metering, is your organisation intending to commence relevant meter transition activities before the 5MS commencement date? | Does your business currently support, or is intending to develop meter data aggregation capability (e.g. 5 to 30 or 15-minute intervals)? | Are you intending to enter into agreements to deliver or receive metering data in sub-multiples of a trading interval (NER Chapter 7.10.5)? | Does your organisation intend to commence 5-minute bidding during the bidding transition period (1 Apr 2021 to 1 Oct 2021)?
Yes | 4 | 5 | 6 | 13
No | 10 | 7 | 25 | 2
Figure 7: Participant transition activities
Observations:
13 out of 15 generators (87%) responded that they intend to commence 5-minute bidding during the bidding transition period.
Six out of 31 (19%) organisations representing Retailers, MDPs, DNSPs and TNSPs intend to enter into agreements to deliver or receive metering data in sub-multiples of a trading interval. All respondents that noted timeframes for these agreements reported delivery and receipt of sub-multiples within 6 months of 5MS commencement.
Five out of 12 (42%) MDPs currently support or intend to develop meter data aggregation capability.
Four out of 14 MDPs, MPs and MCs intend to commence meter transition activities for type 4 and 4A meters before the 5MS commencement date. Out of the four MDPs, three intend to have metering data aggregation as a component of their operations.
n = 15
n = 31
n = 12
n = 14
Generators:
Retailers, MDPs, DNSPs, TNSPs:
MDPs:
MDPs, MPs, MCs:

## Slide 38: Results - Summary of responses, by participant type (1)
 | Total respondents | Extent of that 5MS and GS delivery has changed as a result of rule determination |  |  | Deferred resources or activities before rule change |  | Delivery against new commencement dates |  | Suggestion of additional support from AEMO | 
Participant type |  | No change to program | Minor change to program | Major change to program | Deferred | Not deferred | On track | Not on track | Yes | No
Generator | 15 | 7 | 8 | 0 | 4 | 11 | 15 | 0 | 2 | 13
Retailer | 15 | 6 | 9 | 0 | 6 | 9 | 15 | 0 | 4 | 11
DNSP | 9 | 2 | 6 | 1 | 4 | 5 | 9 | 0 | 2 | 7
TNSP | 3 | 2 | 0 | 1 | 1 | 2 | 3 | 0 | 1 | 2
MP | 13 | 5 | 6 | 2 | 5 | 8 | 13 | 0 | 3 | 10
MDP | 12 | 4 | 6 | 2 | 5 | 7 | 12 | 0 | 3 | 9
MC | 12 | 5 | 5 | 2 | 5 | 7 | 12 | 0 | 4 | 8
All participants* | 79 | 31 | 40 | 8 | 30 | 49 | 79 | 0 | 19 | 60
All organisations* | 37 | 15 | 20 | 2 | 13 | 24 | 37 | 0 | 7 | 30
*Each organisation may represent multiple participant types (e.g. generator and retailer)
Table 2: Summary of responses (i)

## Slide 39: Results - Summary of responses, by participant type (2)
 | Total respondents | Intention to deliver or receive metering data in sub-multiples of trading interval |  | Capability to aggregate metering data (e.g. 5 to 30 or 15-minute intervals) |  | Commencement of type 4 and 4A metering transition activities before 1 Oct 2021 |  | Commencement of bidding during transition period (1 Apr 2021 to 1 Oct 2021) | 
Participant type |  | Yes | No | Yes | No | Yes | No | Yes | No
Generator | 15 | - | - | - | - | - | - | 13 | 2
Retailer | 15 | 2 | 13 | - | - | - | - | - | -
DNSP | 9 | 2 | 7 | - | - | - | - | - | -
TNSP | 3 | 1 | 2 | - | - | - | - | - | -
MP | 13 | - | - | - | - | 4 | 9 | - | -
MDP | 12 | 3 | 9 | 5 | 7 | 4 | 8 | - | -
MC | 12 | - | - | - | - | 3 | 9 | - | -
All participants* | 79 | 8 | 31 | 5 | 7 | 11 | 26 | 13 | 2
All organisations* | 37 | 6 | 25 | 5 | 7 | 4 | 10 | 13 | 2
*Each organisation may represent multiple participant types (e.g. generator and retailer)
Table 3: Summary of responses (ii)

## Slide 40: Metering Transition responses
Delivery of Metering Data in sub-intervals
  1 MDP, 3 retailers (2 with plans tbc), 2 network (1 only for NCONUML)
  For Discussion:
    intention of participants to process 5 minute metering data in line with MTP timeframes (Tranche 1 communicating 1 month prior to rule commencement)
    5 MS metering delivery “big bang” risk for MDP’s, Retailers
    MDP support for AEMO discussion on timing of 5 minute B2M delivery
4 / 4A metering Data transition
  4 participants responded in affirmative:
    1 MDP will convert meters but continue to send 15/30 minute metering Data
    1 MDP – as per MTP supplied plan
    1 MDP – Q3 2021 – small subset of sample meters
    1 MDP- currently converting meters – data sent by 1 Dec 2022
  Discussion:
    Confirm this will be reflected in MTP plans included revised rollout plans from other participants
    Indicates no immediate bow wave of type 4 metering data
    Transaction volume management viewed as post Oct 2021 issue

## Slide 42: Next steps and general questions
Greg Minney

## Slide 43: Reflection on session objective
Update the MTP to accommodate the 3-month delay to the 5MS and GS Rule commencement dates. The updated MTP will:
Become the latest version for industry and AEMO given the revised rule commencement dates.
Provide a basis for participants to evaluate impact to their project plans.
Provide the baseline against which participants will report progress on their metering transition activities

## Slide 44: Next steps
Continued implementation of MTP
TFG to provide feedback on MTP updates to 5ms@aemo.com.au by Wed, 5 Aug 2020
RWG review 13 Aug 2020
Other?

## Slide 45: General questions

## Slide 46: Thank you for your attendance and participation!

## Slide 47: APPENDIX: Refresher on 5MS and GS metering and metering data obligations

## Slide 48: 5MS Metering installation requirements
Metering Type | Requirement | Date
Types 1, 2, 3 and 7 | Must be capable of recording and providing, and configured to record and provide, five-minute trading interval energy data. | By 1 July 2021 By 1 Oct 2021
Subset of Type 4* | Must be capable of recording and providing, and configured to record and provide, five-minute trading interval energy data. | By 1 July 2021 By 1 Oct 2021
Types 4, 4A and 5 | All new or replacement metering installations (other than type 4A metering installations) installed from 1 December 2018 must be capable of recording and providing, and configured to record and provide, five-minute trading interval energy data. All new or replacement type 4A metering installations installed from 1 December 2019 must be capable of recording and providing, and configured to record and provide, five-minute trading interval energy data. | By 1 Dec 2022 (no date change)
Note:
AEMO may grant an exemption where 1 type 1, 2, 3 or subset of type 4 meter is not quite capable of storing 35 days of metering data (i.e. 30-34 days) if it is reasonably satisfied that the Metering Provider will be able to otherwise satisfy the requirements of Chapter 7.
* Subset type 4 meters definition:
Type 4 metering installations at a:
  Transmission network connection point; or
  Distribution network connection point where the relevant financially responsible Market Participant is a Market Generator or Small Generation Aggregator

## Slide 49: 5MS/GS metering data delivery to AEMO
Topic | Requirement | Date
File Format | MDFF NEM12 files to be the required file format For all interval metering data being delivered to AEMO MDFF NEM13 files to be supported by AEMO MDMF files for basic meter reads will continue to be supported and accepted | From 1 July 2021 From 1 Oct 2021
Granularity | NEM12 interval metering data to be: Delivered at the register level (E, B, Q and K) NEM12 200 records must be accurate As per the meter’s trading interval configuration i.e. 5, 15 or 30-minute intervals | From 1 July 2021 From 1 Oct 2021
Energy | Metering data which must be sent to AEMO: Import and Export Active energy (kWh) (E and B) Import and Export Reactive energy (kVarh) (Q and K), where applicable All other forms of measurement (such as volts and amps) are not required to be delivered to AEMO but will be processed if they are provided. | From 1 July 2021 From 1 Oct 2021

## Slide 50: 5MS/GS: MSATS datastream standing data
Metering Type | Requirement | Date
Types 1, 2, 3 and 7 | Net datastreams (N1) must be converted to Register level datastreams (E1, B1, etc.) | By 1 July 2021 By 1 Oct 2021
Subset of Type 4* | Net datastreams (N1) must be converted to Register level datastreams (E1, B1, etc.) | By 1 July 2021 By 1 Oct 2021
Types 4, 4A and 5 | All new records relating to interval meters must be created at the register level e.g. E and B. Existing net datastream records can remain active post 1 July 2021, until an update to the datastream record is required e.g. meter replacement. Where an update is required to a CNDS record, the net datastream record is to be inactivated and any new active datastreams records are to be created at the register level. Datastreams associated with import and export reactive energy e.g. Q and K must be created in the CNDS table if they exist in the CRI table. Datastreams must be established in a manner that ensures they are not included in market settlements. | From 1 July 2021 From 1 Oct 2021
Basic Meters | All 1st tier datastreams must be activated and meter reads delivered to AEMO, for UFE purposes | By 1 July 2021 By 1 Oct 2021

## Slide 51: 5MS/GS: MSATS standing data - general
By 1 July October 2021
  Non-contestable unmetered load (NCONUML) NMIs and associated standing data created in MSATS
  NMI Classification Code updates, for affected existing NMIs, to reflect the new code requirements
NMI Classification Code | Description
BULK | Connection point where a transmission network connects to a distribution network - also termed 'Bulk Supply Point’
DWHOLSAL | Distribution network connection point where energy is directly purchased from the spot market by a Market Customer
NCONUML | Non-contestable unmetered load
NREG | Connection point associated with a non-registered embedded generator, i.e. a generating unit that is not classified by a Market Generator, but may be classified by a Small Generation Aggregator as a market generating unit.
WHOLESAL | Transmission network connection point where energy is directly purchased from the spot market by a Market Customer
XBOUNDRY | Connection point where a distribution network connects to another to distribution network