## Slide 1: 5MS/GS Transition Focus Group #9:
Wednesday 7th Oct, 2020
WebEx only [details in calendar invitation]
**Please disconnect from your workplace VPN for the WebEx call**
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda **Please disconnect from your workplace VPN for the WebEx call**
NO | Time | AGENDA ITEM | Responsible
1 | 9:30 - 9:40 | Welcome and introduction | Greg Minney
2 | 9:40 – 10:10 | MC and MDP rollout plans | Paul Lyttle
3 | 10:10 – 10:45 | MTP CATS transaction volume management | Blaine Miner
4 | 10:45 – 11:10 | Cross Boundary categories, conditions and requirements | David Ripper
5 | 11:10 – 11:30 | Next steps and general business | Greg Minney

## Slide 4: Introduction
Greg Minney

## Slide 5: Session Objectives
Objectives from Today’s Session:
Review and consider the consolidated metering rollout plans for Tranche 1 and Tranche 2 metering
Consider CATS transaction volumes management approaches associated to the MTP
  Key assumptions and inputs
  Indicative timings
  Impacts and constraints on individual participants e.g. daily initiation and processing constraints
  Preferred transaction management approaches
Identify areas for further assessment for the management of transitional elements
Discuss Cross Boundary categories, conditions and requirements

## Slide 6: MC and MDP rollout plans
Paul Lyttle

## Slide 7: MC and MDP Rollout Summary
As outlined in the Metering Transition Plan, MCs were responsible for providing updates on their Tranche 1 meter rollout plans and MDPs were responsible for providing their Tranche 2 meter rollout plans.
11 plans received from MCs (92% coverage)
Metering Dynamics
Mondo
PLUS ES
Intellihub
Powerlink
Evoenergy
Transgrid
ElectraNet
AusNet Services
Ausgrid
Origin
9 plans received from MDPs
Ausnet Services
CitiPower/Powercor
United Energy
Intellihub
Jemena
Metering Dynamics
Mondo
PLUS ES
Vector
Tranche 1
Meters expected to record and provide 5-min metering data by 1 October 2021:
BULK/Wholesale Meters
Type 1-3 meters
Subset of type 4 meters – TNI, Market Generator or SGA
Tranche 2
Meters expected to record and provide 5-min metering data by 1 December 2022:
New and replacement type 4/4A
VIC AMI
SAMPLE meters

## Slide 8: MC and MDP Rollout Plan Observations
Type 1 – 3 & subset Type 4 meter rollout
  Planned upgrade currently in progress
  Rollout peaks in December 2020 with 7,000 meters for the month
  Does not include registration of new Cross Boundary Connection Points
Basic DS registration
  No plan requested by AEMO, therefore indicative meter counts with no active datastreams extracted from MSATS as a guide
  Allows for 2 full read cycles (7 months) for registration and 1 full read cycle (3 months) prior to 5MS start, as per the MTP
    Assumes a first and last month ramp rate of 50%
UMCP upgrade
  No plan requested by AEMO, therefore indicative meter counts for Type 7 have been extracted from MSATS as a guide
  Assumes 3 full cycles (3 months) for upgrade and 1 full cycle (1 month) prior to 5MS start
  Does not include the registration of Non Contestable Unmetered Loads

## Slide 9: Tranche 1 Aggregate Volumes
Peak months between Jan and May 2021 peaking at 200,000 meters updated per month.
Chart: Pre 5MS Go Live - Meters To-Be Updated
| Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
1-3 | 980 | 973 | 361 | 6925 | 435 | 480 | 665 | 665 | 465 | 365 | 1065 | 913 | 150 | 0
COMMS4/4A/VicAmi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1100 | 1175 | 1275 | 2675
BASIC | 0 | 0 | 0 | 99984 | 199967 | 199967 | 199967 | 199967 | 199967 | 99984 | 0 | 0 | 0 | 0
UMCP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635 | 1635 | 1635 | 0 | 0
Total | 980 | 973 | 361 | 106909 | 200402 | 200447 | 200632 | 200632 | 200432 | 101984 | 3800 | 3723 | 1425 | 2675

## Slide 10: Tranche 2 Aggregate Volumes
COMMS4/4A/VICAMI meter rollout
  Roll out begins in January 2022
  Continuous rump up until peak in July and August
  Ramp down for the following 3 months
Peak months between Jul and Aug 2022 peaking at 290,000 meters updated per month
Chart: Pre 1 Dec 2022 - Meters To-Be Updated
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMMS4/4A/VicAmi | 2675 | 12075 | 16075 | 119075 | 134036 | 147686 | 159108 | 212108 | 222108 | 289708 | 279708 | 210708 | 184408 | 158797 | 0
BASIC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UMCP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 2675 | 12075 | 16075 | 119075 | 134036 | 147686 | 159108 | 212108 | 222108 | 289708 | 279708 | 210708 | 184408 | 158797 | 0

## Slide 11: MTP CATS Transaction Volume Management
Blaine Miner

## Slide 12: Applicable MTP Activities
SID | Sub-Category | AID | Activity | Actions | Role | CATS CRs | Transition Start Date | Transition End Date | Rule Date
S13 | BULK/Wholesale Meters | A36 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S13 | BULK/Wholesale Meters | A36b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S14 | Type 1-3 meters | A40 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S14 | Type 1-3 meters | A40b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S15 | Cross Boundary meters (Known) | A45 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S15 | Cross Boundary meters (Known) | A45b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S15 | Cross Boundary meters (Known) |  | Update Meter Read Type code with RWDA | 1. Update TNI2 & NSP3 | AEMO | CR51xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2022
S17 | New and replacement Type 4 | A57 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S17 | New and replacement Type 4 | A57b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S18 | New and replacement Type 4A | A63 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S18 | New and replacement Type 4A | A63b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S19 | New and replacement VIC AMI meters | A69 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S19 | New and replacement VIC AMI meters | A69b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022

## Slide 13: Applicable MTP Activities
SID | Sub-Category | AID | Activity | Actions | Role | CATS CRs | Transition Start Date | Transition End Date | Rule Date
S20 | New and replacement SAMPLE Meters | A75 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S20 | New and replacement SAMPLE Meters | A75b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S22 | Type 7 metering installations | A83a | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S26 | Cross-boundary supplies | A95 | Create cross-boundary NMIs | 1. Create and activate NMI 2. Update NMI to active status | LNSP | CR20xx CR50xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S26 | Cross Boundary meters (Known) |  | Update Meter Read Type code with RWDA | 1. Update TNI2 & NSP3 | AEMO | CR51xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2022
S26 | Cross-boundary supplies | A96 | Create Datastreams in MSATS | 1. Create Datastreams at Suffix Level | MDP | CR40xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S26 | Cross-boundary supplies | A97 | Create registers in MSATS | 1. Install meter (includes Meter read type = RWDA) | MPB | CR30xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27 | Non-contestable unmetered loads | A99 | Create Non-contestable unmetered load NMIs | 1. Create and activate NMI 2. Update NMI to active status | LNSP | CR20xx CR50xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27 | Non-contestable unmetered loads | A100 | Create Datastreams in MSATS | 1. Create Datastreams at Suffix Level | MDP | CR40xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27 | Non-contestable unmetered loads | A101 | Create registers in MSATS | 1. Install meter (includes Meter read type = RWDA) | MPB | CR30xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27a | Convert 'SASCALE NMI' | A101a | Create cross-boundary NMIs | 1. Make bulk NMI Extinct | LNSP | CR50xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27a | Convert 'SASCALE NMI' | A101b | Create Datastreams in MSATS | 1. inactive Datastreams at Suffix Level | MDP | CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27a | Convert 'SASCALE NMI' | A101c | Create registers in MSATS | 1. inactive meter (includes Meter read type = RWDA) | MPB | CR35xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S28 | New NMI classification codes - BULK | A103 | Update NMI Class Codes for existing NMIs as required | 1. Update NMI Classification Code | TNSP | CR50xx | 1-May-21 | 31-Aug-21 | By 1 Oct 2021

## Slide 14: Applicable MTP Activities
SID | Sub-Category | AID | Activity | Actions | Role | CATS CRs | Transition Start Date | Transition End Date | Rule Date
S30 | New NMI classification codes - DWHOLESAL | A107 | Update NMI Class Codes for existing NMIs as required | 1. Update NMI Classification Code | LNSP | CR50xx | 1-May-21 | 31-Aug-21 | By 1 Oct 2021
S31 | New NMI classification codes - NREG | A109 | Update NMI Class Codes for existing NMIs as required | 1. Update NMI Classification Code | LNSP | CR50xx | 1-May-21 | 31-Aug-21 | By 1 Oct 2021
S32 | New NMI classification codes - XBOUNDRY | A111 | Update NMI Class Codes for existing NMIs as required | 1. Update NMI Classification Code | LNSP | CR50xx | 1-May-21 | 31-Aug-21 | By 1 Oct 2021
S35 | LR and FRMP fields | A116 | Update LR and FRMP to GLOPOOL for existing NMIs as required | 1. Update LR and FRMP to GLOPOOL for existing NMIs as required | AEMO | BC00 | 1-May-22 | 1-May-22 | 1-May-22
S36 | Tier 1 basic metering data | A118 | Create/activate tier 1 basic meter datastreams as required | 1. Create datastreams | MDP | CR40xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S38 | VIC TUOS datastreams | A120 | Update Datastream type codes from 1-4 to 'I' or 'N' as required | 1. Update Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021

## Slide 15: MTP CATS Transaction Volume Management
Initial assumptions:
1 transaction per ‘Action’
  e.g. S13 has 3 actions therefore 3 CATS transactions are assumed
    Create datastreams at suffix level - All applicable datastreams for a NMI created in one CR400x transaction
    Inactive Net datastreams - All applicable Net datastreams for a NMI inactivated in one CR405x transaction
    Update Meter Read Type code - All applicable registers for a NMI updated in one CR305x transaction
3 notifications per CATS CR (Requested, Pending and Completed)
All 3 notifications processes in the same month
Linear volumes per day
Linear activation of Basic meter datastreams over a 8mth period (Nov 20 to June 2021) – LR impact
  More sophisticated assumption required to reflect likely volume shape
    AEMO to engage with key Participants
Key inputs:
Participant Tranche 1 and Tranche 2 rollout plans
AEMO data extracts from MSATS
Potential constraints:
MSATS Daily limits - Number of transactions a Participant can initiate/process
Stop files/unprocessed transition limits
Need to consider these MTP related volumes on top of BAU notification volumes

## Slide 16: Pre 5MS Go Live CATS Transaction Volume Estimates
Single CATS CR for the majority of the changes
Numbers of CR Transactions to peak at 200,000+ month
  Majority of changes related to Tier 1 Basic Meter Datastream activation
Numbers of CR Notifications (“REQ”, “PEND”, “COM”) estimated to peak at 600,000+ month
Chart: Pre 5MS Go Live - CATS CR Numbers
| Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct
1-3 | 3087 | 3064.95 | 1137.15 | 21813.75 | 1370.25 | 1512 | 2094.75 | 2094.75 | 1464.75 | 1149.75 | 3354.75 | 2875.95 | 472.5 | 0
COMMS4/4A/VicAmi | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3311 | 3536.75 | 3837.75 | 8051.75
BASIC (No Act DS) | 0 | 0 | 0 | 99984 | 199967 | 199967 | 199967 | 199967 | 199967 | 99984 | 0 | 0 | 0 | 0
UMCP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4905 | 4905 | 4905 | 0 | 0
Total | 3087 | 3064.95 | 1137.15 | 121797.75 | 201337.25 | 201479 | 202061.75 | 202061.75 | 201431.75 | 106038.75 | 11570.75 | 11317.7 | 4310.25 | 8051.75

## Slide 17: Post 5MS Go Live to 1 Dec 2022 CATS Transaction Volume Estimates
Three CATS CRs required for the majority of changes
Numbers of CR Transactions to peak at 870,000+ month
Numbers of CR Notifications (“REQ”, “PEND”, “COM”) estimated to peak at 2,610,000+ month
  Does not consider multiple Participants receiving Notifications
Chart: Post 5MS Go Live to 1 Dec 2022 - CATS CR Numbers
| Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1-3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
COMMS4/4A/VicAmi | 8051.75 | 36345.75 | 48385.75 | 358415.75 | 403448.36 | 444534.86 | 478915.08 | 638445.08 | 668545.08 | 872021.08 | 841921.08 | 634231.08 | 555068.08 | 477978.97 | 0
BASIC (No Act DS) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UMCP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 8051.75 | 36345.75 | 48385.75 | 358415.75 | 403448.36 | 444534.86 | 478915.08 | 638445.08 | 668545.08 | 872021.08 | 841921.08 | 634231.08 | 555068.08 | 477978.97 | 0

## Slide 18: Cross Boundary categories, conditions and requirements
David Ripper

## Slide 19: Cross Boundary Categories
Cross Boundary Supply Categories
Metered at the Boundary
Not Metered at the Boundary
  Unmetered – emergency connection between supply and receiving distribution networks that is used infrequently
  Metered at End User connection point – generally a single connection point in the receiving distribution network connected to a service or a circuit from the supply distribution network

## Slide 20: Cross Boundary conditions and Requirements
Metered at the Boundary
DNSPs, in consultation with AEMO, will create Cross Boundary NMI
LNSP = Supply DB Participant ID
TNI = Supply DB TNI
NSP2 = Receiving DB Participant ID – populated by AEMO
TNI2 populated by AEMO
Not metered at the Boundary
Approval must be obtained from AEMO
AEMO, in consultation with DNSPs, will determine the metering or energy volume assessment arrangements for the Cross Boundary Supply

## Slide 21: Cross Boundary conditions and Requirements
Unmetered at the Boundary (Emergency)
LNSP, in consultation with AEMO and receiving DB, must provide methodology for assessing energy volume flowing at the Unmetered Cross Boundary Supply
LNSP must develop processes and procedures that include:
  Energy volume assessment methodology,
  Identification of time period the Unmetered Cross Boundary Supply was in use,
  NMI and datastream activation process, and
  Provision to AEMO of details of the form in which information related to each use of an Unmetered Cross Boundary Supply

## Slide 22: Cross Boundary conditions and Requirements
Unmetered at the Boundary (Emergency) - continued
DNSPs, in consultation with AEMO, will create Cross Boundary NMI
LNSP = Supply DB Participant ID
TNI = Supply DB TNI
NSP2 = Receiving DB Participant ID – populated by AEMO
TNI2 populated by AEMO
LNSP must ensure that NMI and datastreams are active only for the period when the Unmetered Cross Boundary Supply is in use, otherwise the NMI and datastreams must not be active

## Slide 23: Cross Boundary conditions and Requirements
Metered at End User connection point
DNSPs must provide AEMO with End User NMIs
End User connection point must have remotely read interval meter (can be 5, 15 or 30-minute)
DNSPs, in consultation with AEMO, will create/maintain “Cross Boundary NMI”
LNSP = Receiving DB Participant ID
TNI = Supply DB TNI
NSP2 = Supply DB Participant ID – populated by LNSP (new CR6xxx)
Targeting the end of October 2020 to provide the draft ‘Cross Boundary Supply Guideline’

## Slide 24: Next steps and general business
Greg Minney

## Slide 25: Next steps & general business
Participants to consider:
  Initial aggregate estimates and underlying assumptions
  How these estimates support Participant impact assessments
    Potential system and process impacts
  What additional engagement will be required with other Participants to complete assessments and planning
  Potential bulk capability requirements
  Potential alternative management options
AEMO to engage relevant Participants to assist in refining Basic meter and NCONUML assumptions
AEMO to schedule monthly TFGs
  Sessions to be cancelled when not deemed necessary

## Slide 26: Thank you for your attendance and participation!