## Slide 1: 5MS/GS Transition Focus Group #10:
Thursday 26th Nov, 2020
WebEx only [details in calendar invitation]
**Please disconnect from your workplace VPN for the WebEx call**
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda **Please disconnect from your workplace VPN for the WebEx call**
NO | Time | AGENDA ITEM | Responsible
1 | 10:00 - 10:10 | Welcome and introduction | Greg Minney
2 | 10:10 – 10:40 | MTP CATS transaction volume management | Blaine Miner/ Paul Lyttle
3 | 10:40 – 11:10 | Upcoming MTP Activities | Blaine Miner
4 | 11:10 – 11:30 | GLOPOOL Update | Paul Lyttle
5 | 11:30 – 11:45 | Cross boundary guidelines | David Ripper
6 | 11:45 – 12:00 | Next steps and general business | Greg Minney

## Slide 4: MTP CATS transaction volume management
Blaine Miner/Paul Lyttle

## Slide 5: Objective
The objective of the analysis is to create a consolidated Industry view of indicative transaction volumes relating to the MTP activities
  Detailed at a monthly level
  Spanning from today to Dec 2022
The analysis is being performed to:
  Support Participant and AEMO system and general business impact assessments
  Facilitate Participant to Participant engagements
  Create appropriate inputs into the MSDR Data Transition working group
Questions:
  What level should this analysis be performed at for industry overview: CR transaction, notification, acknowledgement?
  Do MDPs intend to convert datastreams to register level as they convert metering data delivery to 5min for type 4, 4A and VicAMI meters?

## Slide 6: Scope
In-scope considerations:
  By 31 Aug 2021
    Convert type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level
    Update type 1-3, subset type 4, type 7 and existing cross boundary ReadTypeCodes to ‘A’, where required
    Create NCONUML and ‘new’ Cross boundary NMIs, Registers and Datastreams
    Update NMI Classification codes, where required
    Create/activate Basic meter 1st tier datastreams
    Update VIC TUoS datastreams from 1-4 to ‘N’
  By 30 Nov 2022
    Update new and replacement type 4, 4A and VIC AMI meter ReadTypeCodes to ‘A’, where applicable
Out-of-scope items:
  MSDR standing data updates
  Other standing data updates associated to:
    Market reform initiatives
    Non-market based initiatives
      E.g. Participant based activities/initiatives

## Slide 7: Required Participant Inputs
In-scope Item | Inputs Currently Being Received | Additional Inputs Required
Convert type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level |  | MDP conversion plans for Type 1-3, subset type 4, type 7 and existing cross boundary datastreams to register level
Update type 1-3, subset type 4, type 7 and existing cross boundary ReadTypeCodes to ‘A’, where required | MP Type 1-3 reconfiguration plans | MP Reconfiguration plans to also include subset type 4, type 7 and existing cross boundary
Create NCONUML and ‘new’ Cross boundary NMIs, Registers and Datastreams |  | LNSP NCONUML and cross boundary NMI creation plans
Update NMI Classification codes, where required |  | TBD
Create/activate basic meter 1st tier datastreams | Participant information as requested | 
Update VIC TUoS datastreams from 1-4 to ‘N’ | MDP Type 4, 4A and VIC AMI rollout plans | 
Update new and replacement type 4, 4A and VIC AMI meter ReadTypeCodes to ‘A’, where applicable | MDP Type 4, 4A and VIC AMI rollout plans | 

## Slide 8: MTP CATS transaction volume management
Graphs have been updated
  A large number of Basic meter datastream updates were completed in October
  Due to variable notification per Change Request we have removed notification assumptions graphs (emphasis at the transaction level)
Participant will need to conduct impact assessments
  What do you need and from who?
Other considerations
  MSDR – Proposed updated required as part of the review.
    Focus group commencing early next year
    How will MTP activities be considered as part of this focus group
    Additional Change Request daily limits
MDSR – MSATS Standing Data Review
MTP – Metering Transition Plan

## Slide 9: Pre 5MS Go Live CATS Transaction Volume Estimates
Tranche 1 updates:
  Large number of updates in October – 425,000
  Participant impacts ?
Reduces the expected peak to 180,000+ month for April & May 2021.
  Majority of changes related to Tier 1 Basic Meter Datastream activation
Red line current date Green line 5MS go live

## Slide 10: Pre 5MS Go Live CATS Transaction Volume Estimates
Tranche 1: Meters impacted
  Including Accumulation Tier 1 Meters
  Large volume completed Oct
Peak during Apr and May
  Majority of changes related to Tier 1 Basic Meter Datastream activation
  Graph at different scale
    Peak Volume Dec 2020
Estimated Peak 6800+
Red line current date Green line 5MS go live

## Slide 11: Pre 5MS Go Live CATS Transaction Volume Estimates
Tranche 2 updates:
  Large number of updates in Jul and Aug – Approx. 850,000
  No changes advised since pervious reporting period

## Slide 12: Applicable MTP Activities
SID | Sub-Category | AID | Activity | Actions | Role | CATS CRs | Transition Start Date | Transition End Date | Rule Date
S13 | BULK/Wholesale Meters | A36 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S13 | BULK/Wholesale Meters | A36b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S14 | Type 1-3 meters | A40 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S14 | Type 1-3 meters | A40b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S15 | Cross Boundary meters (Known) | A45 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S15 | Cross Boundary meters (Known) | A45b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S15 | Cross Boundary meters (Known) |  | Update Meter Read Type code with RWDA | 1. Update TNI2 & NSP3 | AEMO | CR51xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2022
S17 | New and replacement Type 4 | A57 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S17 | New and replacement Type 4 | A57b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S18 | New and replacement Type 4A | A63 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S18 | New and replacement Type 4A | A63b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S19 | New and replacement VIC AMI meters | A69 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S19 | New and replacement VIC AMI meters | A69b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022

## Slide 13: Applicable MTP Activities
SID | Sub-Category | AID | Activity | Actions | Role | CATS CRs | Transition Start Date | Transition End Date | Rule Date
S20 | New and replacement SAMPLE Meters | A75 | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S20 | New and replacement SAMPLE Meters | A75b | Update Meter Read Type code with RWDA | 1. Update Meter Read Type code with RWDA | MPB | CR305x | 9-Mar-21 | 30-Nov-22 | By 1 Dec 2022
S22 | Type 7 metering installations | A83a | Create/activate export and import (active (kWh) and reactive (kVarh)) energy datastreams in CNDS table | 1. Create Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S26 | Cross-boundary supplies | A95 | Create cross-boundary NMIs | 1. Create and activate NMI 2. Update NMI to active status | LNSP | CR20xx CR50xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S26 | Cross Boundary meters (Known) |  | Update Meter Read Type code with RWDA | 1. Update TNI2 & NSP3 | AEMO | CR51xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2022
S26 | Cross-boundary supplies | A96 | Create Datastreams in MSATS | 1. Create Datastreams at Suffix Level | MDP | CR40xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S26 | Cross-boundary supplies | A97 | Create registers in MSATS | 1. Install meter (includes Meter read type = RWDA) | MPB | CR30xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27 | Non-contestable unmetered loads | A99 | Create Non-contestable unmetered load NMIs | 1. Create and activate NMI 2. Update NMI to active status | LNSP | CR20xx CR50xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27 | Non-contestable unmetered loads | A100 | Create Datastreams in MSATS | 1. Create Datastreams at Suffix Level | MDP | CR40xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27 | Non-contestable unmetered loads | A101 | Create registers in MSATS | 1. Install meter (includes Meter read type = RWDA) | MPB | CR30xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27a | Convert 'SASCALE NMI' | A101a | Create cross-boundary NMIs | 1. Make bulk NMI Extinct | LNSP | CR50xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27a | Convert 'SASCALE NMI' | A101b | Create Datastreams in MSATS | 1. inactive Datastreams at Suffix Level | MDP | CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S27a | Convert 'SASCALE NMI' | A101c | Create registers in MSATS | 1. inactive meter (includes Meter read type = RWDA) | MPB | CR35xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S28 | New NMI classification codes - BULK | A103 | Update NMI Class Codes for existing NMIs as required | 1. Update NMI Classification Code | TNSP | CR50xx | 1-May-21 | 31-Aug-21 | By 1 Oct 2021

## Slide 14: Applicable MTP Activities
SID | Sub-Category | AID | Activity | Actions | Role | CATS CRs | Transition Start Date | Transition End Date | Rule Date
S30 | New NMI classification codes - DWHOLESAL | A107 | Update NMI Class Codes for existing NMIs as required | 1. Update NMI Classification Code | LNSP | CR50xx | 1-May-21 | 31-Aug-21 | By 1 Oct 2021
S31 | New NMI classification codes - NREG | A109 | Update NMI Class Codes for existing NMIs as required | 1. Update NMI Classification Code | LNSP | CR50xx | 1-May-21 | 31-Aug-21 | By 1 Oct 2021
S32 | New NMI classification codes - XBOUNDRY | A111 | Update NMI Class Codes for existing NMIs as required | 1. Update NMI Classification Code | LNSP | CR50xx | 1-May-21 | 31-Aug-21 | By 1 Oct 2021
S35 | LR and FRMP fields | A116 | Update LR and FRMP to GLOPOOL for existing NMIs as required | 1. Update LR and FRMP to GLOPOOL for existing NMIs as required | AEMO | BC00 | 1-May-22 | 1-May-22 | 1-May-22
S36 | Tier 1 basic metering data | A118 | Create/activate tier 1 basic meter datastreams as required | 1. Create datastreams | MDP | CR40xx | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021
S38 | VIC TUOS datastreams | A120 | Update Datastream type codes from 1-4 to 'I' or 'N' as required | 1. Update Datastreams to Suffix Level 2. Inactivate Net datastream | MDP | CR400x CR405x | 9-Mar-21 | 31-Aug-21 | By 1 Oct 2021

## Slide 15: Upcoming MTP Activities
Blaine Miner

## Slide 16: Upcoming MTP Activities
Description | Date | Activity ID
MPs to provide progress and amendments to forward plans for Type 1-3 and subset of 4 meters to AEMO | Due by 1 Dec 2020 | A3a, A8a, A13a
MDPs to provide progress and amendments to forward plans for Type 4, 4A, VICAMI and Sample meters to AEMO | Due by 1 Dec 2020 | A52a, A58a, A64a, A70a
MDPs to create/convert export and import Active (kWh) and Reactive (kVarh) energy datastreams, where applicable, in the CNDS table | Start from 9 Mar 2021 | A36, A40, AA45, A51, A57, AA63, A69, A75
MPs to update the Meter Read Type code with RWDA, where applicable | Start from Now | A36b, A40b, A45b, A51a, A57b, A63b, A69b, A75b
MCs to provide visibility of approach & timeframe for required new cross boundary metering installation | Due by 31 Mar 2021 | A23
MCs to coordinate with LNSPs, MSPs, FRMPs(LR) and end users agreements on NCONUML profiles and algorithms | Due by 31 Mar 2021 | A87
Participants to establish agreements to allow the delivery of 5min metering data pre 1 Oct 2021 between NSP, Retailer, MDP and AEMO, as applicable | Due by 31 May 2021 | A32, A37, A42, A47, A53, A59, A65, A71, A84, A88
AEMO to establish agreements with MDPs to allow the delivery of 5min metering data pre 1 Oct 2021 for B2M purposes | Due by 31 May 2021 | A34, A39, A44, A49, A55, A61, A67, A73, A85, A91

## Slide 17: GLOPOOL Update
Paul Lyttle

## Slide 18: GLOPOOL Update – FRMP
Financial Responsible Market Participant updates
  Update of FRMP Participant ID will use Bulk Change Tool
    AEMO will provide a list of known impacted NMIs to FRMP Participants for validation.
    FRMP/LR Participants will be required to validate and/or update NMI list
      Changes to include all known: BULK (TNI) and XBONDARY (Cross Boundary) connection points
    Changes will be done retrospectively
    CATS Notifications will be provided as part of the BCT updates.
  Update Rules:
    Update the FRMP Participant Code to “GLOPOOL” Effective 1-May-2022
    Applies to all identified and validated NMIs
    Excludes all NMIs not identified on the list.
  Edge Cases:
    No edge cases have been identified
  Test Timings:
    No testing has been performed as this is a proven operational process.

## Slide 19: GLOPOOL Update – LR
Local Retailer updates
  Update of Participant ID to use Bulk Change Process
    This process uses the same update code as BCT
    Changes will be done retrospectively
    No CATS Notifications will be provided as part of the Bulk Change Process.
  Update Rules:
    Update the Local Retailer Participant Code to “GLOPOOL” Effective 1-May-2022
    Applies to all Distribution connected NMI’s
    Excludes any NMI that has an Embedded Network code in the Child field
    Excludes all NMIs that have “POOL%” as the LR participant code (transmission)
  Edge Cases:
    Sample NMIs where LR participant code Not Equal “Sample” will be updated.
    Isolated Jurisdictions will be included in the updated NMIs
      This allows for incorrect TNI assignment to be updated with minimal impacts.
  Test Timings:
    A full 11.3 million updates were tested with the process completing in 8 ½ hours.

## Slide 20: GLOPOOL Update – LR Reconciliation
Local Retailer Reconciliation Files
  Registration:
    Participants will be requested to register 2 email addresses with AEMO
      One email address will be used to be able to access a share directory containing the reconciliation report(s)
      The second email address will be provided the password to access the reconciliation file.
  Reconciliation Report:
    A reconciliation report will be provided to all registered Participant codes
  Report Example:
    Report will include 3 rows per NMI role change
      Existing record set to inactive
      New record for old participant including start and end dates
      New record for new participant including start and end dates.

## Slide 21: GLOPOOL Update – Timeline & Considerations
High Level Timeline
  List Validation:
    List to be provide to FRMP/LR participant by 25 April 2022
    Lists to be validated and returned by 28 April 2022
      List provided to FRMPs will be used if validated list is not returned.
  Update process:
    Update will be processed into MSATS on 2 May 2022 with an effective date of 1 May 2022.
  Reconciliation reports:
    Reconciliation reports will be available for Participants by 6 May 2022
Considerations
  Pre-Conversion:
    To ensure no LR changes are inflight for GS update the following is requested
      Ensure no new NMI create CRs are active at time of update
      Ensure no new LR update CRs are active at time of update
      AEMO will Cancel any CRs that include LR changes during update process

## Slide 22: Cross boundary guidelines
David Ripper

## Slide 23: Cross Boundary Categories
Cross Boundary Supply Categories
Cross Boundary connection points in regular use
  Circuit connecting supply DB’s distribution network to receiving DB’s distribution network
  Service connecting end user connection point in receiving DB’s Local Area to supply DB’s distribution network
Cross Boundary circuit connecting supply and receiving distribution networks, used infrequently under emergency conditions

## Slide 24: Cross Boundary conditions and Requirements
Cross Boundary circuit connecting supply and receiving distribution networks
DNSPs, in consultation with AEMO, will create Cross Boundary NMI
LNSP = Supply DB Participant ID
TNI = Supply DB TNI
NSP2 = Receiving DB Participant ID – populated by AEMO
TNI2 populated by AEMO
Where a Cross Boundary circuit supplies a singe distribution substation only, NER compliant metering at the distribution substation may be used.

## Slide 25: Cross Boundary conditions and Requirements
Cross Boundary service connecting end user connection point in receiving DB’s Local Area to supply DB’s distribution network
DNSPs must provide AEMO with End User NMIs
End User connection point must have remotely read interval meter (can be 5, 15 or 30-minute)
DNSPs, in consultation with AEMO, will create/maintain “Cross Boundary NMI”
LNSP = Receiving DB Participant ID
TNI = Supply DB TNI
NSP2 = Supply DB Participant ID – populated by LNSP (new CR6xxx)

## Slide 26: Cross Boundary conditions and Requirements
Cross Boundary – emergency conditions
Cross Boundary circuit connecting supply and receiving distribution networks, used infrequently under emergency conditions
Approval must be obtained from AEMO
AEMO, in consultation with DNSPs, will determine the “metering” arrangements for the Cross Boundary Supply
As there are a number of scenarios related to determination and provision of metering data for emergency Cross Boundary supplies, further analysis is still required
Energy volume assessment methodology
MDPs to collate metering data into 5-minute trading intervals
Identification of time period the Unmetered Cross Boundary Supply was in use
NMI and datastream activation process
Provision to AEMO of details of the form in which information related to each use of an Unmetered Cross Boundary Supply

## Slide 27: Cross Boundary conditions and Requirements
Cross Boundary – emergency conditions
Emergency Cross Boundary NMIs
DNSPs, in consultation with AEMO, will create Cross Boundary NMI
LNSP = Supply DB Participant ID
TNI = Supply DB TNI
NSP2 = Receiving DB Participant ID – populated by AEMO
TNI2 populated by AEMO
Emergency Cross Boundary datastream activation to be determined

## Slide 28: Next steps and general business
Greg Minney

## Slide 29: Next steps & general business
Participants to consider:
  What additional engagement will be required with other Participants to complete impact assessments and planning
  Potential bulk capability requirements
  Potential alternative management options
Next TFG (14 Jan 2021) agenda items

## Slide 30: Thank you for your attendance and participation!